## 00_Cover
Project Resource Assignment Program (PRAP)
Application Development Plan
Document ID | PRAP-PLAN-001
Document type | Development plan (Step 1 deliverable) - change against the v1.3 baseline
Version | v2.73
Status | Baseline v2.0 + Step 4 progress. Application v1.62, source schema 16 - Gate 4 refinements, the work scope and the biosimilar split, the shared-role division, the delivered default assumptions, milestone and period highlighting, and the manager's review of issues.
Issue date | 2026-07-31
Author | Claude Code
Reviewer | Requester - four review rounds: v0.11, v0.2, v0.3, v0.4 reviewed
Baseline | v1.3, approved by Dan 2026-08-01
Repository | Dan5050-now/project1
Branch | claude/project-resource-assignment-app-1vjdzh
Supersedes | v1.4 (draft) and, once approved, v1.3. v1.3 remains the baseline until then
Status of this issue
v1.0 was approved by Dan on 2026-08-01, closing Gate 1. It remains the approved baseline.
This issue, v1.1, carries a change request raised after that approval: two additions marked on sheet 11
and a set of edits made directly to the derivation table on sheet 05. Because v1.0 is a baseline, these
cannot simply be absorbed - they are presented as a numbered change against it, and v1.1 needs its own
approval before it supersedes v1.0. The approval block on sheet 12 now holds both.
WHAT CHANGES
1. 'Inspection' becomes a standard milestone, and unlike the others it may occur SEVERAL TIMES in one
project. A milestone name is therefore no longer unique within a project.
2. A seventh period, 'After Close-out (final)', spans the inspection activity. The clinical-trial
period set grows from five names to six.
3. Three boundaries now prefer a milestone where one is recorded: Before-Start-up ends at
'Protocol (v1)', Start-up begins the day after it, and Start-up ends at 'First SIV'.
4. 'FPI' returns as a permitted milestone - as the fallback for 'First SIV'. It had been dropped from
the standard list at Q-15, so this reverses that.
The revised derivation was tested against seven timelines and is contiguous in all of them. One case
needed a rule that was not in the mark-up: an inspection dated BEFORE the final DB lock. Taken
literally it makes the seventh period start before the sixth. Inspections on or before the final DB
lock are therefore treated as markers inside the existing periods, and only later inspection activity
opens period 7. Raised as R-03 and CONFIRMED by the reviewer at the v1.1 review.
v1.3 was approved by Dan on 2026-08-01 and remains the baseline. This issue carries five changes against
it - R-05 from the Step 3 review, R-06 to R-08 from the specification v0.3 review, and R-09 to R-13
from the component-list reviews. All were approved by Dan on 2026-08-02, and this issue is now THE
BASELINE, superseding v1.3. Steps 1 to 3 are closed; Step 4, code generation, is authorised.
v1.3 carries change R-04: every sheet of the source workbook now holds at least one free-text note
column. Four sheets had none - Milestone, ProjectPeriod, PeriodWeightStandard and Lists - and each gains
note_1. The other six already had one: Project and Person carry note_1..note_5, Assignment
note_1..note_3, RoleFactor role_note, PersonPeriodWeight reason, and Config note.
Because columns change, the source schema version steps from 1 to 2. Nothing else moves: notes are
carried through import and export unchanged and are never read by the calculation, so re-running the
dummy dataset gives identical figures to v1.2.
WHAT THIS PLAN NOW FIXES
65 requirements (sheet 03) as the contract for Steps 2-5
21 validation rules (sheet 04) applied on import and on every on-screen edit
11 engineering decisions, C-01 to C-11 (sheet 05), all confirmed
a source schema of 10 sheets at version 2 (sheet 04)
the five-step build with a review gate at the end of each (sheet 08)
Nothing in this document is open. Six review rounds produced 28 questions and 4 change requests; all 32
are answered and applied, and the review log on sheet 12 carries no open item.
The plan in one page
Output One HTML file, opened by double-click on Windows, offline, no install. One Excel
workbook alongside it holds the data and remains the archive of record.
Calculation load = project period weight x role factor x person weight x month coverage,
in FTE where 1.00 FTE = 160 hours per month.
Over-allocated above 1.50 FTE in a month; under-allocated below 0.80 FTE for three
or more consecutive months, reported as a run.
Periods Clinical Trial: five period names derived from milestone dates and month offsets,
with the conduct phase split into 'Conduct (interim)' and 'Conduct (final)' where an
interim DB lock divides it. Weights come
from the trial's clinical phase.
Others: three periods, dates and weights both entered by hand.
Dashboard Overall (monthly simulation per project and per person, tables and graphs),
Source data (project), Source data (person). Every field editable, with identifier
edits cascading to referencing rows.
Build Five steps, each ending at a review gate. This document closes Step 1.
What approving this document means
Gate 1 approval on sheet 12 baselines the 63 requirements on sheet 03 as the contract for Steps 2-5,
and confirms the six engineering decisions C-06 to C-11 on sheet 05 that were proposed but never
explicitly answered across the review rounds. Those six are listed there with their rationale; if any
is wrong, say so at approval rather than after.
How to read this workbook
Sheet | Contents
00_Cover | Document control, what changed, reading guide.
01_Version_History | Change log for this plan.
02_Scope | Background, objectives, in scope / out of scope.
03_Requirements | Numbered requirement register - the contract for Steps 2-5.
04_Data_Model | Every sheet and column of the single source workbook, with rules.
05_Resource_Logic | The calculation that turns assignments and weights into monthly FTE.
06_Dashboard_Design | The three dashboard tabs: tables, graphs, filters, editing.
07_Architecture | Single-file HTML + Excel-on-disk design and the file-access decision.
08_WBS_Schedule | The five steps broken into tasks, deliverables and review gates.
09_Version_Control | How plan, specification and output files are versioned together.
10_Risks | Risks and assumptions with mitigations.
11_Open_Questions | All 28 questions and their answers. Nothing open.
12_Review_Log | Every change made across the four review rounds, and why. Gate 1 approval block.
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 01_Version_History
Version history
One row per issued version. Numbering rules are on sheet 09_Version_Control.
Version | Date | Author | Reviewer | Summary of change | Status
0.1 | 2026-07-25 | Claude Code | - | First draft issued for review. Built from the requirements supplied by the requester, incorporating two confirmed decisions: browser file-picker + SheetJS for Excel access (option a), and the five-step plan. | Superseded
0.11 | 2026-07-31 | Requester | Requester | Reviewer mark-up returned as PRAP_Development_Plan_v0.11_reviewed.xlsx. Answered all 12 open questions; added one Import/Export requirement; added clinical phase, four system-responsibility columns, three system-name columns, and denormalised name columns to the data model. | Review input
0.2 | 2026-07-31 | Claude Code | Requester | Reviewer answers propagated across all sheets: single source workbook; calculation reduced to project weight x role factor x person weight x coverage; FTE capacity with 1.50 over-allocation and 0.80/3-month under-allocation thresholds; in-application editing added; real role, period and milestone names adopted; performance target reduced to the stated data volume. Eight follow-up questions raised. | Superseded
0.21 | 2026-07-31 | Requester | Requester | Second reviewer mark-up returned as PRAP_Development_Plan_v0.2_reviewed.xlsx, answering Q-13 to Q-20. | Review input
0.3 | 2026-07-31 | Claude Code | Requester | Q-13 and Q-17 closed, clearing both blockers. Milestone list replaced (First SIV in, FPI out, DB lock cut-off and DB lock split interim/final). Period sets made type-specific: Clinical Trial keeps its four, 'Others' gets Planning / Develop / Close. Period boundaries now computed from milestone dates plus month offsets. outsourcing_type fixed to three values; system_prepared_by dropped. All fields made editable with cascading referential integrity. Three coverage gaps in the supplied period mapping identified and raised as Q-21 to Q-23. | Superseded
0.31 | 2026-07-31 | Requester | Requester | Third reviewer mark-up returned as PRAP_Development_Plan_v0.3_reviewed.xlsx, answering Q-21 to Q-26. | Review input
0.4 | 2026-07-31 | Claude Code | Requester | Period model settled. Close-out starts 3 months before DB lock; a trial with an interim lock carries two close-out periods with Conduct resuming between them, so 'Conduct' may occur twice and ProjectPeriod gains period_seq. Clinical-trial period set grows to five names. PeriodWeightStandard re-keyed on clinical_phase. 'Protocol (v1)' added as the eighth milestone. Derivation verified contiguous against five timelines including four degenerate ones. Two questions remain. | Superseded
0.41 | 2026-07-31 | Requester | Requester | Fourth reviewer mark-up returned as PRAP_Development_Plan_v0.4_reviewed.xlsx, answering Q-27 and Q-28. | Review input
1.0 | 2026-07-31 | Claude Code | Pending | FINAL Step 1 issue. Both remaining answers confirmed the v0.4 design. A single close-out keeps the name 'Close-out (final)'. 'Others' projects need no distinguishing and take manual weights as well as manual dates, so PeriodWeightStandard becomes a clinical-trial reference table only. All 28 review questions closed; no open items. Issued for Gate 1 approval. | APPROVED 2026-08-01 by Dan - baseline
1.01 | 2026-07-31 | Requester | Requester | Post-approval change request returned as PRAP_Development_Plan_v1.0_reviewed.xlsx: add 'Inspection' as a standard milestone, add a seventh period covering inspection activity, and prefer 'Protocol (v1)' and 'First SIV' as period boundaries where recorded. | Change request
1.1 | 2026-07-31 | Claude Code | Pending | Change against the v1.0 baseline. 'Inspection' added as a standard milestone that may repeat within a project; 'FPI' restored as the fallback for 'First SIV'; seventh period 'After Close-out (final)' added, taking the clinical period set to six names; Before-Start-up, Start-up start and Start-up end now prefer a recorded milestone. Derivation re-verified contiguous against seven timelines. Needs its own approval. | Superseded by v1.2
1.11 | 2026-07-31 | Requester | Requester | Reviewed v1.1 and confirmed R-03 - inspections dated on or before the final DB lock stay markers and do not open the seventh period. No other change requested. | Review input
1.2 | 2026-07-31 | Claude Code | Pending | R-03 confirmed and closed. No content change beyond recording it: the derivation, requirements and validation rules are as issued at v1.1. Every question and change request raised across five review rounds is now settled. | APPROVED 2026-08-01 by Dan - superseded by v1.3 once approved
1.3 | 2026-07-31 | Claude Code | Pending | Change against the v1.2 baseline (R-04): a free-text note column added to every source sheet that lacked one - Milestone, ProjectPeriod, PeriodWeightStandard and Lists each gain note_1. Source schema version steps from 1 to 2. No calculation, validation or UI behaviour changes. Issued FINAL: this is the last planned issue of the development plan. | APPROVED 2026-08-01 by Dan - FINAL
1.4 | 2026-07-31 | Claude Code | Pending | Change against the v1.3 baseline (R-05), from the Step 3 prototype review: project_type splits into 'NewDrug CT' and 'Biosimilar CT'. REQ-PRJ-01 and REQ-PRJ-02 reworded; RoleFactor and PeriodWeightStandard keyed on the type; source schema version steps 2 to 3. | Superseded by v1.5
1.5 | 2026-07-31 | Claude Code | Pending | Changes R-06, R-07 and R-08 against the v1.3 baseline, from the specification v0.3 review. REQ-NFR-03 re-baselined to 100 projects and 1,000 people and raised to Must; both allocation thresholds confirmed ABSOLUTE with the under-allocation floor moved 0.80 to 0.60; repeated period names must be distinguishable on screen. REQ-DSH-09, REQ-DSH-10 and V-22 added. | Superseded by v1.6
2.40 | 2026-09-03 | Claude Code | Pending | R-32, REQ-CAL-19 AMENDED: A PROJECT-MONTH IS ITS STANDARD, and person_weight now decides how it is DIVIDED rather than how big it is. The reviewer reported that the standard was being ignored on import; it was not - it was applied, indexed and in the arithmetic on every line, and doubling one doubled the figure. What made it look ignored was person_weight: on the delivered fixture the median project-month came to 30% of standard x period weight, because the median person weight is 0.29 and each person's share was scaled by their own weight AFTER the demand was divided. That was v2.39's chosen reading, taken deliberately so a shortfall would be visible. Asked again with the arithmetic in front of them, the reviewer chose the other one. So person_weight, month coverage and the role factor now all make a CLAIM on the month, and the share is that claim over the sum of the claims: fte = demand x claim / sum(claims), where demand = standard_fte x period weight x the month the project actually ran. The shares add to one BY CONSTRUCTION, so the month is its demand however many people are on it and whatever their weights - checked on 1,557 and 203 automatic project-months of the two fixtures, all exact. THE DEMAND IS SCALED BY THE MONTH THE PROJECT RAN, taken as the largest coverage any of its people have, or every project would spike to a full standard month in the month it opened and the month it closed. Two consequences worth stating: a part-time person now pushes load ONTO their colleagues instead of lowering the project, so under-staffing shows on the PEOPLE as months over the ceiling; and split_shared_role_fte can no longer inflate a project total, so on a single-role project it is inert - it still decides the split where roles have different numbers of holders, which is the case it was always really about. The results export gains month_run and demand_fte, and every row is now demand x share rather than a five-term product. Figures move throughout: the 62-project fixture goes from 731 to 4,334 FTE-months, which is the demand it always described and never showed. | Superseded by v2.41
2.73 | 2026-10-11 | Claude Code | Pending | R-64, REQ-PRJ-17: THIRTEEN HIGHLIGHT COLOURS. Asked for from the field: 'at least 12 distinctive colours' for highlighting - five ran out as soon as a team gave each kind of milestone or period its own. The palette is now red, orange, yellow, lime, green, teal, cyan, blue, navy, purple, magenta, pink and brown, for milestones and periods alike, each defined for the light and the dark theme and no two closer than a set distance in either (yellow was moved away from orange to get there - the two of the original five that were nearest). A band's label is dark on the four pale ones. The template's Lists offer all thirteen; a workbook made before them, whose Lists hold five, is offered the other eight as well, so the new colours can be chosen without editing its Lists. The value chooser shows each colour as a swatch beside its name. THE COLOUR WORD IS NOW READ AS A WORD: 'Highlight (Green) - redo' used to be red, because the letters r-e-d appear in it; now a colour word must stand on its own and the first one named wins - Korean text beside it does not hide it. Mirrored in the Python reference. No figure moves; no schema change. Template v1.21, examples v1.23 and v1.15. tools/test_highlight.py gains ten checks. Python edition 1.36. Also asked for: the Monthly estimation panel on Source data (project) is titled by the project's NAME, with its identifier quieter beside it, instead of the identifier alone (an assignment's panel keeps its id, with the line under it). | Issued for review
2.72 | 2026-10-09 | Claude Code | Pending | R-62, REQ-DSH-20: AN ISSUE A MANAGER HAS REVIEWED IS SHOWN AS REVIEWED. Asked for from the field: a month short of its standard, over it or with nobody on it may be a decision rather than a problem - 'over in the run-up to the interim lock, the sponsor is paying for it' - and drawing those in the same alarm colour as the ones nobody has examined hides the real alarms among them. A new sheet, IssueReview (project_id, month, issue, status, gap_fte, rationale, reviewed_by, reviewed_at), holds one review per project, month and issue; source schema steps 15 to 16. CLICKING AN ISSUE MONTH in Resource by project, or its row in the Standard vs staffed list, opens the month with a Manager review box: a decision ('Confirmed - no issue', 'Accepted', 'To be fixed'), who confirmed it, the reason, and 'Apply to the whole run' for the consecutive months carrying the same issue - or 'Open the project' to change the data instead. The first two CLOSE the issue and need a reason; 'To be fixed' keeps it open with a note. A closed month STAYS MARKED BUT IS DRAWN MUTED, gray, and clicking it shows the decision, who made it, when and why, which can be changed or removed at any time. The counts on the control, the tile and the list are OPEN issues, with the reviewed ones counted apart ('2 reviewed'); the list filters Any review / Open / Reviewed and sorts open issues first, and Show in Resource by project gains 'Reviewed and closed'. A REVIEW COVERS THE FIGURES IT WAS MADE ON: gap_fte records the gap reviewed, and if the month's gap moves, the review no longer closes it - the month is open again, marked 're-check' - and V-40 (new, information) says so; a review of an issue that has gone is kept as history and V-40 says that too. A review is an edit like any other: held until Save, in the change log, exported and read back, and judged identically by the Python reference. A workbook from before schema 16 opens with no reviews (V-09 information). No figure moves; template v1.20, examples v1.22 and v1.14, the small one carrying two accepted months and one to be fixed. Clicking an issue month used to fold its project row open or shut instead - the row's own click came first - and that is fixed. THE STANDARD VS STAFFED LIST IS IN ORDER OF PROJECT ID, THEN MONTH, both ascending (asked for straight after), and lists every month: it was largest gap first and capped at 40, which in project order would have cut whole projects off the end. tools/test_review.py is new: 49 checks, five proved by putting the fault back. R-63 (PYTHON EDITION, desktop plan v1.18): a plan in My plans takes no editing hold and so never times out; a team plan whose hold lapses and is taken over says so in a pop-up that offers to keep your version; and the file window is redrawn - places, a clickable path, type badges, how long ago and date groups, a filter, list or tiles, details, the keyboard, and who saved or is editing a plan. Python edition 1.35. | Superseded by v2.73
2.71 | 2026-10-08 | Claude Code | Pending | R-60, REQ-PRJ-16: PERIOD COLOURS ARE AN ASSUMPTION, AND A PROJECT MAY STILL CHOOSE ITS OWN. Asked for straight after R-59: every project's periods take their colour from the General assumptions tab, and where no colour is assumed for a period, a project may choose one. A new sheet, PeriodHighlight (period_name, period_highlight, note_1), holds one row per period name; source schema steps 14 to 15. The colour of a band is the project's own choice (ProjectPeriod.period_highlight), else the default for its period name, else gray - the more specific statement winning, as a project's period weight adjusts the standard rather than the other way round. The pop-up says which level chose it. The template and both examples ship defaults that restore what the O-10 review asked for - start-up red, conduct green, close-out orange, develop green, close orange - as a choice the plan holds rather than a palette in the code; the quiet ends (before start-up, after close-out, planning) are left gray. Periods DERIVED from milestones, which have no row to hold a project colour, now take the defaults. A plan started blank is seeded with the same rows. A workbook from before schema 15 opens with no defaults (V-09 information), exactly as one without MonthlyEstimate does; the interchange reader tolerates the sheet's absence the same way. V-39 is new: a default naming no colour, a period name given twice, or a name neither period list knows. No figure moves; template v1.19, examples v1.21 and v1.13. R-61: KEEP YOUR VERSION WHEN THE SHARED PLAN IS NO LONGER YOURS TO WRITE (Python edition). A session whose hold lapsed and was taken over (NR-STO-14), or whose plan a colleague saved since it was opened (NR-STO-16), has its Save refused - rightly - and was told to Save as or Reload, the second of which discards the work on screen. Now a bar offers one press, 'Save my version to My plans', which writes what is on screen as a NEW file in the person's own folder - their name and the time in its name, never on top of an existing file - and carries on in it; the team's plan is not touched. Also on the File menu at any time. Python edition 1.33. | Superseded by v2.72
2.70 | 2026-10-08 | Claude Code | Pending | R-59, REQ-PRJ-15: A PERIOD IS DRAWN IN THE COLOUR SOMEBODY CHOSE, AND GRAY OTHERWISE. Asked for from the field: the Periods table gains a Highlight column like the Milestones one, each project's period may be given a colour, and a period with none is gray. ProjectPeriod gains period_highlight after period_end; source schema steps 13 to 14. The values come from a list of their own in the Lists sheet (period_highlight, the same five colours as milestone_highlight) because a team may mean one thing by blue on a milestone and another on a period, and what is read is the COLOUR WORD inside the value, exactly as R-50 does it. THIS SUPERSEDES THE O-10 COLOUR RULE. Since the component-list v0.3 review the bands took a hue per period NAME (D-06 superseded); now the colour belongs to the user and an unmarked period is a quiet gray, so the periods somebody marked are what the eye finds. Nothing O-10 carried is lost: the weight still shades every band, the period's name is still written on it and in its pop-up, and the legend still lists the period names - each still picks that period out across the chart - under one gray swatch, followed by each colour in use in the words the file uses for it. Labels are dark on gray and on yellow and white on the four strong colours. V-38 IS NEW, the period twin of V-37: a value naming no colour leaves the period gray, which looks exactly like nobody having chosen, so it is said out loud. Warning, never a refusal. Periods DERIVED from milestones (a trial whose workbook carries none) have no row to hold a colour and stay gray until Auto derivation writes them. NO FIGURE MOVES: both example workbooks calculate identically to their predecessors, checked person-month by person-month. Template v1.18, examples v1.20 and v1.12, which mark the final Conduct period of every fifth project blue. tools/test_highlight.py gains ten checks, two proved by putting the fault back. | Issued for review
2.69 | 2026-10-08 | Claude Code | Pending | R-58. 'THE AUDIT TRAIL IS NOT WORKING' - IT WAS, AND THE APPLICATION BEHIND IT HAD STOPPED. In the Python edition a save said 'Saved - but the change log could not be written to the audit folder ... Failed to fetch'. Checked end to end: a saved change is appended to data/audit/PRAP_changes_<month>_<account>.csv with when, who, the record, the column and both values, and findings to the matching file. 'Failed to fetch' meant no answer at all: the application had shut itself down, because its backstop stopped it after fifteen minutes without the page's heartbeat - which is what a browser does to a tab it puts to sleep, and what a sleeping laptop does. The window looked alive and could save nothing. Fixed on both sides: only the page saying it is closing stops the application now (desktop plan v1.16, NR-DEP-17); and if it has stopped anyway, the window says so in words and keeps a red bar up with the browser's own download of the plan and of the change-log entries that never reached the audit folder. Python edition 1.31; the web edition is unchanged. | Issued for review
2.68 | 2026-10-08 | Claude Code | Pending | R-57. A DEFECT IN THE PYTHON EDITION'S FILE BROWSER, reported as 'sub-folders under a level-1 folder do not appear'. They did appear - for a single click. A folder opens on its first click and the list is redrawn, so the SECOND click of a double-click, which is how everybody opens a folder in Windows, landed on whatever row was now under the pointer and opened that as well: double-clicking a level-1 folder put you inside one of its sub-folders, usually an empty one, and the folder asked for was never shown. Worse with R-56's newest-first order, which puts a recently touched sub-folder at the top, exactly where the pointer is. The listing itself was right throughout - fs/list returned every sub-folder. Now the rest of a click sequence that began on another row is ignored, by the browser's click count and by time in case a redraw resets it, and a double-click chooses only the row its own first click was on, so a file is never chosen by a click meant for the folder above it. tools/test_python_app.py double-clicks at a person's pace rather than a robot's - the fast double-click a test driver sends never showed it - and the guard was proved by taking it out. Python edition 1.30; the web edition is unchanged. | Issued for review
2.67 | 2026-10-07 | Claude Code | Pending | R-56. FIVE THINGS ASKED FOR FROM THE FIELD, all about finding your way. (a) THE PROJECT AND PERSON FILTERS LIST NAMES. Nobody looks for PRJ-037; they look for the study. The label is the name, sorted by name, with the identifier added only where the name alone would not say which row it is; the value behind each tick is still the identifier, which is what the filter matches and the export's ReadMe names. A list long enough to scroll gets a search box that matches name or identifier and never ticks anything. (b) A NEW PROJECT OR PERSON STAYS SELECTED. + row left the selection on the row it was pressed from, and the tab reset any selection the filters did not list to the first row - so the milestones, periods and assignments typed next went to somebody else's project, and after Save the new one was not even selected. A row added in this session is now the selection from the moment it exists, through typing, Save and a change of its own identifier. (c) RESOURCE BY PROJECT SAYS HOW EACH FIGURE WAS MADE: a pill per project - Auto, Manual, or Auto with n assignments stated - a pencil on every month carrying a stated figure, and a 'manual' tag on the person rows behind it. A stated figure is a judgement about this study and an automatic one is what a study of its kind takes; the table drew them identically. (d) IT NARROWS TO ITS PROBLEMS - issues only, short, over, not staffed, stated by hand - in the months on screen. The rows only: the control beside it and the tiles go on counting everything, for the reason R-53 gives. (e) NOT STAFFED IS COUNTED. A month the periods ask for with nobody on it is the widest gap there is, and the table drew it while the Standard vs staffed control, the tile and the list said nothing. All three now count it under its own direction, and its row takes you to the project, where people are assigned. AND FILES ARE FOUND BY DATE. The Python edition's file browser shows every file's modified date and time, lists newest first (switchable back to name) and marks the newest; the browser edition has only the operating system's own window, so exported names carry the date AND time and an earlier stamp is no longer stacked on. tools/test_r56.py covers the web half and test_python_app.py the browser; each guard was proved by putting the fault back. No figure moves. | Issued for review
2.66 | 2026-10-04 | Claude Code | Pending | R-55, REQ-OUT-06 AMENDED. THE RESULTS EXPORT SAYS WHICH PROJECTS ARE SHORT. Asked for so the file can be analysed outside the application - by a person or by an AI - and the first question any such analysis asks is which projects have too little or too much. The file could not answer it. ProjectMonth carried what each project was GIVEN and nothing about what it NEEDS; Flags carried people only; and a month nobody is on had no row at all, so the largest shortfall the plan can contain - a project with nobody assigned (V-36) - was the one the file could not show. The obvious workaround was a trap: demand_fte is on Detail, but repeated on every person's row, so adding it up multiplies a project's demand by its headcount. ProjectMonth now carries demand_fte, staffed_fte, gap_fte and gap_dir, taken from the calculation's own maps rather than recomputed, and a row for every month the project's periods ask for and nobody is on, with fte 0 and the whole demand as its gap. staffed_fte is the WHOLE project's and fte the part in view: unfiltered they are the same, and filtered to one department the gap is still the project's own - a project is not short because the reader chose not to look at half of its people. Flags gains project_id and project_name and three project kinds - short of standard, over standard, unallocated demand - one row per run of consecutive months, with the run's gap in total; short and over are never netted (V-34). Summary gains the standard demand and the three totals, summed from ProjectMonth so the two cannot disagree, and the ReadMe defines the columns and warns against summing Detail's demand. PersonMonth gains a row for every month a person is EMPLOYED and on nothing - fte 0, flag 'unassigned' - so the file says who is free as well as who is overloaded, and somebody who has left is never offered as spare capacity. Checked against the Python reference on a plan with all three kinds in it, and each new guard proved by putting the fault back. No figure moves. ALONGSIDE IT, NOT IN THE APPLICATION: tools/prap_analyze.py scores a plan 0-100 from the export or from a source plan, by a fixed formula with every input written out, lists what is short, overloaded and coming, proposes candidate moves, and compares two plans for a what-if; docs/PRAP_AI_Analysis_Guide.md is the method and the prompt for handing that to an AI. It names the shortage the gap column cannot: a project-month IS its demand, shared among whoever is on it, so a project with too few people shows as its people over the ceiling - and that excess is attributed back to the projects making it up. tools/test_analyze.py holds the scorecard identical by both routes. | Issued for review
2.65 | 2026-10-01 | Claude Code | Pending | R-54. TWO THINGS, BOTH RAISED BY A READER LOOKING AT THE SCREEN. (a) A DEFECT: THREE MARKS WERE PRINTING THEIR OWN SOURCE CODE. The arrow that REQ-DSH-15 puts on a month off its standard, in both directions, and the warning sign V-33 puts on a clashing cell, were written in the stylesheet with a DOUBLED backslash - content:"\\25B2" where content:"\25B2" was meant. In CSS the single backslash IS the escape; the doubled one is an escaped backslash followed by five ordinary characters. So every marked month carried the text \25B2 or \25BC in nine-pixel type in its corner, and every clashing cell carried \26A0, for weeks. It was reported as a question - what does this symbol mean - which is how a reader meets a mark that says nothing. THE SUITE COVERED IT AND PASSED. tools/test_gap.py asked whether the ::after content was non-empty, and \25B2 is non-empty. A mark that is PRESENT but says the wrong thing is precisely what that question cannot see, and it is the failure D-04 is about: amber and red are the confusable pair, so where the two directions are drawn in them the ARROW is the whole of what tells them apart. Three guards now: a static one in tools/test_layers.py, since a doubled backslash inside a content: rule has no legitimate use in this stylesheet, and two that compare the RENDERED character against the one that was meant, in test_gap.py and test_manual.py. Each was proved by putting the fault back. (b) THE ORDER COLUMN IS NO LONGER DRAWN ON MILESTONES. Asked for, and safe for that table only: milestone_seq orders NOTHING. Both engines place a milestone on the timeline by its DATE, and nothing anywhere sorts by the sequence - so the column's own pop-up, which said 'display order along the timeline', was a false statement about the screen it was on. It is still allocated on insert and still written to the file, because a column the workbook carries must survive a round trip whether or not a screen draws it. PERIODS KEEP THEIRS, deliberately: period_seq is what both engines sort the periods by, V-18 reports a duplicate as an ERROR, and V-05 and the no-period-covers-these-days message name a period BY its sequence. Hiding it would leave a reader told to fix something they could not see. | Issued for review
2.64 | 2026-10-01 | Claude Code | Pending | R-53. TWO THINGS ASKED FOR FROM THE FIELD, both about finding your way around a screen rather than about what is on it. (a) REQ-DSH-15 AMENDED - THE STANDARD VS STAFFED LIST CAN BE NARROWED. Three controls, each answering a question somebody actually arrives with: which direction am I chasing, which project is this about, and what is big enough to be worth my morning. The project control offers only the projects that HAVE a gap, because a drop-down of sixty-two to narrow two rows is a worse screen than no drop-down. IT NARROWS THE LIST AND NOTHING ELSE. The tile and the control in Resource by project's head go on counting every month off its standard whatever is set, because they are the alarm: a figure that moved when somebody narrowed their own view would be an alarm that lies, which is worse than no alarm. The heading says 'n of m' whenever anything is set, and a list emptied BY THE FILTER says so in those words - 'all 66 are hidden' and 'every project is on its standard' are different answers and only one of them is good news. Cleared on load, like the column filters and for the same reason. (b) REQ-DSH-19 IS NEW - A ROW'S IDENTITY STAYS ON SCREEN WHILE ITS TABLE SCROLLS SIDEWAYS. The Project sheet is twenty-five columns and about 3,070px wide in a panel of 1,316px, so less than half of it is ever in view; scroll out to the far columns and you are editing an unlabelled row. What has gone is not the data, it is WHICH PROJECT THIS IS - and that is two columns. The row's handle, its identifier and its name are frozen at the left edge and the rest slides under them. Declared per sheet rather than per call site, and only for a LEADING run of columns, because what makes the offsets arithmetic rather than measurement is that there is nothing between them and the edge. The cost is honest and bounded: 436px, about six data columns on screen at a time instead of ten - six you can attribute to a project beats ten you cannot. They stay editable where they stand. Two things that are not obvious had to be built as well: every background in those tables is mixed against TRANSPARENT, which is right for a cell sitting on the panel and wrong for one with rows passing underneath, so all four states are restated against the surface; and laid out exactly edge to edge a one-DEVICE-pixel seam still opens where the rounding of the sticky offset and the scroll position disagree, showing the row behind as a stray mark beside the identifier - found by magnifying a screenshot, cured by letting each stuck cell start a pixel before the one before it ends. tools/test_pinned.py is new. | Issued for review
2.63 | 2026-10-01 | Claude Code | Pending | R-52, REQ-DSH-15 AMENDED: STANDARD VS STAFFED MOVES ONTO RESOURCE BY PROJECT. Asked for from the field. It is the right home - every month the list names is a cell in that table, and the two sat a scroll apart - but it reverses the one thing v2.47 wrote the requirement to secure: the list was a panel under the tiles precisely so that something whose whole danger is being silent did not sit behind a click. SO THE COST IS PAID BACK RATHER THAN ACCEPTED. The control in that panel's head does not name the screen behind it; it STATES THE FINDING - how many project-months are off their standard and in which direction, with the same arrows and the same amber the cells use. The alarm is therefore on screen with nothing opened, which is what the panel was there for, and the LIST - which nobody reads until they are investigating - is one click away. The tile above still counts it, every cell is still marked where it is drawn, and V-34 still carries it to the findings report, the load banner and the archived change log. The control is drawn even when there is nothing to report, quietly and without a count: one that comes and goes is one nobody learns the position of, and its absence cannot be told from a screen nobody has looked at. A ROW STILL OPENS THE MONTH, now on top of the list rather than instead of it, so Escape comes back to where the next month you want to look at is. AND A BUG THE MOVE EXPOSED. The tile has carried 'jump to the list' since R-42 and has never once done it. The pop-up handler runs in the CAPTURE phase and stops the click for anything carrying a pop-up that is not a button, a link, a field or a summary - and that tile is a div with role='button'. So the click was swallowed before the tile saw it, every time, and nothing anywhere said so. Role now counts as well as tag: a thing that declares itself a button is a button. | Issued for review
2.62 | 2026-10-01 | Claude Code | Pending | R-51, REQ-DSH-18: ANY SECTION CAN TAKE THE WHOLE SCREEN, AND IS STILL EDITABLE THERE. Asked for from the field, about entering data rather than about reading it: the page is 1400px wide at most and every scroll region is bounded on both axes by REQ-DSH-13, with the entry tables capped at 340px - so a sheet twenty-two columns wide is filled in through a window about a fifth of its size, and every committed cell costs a scroll in two directions to find the next one. A CONTROL IN EVERY PANEL HEAD, and the rule for which panels get one is 'is there a bounded region in here' rather than a list somebody maintains - so the charts get it too, and a panel of prose or an empty-state message does not. A control that does nothing visible teaches the reader that the feature is broken. IT IS THE SAME SCREEN, NOT A VIEW OF IT. Nothing is moved and nothing is copied: the panel stays where it is in the page and is drawn against the viewport instead of against the column. Every edit in this application commits through a re-render that replaces a whole pane, so a panel lifted into an overlay would be orphaned by the first keystroke that was saved - which is precisely the keystroke the feature exists for. A modal dialog has that fault and a worse one: it makes the rest of the page inert, and the rest of the page is where Save is. SO THE EDIT BAR AND THE TABS ARE LIFTED ABOVE IT RATHER THAN COVERED. A full screen that hides Save is a trap - a wide comfortable table with nowhere to commit it. The filter bar IS covered, which is the trade; Escape brings the page back, and the per-column filters, the ones used while typing, are inside the tables and come with them. PANELS NOW HAVE NAMES (data-panel), because what has to survive a re-render is an identity. An element does not survive it; a position does not survive the data, since a project's detail section draws a different number of panels for different projects; and a heading does not either, because half of them end in the name of the selected row. Named, 'Periods' stays open as 'Periods' while its heading changes from one project to the next. A tab change, and a load, put it away - a hidden pane draws nothing, and a load's own findings must not appear behind a panel covering the window. No figure moves and no file changes. tools/test_zoom.py is new. | Issued for review
2.61 | 2026-09-23 | Claude Code | Pending | R-50, REQ-PRJ-14: A MILESTONE CAN BE MARKED IN A COLOUR, AND THE MARK FINDS IT ON EVERY TIMELINE. Asked for from the field: the Project timeline draws every milestone the same black triangle, so the two or three that a reader is actually scanning for - the inspection, the date that slipped, the one the sponsor asks about - are indistinguishable from the twenty that are merely on the plan. Milestone gains milestone_highlight, beside the date it marks; source schema version steps 12 to 13. THE COLUMN HOLDS A WORD FROM THE LISTS SHEET, NOT A COLOUR CODE. The template ships 'Highlight (Red)', '(Yellow)', '(Blue)', '(Green)' and '(Orange)', and what the application reads is the COLOUR WORD inside the value - so a team that decides red means something in particular may say so in their own list ('Highlight (Red) - slipped') and keep both the colour and the reason. The legend then prints their words back rather than the word 'red'. That is the whole reason the check is a lookup and not an equality test: the list belongs to the people using it, and a rule that broke the moment somebody explained their own convention in it is a rule they would have to work around. IT BEATS THE DB-LOCK RED THE CHART APPLIES BY ITSELF, deliberately. One is a standing rule about what a milestone does to the period derivation; the other is somebody saying 'look at this one'. The second is the newer statement and the one made on purpose, and nothing is lost by letting it win - the pop-up goes on saying the milestone sets a boundary. WHERE IT SHOWS: the Overall tab's timeline, the project tab's timeline, the milestone table (a colour chip in the cell, drawn as a pseudo-element so it can never become part of what the cell contains), the pop-up, and the legend - which lists only the colours actually in use, because a legend teaching five colours when one is in use answers a question nobody asked. V-37 IS NEW: a value with no colour word in it leaves the milestone unmarked, which looks exactly like forgetting to mark it, so it is said out loud with the values the file itself offers. Warning, never a refusal - a mark changes no figure. NO FIGURE MOVES. The highlight is kept BESIDE the milestone dates rather than inside them: M.milestones stays name -> dates, which is the shape the period derivation, V-14, V-20 and V-21 all read, and a presentation choice has no business inside the structure the arithmetic depends on. Template steps to v1.17 and the two example workbooks to v1.19 and v1.11; a file at schema 12 still opens, with V-09 saying which columns may be missing. tools/test_highlight.py is new. | Issued for review
2.60 | 2026-09-13 | Claude Code | Pending | R-49, REQ-DSH-17: THE DASHBOARD NOW SHOWS THE FIGURE V-36 DESCRIBES. The half of the field report that v2.59 deliberately did not build, asked for once the rule was in: the note told a planner what an unstaffed project needs, and the screen still printed a dot for it. A DOT IS A STATEMENT, AND IT WAS THE WRONG ONE. It says this month costs nothing. For a month inside the project's own run with nobody on it that is false - it costs exactly what its standard says - and the falsehood is the same one V-34 exists for, where a study needing 10.00 and staffed at 5.00 read as a study that only ever needed 5.00. Here it is staffed at nothing and reads as needing nothing. DEMAND IS NOW A PROPERTY OF THE PROJECT-MONTH, computed from the PERIODS alone with no reference to who is on it, by ONE function shared with V-36 - two copies would eventually disagree, and the symptom would be a screen whose figure contradicts the finding beside it. AND IT IS DRAWN AS DEMAND RATHER THAN AS RESOURCE, which is the whole design problem. The applied figures carry a filled sequential background meaning 'this much is being done'; none of this is being done, so it takes an outline and a hatch instead, italic, with a hollow ring glyph so the distinction survives a monochrome print and a colour-blind reader (D-04). IT IS NEVER ADDED TO A TOTAL, and that is not fastidiousness. The specification guarantees that this table's grand total equals the person table's; unallocated demand belongs to no person, so netting it in would break the one reconciliation the screen promises AND would assert that somebody is doing the work. It is totalled on a line of its own and beside each project's applied total - counted apart and never netted, exactly as short and over are. Measured: applied totals 713.78 against 713.78 with an unstaffed project present, and 38.05 unallocated beside them. NOTHING EXISTING MOVES. The fill happens only where the calculation produced no figure at all; a month that already has one keeps it untouched. That rule is not cosmetic - the month_run on a line is the greatest COVERAGE any assignment has in that month, while this is the project's own run, and the two are not always equal, so recomputing a month that already had a figure would silently move it. On the delivered fixture the count of unallocated months is ZERO and every figure is unchanged. THE HORIZON BUG THAT WAS HIDING BEHIND IT IS FIXED TOO. The span offered by 'show everything' came only off the assignment lines, so a project starting after every assignment in the file had ended was not reachable at all - its figures would have been drawn in months that could not be brought on screen. It is taken from these months as well now, and the test pushes a project six years out to prove it. WHAT IS STILL NOT DONE, and is recorded rather than quietly skipped: the demand charts. A stacked bar that mixed allocated and unallocated bands would misstate its own total, and the fix is a separate series rather than a taller stack. The results export is unchanged for the same reason - REQ-OUT-06 promises every monthly figure is the sum of its detail rows, and unallocated demand has no detail rows to be the sum of. | Issued for review
2.59 | 2026-09-13 | Claude Code | Pending | R-48, V-36: A PROJECT WITH NOBODY ON IT NOW SAYS WHAT IT NEEDS. Reported from the field: a project is added, and the application shows no FTE for it until somebody is assigned - even though the figure is computable from the moment its periods exist. IT WAS A ROW OF BLANKS, NOT A WRONG NUMBER, WHICH IS WHY NOTHING CAUGHT IT. And the first wording of this entry got the symptom wrong: it said the project was absent from everything but the timeline. It is not. SCREENSHOTS SETTLED IT - the project IS listed in Resource by project, IS drawn on the timeline and IS counted in the projects tile. What it has is every month EMPTY, nothing on the three demand charts, no legend entry and no line in Standard vs staffed. That is worse than being absent, and it is the very failure V-34 exists for: a row of blanks reads as a project that costs nothing, exactly as a study needing 10.00 and staffed at 5.00 read as a study that only ever needed 5.00. Type, phase, scope and periods are all the standard needs; nothing was missing but the asking. AND THE RULE THAT SHOULD HAVE CAUGHT IT STRUCTURALLY COULD NOT. V-34 compares DEMAND against APPLIED, and a project staffed at nothing is that gap at its widest - but V-34 is built from projGap, which is built from projMonth, which is built from the LINES, and the lines come from the assignments. No assignment, no line, no entry, no finding. The one project short by the whole of its standard was the only shortfall the shortfall rule could not see. Measured on a fixture: a project needing 38.05 FTE-months produced ZERO calculated rows and ZERO findings in both the browser and tools/prap_io.py. V-36 IS INFORMATION AND CLASSED INCOMPLETE, and both were chosen rather than defaulted. A project with nobody on it yet is not a fault - it is the state every project is in for the minute after it is created, exactly as a person with no assignment is (v2.52, and the same argument) - so it must never refuse an edit, never block a save and never ask a question. INCOMPLETE is the class for a row still being built whose finding answers itself, and this one answers itself the moment anybody is assigned. IT CARRIES THE FIGURE, and that is the whole point of raising it from the CALCULATION rather than from the validation. 'PRJ-099 has no assignments' tells a planner what they can already see; 'it needs 38.05 FTE-months over 24 months, peaking at 1.86 in 2026-10' tells them what it will cost to fix. Every term is the one an assignment with blank dates would get (REQ-CAL-15), so the figure is not an estimate OF the application's answer - it IS the application's answer, arrived at early. tools/test_unstaffed.py asserts exactly that in both directions: the total, the span, the peak and the peak month it predicts all equal the project's own once one assignment exists, and the finding then disappears. WHAT IT DELIBERATELY DOES NOT DO. It does not put the project in Resource by project or on the charts. That was the larger option and it was not the one chosen: the demand would have to become a property of the project-month rather than of the assignments, which is a better answer to the original complaint and a much wider change - it also breaks the stated invariant that the project and person tables reconcile, unless demand and applied are kept as separate figures. Recorded here so the option is not lost: the rule reports the number, the dashboard still does not show it. TWO OF MY OWN MISTAKES, BOTH CAUGHT BY THE PROJECT'S OWN CONVENTIONS RATHER THAN BY TESTING HARDER. The severity was written as 'info' where this application's vocabulary is fatal / error / warning / INFORMATION - it would have sorted and filtered wrongly everywhere, including in the suite that checks findings. And the reference implementation named months one later than the browser, because every other call in prap_io.py converts the 1-based month with month_key(y, m - 1) and the two new ones did not. The second was found only by running both engines on the same fixture and reading the two messages side by side, which is what the four-implementation rule is for. | Issued for review
2.58 | 2026-09-13 | Claude Code | Pending | R-47: REQ-NFR-03 IS AMENDED TO 100 PROJECTS AND 150 PEOPLE, AND X-04 STOPS BEING A DEFECT. The decision v2.57 left open is taken, on the measurements v2.56 and v2.57 produced, and it is taken in the MIDDLE: not the 50 x 100 put forward as today's real use, and not a build of row virtualisation, but the largest volume that measures inside budget so there is growth room without code nobody needs. WHY 150 AND NOT 200 OR 400. Candidates were built and driven in one session so they could be compared fairly, at the 60-month horizon, against the 1,000 ms budget for an Overall tab switch that was fixed before any number was seen: 50 x 100 529 ms (53% of budget, worst case 571) ¦ 100 x 100 689 ms (69%, 746) ¦ 100 x 150 810 ms (81%, 894) ¦ 100 x 200 981 ms (98%, 1,225). 100 x 150 IS THE LARGEST VOLUME WHOSE WORST CASE IS STILL INSIDE BUDGET. 100 x 200 is not: its median is 98% and it peaks over. That is the whole of the reason, and it makes the number a measurement rather than a preference. THE MEDIAN REPRODUCES, THE PEAK DOES NOT, WHICH IS WHY THE PEAK DECIDED IT. The same candidates were measured twice in separate runs: 100 x 150 gave 800 ms and then 810, 100 x 200 gave 941 and then 981 - the medians agree to a few per cent. The WORST cases moved much more (100 x 200: 1,026 then 1,225), so a volume chosen on its median alone would have been chosen on the more flattering of two figures. WHAT THE AMENDED REQUIREMENT NOW SAYS THAT THE OLD ONE DID NOT. It names the figure to re-measure: the two Overall tables are (projects + people) rows x horizon months, so 50 x 200 and 100 x 150 are the same rendering problem - 252 rows - and measured within 10 ms of each other. A requirement that named only projects could be doubled by a reader who thought they were staying inside it. It also names where the cliff is - about 400 people - so the next person to ask for more volume knows what it costs before they ask. REQ-DSH-09 LOSES THE VIRTUALISATION CLAUSE AND KEEPS EVERYTHING ELSE. The chart cap stays, because a chart of 200 bars is unreadable at any speed and that is not a performance question. Panel-level scrolling with a frozen header stays. And the one property that matters whether or not rows are virtualised is stated outright: sorting, filtering and totals run over the WHOLE MODEL, never over the drawn slice. X-04 IS NOW 'NOT BUILT, NOT REQUIRED' RATHER THAN AN OPEN DEFECT, with the figures in the entry. It spent five weeks recorded as built, one revision recorded as a defect, and is now recorded as a decision - which is the only one of the three states that a later reader can act on. The desktop plan's A-N01 inherited the old volume by restating it; it now inherits REQ-NFR-03 BY REFERENCE, so the next time this figure moves that document does not silently go stale. AND THE GUARD GAINS THREE CHECKS, FROM THREE BREACHES FOUND WHILE MAKING THIS CHANGE. None was about the figures; all three were the same failure as the one v2.55 diagnosed - a fact kept in two places, with only one of them checked - so each is closed by a check rather than by a resolution to remember. (1) NO HISTORY ROW FOR ITS OWN VERSION. The desktop plan was issued as v1.13 and the desktop specification as v1.5, and NEITHER carried a version-history row for the version on its own cover. REQ-VC-04 requires one of every re-issue, and this is the document set whose own subject is keeping versions in step. Both are back-filled from the change that made them - NR-DEP-17, the console window that outlived its browser - and every controlled document is now checked for a row naming itself. (2) THE CONTRACT STILL PINNED COMPONENT LIST v1.0. There were THREE copies of 'which component list is current' - the application's provenance strip, the path check_consistency.py reads, and prap_contract.UIL - and only the first two were ever compared. So UIL sat at v1.0 from August, straight through the v2.0 re-issue, and docs/PRAP_Manifest.json, the AI agent guide and its workbook all told a reader that the APPROVED v1.0 was the document in force. That manifest is the file the README tells people to trust over filenames, which is what made it worth finding. The contract's pins are now held to the application's provenance strip. (3) THE README CALLED v2.40 CURRENT. Its document index labelled development plan v2.40 and specification v1.14 'current' while v2.57 and v1.28 were in force - eighteen revisions of drift in the file a newcomer reads first. The 'current' labels are now held to the manifest. Only the label is checked, not the prose beside it: a thin summary is not a false one, but a stale 'current' is. BREACH (2) WAS FOUND BY CHECK (3), two artefacts downstream and within a minute of its being added, which is the argument for adding checks rather than for reading more carefully. Each of the three was made to fail on purpose before being trusted. | Issued for review
2.57 | 2026-09-13 | Claude Code | Pending | MEASURED AT THE SCALE ACTUALLY IN USE, AND X-04 LOOKS DIFFERENT FROM THERE. Asked at review to re-measure against 50 projects x 100 people rather than the 100 x 1,000 REQ-NFR-03 names. Done, across a range, so the shape of the curve is visible rather than one point of it. 50 projects and a 60-month horizon throughout; the figure is how long the Overall tab takes to switch to, against a 1,000 ms budget fixed before any number was seen: 50 people 369 ms (37% of budget) ¦ 100 people 503 ms (50%) ¦ 200 people 786 ms (79%) ¦ 400 people 1,044 ms (104%) ¦ 1,000 people 3,207 ms (321%). THE BUDGET IS CROSSED AT ABOUT 400 PEOPLE. Below that the application is comfortable and row virtualisation would change no number anybody feels; above it the Overall pair is the binding cost, exactly as X-04 describes. AT 50 x 100 EVERYTHING IS INSIDE BUDGET with room to spare: import 814 ms against 5,000, the Overall tab 503 ms against 1,000 and worst case 669, editing a cell 67 ms, opening a column filter 45 ms, 152 rows and 9,272 cells, 16 MB of heap. The tightest measurement of any kind is 55% of its budget - about a factor of two of headroom before anything needs doing. SO THE QUESTION IS NOT WHETHER TO BUILD VIRTUALISATION. It is which volume this application is for. At 100 x 1,000 it is a real defect and the figures say so: the tab is 3.3x over and the import 1.7x, of which 3,590 ms is the CALCULATION - 180,160 person-months - which virtualisation cannot touch, so building it would answer the tab and about half the import. At 50 x 100 there is nothing to fix. THIS ENTRY CHANGES NO REQUIREMENT. REQ-NFR-03 still names 100 projects and 1,000 people, and until that is amended X-04 stands as an unmet requirement with its cost now measured rather than argued. Amending it is a decision about what the application is for, which is not a decision to take inside a documentation pass. tools/build_stress_workbook.py takes --projects and --people, so any volume can be re-measured with tools/measure_scale.py in a few minutes. The fixtures are not committed: generated filler, reproduced from a fixed seed by one command. | Issued for review
2.56 | 2026-09-13 | Claude Code | Pending | TWO THINGS FROM THE SAME REVIEW: the guard that should have caught the drift, and the measurement that settles X-04. THE COMPONENT LIST IS NOW CHECKED LIKE EVERYTHING ELSE. check_consistency.py gains four checks over it: no component may cite a requirement the plan does not have; every REQ-DSH-* must reach at least one component; every panel heading in the source and every dialog in the page must be NAMED somewhere in the list; and the version must match the one the application's own provenance claims. The panel check is the one that matters - it is the exact shape of the drift - and it immediately found a SIXTH stale entry that reading had missed: A-01 was still called 'Standard period weights' over the sheet PeriodWeightStandard, both renamed at R-33. Each check was made to fail on purpose before being trusted. X-04 IS A REAL DEFECT, AND THE MEASUREMENT SAYS SO. A fixture at exactly the volume REQ-NFR-03 names - 100 projects, 1,000 people, 8,000 assignments, 60 months - was built and driven (tools/build_stress_workbook.py, tools/measure_scale.py). Budgets were fixed before the numbers were seen. THE OVERALL TAB TAKES 3,058 ms TO SWITCH TO, worst case 4,537 ms, against a 1,000 ms budget: three times over, drawing 67,222 cells in 1,102 rows. That is the cost row virtualisation removes and it is exactly the two tables X-04 names. IT IS NOT THE WHOLE STORY, WHICH IS WHY THE MEASUREMENT WAS WORTH TAKING. The import at that volume is 7,328 ms against 5,000, and 3,076 ms of it is the CALCULATION - 180,160 person-months. Virtualisation touches neither that nor the workbook parse, so building it answers the tab and roughly half the import, not all of it. A first pass at this measured only the import, saw one number over budget, and was about to blame virtualisation for a cost virtualisation cannot reach; splitting the stages is what stopped that. WHAT IS ALREADY FINE AT FULL VOLUME: editing a cell 98 ms, opening a column filter 49 ms, scrolling the tall table 0.1 ms a step, the project tab 404 ms and the person tab 935 ms. The two short tabs are not the question; the Overall pair is. AND THE HORIZON IS PART OF THE ANSWER. The same Overall tab switches in 632 ms at the default 24 months and 3,058 ms at 60, because the tables are rows x MONTHS. Measuring at the default would have reported no problem and been wrong. No code change in this entry. The defect is recorded with its figures so the decision to build or to move the requirement is taken on evidence. | Issued for review
2.55 | 2026-09-13 | Claude Code | Pending | THE UI COMPONENT LIST CATCHES UP, AND ONE REAL FINDING COMES OUT OF IT. Raised at review: the application had changed many times while that document stood still. It had. v1.0 closed the Step 3 gate against plan v2.0; thirty-four change requests later it described an application that no longer existed. Re-issued as v2.0: 22 components added, each naming the change request that introduced it, and FIVE EXISTING ENTRIES CORRECTED because they had become not merely stale but WRONG - a missing entry leaves a reader uninformed, a wrong one leaves them misinformed. IT DRIFTED FOR A MECHANICAL REASON. check_consistency.py holds the plan, the specification, the template, both dummies and the contract to each other on every build, and has been clean throughout - but the component list was not in that set. It was the one artefact nothing checked, so it fell behind in silence while everything else was kept in step automatically. FOUR OF THE FIVE CORRECTIONS ARE EDITORIAL: the export writes eleven sheets and the list said ten; there are six summary tiles and it said five; 'No legend' is true of the chart it was written about and false of the five others; and the 'Mean load per person' bar chart it recorded as unchanged does not exist, having been replaced by the stacked 'Monthly demand by person'. THE FIFTH IS NOT EDITORIAL AND NEEDS A DECISION. X-04 recorded row virtualisation as 'Keep - unchanged', which reads as built. It was never built: there is no virtualisation anywhere in src/, and both Overall tables render every row. At the sizes in use that is fast enough and the chart caps keep the drawing bounded, but REQ-DSH-09 and REQ-NFR-03 name a THOUSAND PEOPLE, and at that size this is an open performance risk that has been carried as done since August. It is now recorded as NOT IMPLEMENTED so it stops passing for finished. The choice is to build it or to move the requirement; this entry does neither, because that is not a documentation decision. No code change, no schema change, no figure moves. The v1.0 review trail is preserved exactly - the reviewer's words, the decisions, the confirm marks - and the 22 additions carry 'Added after approval' rather than a disposition nobody gave them. Component list v2.0. | Issued for review
2.54 | 2026-09-12 | Claude Code | Pending | R-46: MonthlyEstimate.edited_at IS RETIRED. Schema 11 to 12, and the FIRST column this schema has removed rather than added or renamed. IT COULD NOT DO THE JOB IT WAS ADDED FOR. The column was 'when this figure was last set, so a reader can tell a figure somebody typed from one the application copied across on switching' - the distinction REQ-CAL-18 creates, because switching to manual seeds every month at its calculated value and those seeded figures sit in the same column as the ones somebody then types. Three findings, all measured against the running application rather than read off the source. ONE: the ordinary editing path never stamped it. Typing 0.77 over a stated 0.35 in the Monthly estimation table left edited_at null. It was written in exactly three places - the switch, 'fill the missing months', and the gap dialog - none of which is a person typing a figure, which is the single action it existed to mark. TWO: where it WAS written it was not a date. MonthlyEstimate never declared it a date column, so the model rebuild coerced the value to text and the cell held 'Sat Sep 12 2026 10:58:24 GMT+0000 (Coordinated Universal Time)' - saved as a string, not a date serial, unsortable in Excel, and formatted by whichever machine and locale happened to write it. THREE: nothing read it. The engine carried it to every manual line as manual_at and no export, report, screen or rule ever asked for that field. THE QUESTION IT ASKED IS ALREADY ANSWERED, PROPERLY. Every edit pushes a change-log entry carrying the time, the sheet, the row, the column, the value before and the value after, and that log is archived to the shared folder on Save with the editor's identity on it. Two answers to one question is the arrangement that drifts, and this was the worse of the two: partial, mistyped, and read by nothing. Fixing it instead was considered and is recorded here because it is the obvious alternative: stamp every write to fte and declare the column a date. That buys a second, weaker copy of what the change log already holds, and keeps a column in the source workbook whose value the user cannot be responsible for. A FILE WRITTEN TO SCHEMA 11 STILL OPENS AND STILL SAVES. Retiring a column has the same hazard at the edges as renaming one, so it gets the same courtesy: a new RETIRED_COLS map drops the column on the way in and tells the reader once, and the JSON interchange reader drops it too rather than refusing the file over a column this application asked for and then stopped wanting. Nothing is migrated, because there is nowhere for it to go. No calculation change and NO FIGURE MOVES. Template v1.16, dummies v1.18 and v1.10. tools/test_retired.py is new. | Issued for review
2.53 | 2026-09-12 | Claude Code | Pending | R-45, REQ-DSH-16: FIVE THINGS ABOUT READING THE SCREEN, all reported from the field, none of them a change to a figure. ONE. THE TWO UTILISATION CHARTS GROW WITH THE HORIZON. They were a fixed 1,080 wide whatever the span, which is right for the two years almost everybody opens on and wrong for the long plans that most need reading: five years is sixty columns in 790 points of plot, thirteen points each, and a three-letter month does not fit in thirteen points - so the axis ran its labels into one another exactly where the chart stopped being optional. Each month is now guaranteed 32 points and the panel scrolls sideways past the point where they all fit, which is what every other chart on the page already did. 32 rather than a rounder number so that at 24 months the chart is EXACTLY the width it has always been and this change is invisible to anyone who did not need it. TWO. ASSIGNMENTS, WEIGHT OVERRIDES AND MONTHLY ESTIMATION ARE ONE COLUMN, NOT TWO. They were a two-column grid, so each of three wide tables - eleven columns, seven and eight, one of those a sentence of arithmetic - had half a screen and all three scrolled sideways permanently. Stacked full width they also read in the order they are worked in: pick the assignment, then its override windows, then its months. THREE. MONTHLY ESTIMATION NAMES ITS ASSIGNMENT. It is a child of the row selected above it and said so nowhere - eight columns of months with no statement of what they belong to. It now carries the same line Weight overrides carries, word for word from one helper so the two cannot drift: the id, the project, the role, the window and the weight. FOUR. CLICKING A LEGEND ENTRY PICKS THAT SERIES OUT OF THE CHART. Twenty bands in twenty shades of one palette read perfectly well as a total and not at all as a series; finding one project in the stack by colour alone means carrying a swatch in your head down sixty months of bars. Everything that is not the picked series fades back; a second click, another entry, or Escape brings it home. THE PICK APPLIES TO THE WHOLE TAB, because the question is 'where is this project on this page' and not 'where is it in this one drawing' - the trend line, the stack and the timeline all mean the same project by the same id, so one click answers it in all three. A CHART CUT ALONG A DIFFERENT AXIS IS LEFT ALONE: a person's id means nothing to a chart stacked by project, and dimming it anyway would fade a whole chart to nothing and light none of it, which reads as 'this has no data' rather than 'you asked something this chart cannot answer'. A timeline band is a period OF a project and carries both keys, so picking a period lights it across every project and picking a project lights that project's whole row. Marks belonging to the MONTH rather than to any series - the threshold lines, the baseline, the outline that marks a month off its standard - never fade. Every entry is a real button: focusable, operable from the keyboard, and it states whether it is pressed (D-04). FIVE. EVERY HEADING SAYS WHAT THE COLUMN MEANS, AND ONLY THAT. The tables used to show the workbook's own column names: work_scope_type, outsourcing_scope_det, absorbed_by, ref_id - legible to whoever wrote the schema and opaque to the person filling the plan in. The meaning was only ever a hover away, which is to say invisible to anyone who did not know to hover. The heading now prints the plain name and nothing else. THE COLUMN'S OWN NAME IS IN THE POP-UP, NOT ON THE PAGE, and this was decided twice. It was first put on a second line under the label, on the reasoning that the screen and the file are the same thing, so a heading you cannot find in the spreadsheet is one you cannot quote in a mail or look up in a document. That reasoning was right about the NEED and wrong about the PLACE, which the reviewer said plainly: the need is occasional - you go looking for a column name when you are editing the workbook or chasing a finding - and the heading is read on every glance by everyone. Paying for a rare need out of the common one is the wrong way round when the pop-up already answers it in full. Every heading now carries a pop-up naming both, and the identifier is on the element as data-cid for whatever needs to read it. The badge on a derived column names the plain name too - a heading row that has stopped printing identifiers must not keep one in a badge. NOTHING IS RENAMED: the file keeps its columns, every validation message still names them, and the cell still writes back through the identifier. The same head is used on the heading's pop-up, on every cell's and on the filter buttons', so it is learned once. ONE DEFECT EXPOSED, NOT CAUSED, AND FIXED. Widening those three panels put a table into a gap no layout before it had landed in: the two drawn scroll bars decide each other, each costing the region 15px of its own space, and paintCue measured once - so a region that only overflows sideways ONCE ITS OWN VERTICAL BAR IS DRAWN got no horizontal bar, which is exactly the failure REQ-DSH-13 exists to prevent. Measured on the 62-project fixture: scrollWidth 1316 with both flags off and 1318 with the vertical bar there, against a client width of 1316 - two pixels, which is why no earlier layout met it. The flags are now settled before anything is drawn, and it cannot oscillate because padding can only create overflow, never remove it. Found by the REQ-DSH-13 check in test_ui, which failed on this build and passes on the fix. No calculation change, no schema change and no figure moves. tools/test_screen.py and tools/test_labels.py are new, 33 checks between them; test_columns and test_lookup read the identifier from the heading's second line. | Issued for review
2.52 | 2026-09-12 | Claude Code | Pending | R-44, V-35: capacity_fte IS BOUNDED, 0.00 TO 1.00. Reported from the field. It is the one figure on the Person sheet with a hard ceiling and it did not have one - 1.5 went in, was believed, and sat beside everybody else's 1.00 as though it meant something. capacity_fte is how much of ONE PERSON there is; 0.00 is allowed, because somebody on the books and not available is a true thing to say. IT REFUSES, WHICH IS A DEPARTURE AND IS THE POINT. Every other rule added this year reports rather than refuses - V-31 to V-34 all leave the decision with the user, because a period weight, a role factor and a stated month are judgements somebody is entitled to make. A capacity of 1.5 is not a judgement. It is a number in the wrong unit, the usual cause is hours typed into an FTE column, and the moment of entry is the only one at which the person who knows what they meant is still there to be asked. The message names the unit, does the hours-to-FTE arithmetic, and says what to do instead: two assignments, or a person weight above 1.00 on one of them. FOUR PLACES ENFORCE IT, and the fourth is the one that matters most in practice. The application refuses the edit; prap_io and verify_source_workbook raise the same rule at the same severity, because the four-implementation rule applies to what the application REFUSES exactly as it applies to what it calculates; and the TEMPLATE now carries a decimal range on the column, so Excel stops the figure where people actually type it, with a message of its own rather than the generic one. A FILE THAT ALREADY BREAKS IT STILL OPENS - checked, because the alternative would be a rule that locks somebody out of their own plan. Both the save and the edit path compare the COUNT of blocking findings before and after, so a pre-existing breach is reported and only the edits that would make matters worse are stopped. V-22 stands down on an out-of-range row rather than piling on. Template v1.15, dummies v1.17 and v1.9 - the schema is UNCHANGED at 11; only the guard rail is new. No calculation change and no figure moves. tools/test_capacity.py is new, 22 checks across all four places. | Issued for review
2.51 | 2026-09-11 | Claude Code | Pending | R-43: THE STATED CELL IS EDITABLE FOR EVERY PERSON IN THE DIALOG, not only for those already on manual. Reported from the field, and it was the most important half of the section missing: a gap is usually somebody ELSE's figure, and the person whose figure you want to change is very often still on automatic - for whom the cell rendered as a dash, which reads as 'this screen is read-only for them'. THE RULE THAT MADE IT A DASH IS STILL THE RULE, and it is why this is not a one-line change. An automatic assignment ignores MonthlyEstimate entirely, so a lone row written against it is a figure nothing reads; and setting estimation_type without seeding the other months counts every one of them as 0.00, the one change in this application that silently zeroes a figure (REQ-CAL-18). estimation_type has one way in for exactly that reason, and typing it into a cell is refused everywhere else. SO THE CELL ASKS. Type a figure against somebody on automatic and the dialog names how many months will be stated, what they total, and what this month becomes - then the switch, the seeding of every month and the typed figure are applied together, or none of them are. Somebody ALREADY on manual with no figure for that month is the V-31 case and is NOT asked: the months are already theirs, and asking would be asking permission for something already given. A figure that is not a number is refused in the same words the tables use, and nothing is written. ALL OF IT THROUGH beginEditSession AND S.pending, so the switch, the seed and the change are three kinds of entry in one change list, undone together by Leave without change and archived together at Save. The generic cell handler now ignores a contenteditable cell with no data-sheet, which is what lets a creating cell carry its own handler instead of calling applyEdit with an undefined sheet and a NaN row. TWO THINGS WERE CONNECTED WHILE THERE. The Estimation column now reads MANUAL from the ASSIGNMENT rather than from whether this month happens to carry a row - an assignment on manual with a month missing was showing as 'auto', which is the opposite of what is wrong with it. And a row whose Applied is not its Stated now carries the V-33 mark, so two figures differing on one line is explained where it is seen rather than only in the estimation panel on another tab. No calculation change and no figure moves. tools/test_gap.py grows to 49 checks. | Superseded by v2.52
2.50 | 2026-09-11 | Claude Code | Pending | R-42, REQ-DSH-15, V-34: WHAT A PROJECT NEEDS AGAINST WHAT IT IS BEING GIVEN. RAISED AS 'a project's FTE differs from the sum of its people's', AND THAT PAIR CANNOT DIFFER - measured in three states before anything was built: projMonth is built FROM the lines, so it IS that sum, and REQ-OUT-06 rests on it. The pair that does come apart is DEMAND against APPLIED, and nothing reported it. Measured: a project needing 10.00 with one assignment cut to 1.00 shows 5.00, people 5.00, demand 10.00, no finding; the same project set manually to 5.00 gives the same three numbers and the same silence. A study needing ten people and staffed with five looked exactly like a study that only ever needed five. TWO OPTIONS WERE PUT AND NEITHER WAS TAKEN AS PUT. A tab of discrepancies is the surface you visit only once you already suspect a problem, and the findings report is already the list of everything wrong; a note in the hover pop-ups is right that the note belongs where the figure is, but a note you must hover for is nearly as silent as a tab. So: a RULE, a MARK, a TILE and a SECTION. V-34 rides four surfaces that already exist. The figure carries a mark in Resource by project and a dashed outline on the project's own utilisation chart, so nothing has to be hovered. A tile counts it beside the allocation tiles. And 'Standard vs staffed' sits on Overall under the tiles, listing every month. EVERY ROW OPENS THE MONTH AND LETS IT BE FIXED THERE - the requester's own addition, and the part that makes it a working surface rather than a report. The stated figures behind the gap are ORDINARY contenteditable cells over MonthlyEstimate, so the existing editing path validates, logs, marks and undoes them and there is no second way to change a figure. The dialog redraws itself after an edit; a panel still showing the gap you had just closed would read as an edit that did nothing. BOTH DIRECTIONS, COUNTED APART AND NEVER NETTED. Five short in September against five over in October sums to zero and is not a plan in balance - the tests hold that case explicitly. Amber for short and red for over, each with an arrow, because those two hues are the confusable pair and they are exactly the two directions (D-04). IT REPORTS AND NEVER GATES. A warning, so refuses() is false and Save is not held: departing from the standard is the point of a manual figure, and which figure is right is not the application's judgement. An all-automatic plan raises nothing, which is what keeps the rule worth reading. No calculation change and no figure moves. tools/test_gap.py is new: 32 checks, including that the month equals its people's sum in every state the fixture can reach. | Superseded by v2.51
2.49 | 2026-09-06 | Claude Code | Pending | R-41, REQ-DSH-14 EXTENDED: THE DERIVATION COLUMN NOW CARRIES THE WHOLE EXPRESSION, TERM BY TERM, rather than the period alone. Naming the period answered one of six inputs, and a reader who disagrees with an automatic figure needs to know WHICH of the six they disagree with. The project's month reads 'Before-Start-up (standard 2.02) × period weight (1.12) × month run (1.00) = 2.26'; a person's adds a second line, 'role factor (0.72) ÷ sharers (1) × person weight (0.25, no override) × coverage (1.00) = 18.3% of it → 0.41'. TWO HALVES, AND THE SPLIT IS THE CORRECTNESS OF IT. Since R-32 a person's figure is NOT the product of their own terms: those terms make a CLAIM, normalised against every other claim on the project-month to give a SHARE (REQ-CAL-19). The terms above multiply to 0.18 and the figure is 0.41. Written as one product the cell would assert an arithmetic the application does not do and would be wrong by whatever the other claims came to - so the demand is closed off with its own '=', and the person's terms end in a PERCENTAGE of it. AN OVERRIDE IS ONE TERM WITH TWO SOURCES, not two multiplied terms. A PersonPeriodWeight window REPLACES person_weight for the months it covers (REQ-PSN-05); the request asked for it as its own factor, which would have read as a multiplication that does not happen, so the cell names both values and says which was used: 'weight override (0.50, replacing person weight 1.00)'. EVERY FALLBACK NOW SAYS IT IS ONE and names its rule - V-19 for a missing standard, V-23 for a missing role factor, V-12 for a month in no period. A bare 1.00 is indistinguishable from a standard that really is 1.00, which is the whole reason those rules exist. Absorbed cover is named too, with the roles it came from (REQ-CAL-16). The sharer count KEEPS its own short column: the derivation is a sentence, and a sentence cannot be sorted or filtered, while '2 share this role' can. The cost of the change is that the derivation column is no longer a useful filter - it is now nearly unique per row - which is why the short column stays. No calculation change and no figure moves. | Superseded by v2.50
2.48 | 2026-09-06 | Claude Code | Pending | R-40, REQ-DSH-14: THREE LOOKUP COLUMNS, SO A TABLE SHOWING A FIGURE CAN SAY WHAT DECIDED ITS SIZE. Every figure in this application is standard FTE x period weight x (role factor / sharers) x person weight x month coverage, and three tables each showed one term of that and left the rest in another tab. (1) THE PERIODS TABLE now names the STANDARD MONTHLY FTE its period selects, beside the weight, and multiplies the two: 'Start-up 1.12 ¦ 2.02 -> 2.26 a month'. A row reading 'x1.12' said this study is an eighth heavier than usual and did not say heavier than WHAT - answerable only by leaving the tab and reading a 48-row matrix on General assumptions for one figure. (2) BOTH MONTHLY ESTIMATION PANELS name the PERIOD the month falls in and its weight, and (3) THE PERSON'S ALSO NAMES THE DIVISOR - how many people held that role that month. Those are the two usual explanations for a figure that is not the size somebody expected: the month moved into a heavier period, or a second holder arrived and halved the share. The project's panel deliberately does NOT carry the divisor: a project month is divided between several roles, each with its own count, so one number there would average things that do not compare. LOOKED UP, NEVER STORED. None of the three is a column of the sheet it sits beside, and the tests hold them to that - a standard copied onto a ProjectPeriod row would survive the standards being edited afterwards, which is the whole failure the lookup avoids. Read off the calculation's own lines, so a screen cannot name one period while the figure beside it came from another; calculate() now hands out periodAt for the one case the lines cannot answer, a manual project month with nobody assigned to it (V-32). A missing standard says 'none - V-19' rather than printing the 1.00 the calculation falls back to; that fallback is a degradation and showing it as a standard would hide exactly what V-19 reports. No calculation change and no figure moves. tools/test_lookup.py is new: a three-month fixture whose every figure is workable by hand, checking each column against the calculation's own line rather than against a plausible number. | Superseded by v2.49
2.47 | 2026-09-05 | Claude Code | Pending | R-39, PROJECT AND PERSON FIGURES KEPT CONSISTENT, AND SAID TO BE. (1) THE FIRST REQUEST WAS ALREADY THE BEHAVIOUR, which is worth recording rather than quietly re-implementing: a manual PROJECT month has always realigned every person on it, including anyone whose own figure is manual, because applyManual applies the assignment level first and then scales the whole group to the project's stated total. Verified: project set to 10.00 with a person stating 99.00 gives the person 9.97 and the month 10.00. The project figure is the mother figure and wins. (2) WHAT WAS MISSING IS THAT NOTHING SAID SO. The sheet held 99.00, the chart showed 9.97, and nothing connected them. Now V-33 reports it; the Monthly estimation panel carries a table of stated against actually-given against the project's month; the cell is marked; and editing such a figure SOFT-STOPS at the cell - naming both numbers, offering Keep what I typed or Put it back. It never refuses: both numbers were typed deliberately and which is wrong is not the application's judgement. The finding reaches the findings report and the archived change log, so it is on the record either way. (3) automatic_fte and difference in the Monthly estimation tables were the last four-place figures on screen and are now two, like everything else (REQ-CAL-20). A stated 2.41 beside an automatic 2.4120 read as a discrepancy the user had caused rather than as four decimals nothing else uses. One defect found by testing the undo rather than by reading it: rebuild() makes fresh row objects, so the row reference captured before it was orphaned and 'Put it back' silently did nothing. It re-finds the row by number now. | Superseded by v2.48
2.46 | 2026-09-05 | Claude Code | Pending | R-38, THREE REQUESTS. (1) THE IN-APP EXPORT OF THE CHANGE LOG IS REMOVED. The archive is written at every save, so a button handing over the same record afterwards was a second answer to one question and always the staler of the two. The menu items, the date range, the CSV download and the code behind them are gone rather than hidden. (2) THE ARCHIVE IS ONE FOLDER FOR THE INSTALLATION, beside users/ rather than inside any one person's copy of it - the layout PRAP_DATA and the shared-drive deployment already assume (NR-DEP-15). A log split per person answers 'what did I do' and not 'what happened to this plan', and on a shared deployment only the second question is worth asking; every row already names who made the change. NOT YET BUILT, and stated so the gap is not mistaken for done: a CENTRAL SERVER needs network binding, real authentication and sessions, per-user authorisation and concurrent-write handling. The shell today binds to 127.0.0.1 and refuses non-loopback Host headers BY DESIGN - that refusal is what makes an open socket on a company laptop defensible - and 'login' is the Windows account name, a label rather than an authentication. Replacing that is a security-sensitive piece of work to be specified before it is started. (3) REQ-CAL-20, THE DECIMAL RULE - see the requirement for the whole of it. EVERY FIGURE IN EVERY PLAN MOVES slightly: the 62-project fixture goes 4,333.46 to 4,333.77 FTE-months and the 10x10 fixture 713.94 to 713.78, which is the rounding and nothing else. Checked on the 62-project fixture: all 7,001 lines are whole hundredths, all 1,629 project-months have their lines summing to the month with nothing left over, and all 1,557 automatic months still equal standard x weight x month_run to the hundredth. All four implementations agree line for line - 7,001 lines and 1,629 project-months identical between the browser and prap_io. | Superseded by v2.47
2.45 | 2026-09-05 | Claude Code | Pending | R-37, THE POP-UPS NAME THE PROJECT PERIOD. Every figure in this application is standard FTE x PERIOD WEIGHT x the month the project ran, so the period is the row of the plan that decided the size of whatever is being hovered over - and it was the one thing the pop-ups did not say. A reader who thought a month looked heavy had to leave the chart, find the project and read its periods to learn the month was mid-Conduct. All four charts named in the request now carry it: both Overall stacks, and Utilisation on each source-data tab. The WEIGHT goes with the name, because the two are one fact - which row applied, and what it did to the figure. READ FROM THE CALCULATION, not looked up again. calculate() already stamped period_name on every line, so it now also returns projPeriod (project¦month -> name and weight) built from those same lines, exactly as projMonth and persMonth are. A second lookup could name one period while the number beside it came from another; this cannot. Checked on 154 project-months against S.calc.lines, all matching, and the check fails if the tooltip line is removed. WHERE ONE BAND SPANS SEVERAL PROJECTS - the person stack and the person Utilisation chart - the period is tagged against EACH PROJECT rather than against the band, because a person's month is made of projects that need not be in the same period as each other; the delivered fixture has a person in Conduct (final) on one project and Conduct (interim) on another in the same month. A month belonging to no period says so and names V-12, rather than leaving a blank that reads as a defect in the chart. No figure moves. | Superseded by v2.46
2.44 | 2026-09-04 | Claude Code | Pending | R-36, A CHANGE LOG AND COLUMN FILTERS. Two requests; no figure moves for either. (1) THE CHANGE LOG. Every saved change is recorded - the time in UTC, who, which RECORD (its natural key, not its spreadsheet row: inserting a row renumbers everything under it and PRJ-004 does not move), which column, and the value before and after - together with the errors and warnings standing at each save and which of them the user was asked about and chose to keep. It is NOT S.pending: that is emptied at every save because its job is 'what is not saved yet', and this is only ever appended to, with a save being what WRITES it rather than what clears it. Asked for as an in-app tab first and then narrowed by the requester to 'in memory while the session runs, archived to a local folder on Save, CSV is enough' - so there is no tab and no schema change. THE DESKTOP SHELL archives it: an `audit` folder beside the workspaces, one CSV a month, header written when the file is created and rows APPENDED at every save. THE BROWSER CANNOT do that - a file:// page has no folder and cannot append to one - so it holds the record for the session and hands it over from Export, narrowed by a date range, which was the other half of the request. A failed archive never fails a save: the entries stay and the next save carries them too. WHO: the desktop shell takes the Windows account it already signed in with; the browser asks once, in the EDIT BAR rather than in a dialog - a modal blocks the cell being typed into, and a floating card sits on top of the table. Both were built and both were wrong before the bar was tried. (2) COLUMN FILTERS on the six tables named: Projects, Monthly estimation (both tabs), People, Standard period FTE for project types and Role factors. A spreadsheet's filter - tick the values to keep, different columns narrow together, and the values offered are what the OTHER columns leave reachable. It narrows the TABLE and not the plan: the charts and totals above are unchanged, because a row hidden here is still in the plan, and the horizon-and-filters bar remains the one control that changes what the figures mean. Two new suites, test_audit.py and test_colfilter.py; the storage seam budget in test_layers.py re-baselined 150 -> 220 and the reason recorded, since the seam legitimately gained a third responsibility. | Superseded by v2.45
2.43 | 2026-09-04 | Claude Code | Pending | R-35, TWO FAULTS IN THE DATE PICKER, both reported from the field and both reproduced before being touched. (1) THE MONTH ARROWS MOVED ONE MONTH AND NO FURTHER. step() re-read the cell and snapped the grid back to the cell's own month before stepping, so a cell holding 2026-09-01 went to August and stayed at August however many times the arrow was pressed - a date several months away could not be reached by navigating at all. It had a workaround that did not work: blank the cell, render, put the text back, which step() then defeated by re-reading before it rendered. The grid now knows WHO IS STEERING - the cell while it is being opened or typed into, the user while they are working the arrows - and the cell keeps its text throughout. (2) 'TODAY' WROTE THE DATE IN GREENWICH, not on the user's clock. ymd() is toISOString(), which is right for every other date in the application because those are built with Date.UTC(); `new Date()` is an instant, and putting an instant through a UTC formatter asks what day it is in London. In Seoul before 09:00 that is yesterday; in Los Angeles after 17:00 it is tomorrow. The local getters now read the date off the user's own calendar and Date.UTC puts it back into the form the rest of the application stores. The same figure highlights today in the grid and opens an empty cell on the right month. NO CALCULATION CHANGES. test_ui.py gains both: five clicks must move five months (the old test stepped ONCE, which is why this passed for so long - one step did work), and Today is checked in three time zones on a pinned clock, because CI keeps UTC and in UTC the wrong answer and the right one are the same answer. Both verified to fail against the old code. | Superseded by v2.44
2.42 | 2026-09-04 | Claude Code | Pending | R-34, THE PROJECT DEMAND CHART SAYS WHAT ITS MONTH CAME TO. 'Monthly demand by person' ended its pop-up with a rule and the month's total across everyone in view, and gave each band its share of that month; 'Monthly demand by project' gave neither, only the band's own figure. A band read on its own cannot say whether the month came to five FTE or to fifty, which is the question a stacked chart exists to answer - so the reader had to leave the chart and find the Overall table to interpret what they were hovering over. Both are added, worded to match the person chart. The total is summed over every project IN VIEW rather than over the bands actually drawn, for the same reason the person chart sums over every person in view: so the two pop-ups report the SAME figure for a given month, which is what the panel caption already claims about these two charts. Checked on the 10x10 fixture - 24 months, every one identical between the two, and the per-band shares summing to 100% (+/-1, rounding to a whole percent) in all 24. NO FIGURE CHANGES: the total is the sum the chart was already drawing. test_charts.py gains two checks. It already compared the two charts as DRAWN, in pixel heights; these compare what they SAY, which is what a reader acts on - that every band states a month total, and that the total it states is the one the person chart states for that month. Both were verified to fail with the line removed from the build. | Superseded by v2.43
2.41 | 2026-09-04 | Claude Code | Pending | R-33, WHAT THE STANDARDS SHEET IS CALLED, and the notes that describe the calculation. Three things the reviewer reported after using v2.40, none of them arithmetic - every figure in this revision is unchanged, checked at 4,333.46 FTE-months on the 62-project fixture before and after. (1) SHEET RENAMED PeriodWeightStandard -> PeriodFTEStandard, and the panel over it from 'Standard period weights' to 'Standard period FTE for project types'. Schema 10 renamed the COLUMN to standard_fte when it became clear the sheet holds a magnitude in FTE rather than a multiplier; the sheet and the panel went on saying 'weight', which is the reading that made the standards look ignorable in the first place - R-32 exists because of it. Source schema version steps 10 to 11. A schema 10 workbook still opens: the old sheet name is translated on the way in and the reader is told once, exactly as a renamed column is. (2) THE CALCULATION NOTES on the monthly-estimation panels still described the pre-R-32 formula - four factors multiplied together - which has not been how a figure is arrived at since v2.40. They now state it as it is, and separately for the two levels, because under R-32 the two genuinely differ: a PROJECT month is standard FTE x period weight x the part of the month the project ran, and an ASSIGNMENT month is that month divided by share, the share being (role factor / sharers) x person weight x coverage against everyone else's. Same correction to the automatic_fte and ProjectPeriod.weight column help and to the switch-back dialog. (3) THE WINDOW CHROME OVERLAPPED THE PAGE in the Python shell. Its menu bar and status strip are sticky at the top of the window and the page's own sticky band - the edit bar and the four tabs - pinned itself to the same place with a lower z-index, so scrolling slid the tabs and the Save button underneath the File menu. The band now sits below the chrome, at the chrome's MEASURED height: both bars wrap, so a constant would have been wrong exactly when it mattered. | Issued for review
2.39 | 2026-09-02 | Claude Code | Pending | R-31, REQ-CAL-19, SCHEMA 10: THE STANDARD IS WHERE A FIGURE GETS ITS SIZE, and until now it reached no figure at all. PeriodWeightStandard seeded a derived period's weight and fed V-19, and that was the whole of it: every number the application produced came from ProjectPeriod.weight times the role factors, which is a relative SHAPE with no magnitude behind it. Reported by the reviewer. Two things were wrong and the naming was most of the cause. The column was called `weight`, which reads like something to multiply by, so the calculation multiplied by the PROJECT's weight and never asked the standards sheet anything; and the delivered data seeded the project weight FROM the standard, so the two columns held the same number twice and reading both would have squared it. The column is now `standard_fte` and holds the month's DEMAND in FTE - 4.02 against NewDrug CT Phase 3 Start-up means that period takes about four full-time people a month. The formula becomes standard_fte x period weight x role_share x person weight x month coverage, where role_share is this role's effective factor divided by the people holding it, over the sum of the effective factors of the roles ACTUALLY STAFFED. Three consequences, each a decision the reviewer took: the shares add to one, so a fully committed project-month IS standard x period weight however many roles are on it; an unstaffed role's work lands on the others rather than making the project cheaper, which is REQ-CAL-16 arriving by construction (absorbed_by still decides WHERE it lands); and person_weight scales that person's share, so a part-time commitment leaves the project SHORT of its standard, which is the gap worth seeing. A missing standard falls back to 1.00 and V-19 reports it - deliberately the old behaviour, so an incomplete standards sheet degrades to figures its author recognises rather than to zero. stdWeight now nulls the phase for a non-clinical type exactly as stdFactor does; that cost nothing while the figure only seeded a period and is the difference between a real answer and 1.00 now. The delivered defaults are re-authored throughout: the standards carry FTE magnitudes, ProjectPeriod.weight becomes an adjustment around 1.00, and 'Others' projects gain the standards they never had. A schema 9 file still opens - the column is renamed on the way in. NOTE FOR THE REVIEWER: with real magnitudes the delivered 62-project / 20-person example is resourced at 17% of its own standard, which is arithmetic rather than a defect - 62 concurrent trials at these standards need about 59 people. The fixture keeps the size that was requested; the staffing assumptions are a data decision. | Issued for review
2.38 | 2026-08-30 | Claude Code | Pending | R-30, REQ-CAL-18, SCHEMA 9: A FIGURE CAN BE STATED INSTEAD OF CALCULATED. Until now every monthly FTE came from the assumptions, and on a project two years in that is often the worse of the two available answers - the manager knows what the rest of it takes, and a standard period weight multiplied by a standard role factor does not. Project and Assignment each gain estimation_type ('automatic' or 'manual'), and a new sheet MonthlyEstimate carries the stated figures, keyed on (scope, ref_id, month) so one sheet serves both levels. TWO LEVELS, applied in that order: an ASSIGNMENT figure IS that person's contribution and replaces the multiplication outright; a PROJECT figure is the whole month, and the people on it are SCALED so they still add up to it - chosen over the alternatives because a project total that did not equal the sum of its people would put the two utilisation charts in disagreement and cost the results export its one real guarantee. The scaling factor is recorded on every line, so a person whose figure moved without anything of their own changing can find out why. MANUAL IS ALL OR NOTHING for the thing it is set on: switching copies EVERY month across from the figures currently on screen - to TWO DECIMAL PLACES, because a stated figure is one somebody reads and edits and 0.01 FTE is already 1.6 hours, so a month can move by up to 0.005 FTE at the moment of switching - so nothing jumps, and switching back discards the lot. That was chosen over per-month marking deliberately - once a figure has been edited, 'which months are still automatic' has no useful answer, because those would still move under a plan somebody has signed off whenever an assumption changed. What the user takes on in exchange is responsibility for all of them, and the confirmation says so in those words. EVERY CHANGE OF CALCULATION WAY IS CONFIRMED, in both directions, and typing 'manual' into the cell opens the same dialog rather than setting the flag - the flag without the copy would count every month as 0.00, which is the one change in the application that could silently zero a figure. V-31 reports a manual thing with a month carrying no figure; V-32 a project figure in a month nobody is assigned to, which cannot be shared out and is therefore NOT applied. Both are raised from the calculation, like V-23, because they are things that happened to a number. The stated figures round-trip through the source export, and the results export gains four columns - estimation, automatic_fte, project_manual_total, project_scale - so a reader can see which rows were stated, at which level, and what the assumptions would have said instead. Nothing moves on a file that uses none of it: test_app.py's four-way comparison agrees on all 1,227 and 441 person-months, and both dummy sets now carry a manual project and a manual assignment so the rule is under that comparison rather than in one unit test. | Issued for review
2.37 | 2026-08-28 | Claude Code | Pending | R-29, REQ-OUT-06: THE APPLICATION EXPORTS ITS ANSWERS AS WELL AS ITS QUESTIONS. Until now Export meant one thing - the plan, so it could come back - and there was no way to get the monthly figures out for a report, a spreadsheet or somebody else's model short of reading them off the screen. The export control is now a MENU with the choice on it: the plan as .xlsx or as the interchange file, both of which round-trip, or the CALCULATED MONTHLY FTE, which deliberately does not. Each item says which it is, so the choice can be made without trying it. The results workbook carries seven sheets: a ReadMe that states it cannot be imported and gives the formula; Summary, the Overall tab's tiles as figures; ProjectMonth and PersonMonth, one row each per month; DETAIL, one row per assignment per month carrying every term of the multiplication that produced it - period weight, the role factor before and after absorption, the number of sharers, the person weight and which row it came from, the month coverage; Flags, the over-allocated months and under-allocated runs; and Assumptions, the settings in force, marked for whether each one changed a figure or only its display. Two properties are held by test_results.py rather than asserted: every project-month and person-month is EXACTLY the sum of its Detail rows and all four totals in the file are the same number - the monthly sheets are summed FROM the detail rather than from the engine, so a reader who adds the column gets the total - and every Detail row reconciles to its own four numbers. The file covers what was ON SCREEN, horizon and filters included, and the ReadMe names them, so a file that has left the building can still say what it does and does not cover. The calculation now records each term as it works it out (calculate() returns `lines`), because an explanation assembled afterwards from the sheets could drift from the figure it claims to explain. | Issued for review
2.36 | 2026-08-28 | Claude Code | Pending | R-28, REQ-IMP-14: AN IMPORT SAYS WHICH SETTINGS IT BROUGHT WITH IT. Config stays in the source workbook and an import still applies it - that is deliberate and is what makes a plan reproducible from the file alone. What was missing was being told. A Config row is not like any other row in the file: every other sheet describes the PLAN, and replacing it is the point of an import, while Config describes how the plan is READ. Two of its settings switch calculation rules on and off and three more set the thresholds every allocation flag is measured against, so importing a colleague's workbook to look at their projects took their thresholds with it and every figure and flag on the screen shifted for a reason that was nowhere on it. Now the settings in force are captured before the model is replaced, compared by name afterwards, and any that differ are named on the banner with a screen of their own: what each one was, what it is now, and what it affects - calculation, flags or display only. Nothing is refused. It is a check, not a gate. Done in adopt(), which every import path funnels through - the web picker, the Python shell's open, a version restore and the difference report's apply - so it is asked once and asked of all of them. A first load has nothing to compare against and says nothing; a blank start counts as a baseline, because somebody who started blank, entered a plan and then imported over it is exactly who this is for. Also in this version: the reviewer confirmed that the display unit needs neither to survive an edit nor to reach the exported file - it is information while the application is open - so REQ-CAL-08 is unchanged and only the wording that read '3 informations' is corrected. | Issued for review
2.35 | 2026-08-27 | Claude Code | Pending | R-26: THE NOTE ON capacity_unit WAS WRONG, and wrong in the way that matters - it named a value the application has never understood. It read "Display unit: 'FTE' or 'percent'"; the two values actually implemented are 'FTE' and 'hours', and anything else, 'percent' included, silently displays as FTE. So a user following the note would type a value, see nothing change, and have no way of telling whether they had misunderstood the setting or the setting was broken. The note now says what the unit IS: FTE is a WEIGHT, 1.00 being one person working a full month on the project, so ordinary values run about 0.1 to 1.0 - and 'hours' is that same weight multiplied by fte_hours_per_month. It also says the setting is display only. Corrected in the one place it is written and carried from there into the template, both dummy sets, the blank start's seed, this plan, the specification and the machine-readable contract. Template v1.11, dummies v1.13 and v1.5. No code and no figure changes. R-27, THE SAME REVIEW: the Configuration table no longer offers 'Delete' - or '+ row'. Nothing references a Config row, so V-17 had no hold on a deletion and nothing refused it; nothing reported it either, because every setting is read through a fallback to a built-in default. Measured on the 10x10 dummy with a house floor of 0.80 and the shared-role division turned off, deleting those two rows moved the total from 356.64 to 346.59 FTE-months and said nothing at all. Removing the control is a better answer than confirming it: there was never a good reason to press it, since the nine settings are read BY NAME and what a user changes is a VALUE, which stays as editable as any other cell. '+ row' goes with it because a row that can be created but never removed is a worse trap than the one being closed. New rule V-30 covers the case the control is no longer responsible for: a workbook that arrives without a setting, hand-edited or from a version that predates it, is told which default is in force. | Issued for review
2.34 | 2026-08-27 | Claude Code | Pending | FIVE REVIEW POINTS, all about the application rather than the arithmetic - no figure moves. (1) R-21, REQ-IMP-12: A DATE COLUMN OFFERS A CALENDAR and stays typeable. Picking is what you want when the question is 'is the 14th a Tuesday'; typing is what you want on the twentieth row of a set you already know. So the panel is laid BESIDE the cell, never in front of it: the caret stays put, every key still reaches the cell, and what is typed steers the grid. Deliberately not <input type=date>, which would bring one editing model for text cells and another for dates. (2) R-22: THE PERIOD GENERATOR THAT FITS THE PROJECT. Auto derivation was offered on 'Others' projects, where it could only ever answer no - the rule hangs on CTA submission and the DB locks, which an internal project does not have and never will - and a control that refuses every time it is pressed teaches the reader the feature is broken. 'Others' is now offered Standard periods, which lays out Planning / Develop / Close with the dates blank; a trial not ready yet keeps the derivation, disabled, with the two missing milestones named, because that answer changes. The derivation itself was checked across all 62 dummy projects and is correct for all 50 trials. (3) R-23, REQ-DSH-13: THE APPLICATION DRAWS ITS OWN SCROLLBARS. Twice the browser was asked for a bar and twice it gave an overlay occupying no layout space - measured, a plain div with an explicit 14px ::-webkit-scrollbar still reports offsetHeight === clientHeight - so a table with eleven columns off to the right looked like one with none. Native scrolling is untouched. (4) R-24: THE STICKY BAND IS ONE ELEMENT, AND OPAQUE. Two independently sticky bars needed the second to know the height of the first, so a hairline ran between them that the page showed through, and at 92% opacity the rows underneath ghosted through the text. (5) R-25, REQ-IMP-13: WHAT AN ERROR IS ALLOWED TO DO is now a property of the rule, in three values. MUST refuses - something is wrong with the row itself. CONDITIONAL asks at Save, names what will be left unresolved and lets the user go ahead knowingly. INCOMPLETE reports and says nothing else - the row is still being built and asking would put a dialog in front of somebody every time they save a project they are half way through typing. The findings report and prap_io both label every error with its class. | Issued for review
2.33 | 2026-08-27 | Claude Code | Pending | TWO REQUESTS. (1) R-19: THE ROLE/FACTOR CHECK REPORTS, AND STOPS REFUSING ROWS - and it is asked on the right composition. V-28 was retired at v2.32 for refusing data entry, but it was only the newest of three rules doing it: V-03 and V-23 refused as well, and for the same reason, so the complaint came straight back. All of them ask one question - has anybody entered a factor for this role - and the answer 'not yet' is a fact about the ASSUMPTIONS, a standing document maintained separately and often by somebody else. The person really is on the project. So both keep their severity, because the figures for that role really are wrong, and neither can refuse an edit any more. V-23 is also re-asked properly: it is now raised BY the calculation, keyed on the whole composition the lookup uses (project_type, clinical_phase, work_scope_type, period_name, role_name) and counted in the person-months that were actually calculated at 1.00. Asked off the sheets it walked every period of every project an assignment belonged to and demanded a row for each, including periods nobody was ever booked into. (2) R-20, REQ-CAL-17: THE PROJECT'S WINDOW COMES FROM ITS PERIODS, NOT ITS MILESTONES. Milestones are reference dates - the derivation reads them to lay the periods out, and several of them mark moments inside the run rather than its edges. Taking the window from them stretched the project over months belonging to no period at all, which are costed at weight 1.00, so the utilisation chart grew a flat shoulder at each end that no period justified. Now: the earliest period_start to the latest period_end, with a project that has no periods keeping its own typed dates because there is nothing to take a window from. Save writes the same window back, reading the periods the user TYPED and falling back to the milestone span where there are none - a derived period opens at the project's own start_date, so reading the saved window back from it would mean a wrong window could never correct itself. Figures move where the periods and the milestones disagreed: the 62-project dummy goes from 1,225 to 1,227 person-months. | Issued for review
2.32 | 2026-08-26 | Claude Code | Pending | R-18: V-28 IS RETIRED, one version after it was added, because of what it did rather than what it said. An error refuses the edit that raised it (REQ-IMP-09) - that is deliberate and stays - and V-28 was the first error about the ASSUMPTIONS that could fire on a project with no periods. So it fired while a project was still being built, which is exactly when its assignments are typed in: a user could not record who was on the project until RoleFactor already carried a factor for their role. That is backwards. The plan is the document being written; the assumptions are a standing document maintained separately, often by somebody else, and entering the plan must not wait on them. The gap V-28 filled is real and is not being denied: V-03 still refuses a role that is not valid for the project type, and V-23 still reports a role with no factor for a period the project spans - the same finding, at the point where the user can act on it. V-27 is unchanged: it is about the project's own type, phase and scope, which are on the row being edited, and the delivered defaults cover every combination the value lists offer, so it does not stand between a user and their own data. REQ-CAL-16 and the absorption arithmetic are untouched - no figure moves. | Issued for review
2.31 | 2026-08-26 | Claude Code | Pending | TWO REQUESTS, and the second changes figures. (1) CROSS-CHECKS BETWEEN THE ASSUMPTIONS AND THE DATA: V-27 reports a project whose type, phase and work scope have no PeriodWeightStandard rows at all, and V-28 a role given to somebody on an assignment that has no RoleFactor rows at all. V-19 and V-23 already checked both, precisely - but only for periods a project actually HAS, so a project whose milestones are missing was never checked, and a combination nobody had entered was reported once per period rather than once as the one thing wrong. These ask the blunter question first, on the project. (2) R-17, REQ-CAL-16: WHERE NOBODY HOLDS A ROLE, its factor is absorbed by the role named to cover for it. A trial with no Clinical Data Associator still has the data to handle; it lands on the lead data manager, and a project costed without it looks cheaper than it is. Counted per month; one hop only; and WHICH ROLE COVERS FOR WHICH IS DATA - the new column RoleFactor.absorbed_by - because REQ-CAL-06 has said since the first plan that factors live in the workbook and never in the program. V-29 reports the case the rule cannot fix: an unstaffed role that nothing covers for, where the under-estimate remains and nothing else would mention it. Schema 7 to 8. A fifth of the dummy's projects now run without one of those roles, so the rule is under the four-way comparison rather than in one unit test. | Issued for review
2.30 | 2026-08-25 | Claude Code | Pending | R-16, SCHEMA 7: outsourcing_type becomes outsourcing_scope_det, and becomes FREE TEXT. Schema 6 put work_scope_type in the weights and left outsourcing_type beside it as a second controlled vocabulary on the same axis - two fields to keep in step, one of which decided nothing. It is now a note in the requester's own words: what is outsourced and to whom, the detail a category cannot carry. Three things follow. V-25 is RETIRED, because it existed only to police the two against each other and can no longer fire. The dashboard's scope filter moves to work_scope_type, since a drop-down built from whatever sentences people have typed is not a filter - and the field it used to offer is the one that no longer decides anything. And a workbook still carrying outsourcing_type is READ rather than refused: the column is renamed on the way in and the application says so once, because a rename is the one schema change that otherwise loses a filled-in column in silence. | Issued for review
2.29 | 2026-08-25 | Claude Code | Pending | R-15, REQ-CAL-15: BOTH ASSIGNMENT DATES ARE OPTIONAL, and a blank one means the project's own. Most people are on a project for the whole of it, and requiring two dates that simply repeat the project's asks somebody to copy the same pair onto every row and then keep them in step when the project moves. The end date already worked this way; the start did not, and a blank one was the worst of the three possible behaviours - the assignment contributed NOTHING, the person looked unassigned, and no finding said why. The window is now computed by one function shared by the calculation and by the role-sharing pre-pass, so the months a person is counted IN cannot differ from the months they are counted AMONG; an undated person is a sharer like any other. Roughly a third of the dummy fixture now leaves both dates blank, which is what a real file looks like and puts the inherited window under the four-way comparison rather than in one unit test. | Issued for review
2.28 | 2026-08-22 | Claude Code | Pending | TWO CHANGES, BOTH REQUESTED, AND THE FIRST CHANGES EVERY FIGURE A SHARED ROLE EVER PRODUCED. (1) R-13, REQ-CAL-14: where several people hold the same role on the same project in the same month, the role factor is DIVIDED BETWEEN THEM. The factor states what the ROLE costs the project in that period, not what each holder costs, so until now a trial staffed by two data managers cost twice a trial staffed by one - the same work, priced by how many people were named against it. Counted per month, so a sharer leaving restores the others without an edit; by distinct people, so one person on two rows is one person; and each person's own weight still applies to their share. Kept as the setting split_shared_role_fte, default 1, so a figure produced before this rule can still be reproduced and compared. (2) R-14: THE DELIVERED DEFAULTS. PeriodWeightStandard and RoleFactor arrived empty in the template and were filled with a placeholder 1.00 by a blank start - and 1.00 everywhere is not a starting point, it is the absence of one: at 1.00 the period weight and the role factor cancel out of the arithmetic entirely, so the application produced figures that looked like an answer and were not. Both now arrive filled in - 84 period weights and 429 role factors - defined once and read by the template, the blank start and the dummy datasets alike, so the workbook and the application hold the same assumptions by construction. check_consistency.py fails if they drift, and fails too if the figures ever revert to one flat value. A defect was found while testing: prap_io read Config with `or default`, so a setting deliberately set to 0 silently came back on. | Issued for review
2.27 | 2026-08-20 | Claude Code | Pending | SCHEMA 6 - THE WORK SCOPE, AND THE BIOSIMILAR SPLIT. Requested 2026-08-20, and the first change to the data model since the plan was baselined. (1) work_scope_type joins PeriodWeightStandard and RoleFactor beside clinical_phase, and the keys become (project_type, clinical_phase, work_scope_type, period_name) and that plus role_name. How much of the work is kept in-house changes how much of it lands on this team, and until now the model had nowhere to say so. (2) A ROW WITH AN EMPTY work_scope_type APPLIES TO EVERY SCOPE, and a project falls back to it when there is no row for its own scope. That is a judgment made here rather than requested: without it RoleFactor is 1,269 hand-entered rows instead of 429, two thirds of them repeating their neighbour, and every schema 5 file would stop calculating on the day it was opened. With it, a schema 5 file's rows ARE the every-scope rows and keep working. (3) Project gains work_scope_type, because the key selects a row FOR A PROJECT and nothing could choose between the three scope rows without it - implied by the request rather than stated in it. outsourcing_type stays, descriptive, and V-25 reports the two contradicting each other. (4) 'Biosimilar CT' becomes 'Biosimilar CT (Healthy)' and 'Biosimilar CT (Patient)'. A project type is now recognised as a clinical trial by the START of its name, so the next subdivision is a value-list change rather than a code change. V-26 reports the retired value with the two it became, because only the reader knows which of them a given trial was. Template v1.8, dummies v1.10 and v1.2. | Issued for review
2.26 | 2026-07-31 | Claude Code | Pending | Gate 4 round 25, application v1.24. (1) EVERY FILTER NOW TAKES SEVERAL VALUES AT ONCE. Each is a drop-down of tick boxes built on <details>, which gives open, close, keyboard operation and focus for nothing; a plain <select multiple> would have cost seven tall boxes across the bar and asked the reader to know that ctrl-click means 'and also'. Nothing ticked means All, which is what the closed control says, so the bar reads as it did with single selects; one ticked reads as that value, more than one as a count with the full list on hover. Values within one filter are an OR - ticking a second project type WIDENS the view - while the filters remain an AND with each other, which is the only reading that makes 'NewDrug CT and Others, in-house' mean anything. Each has its own Clear; Reset still empties them all; and a value that has gone from the file is dropped from the selection, since the page must not stay filtered by something the reader can no longer see. (2) AUTO DERIVATION in the Periods section builds a project's periods from its milestones by the rule on sheet 05, and (3) BLANK LIST in the Milestones section lays out the ten standard milestone names with their dates empty, so only the dates have to be typed. Both produce ORDINARY ROWS - provisional until Save, editable and deletable afterwards, subject to every rule - because the point is to save the typing, not to take the decision away. Auto derivation reads the milestones from the raw sheet so a set just typed and not yet saved still counts, which is the ordinary case when the two buttons are used one after the other; it asks before replacing an existing set; and it refuses what it cannot do, naming the reason: an 'Others' project (the rule hangs on CTA submission and the DB locks) or a trial missing either of those (V-16). Blank list does not repeat a name already listed, since a second 'CTA submission' is the duplicate V-20 exists to catch. A LATENT CRASH was found while testing them and fixed: clicking a row that had not been saved yet made its identifier the selection, and the detail panels below need a RECORD - dates, a name, a calculation - which a draft has none of. projDetail threw, taking the whole re-render with it, so the click appeared to do nothing at all. Both detail panels now fall back to the scratch panels built for exactly that state. tools/test_generate.py checks the derivation against the rule term by term on a project built to exercise every branch. No requirement, rule, calculation or schema version changed. | Issued for review
2.25 | 2026-07-31 | Claude Code | Pending | Gate 4 round 24, application v1.23. Three changes to the filter bar and to what the unsaved-change counter can tell you. (1) OUTSOURCING TYPE joins the filter conditions, driving the same machinery as the other six - the charts, both Overall tables and the source-data tabs - and Reset puts it back with the rest. (2) THE HORIZON NOW FOLLOWS THE FILTERS. Narrowing to one project type left the window the whole portfolio needed, so a two-year span went mostly empty and the reader was looking at a chart of nothing with no way to tell whether that was the answer or the view. Changing a filter now pulls From and To in to the months the surviving rows actually reach. Two things are deliberately left alone: a combination that matches NOTHING keeps the window where it was, because jumping to an arbitrary span would hide the reason the screen is empty; and typing in From or To is the user moving the window themselves, so the re-fit runs only when a filter DROPDOWN moves. (3) A SHOW DETAILS button beside the counter opens every change waiting to be saved, as a table: the time it happened, which tab, which section, which row, which item, what it was before and what it is now. Newest first, because the question it answers is almost always 'what did I just do' - the edit you are unsure about is the one you made a moment ago - and the first row is tinted for the same reason. The dialog closes, goes full screen for a log too wide or too long for the ordinary box, and scrolls with the same visible bar and edge shading as every other scroll region. The section column shows the name the panel goes by on screen rather than the sheet name, because the point of the log is being able to walk back to the thing you changed; the sheet is still what is recorded underneath. Every pending entry now carries the time it was made, which nothing did before. tools/test_filters.py covers all three. No requirement, rule, calculation or schema version changed. | Superseded by v2.26
2.24 | 2026-07-31 | Claude Code | Pending | Gate 4 round 23, application v1.22. Four values that were typed by hand while the rows underneath already said what they should be. (1) A project's WINDOW is now recalculated on Save: start_date becomes the earliest of its milestone dates and end_date the latest, and total_period_months follows without anyone touching it. (2) planned_member_count becomes the number of DISTINCT people assigned to the project - people, not assignment rows, since one person may hold several. Both are done at SAVE rather than at load, deliberately: doing them at load would rewrite a workbook produced elsewhere the moment somebody opened it, and the delivered examples set a project start before its first milestone quite legitimately. At Save it is a consequence of an edit just made, and the banner names every value it changed. Two guards keep the change from destroying information: a project with NO milestone dates keeps the window that was typed, because there is nothing to derive it from; and a project with NO assignments keeps the team size that was typed, because 'nobody is assigned yet' is not the statement 'this needs nobody'. ONE CONSEQUENCE IS WORTH STATING: a project now ends at its last milestone, so work that legitimately continues past the final DB lock - close-out, archiving, an inspection - has to be carried by a milestone if it is to be inside the window, and an assignment running past it is reported as V-07. The period derivation already allowed for that headroom by running Close-out (final) to the later of the DB lock and the project end; deriving the end from the milestones removes it. (3) A new row in Periods is given the next PERIOD_SEQ for its project. The request named a 'period_id': the sheet has none, it is keyed on (project_id, period_name) per change R-11, and period_seq is the field that carries the order - so that is the number allocated, one past the highest in that project, exactly as milestone_seq is. (4) A weight-override window now shows the PROJECT and ROLE of its assignment even when that assignment has not been saved. It read them from the validated model, which excludes anything still being entered, so the two lookup columns went blank until Save - and they exist precisely so that, while typing, the user can confirm the window is attached to the right piece of work. They are read from the raw sheets now, and the same two columns were added to the scratch panel that a plan started blank uses. tools/test_derive.py covers all four; seven of its ten checks fail against the previous build. No requirement, rule, calculation or schema version changed. | Superseded by v2.25
2.23 | 2026-07-31 | Claude Code | Pending | Gate 4 round 22, application v1.21. Three changes to what a new row arrives with, and to whether the reader can tell there is more to see. (1) IDENTIFIERS are now allocated on insert for project_id, person_id and milestone_seq as well as assignment_id, and the rule is ONE PAST THE HIGHEST already in the sheet rather than the smallest unused. The old rule was about tidiness - a file whose ids ran 1..46 and then jumped to 901 for a few hand-placed rows would not start climbing from 902; the new one is about being able to tell at a glance which rows were added today, and a gap left by a deleted row now stays a gap, which is how an identifier sequence behaves everywhere else. milestone_seq counts within its own PROJECT, not across the file, because that is the list it orders. (2) WEIGHTS start at 1.00: ProjectPeriod.weight, Person.capacity_fte, Assignment.person_weight and PersonPeriodWeight.weight_override. 1.00 is the neutral multiplier, and the alternative is not 'no value' but ZERO - an empty weight reads as 0.00 in the calculation, so a row left alone contributed nothing at all and nothing on screen said so. A row that contributes too much is noticed; a row that contributes nothing is not. This required a second concept alongside 'blank': a row carrying only the values the APPLICATION put there is still an empty row, so Save does not promote it and Export refuses to write it - otherwise every insert would immediately become a half-record complaining about what it is missing. (3) SCROLL REGIONS now say which way there is more. Every section was already bounded on both axes, but scrollbar-width:thin bought a browser OVERLAY bar that occupies no layout space and fades when idle - measured, offsetWidth === clientWidth - so a table with eleven columns off to the right looked exactly like a table with none. The bar is now a real 12px with a visible thumb; and because overlay scrollbars are the default on some platforms whatever the CSS asks for, each region ALSO carries a soft shade on any edge that has content beyond it, drawn over the box so table rows cannot paint on top of it, and removed the moment that edge is reached so it always means 'more this way'. tools/test_newrow.py covers all three. Two existing tests had to change, and both were encoding old behaviour rather than finding new faults: test_rows was promoting an override row with no window and no weight in it, which isSkeleton now declines to do, and test_nokey could no longer reach a keyless row by skipping the identifier - the application supplies one - so it clears it explicitly instead. No requirement, rule, calculation or schema version changed. | Superseded by v2.24
2.22 | 2026-07-31 | Claude Code | Pending | Gate 4 round 21, application v1.20. A ROW WITH NO IDENTIFIER IS NO LONGER TREATED AS A RECORD, which fixes three reported faults that were all one fault. A project saved with every field filled in EXCEPT project_id was indexed as M.projects[null] - and JavaScript turns a null key into the STRING 'null'. The application then believed in a project called 'null'. It became the selection; and the row filter, which keeps a row when the set of visible project_ids contains it, compared the set {'null'} against the row's actual null and missed - so the Projects table the user had just typed into reported 'No rows. Use + row to add one.' The Milestones and Periods sections beneath went looking for a parent named 'null', found none, and reported the same; a row added there would have been stamped 'null' and lost. A person saved without a person_id did exactly the same, which is why the Assignments and Weight overrides sections beneath them offered nothing to fill in. One cause, three symptoms, on both tabs. The rule now is explicit: a row becomes a RECORD when it carries its sheet's identifier and not before. Until then it is not indexed, it is reported as an error naming the column to fill in, and Save is refused rather than silently creating the phantom - which matches the export guard, that has always refused to write such a row. Crucially the row STAYS ON SCREEN, because it is the row the user is in the middle of repairing: both the project and people tables keep any row that has no identifier alongside the real ones, and a child table now shows a row carrying no parent key wherever the user is, since a row that cannot be seen cannot be repaired or deleted, only silently dropped. Supplying the identifier recovers completely. The same rule went into tools/prap_io.py, so the command line and the page still report the same findings. tools/test_nokey.py covers all of it for a project, for a person, and for a workbook that already carries such a row; four of its eleven checks fail against the previous build, reproducing the reported symptoms exactly - '0 rows on screen', projects=['null'], and 'No rows. Use + row to add one.' No requirement, calculation or schema version changed. | Superseded by v2.23
2.21 | 2026-07-31 | Claude Code | Pending | Gate 4 round 20, application v1.19. SCROLL POSITION now survives a re-render. Committing a cell re-renders the panel it lives in, and a freshly built element starts at the top left - so filling one cell in a table twenty-two columns wide sent every scroll box back to the first row and the first column, and the next cell the user meant to fill was off screen again. On a dashboard that is invisible; during data entry it costs a re-scroll for every single cell, which is the difference between a usable table and an unusable one. It showed up as soon as a plan could be typed in from scratch (round 18) because that is the first time anyone fills in cells one after another. Every scroll offset on the page is now captured and put back around each re-render, along with the page's own scroll position, which a re-render can also move because the edit banner changes height between 'no changes' and 'n changes not yet saved'. The key has to survive the DOM being rebuilt: a data table names itself by its sheet, and everything else - the charts - is keyed by where it sits among the other keyless boxes in its own pane. The same wrapper covers the three other places that redraw part of the page: selecting a parent row, selecting an assignment, and the matrix/rows toggle on General assumptions. Changing TAB still takes the page to the top, because that is the user moving somewhere else rather than the page moving underneath them. tools/test_scroll.py drives the real browser and checks all four commit paths, the page scroll, a row 900px down a 289-row table, and that the cell just filled is still on screen afterwards; five of its eleven checks fail against the previous build. The test itself needed care: Playwright's own click scrolls its target into view first, and Chromium's scrollIntoView scrolls EVERY scrollable ancestor, so a naive click on an off-screen cell moves the box before the application has run a line - the first draft of the test was measuring the driver rather than the page. No requirement, rule, calculation or schema version changed. | Superseded by v2.22
2.20 | 2026-07-31 | Claude Code | Pending | Gate 4 round 19, application v1.18. The four CHILD sections are now on screen from the moment a blank plan is started, and can be filled in before their parent is saved. Round 18 made a plan enterable but only in one order: the project tab showed the Projects table alone until a project had been saved, and the person tab the People table alone. Both were literally true - the detail panels need a parent RECORD, with dates for the timeline and a name for every heading, and a row still being typed is not even parsed into the model - but the consequence was that Milestones, Periods, Assignments and Weight overrides were invisible to anyone building their first plan. A section that appears only after you have done something else reads as a section that does not exist. So the tables are drawn from the start, in the same two-column arrangement they have when a workbook is loaded, and they behave in three states. With no parent at all they are LOCKED and carry the reason where the '+ row' button would be, because a child row whose parent does not exist has nothing to attach to and would be dropped when the file is read back - saying so beats offering a button that creates a row nobody can rescue. The moment the parent row carries an IDENTIFIER - before it is saved - they unlock and scope themselves to it, so a plan can be entered the way a person actually thinks about one: the project and its milestones together, the person and their assignments together, each committed in a single Save. Two fixes were needed for that to work. The draft row now becomes the tab's selection, since child rows inherit their parent key from the selection and without it they were created parentless. And the fallback that finds the assignment for a new override row now reads the raw sheet rather than the validated array: the validated array excludes anything still being entered, so on a plan being typed from scratch the only assignment on screen was not found. tools/test_blank.py now enters the milestones BEFORE saving the project and the assignment BEFORE saving the person, checks each child inherited the right foreign key, and adds a weight override window to prove the fourth section works and REPLACES the person weight for its three months and no others. No requirement, rule, calculation or schema version changed. | Superseded by v2.21
2.19 | 2026-07-31 | Claude Code | Pending | Gate 4 round 18, application v1.17. A PLAN CAN NOW BE STARTED IN THE APPLICATION ITSELF. The landing screen offers two ways in, given equal weight: load a source workbook, or start blank and type. 'Start blank' opens every tab and every section an upload opens - it is the same code path, so it is not a lesser mode with its own rules - and the plan it produces exports to the same .xlsx as any other. A blank start is not an EMPTY workbook: with no Lists sheet there would be no vocabulary, so every typed value would be reported as unrecognised (V-11) and no field could offer a choice, and with no Config there would be no thresholds. It therefore begins from the reference content of the delivered template, embedded in the HTML by tools/build_app_seed.py and held to the template by check_consistency.py. The PeriodFTEStandard and RoleFactor grids are NOT embedded: the application builds them from the value lists it was just seeded with - 56 standard weights and 289 role factors, every combination a project can reach - so a company that adds a role to Lists gets it without anybody regenerating anything. Every seeded figure is a placeholder 1.00 that says so on its own row, because an invented weight that looks like a company standard is worse than an obvious placeholder: only one of the two gets questioned. Four things had to be fixed before the path worked at all, each found by walking it rather than by reading it. (1) A DEADLOCK at the first save: a clinical trial saved before its milestones exist raises V-16 by definition, and its milestones cannot be entered until it is saved, because the milestone table hangs off a SELECTED project. The save guard now treats V-12 and V-16 as INCOMPLETENESS rather than error - the same line the specification already draws for drafts - names what is still missing in the banner, and refuses everything else exactly as before. (2) A row still being typed is not yet parsed into the model, so on a plan with no saved projects the Projects table said 'nothing matches the filters' and hid the very row the user was filling in. (3) The first assignment was the one row the application refused to name, having named every one after it: nextKey had nothing to copy a house style from, so the sheets that allocate their own keys now carry a pattern to start from. (4) FIVE PROJECT COLUMNS HAD NO HOME ANYWHERE IN THE APPLICATION. The project and people tables showed a curated subset, which was survivable while every plan arrived as a workbook filled in elsewhere; it is not survivable now that a plan can be built here, because DataReviewSystem_setup could never be entered and V-10 would warn about it forever. Both tables now carry every column the schema lets a user type into. Also: a person with no assignment yet is listed on the person tab, which is the state everybody is in for the minute after they are created; and the default horizon no longer anchors to year 0 when nothing has been calculated. tools/test_blank.py never touches a fixture - it clicks Start blank and builds a plan the way a person would, then checks every monthly figure against the formula worked by hand. No requirement, rule, calculation or schema version changed. | Superseded by v2.20
2.18 | 2026-07-31 | Claude Code | Pending | Gate 4 round 17, application v1.16. REFERENCE MATERIAL FOR ANOTHER AI SYSTEM, and an interoperability audit of everything delivered so far. The audit found one thing, and it was structural: of 95 files in the repository, 72 were .xlsx and 2 were Markdown. Every fact this project has established - the schema, the value lists, the formula, the twenty-four validation rules - existed only inside a ZIP of XML or inside the application's own JavaScript. A person with Excel could read all of it; a program, a script or a language model could read none of it. Four deliverables close that. (1) docs/prap_contract.json, a machine-readable contract carrying the schema, every column with its type and meaning, the value lists, the Config parameters, the formula term by term, the period derivation, all twenty-five rules with the severity the application actually reports, the interchange format and the task recipes. It is GENERATED - from the template builder, from this plan's own rule table, and from the application source - so it cannot drift from what it describes. (2) docs/PRAP_AI_Agent_Guide.md, the same contract written for a reader in the order an agent needs it, plus the same document as a workbook for human review. (3) A JSON INTERCHANGE FORMAT: the whole workbook as row objects keyed by column name, dates as yyyy-mm-dd. The application loads it and exports it, and tools/prap_io.py converts either way, so an agent that cannot write a ZIP of XML can still produce a file PRAP opens. (4) tools/prap_io.py also VALIDATES and CALCULATES from the command line, implementing the same rules and the same formula as the page - so an agent can check its own draft without a browser. tools/test_interop.py holds the two implementations to each other: same findings at the same severities, and every person-month equal to 1e-6, on both worked examples. The audit also found a rule the documents promised and the code did not keep: V-14 has been in the data model since v1.0 and the application never reported it. It does now - a milestone outside its project's window, or a boundary milestone out of order - with the one exception that is legitimate rather than merely noisy, an Inspection after the final DB lock, reported as information because the derivation deliberately extends the timeline to reach it. No requirement, calculation or schema version changed. | Superseded by v2.19
2.17 | 2026-07-31 | Claude Code | Pending | Gate 4 round 16, application v1.15. A visual design pass over the whole interface, taking Apple's Human Interface Guidelines as the reference and applying them to a dense data tool. The stylesheet is rebuilt around TOKENS - one palette, one type scale, one radius scale, one motion curve - so that no value is chosen by eye at the point of use, which is what keeps a hundred small decisions consistent. Four changes carry most of the difference. (1) MATERIAL: white cards on a grey field, separated by soft shadow instead of by a 1px outline round every panel; dark mode inverts to lifted grey cards on near-black. (2) VIBRANCY: the two sticky bars are translucent and blurred, so content scrolling beneath stays legible as context - at an opacity that keeps their own labels readable over a chart, because blur alone is not enough when what is underneath is high-contrast. (3) The tab strip becomes a SEGMENTED CONTROL, and buttons take Apple's filled / tinted / plain hierarchy; the row actions that appear twice on every table row are furniture at rest and take colour only on hover, where blue means 'adds' and red means 'removes'. (4) COLOUR MEANS SOMETHING: blue is interactive, red is over the ceiling, amber is under the floor, everything else is a grey. Chart series colours are exempt, because there the colour IS the data, and they are unchanged. Contrast is now measured rather than judged: tools/test_contrast.py composites every text colour onto the surface it actually sits on and applies WCAG AA at the rendered size. The previous design had five colours below AA; this one has none. Two defects were found and fixed in passing: the drop zone still named template v1.6, and #editbar set display:flex from an id selector, which outranks the `hidden` attribute - so an empty edit bar showed before any workbook was loaded. No requirement, rule, calculation or schema changed, and every existing selector is retained. | Superseded by v2.18
2.16 | 2026-07-31 | Claude Code | Pending | Gate 4 round 15, application v1.14, template v1.7, dummy v1.9 and 10x10 v1.1. DERIVED columns in the source workbook are now distinguished from entry columns by more than a colour: their cells are LOCKED, and the column heading carries a note saying what the column is, that the lock has no password, and what a hand-typed value would actually do. A green fill is a convention the reader must have been told about, and the telling is on a README sheet they may never open; a lock is the file itself refusing the edit at the moment it is attempted. Every other cell on those sheets is explicitly UNLOCKED, and protection is set so that inserting, deleting and sorting rows all still work - only adding or removing COLUMNS is blocked, because the column set is the schema. There is no password: it is a guard rail, not security, and anyone who genuinely needs to paste a column can turn it off in two clicks. The application's EXPORT now writes the same locks and the same sheet protection, so the guard rail survives a round trip instead of disappearing the first time a file goes through PRAP. check_consistency.py now verifies all of it against the plan's own data model - which surfaced a documentation gap the change had to close: Milestone.project_name and Assignment.person_name were typed 'Text' in the data model although the application recomputes both on import and reports any disagreement as V-13. They are typed 'Derived' now, which is what they have always been. No requirement, rule, calculation or schema version changed. | Superseded by v2.17
2.15 | 2026-07-31 | Claude Code | Pending | Gate 4 round 14, application v1.13. (1) A LINE CHART of monthly resource now stands as the FIRST panel of every data tab - one coloured line per project on Overall and on the project tab, one per person on the person tab, each keeping the colour it already carries elsewhere. The stacked charts say what a month's total is MADE OF; they cannot say whether one series is rising or falling, because in a stack every band's baseline moves with the bands beneath it. Lines share one baseline, which is the whole reason to draw the same numbers a second way. Each line carries its total, mean and peak month, and is capped at the twelve largest by total because sixty lines on one axis is a texture, not a reading. On the person chart the over-allocation ceiling is marked, since there it applies to a single series' own value. (2) A design pass over every section. Summary tiles move to the TOP of the Overall tab: they are the headline figures and sat below a chart. Every panel now carries ONE header shape - title on the left, what the panel covers on the right - where scope had been stated three different ways: inside the caption, in a note under the table, or not at all, so the reader had to hunt for it in a different place in each section. Captions are bounded to a readable measure. Two long-standing chart faults were fixed on the way: a transparent stroke is not a PAINTED one, so the line hit strips needed pointer-events stated explicitly, and the visible stroke sits on top of them and had to be taken out of hit testing or it swallowed the pointer and offered no tip of its own. No requirement, rule, calculation or schema changed. | Superseded by v2.16
2.14 | 2026-07-31 | Claude Code | Pending | Gate 4 round 13, application v1.12. PersonPeriodWeight is treated as what the schema says it is - a CHILD of Assignment - so on the person tab it now follows the assignment SELECTED above it, exactly as Milestones and Periods follow the project selected above them. Clicking a row in Assignments selects it and the overrides table redraws to that assignment's windows and no others; a new override row is seeded with the selected assignment rather than the person's first, so it is filed under the project on screen. Scoping the table to the PERSON instead - which is what round 12 left it doing - listed every window that person carries across every project at once, a set of rows with nothing to do with each other. Both headings now name the person ('Assignments - Kim S. (PSN-001)'), and the overrides panel restates the assignment it belongs to above the table: identifier, project, role, dates and weight. One structural change was needed to make this safe: the overrides panel is rendered into its own element, because clicking a cell both selects the row and puts the caret in it, and redrawing the whole person panel would rebuild the Assignments table under the caret so the edit could never be typed. The project and person tables escape this by living outside the panel they drive; this table drives a panel beside it. No requirement, rule, calculation or schema changed. | Issued for review
2.13 | 2026-07-31 | Claude Code | Pending | Gate 4 round 12, application v1.11. Three changes, none touching a requirement, rule, calculation or schema. (1) The Overall tab's 'Mean load per person' is replaced by 'MONTHLY DEMAND BY PERSON': the same months as 'Monthly demand by project' directly above it, cut the other way, one stacked band per person with a colour per person. The two charts total the same figure every month, because they are the same person-months summed along different axes - and that is now an executable check, not a claim. The mean-and-thresholds reading the old chart gave is not lost: a segment is OUTLINED where that person's own month crosses the ceiling or the floor, so the flag never rests on fill colour, which here already means 'which person' (D-04). The 20-person cap from D-14 carries over to the stack and its legend (REQ-DSH-09). (2) 'Utilisation' on the project tab is stacked by PERSON on the same terms, with each segment's pop-up naming the person, their role on this project, their FTE and share of the month, and the project's total. Its relative reference lines are unchanged, and a month whose TOTAL crosses one is outlined behind the stack rather than coloured into any one person's segment. (3) DEFECT: a row drafted on one person's tab appeared on every other person's tab. The child-table filters carried a bare '¦¦ r.__new', added at round 6 so a new row would be visible before its key was filled in; being unconditional it admitted every draft everywhere. On 'Weight overrides', whose project and role columns are looked up FROM the assignment, such a row then described another person's work - the incorrect mapping reported. A draft is now admitted only while its parent key is empty, applied through one helper to all four child tables. The overrides table is also scoped correctly as a GRANDCHILD of the person: by the identifiers of the assignments shown above it, not by the person's own. | Superseded by v2.14
2.12 | 2026-07-31 | Claude Code | Pending | Gate 4 refinements round 11, application v1.10. Two changes, neither touching a requirement, rule, calculation or schema. (1) A PROJECT TIMELINE run-chart now stands before the Utilisation panel on the project tab - the Overall tab's chart drawn for the selected project alone, with one band per period shaded by period weight, every milestone marked, the two DB locks in red, and each band labelled with its average FTE per month. The row-label gutter the Overall chart needs is dropped, since the panel heading already names the project. (2) The UTILISATION bars on the person tab are now STACKED BY PROJECT: one coloured segment per project per month. The total says whether someone is over the ceiling; only the split says because of what. Each segment's pop-up answers both halves at once - the project (name, type, the milestones that project passes THAT month, this person's FTE on it and its share of the month) and the person (name, identifier, total FTE that month, how many projects it is spread across, capacity, and which threshold if any it crosses). Over- and under-allocation is now drawn as an outline BEHIND the stack, because it is a property of the month's total and not of any one project in it. Supporting this, project colours are now allocated from the sorted list of ALL project ids and held for the session, so one project carries ONE colour everywhere - the Overall stacked chart picked its colours from the filtered draw order, which meant the same colour meant different projects on different tabs and after every filter change. | Superseded by v2.13
2.11 | 2026-07-31 | Claude Code | Pending | Gate 4 defect fix round 10, application v1.9. Reviewer reported that dragging the scroll bar of a type-ahead value list closed the list, making a list taller than its box impossible to read to the bottom of. Two independent causes, both now fixed. (1) A capturing scroll listener closed the list on ANY scroll anywhere in the document - including the list's OWN scrolling. It existed because the list is a fixed box anchored to its cell and a page scroll would leave it stranded; closing was the crude answer. It now ignores its own scrolling and RE-ANCHORS on any other, closing only once the cell itself has left the screen. (2) Pressing on the list's scroll bar took focus off the cell, and the focus-out handler closed the list underneath the hand scrolling it. The press is now held for its whole duration and the caret is restored on release. The list closes on exactly the three things asked for: choosing a value, Escape, or a click outside. Because Escape leaves the caret in the cell and so fires no focus event, a click in the field now re-opens the list. Matching is also improved: tokens match in ANY ORDER, so 'phase 1 onv' finds 'ONV-101 Phase 1'; every matched fragment is marked, not just the first; results rank a typed prefix above a mere containment; and a query matching nothing now shows the whole vocabulary with an explanation instead of vanishing and stranding the reader. That last change exposed a pre-existing trap - render() highlighted the first row, so Enter silently swapped in a value the user never chose, which had escaped notice only because a query matching nothing used to hide the list and put Enter out of its reach. Nothing is highlighted now until an arrow key highlights it. No requirement, rule, calculation or schema changed. | Issued for review
2.10 | 2026-07-31 | Claude Code | Pending | Gate 4 defect fix round 9, application v1.8. Reviewer reported that choosing an assignment_id on a new Weight-overrides row raised a warning offering to change every other override of the assignment being moved away from, so a second window could not be added. Cause: the edit path cascaded an identifier change whenever the edited column was the sheet's KEY_COL, but on a CHILD sheet that column is a FOREIGN key - PersonPeriodWeight.assignment_id points at an assignment, it does not define one. Re-pointing one row therefore rewrote every row sharing the old value, which on the overrides table is the sibling windows of that same assignment. Accepting the prompt destroyed them; declining abandoned the edit, so the assignment could not be changed at all and the row stayed on whichever assignment it was seeded with. The cascade is now confined to the sheet that OWNS the identifier, using the OWNER map that deleteRow has used for the same distinction since round 4. In place of the warning, picking an assignment that already carries windows now states how many the row joins and names V-06 and V-24 - an additional window is the normal case, and only an overlapping one is refused, at Save. No requirement, rule, calculation or schema changed. | Superseded by v2.11
2.9 | 2026-07-31 | Claude Code | Pending | Gate 4 refinements round 8, application v1.7. Three changes, none touching a requirement, rule, calculation or schema. (1) EVERY scroll region now scrolls in BOTH directions and is bounded on both axes. A panel bounded on one axis only can still hide content on the other, and the reader has no way of telling that it has - there is no scrollbar to suggest anything is missing. The findings dialog and the provenance strip were the two regions with no bound at all; the three chart panels were bounded sideways only. (2) On the Assignments table the project is now identified by NAME: project_name is the field typed into and project_id is derived from it, with a type-ahead over the project names. Editing the identifier directly still works and the name follows instead - the two are one field seen from two ends. A name matching no project is refused, naming near matches; an ambiguous one is refused too, since only the identifier is guaranteed unique. The name is never STORED on the assignment row: the sheet has no such column, so a copy could not survive an export and re-import, and it would be a second version of a fact the Project sheet already owns. (3) '+ row' on the Assignments table allocates the next free assignment_id - the smallest unused number in the pattern the file already uses, not the largest plus one, so a file whose ids jump to 901 for a few hand-placed rows does not start allocating 905. | Superseded by v2.10
2.8 | 2026-07-31 | Claude Code | Pending | Gate 4 round 7, application unchanged at v1.6. A second dummy dataset at the reviewer's requested size - 10 projects and 10 people - issued as PRAP_SourceData_Dummy_10x10_v1.0.xlsx on schema 5, alongside the 62-project set rather than replacing it. The generator now runs from size PROFILES, so one code path produces both and neither can drift from the schema the other follows; the 62-project file rebuilds with every sheet byte-identical, confirmed by unpacking both .xlsx containers. The small set is not a lighter test: it holds both clinical types, all four phases, trials with and without an interim DB lock, inspections that open the seventh period, hand-entered 'Others' periods, two part-timers, multi-window weight overrides, and both allocation thresholds crossed. Its load distribution matches the large set's (median 0.80 against 0.87 FTE). tools/test_app.py now runs over BOTH fixtures. No requirement, rule, calculation or schema changed. | Superseded by v2.9
2.7 | 2026-07-31 | Claude Code | Pending | Gate 4 defect fix round 6, application v1.6. Reviewer reported that inserting and deleting rows did not work on Milestones, Periods, Assignments and Weight overrides - the four CHILD tables, which are the four rendered filtered to a selected parent. Three defects, all in the shared insert/rebuild path, none touching a requirement, rule, calculation or schema. (D-1) A new row was created with every column empty, so the parent filter that decides which rows the table shows excluded it: the row existed but was invisible. A new child row is now seeded with the parent it was created under, and each filter admits a row still being drafted. (D-2) Every edit and delete re-parses the data, and the parser discards blank rows - correct for a file being read, wrong for a row the user has not filled in yet, which was silently destroyed by the next action. Rows the parser would discard are now held out of the parse and put back in place. (D-3) The parser numbers rows by position, so deleting a row renumbered every row below it while pending edits, edit highlights and the rendered cells still named the old numbers - an edit could end up attached to a different record, and a drafted row could be duplicated. Row identity is now preserved across a rebuild. A drafted row is exempt from validation while it is being written and is validated when Save is pressed; a draft that would break a rule is refused by name rather than kept. | Superseded by v2.8
2.6 | 2026-07-31 | Claude Code | Pending | Gate 4 refinements round 5, application v1.5. Five changes, none touching a requirement, rule, calculation or schema. (1) and (2) The Assignments and Weight-overrides tables carry the project name, and the overrides table also the role - looked up from the master row and marked as such, since an identifier alone does not tell a reader which project they are looking at. (3) Every data cell shows its value and its column's meaning on hover or focus. (4) The Periods table and the General-assumptions tables gain row actions. The two weight sheets and the value lists keep their matrix view for reading and gain a rows view for editing, because a matrix row is six or seven workbook rows and cannot carry a per-row action. (5) Type-ahead on every column with a vocabulary: the Lists sheet where the column is backed by one, the distinct values already present where it is not, and the type-dependent set for period_name and role_name. | Superseded by v2.7
2.5 | 2026-07-31 | Claude Code | Pending | Gate 4 refinements round 4, application v1.4. (1) Information pop-ups: every column heading on the source-data tabs explains what its column is for, and the summary tiles, month headings and project type pills explain what they count. They open on HOVER and PIN on CLICK, which is also what makes them reachable on a touch screen and from the keyboard, where there is no hover at all. (2) Every editable table gains a Delete control beside Insert. V-17 governs it: a row still referenced cannot be deleted and the refusal names what refers to it, and a delete is NEVER cascaded - that asymmetry with the cascading identifier edit is deliberate, because a cascaded rename is reversible and a cascaded delete is not. Deletion is provisional like any other change. No requirement, rule, calculation or schema changed. | Issued for review
2.4 | 2026-07-31 | Claude Code | Pending | Gate 4 refinements round 3, application v1.3. Three changes. (1) Column headings stay visible in EVERY scroll region, and the corner cell of the two Overall grids is pinned in both directions - a month heading that scrolls away turns the table into unlabelled numbers. (2) The two utilisation charts carry the year on the x axis, shown where the year changes with a divider at each boundary. (3) EDITING IS NOW PROVISIONAL: a change is applied on screen so its effect is visible, but is held as pending until the user presses Save or Leave without change. Save commits it to the working data; Leave without change restores the snapshot taken before the first pending edit. Export is HELD while anything is pending, so nothing unconfirmed can reach a file. This is a behavioural change to REQ-IMP-07 and REQ-IMP-08 and is recorded for the specification to take up at the next issue. | Issued for review
2.3 | 2026-07-31 | Claude Code | Pending | Gate 4 refinements round 2, application v1.2. The application now shows, at the top of the page, which controlled documents the build implements - development plan, programming specification, UI component list and source-data template - collapsed to one line with the full table on demand, and a row comparing the loaded workbook's schema version against the one the application expects. This is REQ-VC-01 made visible in the product rather than only in the repository. The list is data in one place and is verified against the repository by tools/check_consistency.py on every run, which was proved to fire by naming a superseded plan version. No requirement, rule, calculation or schema changed. | Issued for review
2.2 | 2026-07-31 | Claude Code | Pending | First refinements from the Gate 4 review (WBS 4.9), applied to application v1.1. Three UI changes, no change to any requirement, rule, calculation or schema. (1) The three named Overall sections - monthly demand, resource by project, resource by person - are up to twice their previous size. (2) The project timeline scrolls in both directions inside its panel, which also let the 20-project display cap be removed: every project in the filter is now drawn. (3) Chart text is larger and higher contrast, and each threshold or reference label moved out of the plot area into a right-hand margin - drawn over the bars they were unreadable at any size, and enlarging them made the collision worse rather than better. Breaching bars on the person chart now state their own value. | Issued for review
2.1 | 2026-07-31 | Claude Code | Pending | Step 4 progress against the v2.0 baseline. The application is built: app/PRAP.html, one offline file with its own .xlsx reader and writer. WBS tasks 4.1 to 4.8 move to Complete; 4.9 - your review of the output against real data - is the Gate 4 review and is what remains. No requirement, rule or schema changed: this issue records progress, not a change of intent. The calculation engine was checked cell-by-cell against tools/verify_source_workbook.py and matches exactly across all 1,225 person-months of the dummy dataset. | Issued for review
2.0 | 2026-08-02 | Claude Code | Dan | APPROVED BASELINE. Content identical to v1.10; the version number changes because the numbering rule on sheet 09 reserves x.0 for an approved baseline and v1.10 was a change awaiting signature. Approved together with programming specification v1.0 and UI component list v1.0. Changes R-05 to R-13 are now part of the baseline rather than pending against v1.3, and Step 4 is authorised. | APPROVED 2026-08-02 by Dan - BASELINE
1.10 | 2026-07-31 | Claude Code | Pending | Change R-13, from the component-list v0.7 review. All 13 changed components and all 7 changed decisions were confirmed OK; nothing was marked Rework. Two new requests were raised and both are applied: the interim and final DB lock milestones are emphasised on the timeline, and the project source-data tab gains a utilisation graph. The second needed a new requirement, REQ-DSH-12, because a project has no absolute ceiling or floor - its reference lines are relative to the portfolio average and to the project's own lifetime average. No schema change. | Issued for approval
1.9 | 2026-07-31 | Claude Code | Pending | Change R-12. A reviewer question about the PersonPeriodWeight key - why period_start is needed when assignment_id looks unique - was answered by confirming the key is correct: one assignment may carry several non-overlapping override windows, so assignment_id alone would cap it at one. Checking the question found two rules that were specified but never implemented. V-06's assignment-window half now runs, and V-24 is added for referential integrity and key uniqueness on PersonPeriodWeight. The dummy fixture gains an assignment with two windows, which is what would have caught both. No schema change. | Issued for approval
1.8 | 2026-07-31 | Claude Code | Pending | Change R-11 against the v1.3 baseline. The conduct phase is split by NAME rather than by sequence: 'Conduct (interim)' where an interim DB lock exists and the stretch runs before it, 'Conduct (final)' after it or where there is no interim lock. Period names are therefore unique within a project and ProjectPeriod is keyed on (project_id, period_name); period_seq carries order only. The clinical period set grows to seven names, V-18 becomes a uniqueness check, REQ-CAL-11 and REQ-PRJ-12 are reworded, and REQ-DSH-10 is now satisfied structurally rather than by display numbering. Schema version steps 4 to 5. Weights are unchanged, so the dummy dataset produces identical figures. | Superseded by v1.9
1.7 | 2026-07-31 | Claude Code | Pending | Change R-10 against the v1.3 baseline, from the component-list v0.4 review. The role factor is now keyed on project type, clinical phase, period and role rather than type and role alone, so a role's burden can vary across the life of a project. RoleFactor gains clinical_phase and period_name and grows from 13 rows to 249; REQ-CAL-02 reworded; V-23 added for a factor missing on a period an assignment actually spans; source schema version steps 3 to 4. A consequence is recorded on sheet 04: RoleFactor and PeriodWeightStandard now vary over the same three dimensions and multiply together, so they must not both be edited for the same reason. | Superseded by v1.8
1.6 | 2026-07-31 | Claude Code | Pending | Change R-09 against the v1.3 baseline, from the component-list v0.3 review. Nine components changed; two needed requirements the plan did not have. REQ-DSH-11 added - the standing assumptions get their own tab. REQ-IMP-11 added - a row can be inserted, positioned below the row acted on. REQ-DSH-05 reworded for the clinical-phase filter and to stop implying the display unit is a filter; REQ-IMP-05 reworded for the time zone. Sheet 06 now describes four tabs. Design decision D-06 is superseded by the reviewer's own O-10, which asks for the opposite. Version history rows for v1.4 and v1.5 added above - they were issued without one, which REQ-VC-04 requires. | Issued for approval
The reviewer's file was named v0.11. Under the numbering rule on sheet 09 that reads as a draft increment of v0.1, so it is logged above as review input and this incorporating draft is v0.2.

## 02_Scope
Scope and objectives
Background - the problem being solved
Multiple projects run at the same time, and their timelines change frequently. Deciding who to assign, in which
role, to which project is therefore difficult to do by hand. The resource burden a project places on a person is
not constant: it varies by project, by period within that project, and by the role the person holds.
Today there is no single view that answers 'who is over-committed next quarter, and on which project?' -
nor the quieter question, 'who has been under-used for three months running?'.
Objectives
ID | Objective | How success is measured | Basis
OBJ-1 | Hold project and person data in one controlled place: a single Excel workbook kept outside the application. | The workbook loads without error and round-trips through export. | Q-09
OBJ-2 | Simulate monthly resource demand per project and per person, respecting period weights and role factors. | Monthly FTE reconciles to the worked example on sheet 05. | Q-01
OBJ-3 | Make both over- and under-allocation visible before they bite. | Person-months above 1.50 FTE are flagged; runs of three or more months below 0.80 FTE are flagged. | Q-08
OBJ-4 | Let the user re-run the simulation immediately after a timeline change. | Editing dates in the workbook - or in the application - and re-running updates the dashboard with no code change. | Q-01
OBJ-5 | Run entirely on a local Windows PC with no install, no server and no network. | The HTML file opens by double-click in Edge and Chrome and works offline. | Q-05
In scope
In scope for v1.0 | Basis
Single-file HTML application runnable from local disk on Windows. | v0.1
Import of all project and person data from ONE Excel workbook via a browser file picker or drag-and-drop. | Q-09
Editing imported data inside the application, with the edits carried into the export. | REQ-IMP-07
Export of the current working data back to .xlsx, so the workbook remains the archive of record. | v0.1
Monthly resource simulation in FTE per project and per person, default 24-month horizon, expandable to the latest project end date. | Q-08, Q-11
Three dashboard tabs: Overall, Source data (project), Source data (person). | v0.1
Tables plus graphs on the Overall tab. | v0.1
Over-allocation and under-allocation detection against the agreed FTE thresholds. | Q-08
Version control of plan, specification and application across the development lifecycle. | v0.1
Out of scope
Excluded from v1.0 | Reason | Status
Multi-user concurrent editing, or any server / database component. | Requirement is a local single-file HTML tool. | Confirmed Q-12
Authentication, user accounts, permissions. | No server; the workbook carries whatever access control the file share provides. | Confirmed Q-12
Automatic writing to the workbook on disk without user action. | Browsers cannot do this from a file:// page - see 07_Architecture. Export is always a deliberate act. | Confirmed Q-12
Cost, budget or salary calculation. | Not raised. The data model leaves room to add it. | Confirmed Q-12
Integration with an HR, CTMS or timesheet system. | Not raised. | Confirmed Q-12
Resource optimisation / automatic assignment suggestions. | v1.0 reports and simulates; it does not decide. | Confirmed Q-12
Working-day and holiday calendars. | Q-02 confirmed calendar-day pro-rating. A working-day calendar is a later option. | Confirmed Q-02
Q-12 answer was 'Fine' - the v0.1 exclusions stand. Note that in-application editing has moved INTO scope via REQ-IMP-07; only automatic writing to disk without user action remains excluded.
Users
User | Type | What they do with the application
Resource planner / manager | Primary | Loads the workbook, reviews monthly simulation, spots over- and under-allocation, tries timeline scenarios.
Project lead | Secondary | Checks the resource profile of their own project and who is assigned in which role.
Data maintainer | Secondary | Keeps the source workbook accurate; may be the same person as the planner.

## 03_Requirements
Requirement register
The contract for Steps 2-5. Every specification section and every code module cites the REQ-IDs it satisfies.
REQ-ID | Category | Requirement | Priority | Source | Step
REQ-OUT-01 | Output | The application is a single HTML file that runs on a local Windows PC by double-click, with no install and no network access. | Must | Requester | 4
REQ-OUT-02 | Output | All program logic (HTML, CSS, JavaScript, libraries) is embedded in that one HTML file so it can be copied between PCs as a single artifact. | Must | Requester | 4
REQ-OUT-03 | Output | Source data lives in ONE Excel workbook held separately from the HTML file, and that workbook is the archive of record. | Must | Q-09 | 4
REQ-OUT-04 | Output | The application reads the source workbook and uses it to drive every table and graph. | Must | Requester | 4
REQ-OUT-05 | Output | Plans and specifications are delivered as Excel workbooks. | Must | Requester | 1,2
REQ-PRJ-01 | Project data | Each project records a project type, restricted to 'NewDrug CT', 'Biosimilar CT' or 'Others'. The first two are clinical trials and every clinical trial is exactly one of them. | Must | R-05 | 2
REQ-PRJ-02 | Project data | Each project records a project category. For either clinical trial type the category is the product name; the field is optional for 'Others'. | Must | R-05 | 2
REQ-PRJ-03 | Project data | Each project records a project name, unique within the source workbook. | Must | Requester | 2
REQ-PRJ-04 | Project data | Each project records its conditions: outsourcing type ('Full outsourcing' / 'Partial outsourcing' / 'Full In-house') and the number of project members. | Must | Q-14 | 2
REQ-PRJ-06 | Project data | Each project carries a resource weight per period. For a clinical trial the weight is seeded from a standard keyed on clinical phase; for 'Others' it is entered by hand. | Must | Q-26, Q-28 | 2
REQ-PRJ-05 | Project data | Each project records a timeline: start date, major milestone dates, and total period. | Must | Requester | 2
REQ-PRJ-07 | Project data | The project record accepts further project-related information without a schema change (free/extension columns). | Should | Requester | 2
REQ-PRJ-08 | Project data | Total period is derived from start and end dates rather than typed by hand, so it cannot contradict the timeline. | Should | Derived | 2
REQ-PRJ-12 | Project data | The set of periods a project carries depends on its type: either clinical trial type uses Before-Start-up / Start-up / Conduct (interim) / Close-out (interim) / Conduct (final) / Close-out (final) / After Close-out (final); 'Others' uses Planning / Develop / Close. No name occurs twice in one project. | Must | Q-18, Q-23, R-02, R-11 | 2
REQ-PRJ-13 | Project data | A milestone name may occur more than once in one project. 'Inspection' in particular may record several events; the others are expected once. | Must | R-01 | 2
REQ-PRJ-16 | Project data | The colour each PERIOD is drawn in is a standing assumption: one default per period name, held on the PeriodHighlight sheet and edited on the General assumptions tab, applies to every project. A project's own choice for one of its periods (REQ-PRJ-15) wins over the default; a period with neither is gray. The defaults reach periods derived from milestones too. A colour changes no figure; a default that cannot be applied is reported (V-39). | Should | R-60 | 4
REQ-PRJ-17 | Project data | THE HIGHLIGHT PALETTE OFFERS AT LEAST TWELVE DISTINCT COLOURS - thirteen: red, orange, yellow, lime, green, teal, cyan, blue, navy, purple, magenta, pink, brown - for milestones (REQ-PRJ-14) and periods (REQ-PRJ-15, REQ-PRJ-16) alike. Each is defined for both themes and no two are close in either. Every colour can be chosen in any workbook, including one whose Lists predate the palette, and the chooser shows each as a swatch. The colour word is read as a word, the first one named winning. | Should | R-64 | 4
REQ-PRJ-15 | Project data | A project's period may be given a COLOUR, and the Project timeline draws the period in it - on the Overall tab and on the project's own tab. The colour is chosen from the Lists sheet's period_highlight list in the Periods table's Highlight column; a period with no colour is drawn gray, shaded by its weight. A colour changes no figure and never refuses a save; a value naming no colour is reported (V-38). | Should | R-59 | 4
REQ-PRJ-14 | Project data | A milestone may be MARKED IN A COLOUR, and the mark finds that milestone wherever the Project timeline is drawn - on the Overall tab and on the project's own tab. The colour is chosen from the Lists sheet, so the set belongs to the people using the plan rather than to the code; an empty value means no mark, which is what every milestone was before schema 13. A mark changes no figure and never refuses a save. | Should | R-50 | 4
REQ-PRJ-09 | Project data | A clinical trial of either type records its clinical phase (phase 1 / 2 / 3 / 4). The phase determines the project's period weights, so it drives the simulation rather than merely describing the project. | Must | Q-26 | 2
REQ-PRJ-10 | Project data | A clinical trial of either type records who performs each of EDC set-up, data-review-system set-up, RBQM set-up and DM conduct ('by CRO' / 'by SB'). | Must | Reviewer v0.11 | 2
REQ-PRJ-11 | Project data | A clinical trial of either type records the EDC system, data review system and RBQM system in use, from data-driven value lists. | Must | Reviewer v0.11 | 2
REQ-PSN-01 | Person data | Data is managed by person, by project assigned, and by project role assigned. | Must | Requester | 2
REQ-PSN-02 | Person data | Each assignment records the project(s) the person is assigned to. | Must | Requester | 2
REQ-PSN-03 | Person data | Each assignment records the role(s) the person holds on that project, drawn from the role list valid for that project's type. | Must | Q-03 | 2
REQ-PSN-04 | Person data | Each assignment records the start date the person joins and the end date they leave that study. | Must | Requester | 2
REQ-PSN-05 | Person data | Each assignment carries a person weight saying how much that person works on that project, with optional period-specific overrides. | Must | Q-01 | 2
REQ-PSN-06 | Person data | The person record accepts further project-related information without a schema change. | Should | Requester | 2
REQ-PSN-07 | Person data | One person may hold assignments on several projects simultaneously, and may hold more than one role on the same project. | Must | Derived | 2
REQ-CAL-01 | Calculation | Resource is simulated on a monthly grid, default horizon 24 months, expandable to the latest project end date. | Must | Q-11 | 4
REQ-CAL-02 | Calculation | Monthly load for an assignment = project period weight x (role factor / people sharing that role) x person weight x fraction of the month covered. There is no separate base allocation. The role factor is selected by project type, clinical phase, WORK SCOPE, the period the month falls in, and the role - so a role's burden can vary across the life of a project and with how much of the work is kept in-house. | Must | Q-01, R-10, R-12, R-13 | 2,4
REQ-DSH-20 | Dashboard | AN ISSUE A MANAGER HAS REVIEWED IS SHOWN AS REVIEWED, AND THE REVIEW CAN BE READ FROM THE ISSUE. Each short, over or not-staffed project-month (REQ-DSH-15, REQ-DSH-17) can carry one review on the IssueReview sheet: a decision (Confirmed - no issue, Accepted, To be fixed), who confirmed it, when, why, and the gap it was made at. It is made and changed from the month itself - clicking the issue opens it - optionally across the whole run of consecutive months with the same issue. Confirmed and Accepted CLOSE the issue and need a reason: it stays marked, drawn muted, and its decision and reason are shown whenever it is opened; the open counts leave it out and count it apart. To be fixed keeps it open. A review whose month's gap has since moved, or whose issue has gone, no longer closes anything and is reported (V-40). | Should | R-62 | 4
REQ-DSH-19 | Dashboard | A ROW'S IDENTITY STAYS ON SCREEN WHILE ITS TABLE SCROLLS SIDEWAYS. A source-data sheet can be far wider than the panel that holds it - the Project sheet is twenty-five columns in a panel that shows less than half of them - so a reader editing a far column is working on a row with nothing on screen to say which record it is. The row's handle, its identifier and its name are FROZEN at the left edge and the rest of the table scrolls under them. They remain ordinary editable cells where they stand. Which columns is declared PER SHEET rather than per place the table is drawn, so one sheet cannot be pinned two ways, and only a leading run of columns can be frozen. The frozen cells must be OPAQUE in every state a row can be in - striped, hovered, selected, edited - because a row passing underneath would otherwise show through; and they must leave no seam at their boundaries, which costs a pixel of overlap that nothing can see. This changes no figure and no file. | Should | R-53 | 4
REQ-DSH-18 | Dashboard | ANY SECTION CAN BE GIVEN THE WHOLE WINDOW, AND THE DATA IN IT IS STILL EDITABLE THERE. Every panel holding a bounded scroll region carries a control in its head that draws that panel against the viewport instead of against the 1400px page column: the same table, every column it had, at the height of the screen rather than the 340px REQ-DSH-13 caps an entry table at. It is the SAME SCREEN and not a view of it - nothing is moved, nothing is copied, and editing, validation, the type-ahead, the column filters and the pop-ups all work exactly as they do on the page, because none of them is told it is happening. THE EDIT BAR AND THE TABS STAY IN FRONT: a full screen that hides Save is a trap, so the sticky band is lifted above the section rather than covered by it, and the section begins underneath it. The filter bar is covered and Escape brings it back. A SHELL WITH ITS OWN WINDOW BARS - the desktop and Python editions both put a title strip and a status strip above everything the page draws - keeps those in front too, and the section begins below them; the room they take is measured from the shells' own declaration of which elements they are, so the page layer names none of them. A section is remembered BY NAME, so it stays open across the re-render every committed edit causes, and across a change of selected row that rewrites its heading. Changing tab closes it, because a hidden pane draws nothing; loading a plan closes it, because that load's own report must not appear behind it. No figure changes and nothing is written to the file. | Should | R-51 | 4
REQ-DSH-17 | Dashboard | A PROJECT-MONTH THE PLAN ASKS FOR AND NOBODY IS ASSIGNED TO SHOWS WHAT IT ASKS FOR. Resource by project used to print a dot there, and a dot is a statement: it says this month costs nothing. For a month inside the project's own run with nobody on it that is false - what it costs is exactly what the standard for its type, phase, scope and period says, which the application has had all along (REQ-CAL-19: the project-month IS its standard, and the people on it divide it; a divisor of nobody does not make it nought). The figure is now drawn in the cell. DEMAND, NEVER RESOURCE, AND THE DIFFERENCE IS CARRIED BY THE DRAWING. No filled background - the sequential scale means this much is being done, and none of it is - an outline and a hatch instead, italic, and a hollow ring glyph in the cell so the distinction survives a monochrome print and a colour-blind reader (D-04). IT IS NEVER ADDED TO A TOTAL. Not the row total, not the column total, not the grand total: those stay the APPLIED figure, because the grand total of this table must equal the grand total of the person table and unallocated demand belongs to no person. Netting it in would also assert that somebody is doing the work, which is the opposite of what it says. It is totalled instead on a line of its own, and on the project's own row beside the applied total - counted apart and never netted, exactly as short and over are (V-34). ONLY WHERE THERE IS NOTHING. A month that already carries a figure keeps it untouched, whatever the standard says - V-34 is what reports a month being given less than it asks for, and this is for the months V-34 cannot see because they produced no line at all. So no existing figure moves: on the delivered fixture the count of such months is zero. AND THE HORIZON HAS TO REACH IT. The span offered by 'show everything' was taken from the assignment lines, so a project starting after every assignment in the file ended was not reachable at all and its figures would have been drawn in months off the screen. It is taken from these months too. | Should | R-49 | 4
REQ-DSH-16 | Dashboard | THE SCREEN IS READABLE AT THE SIZE THE PLAN ACTUALLY IS, AND SAYS WHAT ITS COLUMNS MEAN. Five things, none of which changes a figure. (a) A CHART THAT CAN RUN LONG GROWS WITH ITS HORIZON AND ITS PANEL SCROLLS. Every month is guaranteed a minimum width of plot; past the point where they all fit, the panel scrolls sideways rather than compressing the axis until its labels overlap. A fixed width is only readable over the span it was chosen for, and it fails silently - the chart still draws, it simply stops being legible, and it does so on the long plans that most need reading. The default two-year view is unchanged, so the rule is invisible to anyone who did not need it. (b) A WIDE TABLE GETS THE WHOLE WIDTH. Panels are placed side by side only where both are narrow enough to be read there; three tables of eleven, seven and eight columns are stacked, in the order the work is done in - the assignment, then its override windows, then its months - not tiled into halves that each scroll sideways permanently. (c) A PANEL THAT IS A CHILD OF A SELECTION NAMES THE ROW IT BELONGS TO, under its title, from ONE helper shared with every other panel that names the same thing, so two statements of the same fact cannot drift apart. (d) CLICKING A LEGEND ENTRY PICKS THAT SERIES OUT: everything that is not it fades back, a second click or Escape brings it home. Twenty bands in twenty shades of one palette read as a total and not as a series, and the fix is not more colours. THE PICK APPLIES TO THE WHOLE TAB, because the question asked is 'where is this project on this page'; a chart cut along a DIFFERENT axis, which has no mark for that key at all, is left alone rather than faded to nothing, since a chart with everything dimmed and nothing lit reads as 'this has no data' instead of 'this cannot answer that'. A mark standing for two series at once - a timeline band is a period OF a project - answers to either. Marks belonging to the MONTH rather than to a series never fade: thresholds, baselines, and the outline that marks a month off its standard are facts about the month and stay at full strength. Every entry is a button, operable from the keyboard and stating whether it is pressed (D-04). (e) EVERY COLUMN HEADING IS A PLAIN NAME, and the workbook's own column name is in the pop-up rather than on the page. Those column names are not, by themselves, labels, and their meaning existed only in a pop-up - which is to say only for a reader who knew to hover. WHERE THE IDENTIFIER BELONGS WAS SETTLED TWICE and the second answer is the one to keep: it was first printed on a second line under the label, because the screen and the file are the same thing and a heading must be findable in the spreadsheet; but looking a column name up is OCCASIONAL - editing the workbook, chasing a finding - while a heading is read on EVERY glance, so printing it charged the common case for the rare one when the pop-up already answered it in full. Every heading carries a pop-up naming both, and the identifier as data-cid for whatever must read it. Nothing is renamed, the cell still writes back through the identifier, and the same two-part head is used on the heading's pop-up, on every cell's and on the filter buttons', so it is learned once. | Should | R-45 | 4
REQ-DSH-15 | Dashboard | WHERE A PROJECT IS NOT BEING GIVEN WHAT ITS OWN STANDARD SAYS IT NEEDS, THE APPLICATION SAYS SO. Two figures can come apart and the obvious pair is not one of them: a project's month against the sum of its people CANNOT differ, because the month is built from those people (REQ-OUT-06). The pair that does is DEMAND against APPLIED. An automatic month has them equal by construction - the shares add to one (REQ-CAL-19) - and a figure stated by hand at either level replaces the standard rather than adjusting it, after which the application simply drew a different project: a study needing 10.00 and staffed at 5.00 looked exactly like a study that only ever needed 5.00. FOUR SURFACES, chosen so that nothing has to be suspected before it is seen. V-34 reports it, which carries it into the findings report, the load banner, the archived change log and the results export at no further cost. The figure is MARKED where it is drawn - in Resource by project and on the project's own utilisation chart - because a shortfall that must be hovered over is very nearly as silent as one nobody reports. A TILE on Overall counts it beside the over- and under-allocation tiles, in the place people already look. And the LIST of every month with what it needs, what it is getting and the gap opens from RESOURCE BY PROJECT's own head (R-52), where every month in it is a cell in the table beside it. It was a section under the tiles, on the ground that something whose whole danger is being silent must not sit behind a click; moving it keeps that property by moving it to the CONTROL, which states the count and the direction rather than naming the screen - so the alarm is on screen with nothing opened, and only the list, which nobody reads until they are investigating, is a click away. The control is present even when it has nothing to report. THE LIST CAN BE NARROWED - by direction, by project, and by a smallest gap worth looking at - and the narrowing reaches the LIST ONLY: the tile and the control go on counting every month off its standard, since they are the alarm and an alarm that followed somebody's own view would be lying about the plan. A narrowed list says how many of how many, and one emptied by its own filter says that rather than that there is nothing to report. Not a tab either: a tab is the surface you visit only once you already suspect a problem - and the findings report is already the list of everything wrong. EVERY ROW OPENS THE MONTH ITSELF, AND EVERY FIGURE IN IT CAN BE CHANGED THERE. A month that already has a MonthlyEstimate row is an ORDINARY editable cell over it, so the one editing path validates, logs, marks and undoes it; a second way to change a figure is a second way that can drift. A month that has NO row cannot be one - there is nothing to write through - so its cell offers to CREATE the row instead, and it must, because the figure a reader most wants to change on this screen is the one belonging to somebody still on automatic, and a dash there said the screen was read-only for them. WHAT IT MUST NOT DO IS QUIETLY WRITE ONE ROW: an automatic assignment ignores MonthlyEstimate entirely, so a lone row is a figure nothing reads, and setting estimation_type without seeding the other months counts every one of them as 0.00 - the one change in this application that silently zeroes a figure (REQ-CAL-18). So a figure typed against an automatic assignment ASKS, naming how many months will be stated and what this one becomes, and then the switch, the seeding and the typed figure happen together or none of them happen. A thing ALREADY manual with no figure for that month is V-31 and does not ask - the months are already the user's, and asking would be asking permission for something already given. BOTH DIRECTIONS, COUNTED APART AND NEVER NETTED: short of the standard is a project asked to run on less than its kind takes, over it is one deliberately staffed heavier, and five short in September against five over in October is not a plan in balance however the arithmetic reads. Marked with an arrow as well as a colour (D-04) - amber and red are the confusable pair and they are exactly the two directions here. | Should | R-42 | 4
REQ-DSH-14 | Dashboard | WHERE A FIGURE'S SIZE WAS DECIDED SOMEWHERE ELSE, THE TABLE SHOWING THE FIGURE NAMES WHAT DECIDED IT, in a column that is looked up and cannot be edited. Three of them, because three tables each showed one term of an expression and left the reader to find the rest in another tab: the Periods table names the STANDARD MONTHLY FTE its period selects and multiplies it by the project's own weight, so the row carries the month's demand instead of half the expression for it; both Monthly estimation panels carry THE WHOLE DERIVATION OF THE MONTH, TERM BY TERM - the period it falls in, the standard that period selects, the project's own weight, how much of the month it ran, and their product - so a reader who disagrees with an automatic figure can see WHICH of the inputs they disagree with rather than only that they disagree. The person's panel adds their CLAIM on that month: role factor / sharers x person weight x month coverage, ending in the PERCENTAGE of the project's month it won. The two halves are closed off SEPARATELY and the person's is stated as a proportion, never as a product equal to the figure, because since R-32 it is not one - the claim is normalised against every other claim on that project-month (REQ-CAL-19), so terms multiplying to 0.60 can give a figure of 2.40, and writing them as one product would assert an arithmetic the application does not do. A PersonPeriodWeight override is shown as ONE TERM WITH TWO SOURCES rather than as a second factor: it REPLACES person_weight for the months it covers (REQ-PSN-05), and the cell names both values and says which was used. The sharer count also keeps a short column of its own, where it can be sorted and filtered - the derivation is a sentence and is neither. Every fallback SAYS it is a fallback and names its rule - V-19 for a missing standard, V-23 for a missing role factor, V-12 for a month in no period - because a bare 1.00 is indistinguishable from a standard that really is 1.00, which is the whole reason those rules exist. LOOKED UP, NEVER STORED: none of the three is a column of the sheet it is shown beside, so no edit and no save can leave a stale copy of a standard in a file after the standards have moved - which is the failure the lookup exists to prevent. NAMED FROM THE CALCULATION'S OWN WORKINGS, not by asking the sheets again, so a screen cannot name one period while the figure beside it came from another. A missing standard says it is missing and names V-19 rather than printing the 1.00 the calculation falls back to; that fallback is a degradation, and showing it as a standard would hide the very thing V-19 reports. | Should | R-40 | 4
REQ-DSH-13 | Dashboard | Every bounded scroll region draws its own scrollbars rather than relying on the browser's. A region deliberately capped on both axes is only honest if the reader can see there is more and reach it, and the browser's bar does not do that on a build that uses overlay scrollbars: it occupies no layout space and fades out when idle, so a table with eleven columns off to the right looks exactly like one with none. The drawn bar is present whenever there is anywhere to scroll to, can be dragged, and pages when its track is clicked. Native scrolling - wheel, shift-wheel, trackpad, keyboard - is untouched. | Must | R-23 | 4
REQ-CAL-20 | Calculation | EVERY FTE FIGURE THE APPLICATION PRODUCES IS A WHOLE NUMBER OF HUNDREDTHS - not displayed to two places, but IS two places. The rounding happens once, where a person-month is decided, so the screen, the results export, the change log and all four independent implementations report the same number: a figure shown as 4.27 was 4.27 when it was worked out, not 4.2683 dressed up for a table. Two places because that is the granularity the plan is written in: at 160 hours to the FTE, 0.01 is 1.6 hours, the smallest edit that means anything to somebody staffing a study, and already what a manual estimate is typed at (REQ-CAL-18). ROUNDING EACH SHARE ON ITS OWN WOULD NOT DO - round three shares of 4.27 separately and they come to 4.26 or 4.28, so the detail rows would stop summing to the month (REQ-OUT-06) and the shares would stop adding to one (REQ-CAL-19); measured on the 62-project fixture that missed on 644 of 1,629 project-months. So THE MONTH IS ROUNDED FIRST AND ITS HUNDREDTHS ARE HANDED OUT: each line takes its floor and the hundredths left over go to the lines with the largest remainders, one each - the largest-remainder method, which makes both guarantees exact by construction rather than by tolerance. THE TIE-BREAK IS PART OF THE RULE: where two remainders are equal the hundredth goes to the line whose assignment_id sorts first, a total order that does not depend on array order or on the order rows were read from a sheet. Without it two implementations could differ by 0.01 and both be right. A row therefore sits up to 0.01 from the exact product of its own terms - measured worst 0.0070 - and the results export says so. Hundredths are counted as integers throughout, so the arithmetic cannot introduce the error it exists to remove. | Must | R-38 | 4
REQ-CAL-19 | Calculation | A PROJECT-MONTH IS ITS STANDARD. PeriodFTEStandard.standard_fte is the DEMAND in FTE for a project of this type, clinical phase and work scope in this period; ProjectPeriod.weight ADJUSTS it for the particular study (1.00 = an ordinary project of its kind); and the product, scaled by how much of the month the project actually ran, IS the month. The people on it DIVIDE that month rather than each adding to it. Every term that used to reduce a figure now decides a share: role factor / people holding that role, times person_weight, times that person's own month coverage, makes a CLAIM; the claim over the sum of the claims is the SHARE; the share times the demand is the figure. THE SHARES ADD TO ONE BY CONSTRUCTION, so the month is its demand however many people are on it and whatever their weights - an unstaffed role's work lands on the others (REQ-CAL-16 decides on WHOM), and a part-time commitment pushes load onto colleagues rather than making the project cheaper. Under-staffing is therefore visible on the PEOPLE, as months over the ceiling, and never as a project that costs less than the work it contains. The month a project ran is taken as the largest coverage any of its people have, so a project whose period ends on the 10th draws a third of a month rather than a whole one. A missing standard falls back to 1.00 and V-19 reports it. | Must | R-31, R-32 | 4
REQ-CAL-18 | Calculation | A PROJECT, OR ONE ASSIGNMENT, MAY HAVE ITS MONTHLY FTE STATED RATHER THAN CALCULATED. estimation_type on Project and on Assignment selects which; MonthlyEstimate carries the stated figures. TWO LEVELS, applied in that order: an ASSIGNMENT figure IS that person's contribution to that project and replaces the share R-32 would otherwise have given them; a PROJECT figure is the whole month, and every person on it that month is SCALED so they still add up to it - because a project total that did not equal the sum of its people would put the two utilisation charts in disagreement and cost the results export its one guarantee. The scaling factor is recorded on every line, so a person whose figure moved with nothing of their own changing can find out why. MANUAL IS ALL OR NOTHING for the thing it is set on: switching copies every month across from the figures currently on screen, so nothing jumps, and switching back discards them all. The copy is written to TWO DECIMAL PLACES: a stated figure lands in a cell somebody reads and edits, and two places is the finest edit that means anything in the unit people think in - at 160 hours to the FTE, 0.01 is 1.6 hours. A month can therefore move by up to 0.005 FTE, about 48 minutes, at the moment of switching. Per-month marking was considered and rejected - once a figure has been edited, months still calculated would keep moving under a signed-off plan whenever an assumption changed, and 'which months are mine' has no useful answer. Every change of calculation way is CONFIRMED, in both directions. A project figure in a month nobody is assigned to cannot be shared out and is NOT applied (V-32); a manual thing with a month carrying no figure counts that month as 0.00 and V-31 says so. | Must | R-30 | 4
REQ-CAL-17 | Calculation | A PROJECT'S WINDOW, wherever the calculation needs one, is the span of its ProjectPeriod rows: the earliest period_start to the latest period_end. Milestones are reference dates - the period derivation reads them, and several of them mark moments inside the run rather than its edges - so they describe the periods, they do not bound the project. Taking the window from them stretched a project over months belonging to no period, and a month in no period is weighted 1.00, so the project drew resource its own plan did not cover. A project with NO periods keeps its own typed dates, because there is nothing to take a window from and V-12 already reports that. This is what a blank assign_start_date or assign_end_date means (REQ-CAL-15). Save writes the same window back into Project.start_date and Project.end_date, with ONE difference: it reads the periods the user TYPED, and falls back to the milestone span where there are none. A trial whose periods are derived has them opened at its own start_date, so taking the saved window from those would read back the very dates being checked and a wrong window could never correct itself; there the milestones are the only independent statement of when the project runs. Typed periods beat them wherever both exist. | Must | R-20 | 4
REQ-CAL-16 | Calculation | Where NOBODY holds a role on a project, its role factor is added to the factor of the role named in RoleFactor.absorbed_by - because the work still has to be done by whoever is there. A trial run without a Clinical Data Associator still has the data to handle, and it lands on the lead data manager, who is then under more pressure than the factor for their own role alone describes; costed without it, the project looks cheaper than it is. Counted PER MONTH, so cover ends by itself when somebody arrives. ONE HOP: if the absorbing role is itself unstaffed the work is not passed further along - V-29 reports that rather than piling three absent roles onto whoever is left. Which role covers for which is DATA, on RoleFactor.absorbed_by, never in the program (REQ-CAL-06). Kept as the setting absorb_unstaffed_role_factor. | Must | R-17 | 4
REQ-CAL-15 | Calculation | BOTH ASSIGNMENT DATES ARE OPTIONAL. A blank assign_start_date means the project's own start date, and a blank assign_end_date the project's own end date - so an assignment with neither runs for the whole project, which is what most assignments are. Filling them in is for a PARTIAL involvement. The end date already behaved this way; the start did not, and a blank one made the assignment contribute nothing at all with no finding to say why. | Must | R-15 | 4
REQ-CAL-14 | Calculation | Where SEVERAL PEOPLE hold the same role on the same project in the same month, the role factor is DIVIDED BETWEEN THEM. The role factor states what the ROLE costs the project in that period, not what each person holding it costs, so a project staffed by two data managers must not cost twice a project staffed by one. The count is per month, so a sharer leaving restores the others' full share without any edit; it counts distinct PEOPLE, so one person recorded on two rows is one person; and each person's own person_weight then applies to their share. Kept as the setting split_shared_role_fte so a figure produced before this rule can still be reproduced. | Must | R-13 | 4
REQ-CAL-03 | Calculation | Project monthly load is the sum of its assignments; person monthly load is the sum across all their projects. | Must | Requester | 4
REQ-CAL-04 | Calculation | A person-month whose total exceeds the over-allocation threshold (default 1.50 FTE) is flagged as over-allocated. The threshold is absolute, not scaled by capacity (S2-01). | Must | Q-08, S2-01 | 4
REQ-CAL-05 | Calculation | A partial first or last month is pro-rated by calendar days worked, not counted as a whole month. | Must | Q-02 | 4
REQ-CAL-06 | Calculation | All weights, factors and thresholds are data, held in the source workbook, never hardcoded in the program. | Must | Derived | 4
REQ-CAL-07 | Calculation | A person whose monthly total stays below the under-allocation threshold (default 0.60 FTE) for three or more consecutive months is flagged as under-allocated, with the run's start and length reported. The threshold is absolute, not scaled by capacity. | Must | Q-08, S2-01, S2-05 | 4
REQ-CAL-08 | Calculation | Load is expressed in FTE, where 1.00 FTE = 160 hours per month (8 h/day x 5 days/week x 20 days/month). Hours are shown alongside FTE where useful. | Must | Q-08 | 4
REQ-CAL-09 | Calculation | For a clinical trial of either type, period boundaries are computed from milestone dates plus fixed month offsets (sheet 05), so a timeline change re-shapes the periods without re-typing them. For 'Others', periods are entered directly - those projects have no milestone mapping. | Must | Q-16, Q-22, Q-23, Q-25 | 2,4
REQ-CAL-10 | Calculation | Every month of a project's timeline falls in exactly one period. A month left uncovered by the derivation is reported and carries weight 1.00 rather than being dropped from the simulation. | Must | Derived from Q-16 | 2,4
REQ-CAL-11 | Calculation | Where an interim DB lock splits the conduct phase, the two stretches are separate rows carrying DIFFERENT names: 'Conduct (interim)' before the interim lock, 'Conduct (final)' after it. A project with no interim lock carries a single 'Conduct (final)'. Period names are therefore unique within a project. | Must | Q-23, R-11 | 2,4
REQ-CAL-13 | Calculation | Where a period boundary has both a milestone and a month-offset definition, a recorded milestone date wins. The offset is the fallback for a project that does not carry that milestone. | Must | R-02 | 2,4
REQ-CAL-12 | Calculation | Where a timeline squeezes a derived period to zero or negative length, that period is omitted and the omission reported. Boundaries are applied in order so the periods always stay contiguous. | Must | Derived from Q-22, Q-23 | 2,4
REQ-DSH-01 | Dashboard | Tab 'Overall' shows monthly resource simulation per project and per person as tables. | Must | Requester | 3,4
REQ-DSH-02 | Dashboard | Tab 'Overall' shows appropriate graphs of the same simulation. | Must | Requester | 3,4
REQ-DSH-03 | Dashboard | Tab 'Source data (project)' shows project information as a table. | Must | Requester | 3,4
REQ-DSH-04 | Dashboard | Tab 'Source data (person)' shows person information as a table. | Must | Requester | 3,4
REQ-DSH-05 | Dashboard | One filter set drives every tab: date horizon, project type, clinical phase, project, person, role and department, with a single action to clear them all. The display unit is a setting, not a filter - it changes how figures are written, not which are shown. | Should | Derived / O-03 | 3,4
REQ-DSH-06 | Dashboard | Any table on screen can be exported to Excel. | Should | Derived | 4
REQ-DSH-07 | Dashboard | The horizon control offers 24 months by default and a one-click expansion to cover the latest project end date across all projects. | Must | Q-11 | 3,4
REQ-DSH-08 | Dashboard | Over-allocated and under-allocated person-months are distinguishable at a glance, and both are counted in the summary tiles. | Must | Q-08 | 3,4
REQ-DSH-09 | Dashboard | THE PER-PERSON CHART SHOWS AN AGGREGATE OR A RANKED SUBSET rather than one bar per person, and says which it is showing. A thousand bars is not a chart, and neither is two hundred: past the point where a bar is narrower than the gap beside it the drawing stops carrying information, so the cap is on the BARS and not on the data - the remainder is rolled into one band and named, never dropped. A TABLE TALLER THAN THE VIEWPORT SCROLLS INSIDE ITS OWN PANEL, keeping its header row visible, and the page body never scrolls to reach it. Sorting, filtering and totals are computed over the whole model rather than over whatever is currently drawn - which is the property that must hold whether or not the rows are virtualised, and is therefore the one stated here. ROW VIRTUALISATION IS NOT REQUIRED AT THE VOLUME REQ-NFR-03 NAMES, and the clause that required it was removed at R-47 rather than carried as a Must nobody intended to build. Measured: the Overall pair renders 252 rows x 60 months in 810 ms against a 1,000 ms budget, and the budget is first crossed at about 400 people. Virtualisation becomes a requirement if and when a volume past that is asked for; until then it would change no number a user feels, and the measurement that says so is reproducible from two commands. | Must | S2-06, R-47 | 3,4
REQ-DSH-10 | Dashboard | Every period of a project is distinguishable from every other on screen. Since R-11 this is satisfied by the data model rather than by a display rule - no name repeats, so a name alone identifies a period. The display numbering that satisfied it before is retained only as a guard against a repeat reaching the renderer. | Must | S2-04, R-11 | 3,4
REQ-DSH-12 | Dashboard | The project source-data tab shows the selected project's monthly resource over the horizon, against RELATIVE reference lines - a multiple and a fraction of the average an active project draws across the portfolio, and the project's own average over its full life. A project has no absolute ceiling or floor, so the references are context rather than pass or fail. | Should | Reviewer v0.7 | 3,4
REQ-DSH-11 | Dashboard | The standing assumptions the simulation multiplies by - standard period weights, role factors, configuration and value lists - are presented on their own tab, so a reader can see what every figure was derived from without opening the workbook. | Must | G-07 | 3,4
REQ-IMP-01 | Import/Export | The user loads the source workbook through a file picker or drag-and-drop, chosen because a local HTML page cannot open a file from disk unaided. | Must | Decision D-01 | 4
REQ-IMP-02 | Import/Export | Loading validates the workbook and reports every problem found - missing sheet, missing column, bad date, unknown project reference - without stopping at the first one. | Must | Derived | 4
REQ-IMP-03 | Import/Export | A blank source workbook template with correct sheet names, headers, value lists and one example row is delivered with the application. | Must | Derived | 4
REQ-IMP-04 | Import/Export | The user can export current data back to .xlsx, preserving the template layout so the export can be re-imported. | Must | Derived | 4
REQ-IMP-05 | Import/Export | The application records which file was loaded and when, and shows it on screen with its time zone - a bare timestamp is ambiguous to anyone reading it from another country. | Should | Derived / G-02 | 4
REQ-IMP-06 | Import/Export | Loaded data may be cached in the browser so re-opening the page does not force a re-import; the cache never replaces the workbook as the record. | Could | Derived | 4
REQ-IMP-07 | Import/Export | After import, the application lets the user update the data on screen, and those updates are carried into the file produced on export. | Must | Reviewer v0.11 | 4
REQ-IMP-08 | Import/Export | Unsaved edits are visible as such, and the user is warned before any action that would discard them (closing the page, loading another file). | Must | Derived from REQ-IMP-07 | 4
REQ-IMP-09 | Import/Export | Every field is editable, including identifiers. An on-screen edit is re-validated against the same rules as an imported value, so editing cannot introduce data the import would have rejected. | Must | Q-20 | 4
REQ-IMP-10 | Import/Export | Editing an identifier that other sheets reference cascades to every referencing row, after showing how many rows will change. Deleting a referenced row is refused, naming what still points at it. | Must | Q-20 | 4
REQ-IMP-14 | Import/Export | An import that changes any Config setting says so. The settings in force are captured before the model is replaced and compared by name afterwards; every setting whose value differs, or that the incoming file adds or does not carry, is named on the load banner and listed on a screen of its own with what it was, what it is now, and what it affects - a calculation rule, an allocation threshold, or display only. The settings are APPLIED either way: importing a workbook means taking its settings, which is what makes a plan reproducible from the file alone. This is a check, not a gate. A first load has nothing to compare against and reports nothing. | Must | R-28 | 4
REQ-OUT-06 | Output | The application exports the CALCULATED MONTHLY FTE as well as the source plan, and the export control offers the choice with each option described. The results workbook is derived throughout and cannot be imported, which its first sheet states. It carries: the Overall tab's summary figures; one row per project per month and one per person per month; a DETAIL sheet of one row per assignment per month carrying every term of the multiplication that produced it, so any figure can be checked without the application; the allocation flags; and the settings in force, marked for whether each changed a figure or only its display. Every monthly figure is exactly the sum of its detail rows and every total is exactly the sum of those. The file covers the horizon and filters that were on screen, and names them. SINCE R-55 IT ALSO SAYS WHAT EACH PROJECT NEEDS: every project-month carries its demand, its staffed figure, the gap between the two and the direction of the gap, once per project-month, so nobody has to derive demand from the detail rows, where it repeats on every row of the month; a month the periods ask for and nobody is on is a row of its own, because the largest shortfall must not be the one the file cannot show; the gap is the WHOLE project's whatever filter is on; and the flags carry project runs short of, over and unallocated against the standard beside the person flags. Every month a person is employed and on nothing is a person-month row of its own, at 0, so the file shows spare capacity as well as overload. | Must | R-29 | 4
REQ-IMP-12 | Import/Export | A column that holds a DATE offers a calendar panel beside the cell being edited, and the cell stays fully typeable while it is open: the caret does not move, every key still reaches the cell, and what is typed steers the panel to that month. Picking a day commits it through the ordinary edit path, so it is validated exactly like a typed one. Deliberately not the browser's own date control, which would give one editing model for text cells and another for dates - a different keyboard contract, a browser-dependent display format, and no way to leave a date deliberately blank the way every other cell does. | Should | R-21 | 4
REQ-IMP-13 | Import/Export | Every validation rule carries a CLASS saying what the application may do about it, separately from its severity. MUST: something is wrong with the row itself and it is refused, on the cell edit and at Save. CONDITIONAL: the row is sound but something it depends on is missing, so the figures that need it are short an assumption - never refused, and at Save the application names every one that this batch of edits leaves unresolved and asks the user to confirm before keeping them. INCOMPLETE: the row is still being built and the finding will answer itself - reported, never questioned. The class is shown beside the severity wherever findings are listed. | Must | R-25 | 4
REQ-IMP-11 | Import/Export | A new row can be inserted into any editable table, positioned immediately below the row the user acts on rather than appended at the end, and validated on entry like any other edit. | Must | P-01, S-01 | 4
REQ-VC-01 | Version control | Development plan, programming specification and output files are version-controlled together and their versions are cross-referenced. | Must | Requester | 1-5
REQ-VC-02 | Version control | The application displays its own version, and the version of the source data schema it expects. | Must | Requester | 4
REQ-VC-03 | Version control | Loading a source file whose schema version is newer or older than the application expects produces a clear warning. | Should | Derived | 4
REQ-VC-04 | Version control | Every document re-issue adds a version-history row stating what changed and why. | Must | Requester | 1-5
REQ-NFR-01 | Non-functional | The application is built so later requirements can be added without restructuring: parsing, calculation and presentation are separated. | Must | Requester | 4
REQ-NFR-02 | Non-functional | Works in Microsoft Edge and Google Chrome on Windows 10/11, offline. | Must | Q-05 | 4
REQ-NFR-03 | Non-functional | HANDLES 100 PROJECTS AND 150 PEOPLE over a 60-month horizon, with the assignments that implies (order 1,000). MEASURED AT THAT VOLUME, NOT ESTIMATED (tools/build_stress_workbook.py builds the fixture, tools/measure_scale.py drives it): switching to the Overall tab takes 810 ms against a 1,000 ms budget, worst case 894; import 1,182 ms against 5,000; one cell edit 60 ms and opening a column filter 51 ms, each against 1,000 and 600. The budgets were fixed before any number was seen. THE BINDING COST IS THE OVERALL PAIR, whose two tables are (projects + people) rows x horizon months - 252 rows x 60 months here - so the figure to re-measure against is the ROW COUNT and the HORIZON together, not the project count alone. 100 x 150 is the largest volume measured whose WORST case is still inside budget: 100 x 200 medians 981 ms and peaks at 1,225, which is over. The budget is crossed at about 400 people, and only beyond that does row virtualisation become necessary - see REQ-DSH-09. AMENDED AT R-47 from 100 projects and 1,000 people, a figure set at S2-06 and never measured. At 1,000 people the tab takes 3,058 ms; but about half the overage is the CALCULATION - 180,160 person-months - which virtualisation cannot reach, so that volume was never one requirement away from working. | Must | S2-06, R-47 | 4
REQ-NFR-04 | Non-functional | No data leaves the PC: no network calls, no external CDN, no telemetry. | Must | Derived | 4
REQ-NFR-05 | Non-functional | Dates are handled unambiguously (ISO yyyy-mm-dd internally) regardless of Windows regional settings. | Must | Derived | 4
Requirement count by priority
Priority | Count
Must
Should
Could
Total
47 requirements at v0.1, 58 at v0.2, 61 at v0.3, 63 at v0.4 and v1.0. v1.1 adds 2 and rewords 3, as a change against the approved baseline.
'Source' = Requester (in the original request), a Q-number (answered at v0.11 review), 'Reviewer v0.11' (added by the reviewer directly), Derived (engineering consequence), or a Decision ID from 07_Architecture.
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 04_Data_Model
Data model - source Excel structure
ONE workbook, PRAP_SourceData.xlsx, with the sheets below (changed at Q-09). This is the schema Step 2 will fix and the code will parse.
Sheets in PRAP_SourceData.xlsx
Sheet | Purpose | Kind
Project | One row per project. | Master
Milestone | One row per project milestone. | Child of Project
ProjectPeriod | The four standard periods per project, with their start/end and weight. | Child of Project
PeriodFTEStandard | THE STANDARD MONTHLY FTE per project type, phase, work scope and period - where every figure gets its size (REQ-CAL-19). | Reference
RoleFactor | Role burden factor, per project type, clinical phase and period. | Reference
Person | One row per person. | Master
Assignment | One row per person + project + role. | Link
PersonPeriodWeight | Optional time-varying override of the person weight. | Child of Assignment
MonthlyEstimate | Monthly FTE stated by hand instead of calculated, for a project or for one assignment (REQ-CAL-18). | Child of Project or Assignment
Lists | Value lists for every data-driven dropdown, so lists change without code. | Reference
Config | Parameters: schema version, thresholds, horizon, FTE hours. | Reference
Sheet: Project
Column | Type | Required | Definition / rule | REQ-ID
project_id | Text | Yes | Unique key, e.g. PRJ-001. Referenced by every other sheet. | REQ-PRJ-03
project_name | Text | Yes | Unique display name. | REQ-PRJ-03
project_type | List | Yes | 'NewDrug CT', 'Biosimilar CT (Healthy)', 'Biosimilar CT (Patient)' or 'Others'. Everything but 'Others' is a clinical trial. SCHEMA 6 split the single 'Biosimilar CT' in two: a healthy-volunteer study and a patient study are not the same workload, and one value could not say which. A project type is recognised as a trial by the START of its name, so a further subdivision is a change to the value list rather than to the code. | REQ-PRJ-01, R-12
project_category | Text | Conditional | Product name. Required for either clinical trial type. | REQ-PRJ-02
clinical_phase | List | Conditional | 'Phase 1' / 'Phase 2' / 'Phase 3' / 'Phase 4'. Required for either clinical trial type. | REQ-PRJ-09
work_scope_type | List | Yes | How much of the work is done in-house: 'fully in-housed' / 'fully outsourced' / 'Partially outsourced (in-house for EDC)', extensible on the Lists sheet. SCHEMA 6. Part of the key into PeriodFTEStandard and RoleFactor - a trial run entirely in-house costs this team more than the same trial handed to a CRO, and the weights are where that belongs. Since schema 7 it is the ONLY scope field the calculation reads, and the one the dashboard's scope filter offers. | R-12, R-16
outsourcing_scope_det | Text | No | FREE TEXT: what is outsourced and to whom, in your own words - the detail a category cannot carry. Read by people, never by the calculation. SCHEMA 7 renamed it from outsourcing_type and changed it from a value list to free text: with work_scope_type driving the weights, a second controlled vocabulary on the same axis was a field to keep in step for no benefit, and V-25 existed only to police the two against each other. A workbook still carrying outsourcing_type is read - the values move across and the application says so once. | REQ-PRJ-04, R-16
EDC_setup | List | Conditional | Who sets up the EDC system. 'by CRO' / 'by SB'. Required for either clinical trial type. | REQ-PRJ-10
DataReviewSystem_setup | List | Conditional | Who sets up the data review system. 'by CRO' / 'by SB'. | REQ-PRJ-10
RBQM_setup | List | Conditional | Who sets up the RBQM system. 'by CRO' / 'by SB'. | REQ-PRJ-10
DM_conduct | List | Conditional | Who reviews the clinical trial data. 'by CRO' / 'by SB'. | REQ-PRJ-10
EDC_system | List | Conditional | EDC system name, e.g. 'Veeva EDC' / 'Rave' / 'eSOURCE'. Data-driven list. | REQ-PRJ-11
DataReviewSystem | List | Conditional | e.g. 'Veeva DQS' / 'Medidata CDS' / 'No system (manual)'. Data-driven list. | REQ-PRJ-11
RBQM_system | List | Conditional | e.g. 'CluePoints' / 'Medidata CDS' / 'No system (manual)'. Data-driven list. | REQ-PRJ-11
planned_member_count | Integer | No | Planned number of project members; compared against actual assignments. | REQ-PRJ-04
start_date | Date | Yes | Project start. | REQ-PRJ-05
end_date | Date | Yes | Planned project end. | REQ-PRJ-05
total_period_months | Derived | - | Calculated from start_date and end_date; not entered by hand. | REQ-PRJ-08
status | List | No | Planned / Active / On hold / Completed. Drives default dashboard filtering. | REQ-PRJ-07
estimation_type | List | No | SCHEMA 9. 'automatic' (the default, and what a blank means) or 'manual'. Manual means this project's monthly FTE is STATED on MonthlyEstimate rather than worked out from the assumptions, and the people assigned each month are scaled to add up to the stated figure (REQ-CAL-18). | REQ-CAL-18
note_1 .. note_5 | Text | No | Free extension columns. | REQ-PRJ-07
system_prepared_by is dropped at v0.3 (Q-19): the four *_setup columns replace it with more detail.
Sheet: Milestone
Column | Type | Required | Definition / rule | REQ-ID
project_id | Text | Yes | Foreign key to Project. | REQ-PRJ-05
project_name | Derived | No | DERIVED - looked up from Project on import and refreshed from it, so a mismatch cannot corrupt the link. Locked in the template; a value typed here is discarded and the disagreement reported as V-13. | REQ-PRJ-05
milestone_name | List | Yes | Standard list (10) at v1.1: 'Protocol (v1)', 'CTA submission', 'FPI', 'First SIV', 'LPI', 'interim DB lock cut-off', 'interim DB lock', 'final DB lock cut-off', 'final DB lock', 'Inspection'. FPI returns as the fallback for First SIV; Inspection is new and MAY REPEAT within a project. Held in Lists, not fixed in code. | REQ-PRJ-05, REQ-PRJ-13
milestone_date | Date | Yes | Planned date. | REQ-PRJ-05
milestone_highlight | List | No | OPTIONAL, schema 13. Marks this milestone on every Project timeline in a colour - the Overall tab's and the project's own. Held in Lists ('Highlight (Red)' and twelve more since R-64, REQ-PRJ-17); what is read is the COLOUR WORD inside the value, so a team may add what their colour means and keep both. Empty means no mark, which is what every milestone was before schema 13. A value naming no colour is reported as V-37 and drawn unmarked. | REQ-PRJ-14
milestone_seq | Integer | No | Carried in the file and kept on export; allocated on insert. It ORDERS NOTHING - both engines place a milestone on the timeline by its date - and since R-54 the application does not draw it. | REQ-PRJ-05
note_1 | Text | No | Free extension column. | REQ-PRJ-07
Boundary milestones at v1.1: Protocol (v1), First SIV (or FPI), CTA submission, the DB locks, and Inspection. Only LPI and the two cut-off dates remain pure markers. milestone_seq orders repeated Inspection rows; uniqueness is on (project_id, milestone_name, milestone_date), not on name alone.
Sheet: ProjectPeriod [was ProjectPeriodWeight]
Column | Type | Required | Definition / rule | REQ-ID
project_id | Text | Yes | Foreign key to Project. | REQ-PRJ-06
period_name | List | Yes | From the period set for the project's TYPE - see the two sets below. A period name from the wrong set is rejected. UNIQUE within a project since R-11, so (project_id, period_name) is the key. | REQ-PRJ-12, REQ-CAL-11, R-11
period_seq | Integer | Yes | Orders the periods along the timeline. Unique within a project. No longer part of the key - it carries order, not identity (R-11). | REQ-CAL-11
period_start | Date | Yes | Inclusive. For Clinical Trial, computed from milestones (sheet 05) and then editable. For Others, entered directly. | REQ-CAL-09
period_end | Date | Yes | Inclusive. Periods for one project must not overlap and must leave no gap (REQ-CAL-10). | REQ-CAL-09
period_highlight | List | No | OPTIONAL, schema 14. The colour this period is drawn in on every Project timeline. Held in Lists (period_highlight: 'Highlight (Red)' and twelve more since R-64); what is read is the COLOUR WORD inside the value. Empty means GRAY, shaded by weight. A value naming no colour is reported as V-38 and drawn gray. | REQ-PRJ-15
weight | Decimal | Yes | THIS PROJECT'S OWN ADJUSTMENT to the standard for its type, phase and scope (REQ-CAL-19). 1.00 means an ordinary project of its kind; 1.20 means this one takes a fifth more. SCHEMA 10 changed what it means: until then it carried the magnitude itself and the standards sheet was read by nothing, so the delivered data held the same number in both columns. Values are data (Q-17), not fixed in this plan. | REQ-PRJ-06, R-31
note_1 | Text | No | Free extension column, e.g. why a derived date was overridden. | REQ-PRJ-07
Sheet: PeriodHighlight [schema 15, R-60]
Column | Type | Required | Definition / rule | REQ-ID
period_name | List | Yes | A period name from either period set. One row per name; a second is V-39 and ignored. | REQ-PRJ-16
period_highlight | List | No | The default colour of every project's period of this name, from Lists.period_highlight; the COLOUR WORD is read. Empty = gray. A project's own ProjectPeriod.period_highlight wins. | REQ-PRJ-16
note_1 | Text | No | Free text, e.g. what the colour is meant to say. | REQ-PRJ-07
Sheet: IssueReview [schema 16, R-62]
Column | Type | Required | Definition / rule | REQ-ID
project_id | Text | Yes | The project the issue is on. Must exist on Project. | REQ-DSH-20
month | Text | Yes | The month, YYYY-MM. | REQ-DSH-20
issue | List | Yes | short, over or unstaffed (Lists.issue_kind). One review per project, month and issue; a second is ignored. | REQ-DSH-20
status | List | Yes | Lists.issue_review_status: 'Confirmed - no issue' and 'Accepted' CLOSE the issue (drawn muted, left out of the open counts); 'To be fixed' keeps it open. | REQ-DSH-20
gap_fte | Decimal | No | The gap as reviewed (negative short or not staffed, positive over). If the month's gap is no longer this, to the cent, the review no longer closes it (V-40). | REQ-DSH-20
rationale | Text | No | Why. Required by the application for a closing decision; shown whenever the issue is opened. | REQ-DSH-20
reviewed_by | Text | No | Who confirmed it. | REQ-DSH-20
reviewed_at | Text | No | When, local time, YYYY-MM-DD HH:MM. | REQ-DSH-20
Period sets are type-specific (Q-18). The derivation itself is on sheet 05.
project_type | Period set | How boundaries are set
NewDrug CT / Biosimilar CT | Before-Start-up, Start-up, Conduct (interim), Close-out (interim), Conduct (final), Close-out (final), After Close-out (final) | Seven names, in timeline order. Both trial types share one period set and one derivation; they differ in their WEIGHTS, not their shape. A trial with no interim DB lock simply omits 'Conduct (interim)' and 'Close-out (interim)'.
Others | Planning, Develop, Close | Entered directly - dates confirmed manual at Q-25, weights at Q-28. 'Others' projects are hand-entered throughout.
Sheet: PeriodFTEStandard
Column | Type | Required | Definition / rule | Basis
project_type | List | Yes | A clinical trial type. Part of the key: a biosimilar trial at a given phase is not the same workload as a new-drug trial at that phase. 'Others' take manual weights (Q-28). | R-05
clinical_phase | List | Yes | The phase the standard applies to. | Q-26
work_scope_type | List | No | The work scope this standard applies to. SCHEMA 6. EMPTY means the row applies to EVERY scope - see the note below, which is the important part of this change. | R-12
standard_fte | Decimal | Yes | SCHEMA 10, renamed from `weight`. THE STANDARD MONTHLY FTE for this type, phase, scope and period - a MAGNITUDE, not a multiplier: 4.02 means the period takes about four full-time people a month. This is where every figure gets its size (REQ-CAL-19). It was called `weight` until schema 10 and was read by nothing except the period seeder, which is most of why: a weight reads like something to multiply by. A schema 9 file is read - the column is renamed on the way in. | R-31
period_name | List | Yes | A period from that type's set. | Q-04, Q-18
note_1 | Text | No | Free extension column, e.g. the basis for the weight. | Q-01
SCHEMA 6 - THE EMPTY SCOPE. The key is (project_type, clinical_phase, work_scope_type, period_name) and it is unique. A row whose work_scope_type is EMPTY applies to every scope; a project looks for its own scope first and falls back to that row. Without the fallback this sheet would need 3 types x 4 phases x 7 periods x 3 scopes = 252 rows, of which two thirds would repeat their neighbour, and every one of them hand-entered. With it, 84 rows carry the baseline and a scope-specific row is added only where the scope really changes the number. It also means a schema 5 file keeps working: its rows have no scope, so they are the every-scope rows.
Re-keyed at Q-26: a clinical trial's weights come from its CLINICAL PHASE, not its product category. So a phase 1 trial and a phase 3 trial of the same product carry different period weights, which is the intended behaviour. Q-28 then confirmed that 'Others' projects are not distinguished at all and take their weights by hand - which makes this sheet a clinical-trial table, and leaves 'Others' projects entirely hand-entered: dates and weights alike.
Sheet: RoleFactor [key extended at R-10]
Column | Type | Required | Definition / rule | Basis
project_type | List | Yes | 'NewDrug CT', 'Biosimilar CT (Healthy)', 'Biosimilar CT (Patient)' or 'Others'. Roles are keyed by type, so a factor can differ between the trial types. | Q-03, R-05, R-12
clinical_phase | List | Trials only | The phase this factor applies to. EMPTY on 'Others' rows, which carry no phase. | R-10
work_scope_type | List | No | The work scope this factor applies to. SCHEMA 6. EMPTY means EVERY scope, exactly as on PeriodFTEStandard - and it matters more here, because this is the larger sheet. | R-12
absorbed_by | Text | No | SCHEMA 8. If NOBODY holds this role on a project, which role picks the work up: this row's factor is added to that role's (REQ-CAL-16). Blank means the work is simply not counted, and V-29 says so. Delivered with 'Clinical Data Associator' covered by 'Lead data manager' and 'Other staff' by 'Project lead' - a starting point, and data rather than code because which role covers for which is a judgment about how a team works. | R-17
period_name | Text | Yes | The period this factor applies to. One of the seven clinical periods, or one of the three 'Others' periods, matching the project_type. | R-10, R-11
role_name | Text | Yes | Clinical Trial: 'Project oversight', 'Lead data manager', 'Clinical Data Associator', 'Clinical Database Programmer', 'Data Analyst'. Others: 'Project lead', 'Main staff', 'Other staff'. | Q-03
role_factor | Decimal | Yes | Relative burden of THIS role in THIS period, the same for everyone holding the role. A role's share of the work is not flat across a project: the database programmer is heaviest while the database is built, the data associator while data arrives, the analyst at lock. | Q-01, R-10
role_note | Text | No | Basis for the factor. | REQ-CAL-06
The key is (project_type, clinical_phase, work_scope_type, period_name, role_name) since schema 6, which makes this comfortably the largest sheet in the workbook: 3 types x 4 phases x 7 periods x 5 roles = 420 baseline rows, plus 9 for 'Others'. Filling all three scopes as well would make it 1,269. THAT is why the empty scope exists: fill the baseline once, and add a scope-specific row only where the scope really changes the number. The cost of the change still falls on whoever maintains the file, and the fallback is what keeps it payable.
NOTE A CONSEQUENCE. PeriodFTEStandard and RoleFactor now both vary over (project_type, clinical_phase, period_name), and the calculation multiplies them together. The pair is therefore mathematically collapsible into one table keyed on all four dimensions. They are kept separate deliberately - one says how busy the PROJECT is in a period, the other how much of that falls on a ROLE - but the separation only holds if they are maintained that way. Raising a whole project's Conduct load belongs in PeriodFTEStandard, once; doing it in RoleFactor means five edits and double-counts the next time the period weight moves.
Sheet: Person
Column | Type | Required | Definition / rule | REQ-ID
person_id | Text | Yes | Unique key, e.g. PSN-001. | REQ-PSN-01
person_name | Text | Yes | Display name. | REQ-PSN-01
department | Text | No | Grouping for the dashboard. | REQ-PSN-06
primary_role | Text | No | Usual role; an assignment can override it. | REQ-PSN-03
capacity_fte | Decimal | No | Available capacity in FTE, default 1.00 (= 160 h/month). Lower it for a part-timer. | REQ-CAL-08
employment_start / employment_end | Date | No | Bounds availability; blank end = open. | REQ-PSN-04
note_1 .. note_5 | Text | No | Free extension columns. | REQ-PSN-06
Sheet: Assignment
Column | Type | Required | Definition / rule | REQ-ID
assignment_id | Text | Yes | Unique key. One row per person + project + role. | REQ-PSN-07
person_id | Text | Yes | Foreign key to Person. | REQ-PSN-01
person_name | Derived | No | DERIVED - looked up from Person on import and refreshed from it. Locked in the template; a value typed here is discarded and the disagreement reported as V-13. | REQ-PSN-01
project_id | Text | Yes | Foreign key to Project. | REQ-PSN-02
role_name | Text | Yes | Foreign key to RoleFactor, matched on (project's type, role_name); the phase and period are supplied by the project and the month being calculated. Several rows = several roles on one project. | REQ-PSN-03
assign_start_date | Date | No | Date the person joins the study. BLANK = the project's own start date (REQ-CAL-15). Optional since v2.29: leave both dates blank for somebody on the project throughout, and fill them in only for a partial involvement. | REQ-PSN-04, REQ-CAL-15
assign_end_date | Date | No | Date the person leaves the study. BLANK = the project's own end date. This one has always behaved that way; v2.29 makes the start match it. | REQ-PSN-04, REQ-CAL-15
person_weight | Decimal | Yes | RENAMED from base_allocation. How much this person works on this project, e.g. 0.40. Q-01 folded the two former fields into this one. | REQ-CAL-02
estimation_type | List | No | SCHEMA 9. 'automatic' (the default) or 'manual'. Manual means THIS PERSON'S contribution to this project is stated on MonthlyEstimate rather than taken as a share of the project's month - the level below the project's own, and applied first (REQ-CAL-18). | REQ-CAL-18
estimation_type | List | No | SCHEMA 9. 'automatic' (the default) or 'manual'. Manual means THIS PERSON'S contribution to this project is stated on MonthlyEstimate rather than taken as a share of the project's month - the level below the project's own, and applied first (REQ-CAL-18). | REQ-CAL-18
note_1 .. note_3 | Text | No | Free extension columns. | REQ-PSN-06
Sheet: PersonPeriodWeight
Column | Type | Required | Definition / rule | REQ-ID
assignment_id | Text | Yes | Foreign key to Assignment. | REQ-PSN-05
period_start | Date | Yes | Inclusive. Part of the key: one assignment may carry SEVERAL non-overlapping windows, so assignment_id alone does not identify a row. | REQ-PSN-05
period_end | Date | Yes | Inclusive. Periods within one assignment must not overlap. | REQ-PSN-05
weight_override | Decimal | Yes | REPLACES person_weight for months inside this window - it no longer multiplies it. Where no row covers a month, person_weight applies unchanged. | REQ-PSN-05
reason | Text | No | Why the weight differs, e.g. 'part-time', 'covering start-up peak'. | REQ-PSN-05
Changed at Q-01. The answer named exactly three factors, so a fourth multiplier would have been an invention. This sheet now overrides rather than scales - the same effect, one fewer factor, and no hidden compounding. It is optional: leave it empty and every assignment simply uses person_weight.
Sheet: MonthlyEstimate [new]
Column | Type | Required | Definition / rule | REQ-ID
scope | List | Yes | 'project' or 'assignment' - which of the two this figure is for. The only sheet whose parent depends on a value IN the row, which is why the key carries it. | REQ-CAL-18
ref_id | Text | Yes | The project_id or the assignment_id this figure belongs to, according to scope. | REQ-CAL-18
month | Text | Yes | The month, as YYYY-MM. One figure per month per thing (V-08). | REQ-CAL-18
fte | Decimal | Yes | The monthly FTE, STATED rather than calculated. An assignment figure is that person's own contribution to that project; a project figure is the whole month, and the people on it are scaled to add up to it. | REQ-CAL-18
note_1 | Text | No | Why this figure was stated. The argument for a departure from the assumptions belongs beside it. | REQ-CAL-18
Read only where the owning Project or Assignment carries estimation_type = 'manual'; rows left behind by a switch back to automatic are ignored rather than obeyed. MANUAL IS ALL OR NOTHING for the thing it is set on: the application copies EVERY month across when switching, so no month carries a flag of its own and there is no such thing as a half-manual run. A month with no row after that is a figure somebody removed, and V-31 says so rather than the application quietly filling it back in.
Sheet: Config
parameter | Meaning | Default value | REQ-ID
schema_version | Version of this workbook structure; checked on import. Steps to 3 at v1.4, 4 at v1.7, 5 at v1.8, 6 at v2.27 (R-12), 7 at v2.30 (R-16), 8 at v2.31 (R-17), 9 at v2.38 (R-30), 10 at v2.39 (R-31), 11 at v2.41 (R-33, the standards sheet renamed), 12 at v2.54 (R-46, MonthlyEstimate.edited_at retired - the first column this schema has REMOVED rather than added or renamed), 13 at v2.61 (R-50, Milestone.milestone_highlight), 14 at v2.70 (R-59, ProjectPeriod.period_highlight), 15 at v2.71 (R-60, the PeriodHighlight sheet), 16 at v2.72 (R-62, the IssueReview sheet). | 16 | REQ-VC-02
absorb_unstaffed_role_factor | 1 = where nobody holds a role on a project, its factor is added to the role named in RoleFactor.absorbed_by (REQ-CAL-16). 0 = an unstaffed role simply costs nothing, which is how every version before v2.31 behaved. A setting for the same reason the last one is: it moves every figure on a project that is not fully staffed. | 1 | REQ-CAL-16
split_shared_role_fte | 1 = where several people hold the same role on one project in a month, the role factor is divided between them (REQ-CAL-14). 0 = each carries the whole factor, which is how every version before v2.28 behaved. A setting rather than a constant because it changes every figure a shared role ever produced, and somebody comparing this month's report with last year's has to be able to see where the difference came from. | 1 | REQ-CAL-14
fte_hours_per_month | Hours equal to 1.00 FTE. | 160 | REQ-CAL-08
over_allocation_fte | Person-month total above this is over-allocated. | 1.50 | REQ-CAL-04
under_allocation_fte | Person-month total below this counts toward an under-allocated run. Absolute, not scaled by capacity. | 0.60 | REQ-CAL-07
under_allocation_min_months | Consecutive months below the threshold before flagging. | 3 | REQ-CAL-07
default_horizon_months | Months shown on opening. | 24 | REQ-CAL-01
capacity_unit | Display unit for the figures on screen. 'FTE' shows a WEIGHT: 1.00 is one person working a full month on the project and 0.50 is half of one, so ordinary values run about 0.1 to 1.0. 'hours' shows that same weight multiplied by fte_hours_per_month. Display only - it changes nothing that is stored, and no figure the calculation produces. The value 'percent' was named here until v2.35 and was never implemented: anything other than 'hours' displays as FTE. | FTE | REQ-CAL-08
Sheet: Lists [new]
Two columns - list_name, value - holding every data-driven dropdown: outsourcing_type, clinical_phase,
milestone_name, period_name, EDC_system, DataReviewSystem, RBQM_system, setup_party, project_status.
Adding a permitted value is a data edit, never a code change (REQ-CAL-06). A third column, note_1,
carries free text about a value - when it was added, or what it means.
Referential rules checked on import
ID | Rule | On failure
V-01 | Every Assignment.project_id exists in Project. | Error - row rejected, reported with its row number.
V-02 | Every Assignment.person_id exists in Person. | Error - row rejected.
V-03 | Every Assignment.role_name appears in RoleFactor for that project's type - the coarse half of the question V-23 asks precisely. | Error, CLASS CONDITIONAL (R-25): reported at full severity, never refusing the row, and named at Save so the user can keep it knowingly. Was a warning in v0.1; roles are now type-specific, so a mismatch is a real error and the figures for that role are wrong. It is still not a reason to refuse the row: RoleFactor is a standing document maintained separately from any one plan, and the person really is on the project whether or not somebody has entered a factor for their role yet. Kept alongside V-23 because it catches a mistyped role name at once, where V-23 only speaks once the assignment reaches a period and draws FTE.
V-24 | Every PersonPeriodWeight.assignment_id exists in Assignment, and (assignment_id, period_start) is unique. | Error - an override on an assignment that does not exist is silently ignored, so the weight the user typed never applies and nothing says so.
V-27 | Every clinical trial's (project_type, clinical_phase, work_scope_type) has at least one row in PeriodFTEStandard - checked on the PROJECT, not on its periods. | Error - V-19 is precise but only looks at periods a project actually has, so a project whose milestones are missing is never checked at all, and a combination that was never entered is reported once per period rather than once as the one thing that is wrong. This asks the blunter question first: is there any standard for this project at all. Without one, every period would be weighted 1.00.
V-28 | RETIRED at v2.32 (R-18), one version after it was added. It reported an assignment whose role had no RoleFactor row for that project's (project_type, clinical_phase, work_scope_type) at all. | Retired - and deliberately not reinstated at a lower severity. What the rule SAID was true; what it did not account for was WHEN it said it. An error refuses the edit that raised it (REQ-IMP-09), and unlike V-23 this one did not need the project to have any periods - so it fired on a project still being built, which is exactly when assignments are being typed in. A user could not record who was on a project until the standing assumptions carried a factor for their role, which is backwards: the plan is the document being written, the assumptions are maintained separately. The gap is not denied - V-03 still refuses a role invalid for the project type, and V-23 still reports a role with no factor for a period the project spans, which is the same finding at the point where it can be acted on. The id is not reused.
V-29 | A role that carries a factor, that nobody holds on the project, and that nothing covers for. | Information - the direct consequence of REQ-CAL-16 and the reason it exists. Where an unstaffed role names somebody to cover, the figure is corrected; where it names nobody, the same under-estimate is still there and nothing else would say so. Information rather than a warning, because a project legitimately without a role is ordinary: this is a note about what the figures do NOT include, not a fault to correct.
V-31 | A project or assignment set to MANUAL has months it covers that carry no MonthlyEstimate figure. Named, with the months listed. | Error - those months are counted as 0.00, and a figure silently dropping to zero is the one outcome this feature must never produce quietly. Not a refusal: it is raised from the CALCULATION, like V-23, because it is something that happened to a number rather than a fact about a sheet, and a finding that exists only after the arithmetic cannot refuse the edit that led to it. Switching to manual copies every month across, so a month with no figure is one that has since been removed or a month the thing has grown into - the application offers to fill them from the calculation.
V-40 | An IssueReview row no longer describes its month: the issue it reviewed has gone, or the month's gap is not the gap that was reviewed. | Information - a gone issue's review is kept as history; a moved gap's review no longer closes the month, which is shown open and marked 're-check'. Never a refusal.
V-39 | A PeriodHighlight row cannot be applied: its value names no colour, its period name is given twice, or no period list knows the name. | Warning - the period is drawn gray, or on its first row's colour, which looks exactly like a choice nobody made, so it is said. Never a refusal: a colour changes no figure.
V-38 | ProjectPeriod.period_highlight carries a value that names no colour the application can draw. | Warning - the period is drawn gray, which is what it would have been with the column empty, and the finding says so with the values the file's own Lists sheet offers. The period twin of V-37, for the same reason: a gray period looks exactly like one nobody chose a colour for, so a typo would quietly undo what the user asked for. Never a refusal - a colour changes no figure.
V-37 | Milestone.milestone_highlight carries a value that names no colour the application can draw. | Warning - the milestone is drawn unmarked, which is what it would have been with the column empty, and the finding says so with the values the file's own Lists sheet offers. Never a refusal: a mark changes no figure, and a plan whose highlight column is misspelt is still a correct plan. It is reported rather than ignored because the failure is INVISIBLE otherwise - an unmarked milestone looks exactly like one nobody got round to marking, so a typo in the list value would quietly undo the thing the user asked for. What the application reads is the colour word inside the value ('red', 'yellow', 'blue', 'green', 'orange'), which is what lets a team write what their colour means beside it; the rule fires only when no such word is there at all.
V-36 | A project that has periods and NOBODY ASSIGNED TO IT AT ALL. Raised from the CALCULATION, one finding per project, carrying what the project needs: the total FTE-months, the span, the peak and the month it falls in. | Information - and classed INCOMPLETE, so it never refuses an edit and never questions a save. A project with nobody on it yet is not a fault: it is the state every project is in for the minute after it is created, exactly as a person with no assignment is (v2.52). WHAT IT FIXES IS A ROW OF BLANKS, NOT AN ERROR. The project IS listed - it has a row in Resource by project, it is drawn on the timeline, and it counts in the projects tile - but every one of its months is EMPTY, it puts nothing on the three demand charts, it takes no legend entry and it reaches no line of Standard vs staffed. That is worse than being absent: a row of blanks reads as a project that costs nothing rather than one nobody has been put on yet, which is the same failure V-34 exists for. Type, phase, scope and periods are all the standard needs to say what it costs. REQ-CAL-19 is explicit that the project-month IS its standard and the people on it DIVIDE it; a divisor of nobody does not make the demand nought. AND NOTHING ELSE REPORTED IT: V-34 compares demand against applied, which is this gap at its widest, but V-34 is built from projGap, which is built from projMonth, which is built from the LINES - so no assignment means no line, no entry and no finding, and the one project short by the whole of its standard was the only shortfall the shortfall rule could not see. IT CARRIES THE FIGURE, which is why it is raised from the calculation rather than from the validation, and why every term is the one an assignment with blank dates would get (REQ-CAL-15): the number it states is to the hundredth the number the project shows the moment somebody is assigned, which tools/test_unstaffed.py asserts in both directions. SKIPPED where there is nothing to say or nothing to do: a project with no periods has no demand to state and V-12 or V-16 already says so, and a Completed project is history rather than a gap to fill - its finding would never answer itself, which is what the INCOMPLETE class promises.
V-35 | Person.capacity_fte outside 0.00 to 1.00, in either direction. | Error - and it REFUSES, which almost nothing else in this application does. capacity_fte is how much of ONE PERSON there is: 1.00 is full-time, 0.50 is half a week, 0.00 is somebody on the books who is not available at all and is therefore allowed. Every other figure here is a judgement somebody is entitled to make - a period weight, a role factor, a stated month - and the rules about those report rather than refuse, because which of two deliberate numbers is wrong is not the application's business. This is not a judgement: there is no such thing as one and a half of a person, the number is in the wrong unit, and the usual cause is hours typed into an FTE column - which the message says, with the arithmetic. Somebody doing the work of two people is TWO ASSIGNMENTS, or a person weight above 1.00 on one of them. A workbook that already breaks it still OPENS: the save and edit checks compare the count of blocking findings before and after, so a rule broken by an incoming file is reported without locking anybody out of their own plan. V-22 stands down on the same row - reporting that 1.50 is also not below the under-allocation floor would be true and useless.
V-34 | A project whose month is not what its own standard says it needs - standard FTE x period weight x the part of the month it runs - in either direction. Raised from the CALCULATION, one finding per project, naming the months and the worst of them. | Warning - it reports and never refuses. refuses() acts only on errors, so this reaches the findings report, the load banner, the archived change log and the results export without gating a save or asking a question. Departing from the standard is the POINT of a manual figure (REQ-CAL-18): a manager part way through a trial knows better than the assumptions, and the application has no business calling that wrong. What it does have business doing is saying so, because the departure is otherwise completely silent - the charts just draw a different project. An all-automatic plan raises nothing at all, which is what keeps the rule worth reading.
V-33 | A manual ASSIGNMENT figure that the project's own manual figure overrode. REQ-CAL-18 makes the project figure the mother figure - it is the whole month, and the people on it are scaled so they still add up to it - so somebody can type 2.00 against their own name and be given 1.73, because their figure and a colleague's together had to come to the project's month. That is the specified behaviour and it is what keeps the two utilisation charts agreeing; what was missing is that the application did it SILENTLY, so the sheet said one thing and the chart another with nothing connecting them. Now: a SOFT STOP at the moment the figure is edited, naming both numbers and offering to keep it or put it back; the cell marked; the Monthly estimation panel carrying a table of stated against given; and this finding, which reaches the findings report and the archived change log. WARNING, not error, and it never refuses: both numbers were typed deliberately and which of them is wrong is not the application's judgement. | Warning | R-39 | 4
V-32 | A project set to MANUAL has a figure for a month in which nobody is assigned to it. | Error - the figure is NOT applied. A project month is shared out among the people on it, so there is nobody to give this to; applying it anyway would give the project a total that none of its people account for, which is exactly the disagreement REQ-CAL-18 scales the people to avoid. Assign somebody to those months, or remove the figure.
V-30 | Config has no row for a setting the application reads, so its built-in default is in force. Reported for every such setting, naming the value being used. | Information - the file is not malformed and the application is doing the only sensible thing with it, so this is a note rather than a fault. It exists because the absence is otherwise INVISIBLE: every setting is read through a fallback, and the delivered values equal the defaults, so on a stock file nothing moves. A plan whose under-allocation floor had been set to 0.80, or whose shared-role division had been turned off to compare with last year, would revert the moment its row went missing - every dependent figure changing, and nothing on screen saying why. Since v2.35 the row cannot be DELETED in the application (the Config table offers neither '+ row' nor 'Delete', because each setting is read by name), so this now reports a hand-edited workbook or one from a version that predates the setting.
V-25 | RETIRED at schema 7 (R-16). It reported a project whose work_scope_type contradicted its outsourcing_type. | Retired - the rule existed only because two columns sat on the same axis and one of them drove the weights. outsourcing_scope_det is free text now, so there is nothing left to contradict. A rule that can no longer fire is removed rather than left standing and unexplained; the id is not reused.
V-26 | No project carries a project_type that schema 6 retired - at present 'Biosimilar CT', which became 'Biosimilar CT (Healthy)' and 'Biosimilar CT (Patient)'. | Error - reported as itself rather than as a generic unknown value, because the remedy is a choice the file cannot make on the user's behalf. Only they know whether the trial ran in healthy volunteers or in patients, and guessing would put a wrong weight on real work.
V-23 | Every (project_type, clinical_phase, work_scope_type, period_name, role_name) that a PERSON-MONTH ACTUALLY LOOKED UP has a RoleFactor row. Raised BY the calculation (R-19), grouped on that whole composition, and counted in person-months affected. | Error, CLASS CONDITIONAL (R-25) - a factor missing for one period silently drops that stretch to 1.00, which is a wrong number rather than an obvious gap. Two things changed at R-19. It is keyed on the composition the lookup uses, and reported only where a figure was actually produced - asked off the sheets it walked every period of every project an assignment belonged to, so it demanded rows for periods nobody was ever booked into. And because it exists only after the arithmetic, it CANNOT REFUSE AN EDIT: it says the figures are short of an assumption, not that the row is wrong.
V-04 | project_category is present for either clinical trial type. | Warning - shown as blank in the dashboard.
V-05 | end_date is on or after start_date, for projects, assignments and all weight periods. | Error - row rejected.
V-06 | Periods within one project, and override windows within one assignment, do not overlap. | Error - overlapping pair reported. The assignment half was specified from v1.0 but not implemented until R-12; an overlap there makes the applied weight depend on row order.
V-07 | Assignment dates fall inside the project's own start and end dates. | Warning - kept, but listed for review.
V-08 | project_id, person_id and assignment_id are unique in their sheet. | Error - duplicate rejected.
V-09 | schema_version in Config matches the version the application expects. | Warning - proceeds, banner shown.
V-10 | Clinical-trial projects carry clinical_phase and the four *_setup values. | Warning - the project still simulates; the gap is listed.
V-11 | Every list-typed value appears in the Lists sheet for its list. | Warning - value kept, reported as unrecognised.
V-12 | A project's periods leave no gap and no overlap across its timeline. The full set need not be present - a period may be legitimately omitted (REQ-CAL-12). | Warning - months with no period use weight 1.00 and are listed (REQ-CAL-10).
V-13 | Denormalised project_name / person_name match their master row. | Warning - the master value wins and the copy is refreshed.
V-14 | A milestone date falls inside its project's start..end window, and the boundary milestones appear in chronological order. Repeated 'Inspection' rows are exempt from the uniqueness part of this check. | Error for period-defining milestones - the derivation cannot run. Warning for markers.
V-15 | A period_name belongs to the period set of its project's type. | Error - a 'Planning' period on a clinical trial is a category mistake, not a typo.
V-16 | A clinical trial carries the milestones the derivation needs: CTA submission, and at least one DB lock. | Error - without them no period boundary can be computed.
V-18 | Within a project, period_name is unique, and period_seq is unique. | Error - since R-11 the key is (project_id, period_name), so a repeated name is a duplicate key rather than a legitimate second stretch. period_seq stays unique because it carries the order.
V-19 | A clinical trial carries a clinical_phase, and PeriodFTEStandard has rows for that phase. Not applied to 'Others' projects, whose weights are entered directly. | Error - since Q-26 the phase selects the weights, so a missing phase leaves the project unweighted.
V-20 | A milestone other than 'Inspection' appears at most once per project. | Warning - repeats are allowed but usually a data-entry slip outside Inspection.
V-21 | 'Inspection' dates on or before the final DB lock are treated as markers, not as the start of period 7. | Information - listed so the reader can see why an early inspection did not open a period.
V-22 | No person carries a capacity_fte below the under-allocation floor. | Warning - such a person can never clear the floor however fully they are booked, so the flag would be permanent and meaningless.
V-17 | On editing an identifier, every referencing row is updated; on deleting a row, nothing may still reference it. | Cascade after confirmation / deletion refused (REQ-IMP-10).
Import never stops at the first problem: it collects every finding and presents one report (REQ-IMP-02). Under REQ-IMP-09 the same rules run again on any value edited on screen.
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 05_Resource_Logic
Resource calculation logic
Rewritten at v0.2 from the Q-01, Q-02 and Q-08 answers. Step 2 will fix this as pseudocode plus the worked example as an acceptance test.
Monthly load for one assignment, in one month
load(assignment, month) = project_period_weight(project, month)
x role_factor(project_type, clinical_phase, period, role)
x person_weight(assignment, month)
x coverage(assignment, month)
The result is FTE, where 1.00 FTE = 160 hours per month (8 h/day x 5 days/week x 20 days/month).
project_period_weight is set by the project's category for the milestone period the month falls in.
It is identical for everyone assigned to that project in that period.
role_factor is the standard burden of the role IN THE PERIOD THE MONTH FALLS IN,
identical for everyone holding that role on that kind of project (R-10).
Roles are drawn from the list valid for the project's type. Where no row
matches, the factor falls back to 1.00 and V-23 reports it.
person_weight is how much this person works on this project, given per assignment;
a PersonPeriodWeight row replaces it for the months it covers.
coverage = calendar days worked in the month / calendar days in the month.
1.00 for a full month, a fraction in the joining and leaving months.
Changed from v0.1: base_allocation is gone. Q-01 named three factors, and base_allocation was a fourth that would have silently scaled all of them. person_weight now carries that meaning alone.
Aggregation
Output | How it is computed | Where it appears | REQ-ID
Per project, per month | Sum of load over every assignment on that project. | Overall tab, project table + stacked graph | REQ-CAL-03
Per person, per month | Sum of load over every assignment that person holds, across all projects. | Overall tab, person table + graph | REQ-CAL-03
Per person, per project, per month | The individual load value. | Drill-down when a person row is expanded | REQ-CAL-03
Over-allocation flag | Person-month total > over_allocation_fte (1.50). | Red cell + count in summary tiles | REQ-CAL-04
Under-allocation run | Person-month total < under_allocation_fte (0.80) for >= under_allocation_min_months (3) consecutive months. Reported as a run with its start month and length. | Amber cells across the run + count in summary tiles | REQ-CAL-07
Hours view | load x fte_hours_per_month. | Alternative display unit | REQ-CAL-08
Head-count per project, per month | Count of assignments with load > 0 that month. | Compared against planned_member_count | REQ-PRJ-04
Under-allocation needs a rolling window, not a per-month test: a single quiet month is normal, three in a row is a signal. A run is reported once, at its start, rather than as three separate flags.
Period derivation for a clinical trial - either type [v1.1]
Boundaries come from milestone dates plus month offsets, so moving a milestone re-shapes the periods.
Where a boundary has both a milestone and an offset definition, the RECORDED MILESTONE WINS and the
offset is the fallback (REQ-CAL-13). Boundary milestones: Protocol (v1), CTA submission, First SIV
(or FPI), the DB locks, and Inspection. LPI and the two cut-off dates are markers only.
Seq | Period | Starts | Ends | Basis
1 | Before-Start-up | project start_date | 'Protocol (v1)' where recorded, otherwise the day before Start-up begins | R-02
2 | Start-up | day after 'Protocol (v1)' where recorded, otherwise one month before 'CTA submission' | 'First SIV' where recorded (or 'FPI'), otherwise start + 4 months - 1 day | R-02
3 | Conduct (interim) | day after Start-up ends | day before Close-out (interim) begins | Q-22, R-11
4 | Close-out (interim) | 3 months before 'interim DB lock' | 'interim DB lock' | Q-22, Q-23
5 | Conduct (final) | day after 'interim DB lock' | day before Close-out (final) begins | Q-23, R-11
6 | Close-out (final) | 3 months before 'final DB lock' | day before period 7 begins; where there is no period 7, 'final DB lock' or project end_date if later | R-02
7 | After Close-out (final) | earliest 'Inspection' date that falls after the final DB lock | latest 'Inspection' date, or project end_date if later | R-02
Rows 3 and 4 exist ONLY where the project has an interim DB lock. Where there is none, rows 3 and 4 are omitted and row 5 - 'Conduct (final)' - runs from the day after Start-up ends. That is what makes the names unique: 'Conduct (interim)' exists only when there is an interim lock to be interim to, and every other conduct stretch is 'Conduct (final)' (R-11).
Row 7 exists only where an 'Inspection' milestone falls after the final DB lock - 'Inspection' may be recorded several times, and the period spans from the first such event to the last.
Note the interaction at rows 1 and 2: where 'Protocol (v1)' is recorded, Before-Start-up ends on it and Start-up begins the day after, so the two rules meet exactly and no gap can open between them.
Degenerate timelines [REQ-CAL-12]
Real timelines do not always leave room for every period. Boundaries are applied in sequence order and a
later one wins, so the periods stay contiguous; any period squeezed to zero or negative length is omitted
and reported rather than written with a nonsensical range.
Timeline | What would go wrong | What happens instead
CTA submission is within a month of the project start | Before-Start-up would be empty or negative. | Before-Start-up omitted; Start-up begins at the project start date.
Interim and final DB lock less than 3 months apart | 'Conduct (final)' would be negative, and Close-out (final) would start before the interim lock. | 'Conduct (final)' omitted; Close-out (final) begins the day after the interim DB lock. The project then carries 'Conduct (interim)' but no 'Conduct (final)' - legitimate, since the names describe position, not a required pair.
No interim DB lock recorded | Rows 3 and 4 have no anchor. | Both omitted; a single 'Conduct (final)' runs from Start-up into Close-out (final).
Trial too short for a conduct phase | Start-up's fixed 4 months would overrun the Close-out start. | The conduct period is omitted; Start-up is clipped where Close-out begins.
No CTA submission, or no DB lock at all | Nothing to derive from. | Error, not a silent default - V-16. The project's periods must then be entered by hand.
'Inspection' dated on or before the final DB lock | Period 7 would start before period 6, overlapping the conduct phase. | Those inspections are treated as markers inside the existing periods; only later inspection activity opens period 7. Reported by V-21. See R-03.
'Protocol (v1)' earlier than the project start date | Before-Start-up would be empty or negative. | Before-Start-up omitted; Start-up begins at the project start date.
'First SIV' earlier than Start-up begins | Start-up would end before it starts. | The offset fallback is used instead - start + 4 months - 1 day - and the inconsistency is reported.
All eight cases were run through the derivation, together with a full timeline carrying protocol, SIV, interim lock and three inspections. Every one produces a contiguous set of periods with no gap and no overlap. The check is worth repeating as an automated test at Step 4.
Worked example - the acceptance test for the calculation engine
Element | Value | Note
Assignment | PSN-001 on PRJ-001 (Clinical Trial), role = Lead data manager
person_weight | 0.40 | How much this person works on this project
Assignment window | 2026-03-10 to 2026-12-31 | Joins part-way through March
Project periods | Start-up 2026-01-01..2026-06-30 weight 1.50; Conduct (final) from 2026-07-01 weight 1.00 | Seeded from the project's CLINICAL PHASE (Q-26)
role_factor | 1.20 for Lead data manager | Illustrative. Real values are entered in the source workbook (Q-17), not fixed here
Coverage, March 2026 | 22 / 31 = 0.7097 | 10 Mar to 31 Mar inclusive = 22 days
Load, March 2026 | 1.50 x 1.20 x 0.40 x 0.7097 = 0.511 FTE | 81.8 hours
Load, April 2026 | 1.50 x 1.20 x 0.40 x 1.0000 = 0.720 FTE | 115.2 hours. Full month inside Start-up
Load, July 2026 | 1.00 x 1.20 x 0.40 x 1.0000 = 0.480 FTE | 76.8 hours. The Conduct (final) weight applies
Over-allocated? | No - 0.720 is below the 1.50 threshold | This person would need other assignments to breach it
Under-allocated? | Only if their total across ALL projects stays below 0.80 for 3 months running | Judged on the person total, never on one assignment
Please confirm these numbers at Step 2. The role_factor of 1.20 is a placeholder: the arithmetic is the thing being agreed, not that particular value.
Design decisions inside the calculation
ID | Decision | Rationale | Status
C-01 | Weights multiply rather than add. | Confirmed at Q-01: project weight x role factor x person weight. | CONFIRMED
C-02 | Partial months are pro-rated by calendar days. | Confirmed at Q-02: work is expected in proportion to calendar days from the joined date to the end date. | CONFIRMED
C-03 | A missing PersonPeriodWeight row means person_weight applies unchanged. | Follows from the override semantics. No row is the normal case, not an exception. | CONFIRMED
C-04 | Capacity is FTE. 1.00 FTE = 160 h/month. | Confirmed at Q-08. Note the flag is NOT at 1.00 - over-allocation begins above 1.50. | CONFIRMED
C-05 | The unit shown on screen is FTE, with hours available. | Q-08 was expressed in FTE and hours, so FTE is now the default rather than percent. | CONFIRMED
C-06 | Over- and under-allocation are judged on the person's total across all projects. | The question 'is this person over-committed' is only meaningful across their whole workload. | Confirm
C-07 | Period weights are seeded from the category standard, then editable per project. | Q-01 ties weight to category; real projects still deviate. Seeding keeps them consistent without freezing them. | Confirm
C-08 | A month is attributed to the period containing its first day. | Avoids splitting a month across two weights. Simpler to explain and to check by hand. | Confirm
C-09 | Editing an identifier cascades to every row referencing it; deleting a referenced row is refused. | Q-20 asked for every field to be editable with rules preventing inconsistency. Cascading is what makes an editable ID safe - blocking the edit instead would make the field read-only in all but name. | Confirm
C-10 | Period boundaries are recomputed whenever a milestone date changes, unless the period dates were edited by hand. | Keeps derived dates true to the timeline - the frequent-change problem this tool exists for - without silently discarding a deliberate manual override. | Confirm
C-11 | Derived boundaries are applied in sequence order, a later one overriding an earlier; a period squeezed to nothing is omitted. | The only rule that keeps periods contiguous on every timeline, including the awkward ones. Verified against five cases on this sheet. | Confirm
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 06_Dashboard_Design
Dashboard design
Four tabs: the three specified, plus 'General assumptions' added at the component-list review (R-09). Detailed layout is fixed at the Step 3 UI review.
Tab 1 - Overall
Component | Content | REQ-ID
Control bar | Horizon (default 24 months, one click to expand to the latest project end date), project type, clinical phase, project, person, role, department, and one action to reset them all. Plus 'Load workbook', 'Export', and the loaded-file name and time with its time zone. The FTE/hours unit is NOT here - it is a setting, and it lives on the assumptions tab. | REQ-DSH-05, REQ-DSH-07, REQ-IMP-05
Table A - resource by project | Rows = project, columns = months, cells = monthly FTE. Row and column totals. Expanding a project reveals its assigned people. | REQ-DSH-01
Table B - resource by person | Rows = person, columns = months, cells = FTE summed across projects. Over-allocated cells red, under-allocated runs amber. Expanding a person reveals their projects. | REQ-DSH-01, REQ-DSH-08
Graph 1 - stacked area or bar, by project | Total monthly demand, one band per project. Shows how demand builds and where the peaks land. | REQ-DSH-02
Graph 2 - grouped bar, by person | Monthly FTE per person with reference lines at 1.50 and 0.80, so both thresholds are visible. | REQ-DSH-02, REQ-DSH-08
Graph 3 - project timeline (Gantt-style) | One bar per project across the horizon, with milestone markers and period-weight shading. | REQ-DSH-02, REQ-PRJ-05
Summary tiles | Active projects, people assigned, total FTE in the horizon, over-allocated person-months, under-allocated runs. | REQ-DSH-08
Tab 2 - Source data (project)
Component | Content | REQ-ID
Project table | Every Project column from sheet 04, sortable and filterable, with derived total period. Editable under REQ-IMP-07. | REQ-DSH-03
Milestone sub-table | Milestones of the selected project, in sequence. | REQ-PRJ-05
Period sub-table | The selected project's four periods, their derived dates and their weights. | REQ-PRJ-06
Export | Export the visible table to .xlsx. | REQ-DSH-06
Tab 3 - Source data (person)
Component | Content | REQ-ID
Person table | Every Person column from sheet 04, sortable and filterable. Editable under REQ-IMP-07. | REQ-DSH-04
Assignment sub-table | The selected person's assignments: project, role, start, end, person weight. | REQ-PSN-02, REQ-PSN-03
Person period weight sub-table | Override periods for the selected assignment. | REQ-PSN-05
Export | Export the visible table to .xlsx. | REQ-DSH-06
Editing rules [new at v0.2, from REQ-IMP-07]
Rule | REQ-ID
The v0.1 rule 'nothing on screen is editable' is withdrawn. Imported data can be edited in the application. | REQ-IMP-07
An edited cell is marked as changed, and a running count of unsaved edits is always visible. | REQ-IMP-08
Closing the page or loading another workbook while edits are unsaved raises a warning first. | REQ-IMP-08
Every field is editable, identifiers included (Q-20). Consistency is protected by rule, not by locking fields. | REQ-IMP-09
An edited value is validated exactly as an imported one would be; a rejected edit is refused at the point of entry, not at export. | REQ-IMP-09
Changing an identifier updates every row that references it, after showing how many will change. Deleting a row that is still referenced is refused, naming what points at it. | REQ-IMP-10, V-17
Editing a milestone date re-computes that project's derived periods, unless its period dates were set by hand. | C-10
Export writes the edited data in the template layout, so the exported file can be re-imported unchanged. | REQ-IMP-04, REQ-IMP-07
The application never writes to the workbook on disk by itself - export is always a deliberate act. | Out of scope, sheet 02
Cross-cutting UI rules
Rule
A validation banner appears whenever the last import produced findings, and opens the full report on click.
Empty state: with nothing loaded, every tab shows the same clear 'Load your source workbook' panel and a link to download the blank template.
The application version and expected schema version are shown in the footer at all times (REQ-VC-02).
Any section holding a bounded scroll region can be given the whole window from a control in its head, and the data in it stays editable there; the edit bar and the tabs stay in front of it, and Escape gives the page back (REQ-DSH-18).
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 07_Architecture
Architecture and technical approach
Decision D-01 - how the HTML file reads the Excel data [CONFIRMED: option (a)]
A page opened from local disk (file://) cannot read an .xlsx from a fixed path on its own - the browser's
security model blocks it. Q-05 confirmed local .html files do open on the work PC, so the approach is viable.
Option | Description | Advantages | Disadvantages | Outcome
(a) | User selects the workbook through a file picker or drag-and-drop; an embedded SheetJS-style parser reads it in memory. | True .xlsx support; no install; no server; user controls which file is loaded. | The file must be selected each session (mitigated by optional caching, REQ-IMP-06). | CONFIRMED - adopted
(b) | Data kept as .csv next to the HTML, still opened through a picker. | Simplest possible parsing. | Loses formatting, multiple sheets and validation - and Q-09 asks for one multi-sheet workbook, which .csv cannot express. | Rejected
(c) | Excel is only an export target; browser storage is the working record. | No load step at all. | Contradicts the workbook being the archive of record; clearing browser data would lose everything. | Rejected
Q-09 strengthens this decision: one workbook with ten sheets is exactly what .xlsx does well and .csv cannot do at all.
Technology
Concern | Choice and reason | REQ-ID
Container | One .html file, opened by double-click. | REQ-OUT-01
Excel parsing/writing | SheetJS (xlsx) community build, embedded inline - no CDN, so it works offline. | REQ-OUT-02, REQ-NFR-04
Charts | Inline SVG drawn by the application's own code, or a small embedded chart library. No external requests either way. | REQ-DSH-02, REQ-NFR-04
Framework | None. Plain modern JavaScript. | REQ-OUT-02
Styling | Embedded CSS. Readable on a laptop screen and when printed. | REQ-OUT-01
Persistence | Optional browser cache of the last load, marked as a convenience, never as the record. | REQ-IMP-06
Internal structure - built for later change (REQ-NFR-01)
Layer | Responsibility | Why the boundary is there
1. IO layer | Reads the chosen workbook into raw rows; writes .xlsx on export. | Swapping the file-access method touches this layer only.
2. Validation layer | Applies rules V-01..V-21, produces one findings report. | New rules are added here without touching parsing or maths.
3. Model layer | Typed in-memory objects: Project, Milestone, ProjectPeriod, RoleFactor, Person, Assignment, PersonPeriodWeight, Config, Lists. | New fields are added here and flow outward.
4. Edit buffer | Holds on-screen changes, tracks which rows are dirty, re-runs validation per edit, and feeds export. | Added for REQ-IMP-07. Keeping edits out of the model layer means the calculation never has to care whether a value came from the file or the screen.
5. Calculation layer | The monthly engine above. Pure functions - no DOM, no file access. | Directly unit-testable, and the piece most likely to be refined once you see real output.
6. Presentation layer | Tabs, tables, graphs, filters, editing controls, export buttons. | A new tab or graph is added here alone.
The calculation layer never touches the screen and never touches files. That is what makes both future requirement changes and testing cheap.
Deployment
Point
The user keeps one folder containing the .html file and ONE source workbook. Copying the folder moves the whole tool.
Updating the application means replacing the .html file. Source data is untouched, because it lives outside it (REQ-OUT-03).
The application checks the source schema version on load and warns on a mismatch (REQ-VC-03).
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 08_WBS_Schedule
Work breakdown - the five steps
Each step ends at a review gate. Work on the next step starts only after that gate is passed.
Step | Task | Activity | Deliverable | Status
1 | 1.1 | Draft the development plan. | PRAP_Development_Plan_v0.1.xlsx | Complete
1 | 1.2 | Requester reviews; answers the open questions. | v0.11_reviewed mark-up | Complete
1 | 1.3 | Propagate the answers across all sheets and re-issue. | PRAP_Development_Plan_v0.2.xlsx | Complete
1 | 1.4 | Answer the follow-up questions Q-13..Q-20. | v0.2_reviewed mark-up | Complete
1 | 1.5 | Incorporate round 2; work the period mapping through for coverage gaps. | PRAP_Development_Plan_v0.3.xlsx | Complete
1 | 1.6 | Settle the period-boundary questions Q-21..Q-26. | v0.3_reviewed mark-up | Complete
1 | 1.7 | Incorporate round 3; verify the derivation against degenerate timelines. | PRAP_Development_Plan_v0.4.xlsx | Complete - issued for review
1 | 1.8 | Answer Q-27 and Q-28. | v0.4_reviewed mark-up | Complete
1 | 1.9 | Final plan issue. | PRAP_Development_Plan_v1.0.xlsx | Complete
1 | 1.10 | Apply the post-approval change request (Inspection milestone, seventh period). | PRAP_Development_Plan_v1.1.xlsx | Complete
1 | 1.11 | Confirm R-03. | v1.1_reviewed mark-up | Complete
1 | 1.12 | Record R-03 as closed and re-issue for approval. | PRAP_Development_Plan_v1.2.xlsx | Complete - issued for review
1 | 1.13 | Approve plan v1.2 as a change against the v1.0 baseline. | Approval on 12_Review_Log | Complete
1 | G1b | GATE 1 RE-CONFIRMED - plan v1.2 approved by Dan, 2026-08-01. Step 1 closed. | Approval recorded on 12_Review_Log | Complete
1 | 1.14 | Apply change R-04 (note column on every source sheet). | PRAP_Development_Plan_v1.3.xlsx | Complete - issued for review
1 | 1.15 | Approve plan v1.3 as final. | Approval on 12_Review_Log | Complete
1 | G1c | Plan v1.3 approved by Dan, 2026-08-01. | Approval recorded on 12_Review_Log | Complete
1 | 1.16 | Apply change R-05 (project_type split). | PRAP_Development_Plan_v1.4.xlsx | Complete - issued for review
1 | 1.17 | Apply the specification-review answers (R-06, R-07, R-08). | PRAP_Development_Plan_v1.5.xlsx | Complete - issued for review
1 | 1.18 | Apply the component-list review outcome (R-09). | PRAP_Development_Plan_v1.6.xlsx | Complete - issued for review
1 | 1.19 | Apply change R-10 (role factor keyed on phase and period). | PRAP_Development_Plan_v1.7.xlsx | Complete - issued for review
1 | 1.20 | Apply change R-11 (conduct stretches named apart; ProjectPeriod natural key). | PRAP_Development_Plan_v1.8.xlsx | Complete - issued for review
1 | 1.21 | Close the validation gaps found while answering the PersonPeriodWeight key question (R-12). | PRAP_Development_Plan_v1.9.xlsx | Complete - issued for review
1 | 1.22 | Apply the component-list v0.7 review outcome (R-13). | PRAP_Development_Plan_v1.10.xlsx | Complete - issued for review
1 | 1.23 | Approve the plan as a baseline. | Approval on 12_Review_Log | Complete - APPROVED 2026-08-02
1 | G1d | GATE 1 CLOSED - plan v2.0 approved by Dan, 2026-08-02, superseding v1.3. | Approval recorded on 12_Review_Log | Complete
1 | G1 | GATE 1 - development plan approved by Dan, 2026-08-01. Decisions C-06..C-11 confirmed. | Approval recorded on 12_Review_Log | Complete
2 | 2.0 | Generate the source workbook template and a dummy data file for review. | PRAP_SourceData_Template + _Dummy v1.1 | Complete - issued for review
2 | 2.1 | Fix the source workbook schema: exact sheet names, column headers, types, value lists. | Specification sheet 'Data schema' | In progress
2 | 2.2 | Specify the calculation engine as pseudocode plus the worked example as an acceptance test. | Specification sheet 'Calculation' | Not started
2 | 2.3 | Specify period derivation per project type, and the over/under-allocation detection. | Specification sheet 'Calculation' | Not started
2 | 2.4 | Specify import validation rules V-01..V-21 and the findings report. | Specification sheet 'Validation' | Not started
2 | 2.5 | Specify each dashboard tab: every table, column, graph, filter and interaction. | Specification sheet 'UI spec' | Not started
2 | 2.6 | Specify on-screen editing, the dirty-state model and export round-tripping. | Specification sheet 'Editing & IO' | Not started
2 | 2.7 | Specify the version/compatibility check. | Specification sheet 'IO & versioning' | Not started
2 | 2.8 | Build the requirement-to-specification traceability matrix. | Specification sheet 'Traceability' | Not started
2 | G2 | GATE 2 - programming specification approved. | PRAP_Programming_Specification_v1.0.xlsx | Not started
3 | 3.1 | High-level UI design: tab structure, page regions, navigation. No code behind it. | Prototype HTML (UI only) | Not started
3 | 3.2 | Requester reviews the high-level component design. | Review comments | Not started
3 | 3.3 | Final UI design with clear per-component requirements. | Prototype HTML v1.0 + component list | Not started
3 | G3 | GATE 3 - final design and component list approved. Code generation starts only for approved components. | Approved component list | Not started
4 | 4.1 | IO layer: workbook load, sheet/column mapping, export. | app/PRAP.html | Complete
4 | 4.2 | Validation layer: rules V-00..V-24 and the findings report. | app/PRAP.html | Complete
4 | 4.3 | Model layer, Lists and Config handling. | app/PRAP.html | Complete
4 | 4.4 | Edit buffer: on-screen editing, dirty state, per-edit validation, cascading identifier edits, row insertion. | app/PRAP.html | Complete
4 | 4.5 | Calculation engine, verified against the reference implementation. | app/PRAP.html + test evidence | Complete - EXACT MATCH on all 1,225 person-months of the dummy dataset
4 | 4.6 | Overall tab: tables, graphs, filters, over/under-allocation flagging. | app/PRAP.html | Complete
4 | 4.7 | Source data (project), Source data (person) and General assumptions tabs. | app/PRAP.html | Complete
4 | 4.8 | Blank source workbook template with value lists and example rows. | PRAP_SourceData_Template_v1.21.xlsx | Complete
4 | 4.9 | Requester reviews output against real data; refinements folded in. | Updated code | In progress - rounds 1-25 applied (app v1.24); GATE 4 open
4 | G4 | GATE 4 - application functionally complete. | PRAP_Application_v0.9.html | Not started
5 | 5.1 | Full pass over the traceability matrix: every Must requirement demonstrated. | Completed traceability matrix | Not started
5 | 5.2 | Test on a clean Windows PC in Edge and Chrome, offline. | Test evidence | Not started
5 | 5.3 | Write the user guide: folder layout, how to load, how to maintain source data. | User guide | Not started
5 | 5.4 | Final version alignment across plan, specification and application. | Version alignment table (sheet 09) | Not started
5 | G5 | GATE 5 - release. | PRAP_Application_v1.0.html | Not started
Progress
Measure | Count
Tasks total
Complete
Awaiting the requester
Not started
No duration estimates: the pace is set by review turnaround at each gate, not by build effort.

## 09_Version_Control
Version control across documents (REQ-VC-01)
What is version-controlled
Artifact | Naming convention | Folder | Where its version is recorded
Development plan | PRAP_Development_Plan_v<ver>.xlsx | docs/ | Sheet 01_Version_History
Programming specification | PRAP_Programming_Specification_v<ver>.xlsx | docs/ | Its own version-history sheet
Application | PRAP_Application_v<ver>.html | app/ | Version constant shown in the footer
Source data template | PRAP_SourceData_v<ver>.xlsx (one workbook, was two) | templates/ | schema_version in the Config sheet
Output / evidence files | PRAP_<content>_v<ver>_<yyyymmdd>.xlsx | output/ | Filename plus a header block
Generator scripts | tools/*.py | tools/ | Git history
Version numbering
Pattern | Meaning | Example
0.x | Draft, under review. Content may change substantially. | 0.1 -> 0.2 on each re-issue during review.
x.0 | Approved baseline. Changing it requires a new approval. | 0.9 -> 1.0 at the gate.
x.y | Approved change against a baseline: added requirement, bug fix, layout change. | 1.0 -> 1.1
Schema version | Independent counter for the source workbook structure. Steps only when a sheet or column changes. | schema 1 -> 2
A reviewer mark-up carries the reviewed version's number with a suffix (v0.11_reviewed against v0.1). The incorporating issue takes the next draft number - here v0.2.
Version alignment - which versions belong together
Plan version | Specification version | Application version | Schema version | Date | Note
v0.1 | - | - | - | 2026-07-25 | Plan issued for review
v0.2 | - | - | 1 (draft) | 2026-07-31 | Reviewer answers incorporated; single-workbook schema defined
v0.3 | - | - | 1 (draft) | 2026-07-31 | Round 2 incorporated; type-specific period sets; milestone list replaced
v0.4 | - | - | 1 (draft) | 2026-07-31 | Round 3 incorporated; period model settled and verified
v1.0 | - | - | 1 | 2026-07-31 | Step 1 baseline. APPROVED 2026-08-01 by Dan (Gate 1).
v1.1 | - | - | 1 | 2026-08-01 | Change against baseline: Inspection milestone, seventh period. Superseded.
v1.2 | - | - | 1 | 2026-08-01 | APPROVED 2026-08-01 by Dan. Baseline until v1.3 is approved.
v1.3 | v0.2 | - | 2 | 2026-08-01 | R-04: note column on every source sheet. APPROVED 2026-08-01 by Dan.
v1.4 | v0.3 | prototype v0.2 | 3 | 2026-08-01 | R-05: project_type split. Superseded.
v1.5 | v0.4 | prototype v0.3 | 3 | 2026-08-01 | R-05..R-08. Superseded.
v1.6 | v0.5 | prototype v0.4 | 3 | 2026-08-01 | R-05..R-09. Superseded.
v1.7 | v0.6 | prototype v0.5 | 4 | 2026-08-02 | R-05..R-10. Superseded.
v1.8 | v0.7 | prototype v0.6 | 5 | 2026-08-02 | R-05..R-11. Superseded.
v1.9 | v0.8 | prototype v0.7 | 5 | 2026-08-02 | R-05..R-12. Superseded.
v1.10 | v0.9 | prototype v0.8 | 5 | 2026-08-02 | R-05..R-13. Superseded by v2.0.
v2.0 | v1.0 | prototype v0.8 | 5 | 2026-08-02 | APPROVED BASELINE. Steps 1-3 closed; Step 4 authorised.
v2.1 | v1.0 | application v1.0 | 5 | 2026-08-02 | Step 4 built: app/PRAP.html. Tasks 4.1-4.8 complete.
v2.2 | v1.0 | application v1.1 | 5 | 2026-08-02 | Gate 4 refinements round 1: three UI changes.
v2.3 | v1.0 | application v1.2 | 5 | 2026-08-02 | Gate 4 round 2: the application carries its own document provenance.
v2.4 | v1.0 | application v1.3 | 5 | 2026-08-02 | Gate 4 round 3: sticky headers, year axis, provisional editing.
v2.5 | v1.0 | application v1.4 | 5 | 2026-08-02 | Gate 4 round 4: information pop-ups and row deletion.
v2.6 | v1.0 | application v1.5 | 5 | 2026-07-31 | Gate 4 round 5: lookup columns, cell values, row actions everywhere, type-ahead.
v2.7 | v1.0 | application v1.6 | 5 | 2026-07-31 | Gate 4 round 6: insert/delete fixed on the four child tables.
v2.8 | v1.0 | application v1.6 | 5 | 2026-07-31 | Gate 4 round 7: second dummy dataset, 10 projects x 10 people.
v2.9 | v1.0 | application v1.7 | 5 | 2026-07-31 | Gate 4 round 8: two-way scrolling everywhere, project by name, allocated assignment_id.
v2.10 | v1.0 | application v1.8 | 5 | 2026-07-31 | Gate 4 round 9: a foreign key no longer cascades; second override windows can be added.
v2.11 | v1.0 | application v1.9 | 5 | 2026-07-31 | Gate 4 round 10: the value list survives being scrolled, and matches on tokens.
v2.12 | v1.0 | application v1.10 | 5 | 2026-07-31 | Gate 4 round 11: a per-project timeline, and utilisation stacked by project.
v2.13 | v1.0 | application v1.11 | 5 | 2026-07-31 | Gate 4 round 12: demand by person, project utilisation by person, child tables scoped.
v2.14 | v1.0 | application v1.12 | 5 | 2026-07-31 | Gate 4 round 13: weight overrides follow the selected assignment.
v2.15 | v1.0 | application v1.13 | 5 | 2026-07-31 | Gate 4 round 14: monthly trend line charts, and one header shape for every panel.
v2.16 | v1.0 | application v1.14 | 5 | 2026-07-31 | Gate 4 round 15: derived columns locked in the workbook, template v1.7.
v2.17 | v1.0 | application v1.15 | 5 | 2026-07-31 | Gate 4 round 16: visual design pass; contrast measured, not judged.
v2.18 | v1.0 | application v1.16 | 5 | 2026-07-31 | Gate 4 round 17: AI-agent reference, JSON interchange, interoperability audit.
v2.19 | v1.0 | application v1.17 | 5 | 2026-07-31 | Gate 4 round 18: a plan can be started in the application, with no workbook.
v2.20 | v1.0 | application v1.18 | 5 | 2026-07-31 | Gate 4 round 19: the child sections are enterable from the start, before their parent is saved.
v2.21 | v1.0 | application v1.19 | 5 | 2026-07-31 | Gate 4 round 20: scroll position survives a re-render.
v2.22 | v1.0 | application v1.20 | 5 | 2026-07-31 | Gate 4 round 21: a row with no identifier is not a record.
v2.23 | v1.0 | application v1.21 | 5 | 2026-07-31 | Gate 4 round 22: allocated ids, neutral weights, and scroll regions that say there is more.
v2.24 | v1.0 | application v1.22 | 5 | 2026-07-31 | Gate 4 round 23: the project window and team size derived from the rows beneath.
v2.25 | v1.0 | application v1.23 | 5 | 2026-07-31 | Gate 4 round 24: outsourcing filter, a horizon that follows the filters, and a change log.
v2.26 | v1.0 | application v1.24 | 5 | 2026-07-31 | Gate 4 round 25: multi-value filters, and the two generators on the project tab. 4.9 continues.
One row per release. Answers 'which specification produced this .html, and which source template does it expect?'.
Repository rules
Rule
All work is committed to branch claude/project-resource-assignment-app-1vjdzh.
Documents are generated from scripts in tools/ so their content is reviewable as a text diff, not only as a binary.
One commit per meaningful change, with a message naming the step and the affected REQ-IDs.
A released version is tagged, so any release can be reproduced exactly.
Reviewer mark-ups are committed as received, unedited, so the review trail is auditable.

## 10_Risks
Risks and assumptions
Risks
ID | Risk | Likelihood | Impact | Mitigation
R-01 | The resource formula does not match how burden is actually judged, so output looks wrong. | Medium | High | Reduced from High at Q-01, which fixed the three factors. A worked example (sheet 05) is agreed at Step 2 before code is written, and every factor stays in data.
R-02 | The source workbook is maintained inconsistently - typos, overlapping periods - and the simulation silently misleads. | High | Medium | Fourteen validation rules on import, ID-based references instead of name matching, and a findings report the user cannot miss.
R-03 | Corporate policy blocks local .html files or restricts the browser. | - | - | CLOSED at Q-05: local .html files open on the work PC. Re-test on the target PC at Step 5.2 all the same.
R-04 | Requirements grow after you see real output. | High | Medium | Expected and planned for: six separated layers (sheet 07) plus extension columns already in the schema.
R-05 | Data volume grows beyond what a browser handles comfortably. | Low | Low | Downgraded at Q-06: under 20 projects and 30 people is comfortably inside browser limits, with the headroom target in REQ-NFR-03.
R-06 | Excel date handling differs between Windows regional settings and misreads dates. | Medium | High | Dates normalised to ISO on import; an unparseable date is a hard error, never a guess (REQ-NFR-05).
R-07 | The file must be re-selected each session and this becomes irritating. | Medium | Low | Optional browser caching (REQ-IMP-06) plus a one-click reload of the last file.
R-08 | On-screen edits are lost because the user closes the page without exporting. | High | High | The direct cost of REQ-IMP-07. Mitigated by REQ-IMP-08: a visible unsaved-edit count and a warning before any action that discards them. The browser cache (REQ-IMP-06) becomes more valuable here as a second net.
R-09 | Milestone-derived periods break for a project with missing or out-of-order milestones. | Medium | High | Raised from Medium impact: at v0.3 the derivation depends on specific milestones, so a missing CTA submission or DB lock now stops it outright. V-14 and V-16 make those errors rather than warnings; V-12 catches any remaining gap and falls back to weight 1.00 with a report.
R-10 | The weight and role-factor values are unknown to the plan, so output cannot be checked against reality until they are entered. | Medium | Medium | Downgraded at Q-17: the values are data you enter in the source workbook, not a plan input, which is what REQ-CAL-06 always required. The engine is validated against the worked example on sheet 05; realism of the numbers is validated at WBS 4.9 against your real data.
R-11 | The period mapping leaves parts of a project with no period, so months silently carry a default weight. | Low | Medium | Closed in substance at Q-21..Q-23: the mapping is now contiguous, verified against five timelines including four degenerate ones. REQ-CAL-10 and V-12 keep any residual gap visible rather than silent.
R-12 | Fully editable identifiers let a user break the links between sheets. | Medium | High | The direct cost of the Q-20 answer. Mitigated by V-17 and REQ-IMP-10: identifier edits cascade after confirmation, and a referenced row cannot be deleted. Without that, 'every field editable' and 'no inconsistency' could not both hold.
Assumptions
ID | Assumption | Status
A-01 | Data volume is under 20 projects and 30 people. | CONFIRMED Q-06
A-02 | One person's capacity is 1.00 FTE = 160 hours per month; part-timers carry a lower capacity_fte. | CONFIRMED Q-08
A-03 | Monthly granularity is sufficient; weekly or daily simulation is not required in v1.0. | Standing
A-04 | The source workbook is maintained by hand, not generated by another system. | Standing
A-05 | Windows 10 or 11 with Edge or Chrome, and local .html files open. | CONFIRMED Q-05
A-06 | Only one person maintains the workbook at a time - no concurrent editing to reconcile. | Standing
A-07 | Milestone dates now DRIVE period boundaries (REQ-CAL-09); they are no longer merely informational. | Changed by Q-01/Q-04
A-08 | Period sets are type-specific: seven names for either clinical trial type, three for 'Others'. No name repeats within a project. | CONFIRMED Q-18, Q-23; revised at R-11
A-09 | A clinical trial's period weights are selected by its clinical phase. | CONFIRMED Q-26
A-10 | 'Others' projects have no milestone mapping, so their three periods are entered by hand. | CONFIRMED Q-25
A-11 | No example source file is coming; the structure in this plan is taken as matching the existing one. | CONFIRMED Q-13
Legend
Green = new in v0.2, added from your review answers.
Orange = changed in v0.2 as a consequence of your review.
Yellow = still needs your input.

## 11_Open_Questions
Questions and answers
All 28 questions raised across four review rounds, with their answers and how each was applied. Nothing is open.
Answered at the v0.4 review [round 4 - final]
ID | Topic | Question (short) | Your answer | How it was applied in v1.0
Q-27 | Naming | What is a close-out called on a trial with no interim lock? | With no interim DB lock, the final DB lock falls into 'Close-out (final)'. | Confirms v0.4 as built - one name, no special case in the weight lookup.
Q-28 | Calculation | What selects period weights for 'Others' projects? | No need to distinguish each 'Others' project. They are given manual input for the weight of periods. | Applied - 'Others' weights are entered by hand, so PeriodWeightStandard becomes a clinical-trial table only. Together with Q-25 this makes 'Others' projects hand-entered throughout: dates and weights alike.
Answered at the v0.3 review [round 3]
ID | Topic | Question (short) | Your answer | How it was applied in v0.4
Q-21 | Calculation | Is 'Before-Start-up' the stretch before Start-up? | Yes - project start date to 1 month before CTA submission. | Applied - confirms the v0.3 reading. Sequence 1 on sheet 05.
Q-22 | Calculation | Conduct ends 3 months prior, Close-out starts 2 - which? | Close-out starts from 3 months prior, and runs until DB lock. | Applied - Close-out is now 3 months long and Conduct ends the day before it. This is the opposite of the v0.3 default, which had shortened Close-out instead; corrected.
Q-23 | Calculation | Which DB lock does Close-out end at? | With an interim lock, split into 'Close-out (interim)' and 'Close-out (final)'. The stretches before and after 'Close-out (interim)' are both Conduct. | Applied, and the largest change in v0.4: 'Conduct' can now occur twice in one project. ProjectPeriod gains period_seq; REQ-CAL-11 added; the clinical-trial period set grows to five names.
Q-24 | Data model | Which is the eighth standard milestone? | 'Protocol (v1)'. | Applied - milestone list now holds eight.
Q-25 | Data model | How do 'Others' projects get their period dates? | 'Others' projects don't have milestone mapping. | Applied - confirms the v0.3 assumption; their periods are entered by hand. Assumption A-10 confirmed.
Q-26 | Calculation | What selects a project's weight? | Clinical phase, where project_type is 'Clinical Trial'. | Applied - PeriodWeightStandard re-keyed from project_category to clinical_phase. clinical_phase now drives the simulation, so V-19 makes a missing phase an error.
Answered at the v0.2 review [round 2]
ID | Topic | Question (short) | Your answer | How it was applied in v0.3
Q-13 | Blocker | The '13_Templete_example' sheet is missing. | Structure already provided is similar to the existing one. No example file coming. Close this. | CLOSED. WBS task 1.5 removed; assumption A-11 records that the schema in this plan is taken as matching yours.
Q-14 | Data model | outsourcing_type listed a value twice. | 'Full outsourcing' / 'Partial outsourcing' / 'Full In-house'. | Applied - three values, REQ-PRJ-04 and the Lists sheet.
Q-15 | Data model | Which milestone set is standard? | 'CTA submission', 'First SIV', 'LPI', 'interim DB lock cut-off', 'interim DB lock', 'final DB lock cut-off', 'final DB lock'. | Applied - list replaced; FPI dropped. The answer says eight but names seven, so the count is queried at Q-24.
Q-16 | Calculation | Confirm the milestone-to-period mapping. | Start-up = 1 month before CTA submission, 4 months long. Conduct = after Start-up to 3 months before interim DB lock (final if no interim). Close-out = 2 months before that DB lock, to DB lock. | Applied with three corrections - the mapping as written leaves gaps. See sheet 05 and Q-21, Q-22, Q-23.
Q-17 | Calculation | The weight and role-factor values. | Actual numbers to be filled into the source file (excel). | CLOSED. The plan fixes where the values live, not what they are - which is what REQ-CAL-06 always required. Risk R-10 downgraded. Part (c) of the question is handled by design and re-asked lightly at Q-26.
Q-18 | Calculation | Do 'Others' projects share the same periods? | No - 'Others' uses 'Planning' / 'Develop' / 'Close'. | Applied - REQ-PRJ-12, type-specific period sets, V-15. Raises Q-25: those periods have no milestones to derive from.
Q-19 | Data model | Can system_prepared_by be dropped? | Yes - replaced by the EDC_setup .. DM_conduct fields. | Applied - column removed from the Project sheet.
Q-20 | Editing | Which fields should be editable? | Every field. Validation rules prevent inconsistency between sheets instead. | Applied - REQ-IMP-09 widened, REQ-IMP-10 and V-17 added, decision C-09, risk R-12.
Answered at the v0.11 review [round 1]
ID | Topic | Question (short) | Your answer | How it was applied in v0.2
Q-01 | Calculation | Do weights multiply? | Yes: project weight x role factor x person weight. Project weight comes from the project's category and is the same for everyone on that project in that milestone period. Role factor is the standard weight of the role. Person weight says how much the person works on the project. | Applied - sheet 05. base_allocation removed; PersonPeriodWeight became an override.
Q-02 | Calculation | Pro-rate partial months by calendar days? | Yes - expected work follows the calendar days worked between the joined date and the end date. | Applied - C-02 confirmed; REQ-CAL-05 raised to Must.
Q-03 | Roles | Which roles, and do they differ in burden? | Clinical Trial: Project oversight, Lead data manager, Clinical Data Associator, Clinical Database Programmer, Data Analyst. Others: Project lead, Main staff, Other staff. | Applied - RoleFactor gains a project_type column; V-03 raised to an error.
Q-04 | Project periods | Standard period names and weights? | Before-Start-up, Start-up, Conduct, Close-out. | Applied - sheet 04 ProjectPeriod. Weight VALUES still needed - Q-17.
Q-05 | Environment | Can you open a local .html file? | Yes. | Applied - risk R-03 closed.
Q-06 | Data volume | How many projects and people? | Under 20 projects and 30 people. | Applied - REQ-NFR-03 target reduced; R-05 downgraded.
Q-07 | Milestones | Which milestones? | CTA submission, FPI, LPI, DB lock cut-off, DB lock. | Applied - Milestone list. Conflicts with the v0.11 mark-up in sheet 04 - see Q-15.
Q-08 | Capacity | Capacity and thresholds? | 1 FTE = 160 h/month (8 h/day, 5 days/week, 20 days/month). Over-allocation: total above 1.5 FTE in a month. Under-allocation: below 0.8 FTE for 3 months or longer. | Applied - REQ-CAL-04, REQ-CAL-07, REQ-CAL-08; Config parameters; sheet 06 flagging.
Q-09 | Source files | One workbook or two? | One single workbook with all sheets. | Applied - sheet 04 restructured; REQ-OUT-03 reworded; architecture and deployment updated.
Q-10 | Existing data | Existing spreadsheet structure? | Refer to '13_Templete_example'. | NOT APPLIED - that sheet is not in the returned file. See Q-13.
Q-11 | Horizon | Planning horizon? | 24 months default, expandable to the latest project end date. | Applied - REQ-CAL-01, REQ-DSH-07, Config default_horizon_months.
Q-12 | Scope check | Anything wrongly out of scope? | Fine. | Applied - exclusions confirmed on sheet 02.
Change requests against the approved v1.0 baseline
Raised after Gate 1, so these are handled as a numbered change rather than absorbed silently. All are applied and confirmed; the change needs its approval signature on sheet 12. Note that this register and the risk register on sheet 10 both number their entries R-nn. They are separate ID spaces - change R-07 is the threshold answer, risk R-07 is the file-reselection nuisance. Renumbering either now would invalidate the approval signatures and cross-references already given against these IDs.
ID | Topic | Change requested | How it was applied | Status
R-64 | Data model | Offer at least 12 distinctive highlight colours. | Applied. Thirteen colours for milestones and periods, distinct in both themes; offered in every workbook, older ones included; a swatch per colour in the chooser; the colour word read as a word. REQ-PRJ-17 added; template v1.21; no figure moves. | Applied
R-63 | Python edition | Make the file search windows more graphical and useful; do not apply the session time-out to a private plan; when a session does time out, say so in a pop-up. | Applied (Python edition 1.35; desktop plan v1.18). A plan in My plans takes no hold, so it never times out (NR-STO-20). A lapsed hold on a team plan raises a pop-up naming who took over and offering to keep your version (NR-STO-21). The file window gains places, a clickable path with back/forward/up, type badges, how-long-ago and date groups, a filter, list or tiles, details, the keyboard, and who saved / is editing a plan (NR-IMP-10). | Applied
R-62 | Dashboard | Let a manager confirm a short / over / not-staffed issue - 'no issue' or 'accepted', with a rationale - from the issue itself, changeable later; show confirmed issues distinguished (muted) but still readable, with the confirmation and rationale shown whenever the issue is clicked. | Applied. New sheet IssueReview; source schema steps 15 to 16. Clicking an issue month opens it with a Manager review box (decision, manager, reason, whole run); Confirmed and Accepted close it and need a reason, To be fixed keeps it open. Closed months are drawn muted, counted apart, and filterable. A review covers the gap it was made at; V-40 added; REQ-DSH-20 added; no figure moves. | Applied
R-61 | Storage | Let a user whose session timed out save the working plan into their personal folder. | Applied (Python edition). When the shared plan can no longer be written - the hold lapsed and was taken over, or a colleague saved since it was opened - a bar offers 'Save my version to My plans': a new, uniquely named file in the person's own folder, after which the window works on it. Also on the File menu. The team's plan is never touched. | Applied
R-60 | Data model | Colour every project's periods from an assumption on the General assumptions tab; where none is assumed for a period, let the project choose. | Applied. New sheet PeriodHighlight, one default colour per period name; source schema steps 14 to 15. The project's own Highlight wins, then the default, then gray; derived periods take the default too. Shipped defaults restore the O-10 reading as data. V-39 added; REQ-PRJ-16 added; no figure moves. | Applied
R-59 | Data model | Add a Highlight column to Periods like the Milestones one: choose the colour of each project's period, gray when none is chosen. | Applied. ProjectPeriod gains period_highlight after period_end; source schema steps 13 to 14. Its own list of the same five colours; the colour word inside the value is what is read. Unmarked periods are gray, shaded by weight, superseding the per-period-name hues of O-10. A value naming no colour is V-38. REQ-PRJ-15 added; no figure moves. | Applied
R-58 | Audit | Saving shows 'the change log could not be written to the audit folder ... Failed to fetch' - is the audit trail working? | It works; the Python application behind the window had stopped. Its watchdog gave up after fifteen minutes without a heartbeat, which a sleeping browser tab or laptop reaches. Now only the page closing stops it, and a window whose application has stopped says so and offers downloads of the plan and the unarchived change log. | Applied
R-57 | UI | The import file window does not show the sub-folders of a level-1 folder. | Fixed in the Python edition. A double-click opened the folder on its first click and then the row under the pointer in the redrawn list on its second, so the folder asked for was skipped. The second click of a sequence is now ignored on a freshly drawn list, and a double-click chooses only the row it began on. | Applied
R-56 | UI | Filters by name; a new project or person stays selected after Save; Resource by project to show auto vs manual, to filter to problem projects, and to count not-staffed months; file dates when importing and exporting. | Applied. Project and Person filters list names with a search box. A row added with + row is the selection through typing, Save and a change of identifier. Resource by project gains an estimation pill per project, a mark on stated months and a Show control (issues, short, over, not staffed, stated by hand); not-staffed months are counted on the control, the tile and the Standard vs staffed list. The Python file browser shows modified dates, newest first; exported names carry date and time. | Applied
R-55 | Output | Make the calculated-FTE export usable for analysis outside the application, including by an AI: which projects are short or over, and by how much. | Applied. ProjectMonth gains demand_fte, staffed_fte, gap_fte and gap_dir, and a row for every month nobody is on (V-36), which used to be dropped. Flags gains project runs - short, over, unallocated - and Summary the matching totals. The gap is the project's own whatever filter is on. PersonMonth gains the months a person is employed and on nothing, as spare capacity. REQ-OUT-06 amended. Alongside: tools/prap_analyze.py (scorecard and what-if comparison) and docs/PRAP_AI_Analysis_Guide.md. | Applied
R-54 | UI | Two raised from the screen: three cell marks were printing their own CSS escape, and the Order column on Milestones is not wanted. | Both applied. The marks were written with a doubled backslash, so \25B2, \25BC and \26A0 were drawn as text instead of the arrows and the warning sign; three guards added, one static and two on the rendered character. milestone_seq is no longer drawn - it orders nothing, and its pop-up said otherwise. period_seq is kept: both engines sort by it and V-18 reports a duplicate as an error. | Applied
R-53 | UI | Let the Standard vs staffed list be narrowed, and keep a project's identity on screen while its table scrolls sideways. | Both applied. The list gains three controls - direction, project, smallest gap - which narrow the LIST only; the tile and the control in the panel head go on counting everything, because they are the alarm. The Project table freezes the row handle, project_id and project_name at its left edge. REQ-DSH-15 amended and REQ-DSH-19 added. | Applied
R-52 | UI | Move Standard vs staffed onto Resource by project and open it from a control there. | Applied. The list is now a dialog opened from that panel's head; a row opens the month on top of it. What the move costs - a list behind a click - is paid back by the control, which states how many months are off their standard and in which direction instead of naming the screen. REQ-DSH-15 amended. It also exposed a defect of its own: the tile that was supposed to jump to the old panel had never worked, because the pop-up handler runs in the capture phase and swallowed the click on a div that declares role=button. | Applied
R-51 | UI | Give every section a control that opens it full screen, so wide tables can be read and typed into at the size they actually are. | Applied. The panel is drawn against the viewport rather than moved into an overlay or a dialog - an edit re-renders the pane it lives in, so a detached node would be orphaned by the first keystroke saved, and a modal would make Save inert. The sticky band carrying Save and the tabs is lifted above the section instead of being covered. Panels gained names so the state survives a re-render and a change of selected row. REQ-DSH-18 added. | Applied
R-50 | Data model | Mark a milestone in a colour, and carry the mark to the Project timeline on both tabs. | Applied. Milestone gains milestone_highlight beside milestone_date; source schema steps 12 to 13. The colours live in Lists, and the application reads the COLOUR WORD inside the value - so a team may write what their colour means and keep both. A value with no colour word in it is V-37 and the milestone draws unmarked. REQ-PRJ-14 added. | Applied
R-01 | Data model | Add 'Inspection' as a standard milestone. | Applied. Milestone list grows to ten. Unlike the others, 'Inspection' MAY REPEAT within one project, so REQ-PRJ-13 and V-20 were added and V-14's uniqueness check now exempts it. | Applied
R-02 | Calculation | Sheet 05 derivation edits: Before-Start-up ends at 'Protocol (v1)'; Start-up begins the day after it and ends at 'First SIV' (or 'FPI'); a seventh period 'After Close-out (final)' spans the Inspection dates. | Applied. Clinical period set grows to six names; REQ-PRJ-12 and REQ-CAL-09 reworded; REQ-CAL-13 added for the milestone-beats-offset rule; 'FPI' restored to the milestone list as the First SIV fallback. | Applied
R-03 | Calculation | Not requested - found while applying R-02. | Period 7 was defined as earliest to latest 'Inspection'. Where an inspection is dated on or before the final DB lock, that makes period 7 start before period 6 and overlap Conduct. Only inspections AFTER the final DB lock open period 7; earlier ones stay markers, reported by V-21. CONFIRMED by the reviewer at the v1.1 review. | CONFIRMED
R-13 | UI | Two requests at the component-list v0.7 review: highlight the interim and final DB lock milestones in red, and add a project utilisation graph to the 'Source data (project)' tab. | Both applied. The DB locks are the milestones the whole period derivation hangs on - move a lock and every period after it moves - so red plus a larger marker is warranted; size carries it as well as hue, because D-04 makes 'never colour alone' a floor. The cut-off milestones stay ordinary: the cut-off is preparation, the lock is the event. The utilisation graph needed a new requirement, REQ-DSH-12, because the person tab's equivalent rests on absolute thresholds a project does not have - which the reviewer identified. The references are therefore relative: 2x and 0.5x the portfolio average for an active project-month, plus the project's own lifetime average. | Applied
R-12 | Validation | Raised as a question about the PersonPeriodWeight key - why is period_start needed when assignment_id looks unique? | The key is correct and unchanged: (assignment_id, period_start). assignment_id is unique in Assignment, but PersonPeriodWeight is a CHILD of it, and REQ-PSN-05, V-06 and the data model all allow one assignment to carry several non-overlapping override windows. Keying on assignment_id alone would cap it at one. But checking the question exposed two real gaps, both now closed: V-06's assignment-window half had never been implemented, so an overlapping pair passed silently and the applied weight depended on row order; and nothing checked that a PersonPeriodWeight row referred to a real assignment, so an orphan override was accepted and ignored without a word. V-24 added for the second. The dummy fixture now carries an assignment with TWO windows - it only ever had one each, which is why neither gap surfaced. | Applied
R-11 | Data model | Name the two conduct stretches apart - 'Conduct (interim)' before an interim DB lock, 'Conduct (final)' after it or where there is no interim lock - and key ProjectPeriod on (project_id, period_name). | Applied, and it simplifies more than it costs. The clinical period set grows from six names to seven, but no name now repeats in a project, so ProjectPeriod has a natural key again and period_seq goes back to carrying order rather than identity. V-18 becomes a plain uniqueness check. REQ-CAL-11 and REQ-PRJ-12 reworded. REQ-DSH-10, which existed to number repeated names on screen, is now satisfied by the data model instead - the display numbering is kept only as a guard. This is the alternative offered against decision D-15 at the component-list review, so D-15 is superseded. Schema 4 -> 5: the columns are unchanged but the period_name value set is not, so a v4 file's 'Conduct' rows would fail V-15. PeriodWeightStandard grows 48 -> 56 rows and RoleFactor 249 -> 289; both new Conduct entries carry the same weights the single 'Conduct' did, so the change renames without reweighting - the dummy dataset returns byte-identical load figures. | Applied
R-10 | Data model | The role factor must be given by role AND project type AND clinical phase AND period, not by role and type alone. | Applied. RoleFactor gains clinical_phase and period_name; its key becomes all four columns and the sheet grows from 13 rows to 249. REQ-CAL-02 reworded, V-23 added, schema 3 -> 4. This is a real gain in expressiveness - a role's burden genuinely is not flat across a project, and the dummy data now shows the database programmer peaking at start-up and the analyst at lock. It carries two costs, both stated rather than hidden: 249 rows is a large hand-maintained table, and RoleFactor now varies over the same three dimensions as PeriodWeightStandard, so the two multiply and can double-count if both are edited for the same reason. See the note on sheet 04. | Applied
R-09 | UI | Nine components changed at the component-list v0.3 review: a fourth tab for the standing assumptions, insert-row on every editable table, clinical-phase filter, the unit toggle demoted from filter to setting, the demand-chart legend replaced by a hover pop-up, four timeline changes, a time zone on the load stamp, and the edit counter stating its validation standing. | Applied. Seven were satisfiable by design alone. Two were not: nothing in the plan required the assumptions to be reachable in the application, and nothing said a row could be created at all - so REQ-DSH-11 and REQ-IMP-11 were added. REQ-DSH-05 and REQ-IMP-05 reworded. One conflict surfaced: O-10 asks the timeline to be coloured by period name, which contradicts accepted decision D-06 (shade by weight). O-10 is the more specific instruction, so D-06 is superseded and weight becomes a lightness step within each period hue. | Applied
R-08 | UI | The two 'Conduct' stretches of a project must be distinguishable on screen (S2-04). | Applied as REQ-DSH-10. A display rule, not a data change: period_name stays 'Conduct' in the workbook and the screen shows it with its sequence, 'Conduct (1)' and 'Conduct (2)'. Changing the stored name would have broken the weight lookup and V-15. | Applied
R-07 | Calculation | Thresholds stay ABSOLUTE, not relative to capacity_fte (S2-01), and the under-allocation floor moves to 0.60 FTE (S2-05). | Applied. Taken together these resolve the defect S2-01 was raised about: at a 0.60 floor every capacity in the data can clear it - 1.00 needs 60% utilisation, 0.80 needs 75%, 0.60 needs 100%. The risk only returns for a capacity BELOW the floor, so V-22 warns on exactly that. REQ-CAL-04 and REQ-CAL-07 reworded; Config default 0.80 -> 0.60. | Applied
R-06 | Non-functional | Re-baseline REQ-NFR-03 to 100 projects and 1,000 people (S2-06). | Applied, and it was the most consequential answer in this round. At that volume the person table is 1,000 rows x 60 months = 60,000 cells, and the per-person chart would be 1,000 bars at roughly 1.2px each. Neither survives a naive build, so virtualisation and aggregation became requirements (REQ-DSH-09) rather than optimisations. Priority raised from Should to Must. SUPERSEDED AT R-47, and worth reading as a lesson rather than only as a record: the volume was reasoned about and never measured, the aggregation half was duly built, and the VIRTUALISATION half was recorded as built for five weeks without existing. Measurement then put the rendering budget's crossing point at about 400 people, so REQ-NFR-03 is now 100 projects and 150 people and the virtualisation clause is withdrawn. Priority stays Must. | Applied; volume superseded at R-47
R-05 | Data model | Split project_type: 'Clinical Trial' becomes 'NewDrug CT' and 'Biosimilar CT'; every clinical trial is one or the other. | Applied. REQ-PRJ-01 and REQ-PRJ-02 reworded. Both new types share the clinical period set and the same derivation - they differ in weights, not shape. RoleFactor and PeriodWeightStandard are now keyed on the type, so the split can carry real differences rather than being only a label. Schema 2 -> 3. All outputs regenerated. | Applied
R-04 | Data model | Add at least one free-text note column to every sheet of the source workbook. | Applied. Four sheets had none and each gains note_1: Milestone, ProjectPeriod, PeriodWeightStandard, Lists. Six already had one. Source schema version steps 1 -> 2. Note columns are carried through import and export unchanged and never read by the calculation, so the dummy dataset produces identical figures. | Applied
All four are settled. Nothing on this sheet is open, and the plan is final.
Six engineering decisions - C-06 to C-11 on sheet 05 - were proposed during the review rounds and never explicitly answered. Gate 1 approval of v1.0 confirmed them.

## 12_Review_Log
Review log and approval
Every change made in v0.2, and why. Reviewer input was given as direct mark-up in PRAP_Development_Plan_v0.11_reviewed.xlsx rather than as cell comments.
No. | Sheet / source | Reviewer input | Response | Action taken in v0.2 | Status
1 | 11_Open_Questions | All 12 questions answered. | Accepted in full. | Propagated into sheets 02-10; see rows below. | Closed
2 | 03_Requirements!A43 | New requirement added: 'After importing the source excel file, HTML to provide updating data and the updated data to be absorbed in the exported file when it extracts from the HTML.' | Accepted. Numbered REQ-IMP-07. | Added REQ-IMP-07, plus REQ-IMP-08 (unsaved-edit warning) and REQ-IMP-09 (re-validate edits), which it implies. Withdrew the v0.1 rule that nothing is editable (sheet 06). Added edit-buffer layer (sheet 07) and risk R-08. | Closed
3 | 04_Data_Model - Project | Added clinical_phase; EDC_setup, DataReviewSystem_setup, RBQM_setup, DM_conduct; EDC_system, DataReviewSystem, RBQM_system. Made outsourcing_type required. | Accepted. | All carried into the Project sheet with REQ-IDs REQ-PRJ-09/10/11. Value lists moved to the new Lists sheet. V-10 and V-11 added. | Closed
4 | 04_Data_Model - Project | outsourcing_type list reads 'Full outsourcing' / 'Partial outsourcing' / 'Full In-house' / 'Partial outsourcing'. | Query - 'Partial outsourcing' appears twice. | Flagged as Q-14. Resolved at round 2 - three values, see item 17. | Closed
5 | 04_Data_Model - Milestone | Milestone examples changed to FPI, LPI, LPO, LPLV, interim DB Lock, final DB Lock, CSR. | Query - conflicts with the Q-07 answer, which names five different milestones. | Q-07's list adopted as standard; raised as Q-15. Superseded at round 2 by a replacement list - see item 18. | Closed
6 | 04_Data_Model | Added project_name to Milestone and person_name to Assignment. | Accepted with a safeguard. | Kept as display conveniences, explicitly non-authoritative. V-13 checks them against the master row and refreshes rather than trusting them, so a stale copy cannot break a link. | Closed
7 | Q-09 answer | One single workbook instead of two. | Accepted. | Sheet 04 restructured into one workbook of ten sheets; REQ-OUT-03, REQ-IMP-01/03 reworded; architecture option (b) rejection strengthened; deployment updated. | Closed
8 | Q-01 answer | Three factors: project weight x role factor x person weight. | Accepted, with one consequence. | base_allocation removed - it was a fourth factor the answer did not name. Renamed to person_weight. PersonPeriodWeight changed from a multiplier to an override so no hidden fourth factor returns. Sheet 05 rewritten. | Closed
9 | Q-08 answer | 1 FTE = 160 h/month; over-allocation above 1.5 FTE; under-allocation below 0.8 FTE for 3+ months. | Accepted. | REQ-CAL-04 rewritten, REQ-CAL-07 and REQ-CAL-08 added. Under-allocation needs a rolling 3-month window, so it is specified as a run with a start and length, not a per-month flag. Config parameters added; sheet 06 flags both. | Closed
10 | Q-04 + Q-07 answers | Standard periods and milestones named. | Accepted, with a derivation. | Periods are now derived from milestone dates (REQ-CAL-09) so a timeline change re-shapes them automatically. Mapping raised as Q-16 and answered at round 2 with a different mapping - see item 19. Assumption A-07 changed: milestones now drive weights. | Closed
11 | Q-06 answer | Under 20 projects and 30 people. | Accepted. | REQ-NFR-03 target cut from 100 projects / 200 people / 1,000 assignments to a realistic figure with headroom; R-05 downgraded to Low/Low. | Closed
12 | Q-10 answer | 'Refer to 13_Templete_example'. | Cannot action - the sheet is absent from the returned workbook. | Verified against the file itself: it holds 13 sheets, 00 to 12, none hidden. Raised as Q-13; closed at round 2 - see item 16. | Closed
13 | 02_Scope!A1 | Sheet title cell was blank in the returned file. | Treated as accidental. | Title 'Scope and objectives' restored. | Closed
14 | Q-03 answer | Role lists differ between project types. | Accepted. | RoleFactor gains a project_type column; roles are matched on (project type, role name). V-03 raised from warning to error, since a role from the wrong type is now a real mistake rather than a typo. | Closed
15 | - | Role factors and period weight values. | Not supplied at round 1. | Resolved at round 2 - see item 20. | Closed
16 | Q-13 answer (round 2) | 'No example file provided from me. Close this.' | Accepted. | Blocker cleared. WBS task 1.5 removed; assumption A-11 records that the schema here is taken as matching the existing one. | Closed
17 | Q-14 answer | outsourcing_type has three values. | Accepted. | REQ-PRJ-04 and the Project sheet corrected. | Closed
18 | Q-15 answer | Milestone list replaced - First SIV in, FPI out, DB lock cut-off and DB lock split interim/final. | Accepted, with one query. | Milestone list replaced throughout. The count query was answered at Q-24 - 'Protocol (v1)' is the eighth. See item 27. | Closed
19 | Q-16 answer | Milestone-to-period mapping given for Start-up, Conduct and Close-out. | Accepted in substance; three gaps found. | Worked the mapping through a test project: it leaves 59 days before Start-up, 30 days between Conduct and Close-out, and 183 days after the interim DB lock with no period at all. A no-gap reading was adopted and the three points raised as Q-21..Q-23, all answered at round 3 - see items 24..26. REQ-CAL-10 and risk R-11 added so any residual gap is reported rather than silent. | Closed
20 | Q-17 answer | 'Actual numbers to be filled into the source file (excel).' | Accepted - this closes the question rather than deferring it. | The plan fixes where the values live, not what they are, which is what REQ-CAL-06 required all along. R-10 downgraded from High/High to Medium/Medium. Engine correctness is proven against the worked example; realism against your data at WBS 4.9. | Closed
21 | Q-18 answer | 'Others' projects use Planning / Develop / Close. | Accepted. | REQ-PRJ-12 added; ProjectPeriod and PeriodWeightStandard keyed by project_type; V-15 rejects a period from the wrong set. Q-25 confirmed at round 3 that 'Others' periods are entered by hand. | Closed
22 | Q-19 answer | system_prepared_by can be dropped. | Accepted. | Column removed from the Project sheet. | Closed
23 | Q-20 answer | Every field editable; validation rules prevent inconsistency. | Accepted, with the mechanism made explicit. | REQ-IMP-09 widened to all fields; REQ-IMP-10 and V-17 added for cascading identifier edits and refused deletes; decision C-09; risk R-12. Cascading is what makes an editable identifier safe - blocking the edit would have made it read-only in all but name. | Closed
24 | Q-21 answer (round 3) | Before-Start-up runs from project start to one month before CTA submission. | Accepted - confirms the v0.3 reading. | Sequence 1 of the derivation on sheet 05, unchanged. | Closed
25 | Q-22 answer | Close-out starts 3 months prior to DB lock and runs until DB lock. | Accepted - and it reverses the v0.3 default. | v0.3 had closed the one-month gap by shortening Close-out to two months. Your answer closes it the other way: Close-out is three months and Conduct ends the day before it. Corrected on sheet 05. | Closed
26 | Q-23 answer | With an interim DB lock, split into Close-out (interim) and Close-out (final); the stretches either side of Close-out (interim) are both Conduct. | Accepted. The structural change of v0.4. | A period name is no longer unique within a project - Conduct now occurs twice. ProjectPeriod gains period_seq; REQ-CAL-11 added; V-18 enforces sequence uniqueness; the clinical-trial period set grows from four names to five. Derivation re-verified contiguous. | Closed
27 | Q-24 answer | The eighth standard milestone is 'Protocol (v1)'. | Accepted. | Milestone list now holds eight. Only CTA submission and the DB locks are boundaries; the other six are markers. | Closed
28 | Q-25 answer | 'Others' projects have no milestone mapping. | Accepted. | Confirms the v0.3 assumption. A-10 moves from 'to confirm' to confirmed; their three periods are entered by hand. | Closed
29 | Q-26 answer | A clinical trial's weight relies on clinical_phase. | Accepted, with one consequence worth noting. | PeriodWeightStandard re-keyed from project_category to clinical_phase. clinical_phase stops being descriptive and starts driving the simulation, so V-19 makes a missing phase an error rather than the warning it was under V-10. Raises Q-28: 'Others' projects have no phase. | Closed
30 | Sheet 05 - derivation | Not reviewer input - a check made while applying the answers. | Five timelines tested. | The revised mapping was run against the normal case plus four degenerate ones: interim and final locks a month apart, no interim lock, CTA submission before project start, and a trial too short to have a Conduct phase. All five come out contiguous. Rules recorded as REQ-CAL-12 and decision C-11, and the omission cases documented on sheet 05. | Closed
31 | - | Naming and 'Others' weighting. | Two small points raised. | Raised as Q-27 and Q-28; both answered at round 4 - see items 32 and 33. | Closed
32 | Q-27 answer (round 4) | With no interim DB lock, the final DB lock falls into 'Close-out (final)'. | Accepted - confirms v0.4 as built. | No change needed. One period name covers both cases, so the weight lookup needs no special branch. | Closed
33 | Q-28 answer | 'Others' projects are not distinguished, and take manual input for period weights. | Accepted, and it simplifies the model. | PeriodWeightStandard becomes a clinical-trial reference table only; its '*' rows are gone. Combined with Q-25, 'Others' projects are now hand-entered throughout - both period dates and period weights. V-19 scoped to clinical trials. REQ-PRJ-06 reworded. | Closed
34 | Sheet 05 - decisions C-06..C-11 | Not reviewer input - six decisions proposed during the review rounds and never explicitly answered. | Resolved at approval rather than by a fifth round. | Gate 1 approval confirms C-06 (over/under-allocation judged on the person total), C-07 (period weights seeded then editable), C-08 (a month belongs to the period containing its first day), C-09 (identifier edits cascade), C-10 (boundaries recomputed on milestone change unless hand-edited) and C-11 (ordered clipping). Each is stated with its rationale on sheet 05. | Closed
35 | Gate 1 | Plan v1.0 approved by Dan, 2026-08-01, with direction to proceed to Step 2 starting from the workbook template and a dummy data file. | Recorded. | v1.0 is the approved baseline. Step 2 opened; template and dummy workbook issued for review as WBS task 2.0. | Closed
36 | 11_Open_Questions (post-approval) | Add 'Inspection' as a standard milestone. | Accepted as change R-01. | Milestone list grows to ten. 'Inspection' may repeat within a project, which no other milestone does - REQ-PRJ-13 and V-20 added, V-14 relaxed accordingly. Uniqueness is now on (project, name, date) rather than on name. | Closed
37 | 05_Resource_Logic (post-approval) | Derivation edits: Before-Start-up ends at 'Protocol (v1)'; Start-up starts the day after it and ends at 'First SIV' or 'FPI'; new seventh period 'After Close-out (final)' spanning the Inspection dates. | Accepted as change R-02. | Derivation table rewritten. Clinical period set 5 -> 6 names. REQ-CAL-13 added: where a boundary has both a milestone and an offset definition, the recorded milestone wins. 'FPI' restored to the milestone list - it had been dropped at Q-15, so this reverses that. | Closed
38 | 05_Resource_Logic | Not reviewer input - found while applying R-02. | One case in the mark-up does not resolve. | Period 7 is defined as earliest to latest 'Inspection'. An inspection dated on or before the final DB lock therefore makes period 7 start before period 6 and overlap Conduct. v1.1 counts only inspections after the final DB lock, treating earlier ones as markers (V-21). Verified contiguous across seven timelines. Raised as R-03 - see item 40. | Closed
39 | Version control | v1.0 is an approved baseline. | Changes cannot be absorbed silently. | Per the rules on sheet 09, a change against a baseline takes the next point release and needs its own approval. The approval block on sheet 12 holds v1.0 (signed) and this change (awaiting signature). | Closed
40 | 11_Open_Questions (v1.1 review) | R-03 confirmed: an inspection on or before the final DB lock stays a marker and does not open the seventh period. | Accepted - no content change needed. | R-03 closed. The derivation, requirements and validation rules stand exactly as issued at v1.1; v1.2 records the confirmation and re-issues for signature. V-21 continues to report the case so it is visible rather than silent. | Closed
41 | - | Status of the document as a whole. | Nothing open. | Across five review rounds: 28 questions and 3 change requests, all answered and applied. 65 requirements, 21 validation rules, 11 engineering decisions. | Closed
42 | Gate 1 | Plan v1.2 approved by Dan, 2026-08-01, with direction to continue Step 2. | Recorded. | v1.2 became the baseline and Step 1 closed. Programming specification v0.1 issued. | Closed
43 | Step 2 request | Add at least one note column to every sheet of the source workbook. | Accepted as change R-04. | Four sheets gain note_1. Source schema version steps 1 -> 2, so the data model on sheet 04 and the specification's parse contract both change. Template and dummy workbooks regenerated at v1.2 and re-verified: identical calculation results, confirming the note columns are inert. | Closed
45 | Specification v0.3 review | Six open points answered (S2-01 to S2-06). | Accepted; three change the plan. | S2-02 and S2-03 confirmed the draft with no change. S2-01 + S2-05 became R-07, S2-04 became R-08, S2-06 became R-06. The two calculation answers interact usefully: keeping thresholds absolute would have left the part-timer defect in place, but moving the floor to 0.60 removes it for every capacity in the data. | Closed
46 | Specification 03_Data_Schema!B26 | ProjectPeriod key changed from project_id + period_seq to project_id + period_name + period_start. | Accepted. | A natural key rather than a surrogate, and it disambiguates the two Conduct stretches just as well since their start dates differ. period_seq stays as the ordering column, and V-18 now checks both: the natural key for uniqueness, the sequence for deterministic ordering. | Closed
44 | Approval | Plan v1.3 approved FINAL by Dan, 2026-08-01. | Recorded. | Step 1 is complete. The plan is closed at 65 requirements, 21 validation rules, 11 decisions and a version-2 source schema. Work proceeds under PRAP_Programming_Specification_v0.2.xlsx, whose sheet 10 carries the one decision still outstanding (S2-01) - a specification matter, not a plan matter. | Closed
Disposition summary
Measure | Count
Closed in v0.2
Open - awaiting your answer
Total items
Approval - Gate 1
Document | Approver | Date | Decision
PRAP Development Plan v1.0 | Dan | 2026-08-01 | APPROVED. Finalise plan v1.0 and proceed to Step 2, beginning with generation of the workbook template and a dummy data file for review.
PRAP Development Plan v1.2 | Dan | 2026-08-01 | APPROVED. Finalise plan v1.2 and continue Step 2. This issue supersedes v1.0 as the baseline; R-01, R-02 and R-03 are part of it.
PRAP Development Plan v1.3 | Dan | 2026-08-01 | APPROVED - FINAL. Change R-04 accepted; this issue supersedes v1.2 and closes the development plan. Step 1 is complete.
PRAP Development Plan v2.0 | Dan | 2026-08-02 | APPROVED - BASELINE. Development plan v2.0, programming specification v1.0 and UI component list v1.0 all approved together; Steps 1 to 3 are closed and Step 4, code generation, is authorised. This issue supersedes v1.3 as the baseline. Changes R-05 (project_type split), R-06 (volume re-baselined to 100 projects / 1,000 people), R-07 (absolute thresholds, floor 0.60), R-08 (repeated period names distinguishable on screen), R-09 (component-list review: assumptions tab and insert-row become REQ-DSH-11 and REQ-IMP-11), R-10 (role factor keyed on type, phase, period and role) R-11 (conduct stretches named apart; ProjectPeriod keyed on project_id + period_name; schema 4 -> 5) and R-12 (two unimplemented validation rules on PersonPeriodWeight closed; V-24 added) and R-13 (component-list review: DB lock milestones emphasised, and a project utilisation graph added as REQ-DSH-12).
STEP 1 COMPLETE. v1.3 is the final development plan: the 65 requirements on sheet 03 are the contract for Steps 2-5, decisions C-01 to C-11 on sheet 05 are confirmed, and the source schema is version 2. The plan is closed; further change would need a new approval and a version increment, but none is expected. Work now proceeds under the programming specification.