## 00_README
PRAP source data - scenarios
Schema version 12. Matches PRAP_Development_Plan_v1.0.xlsx, sheet 04_Data_Model.
COLOUR KEY
Blue identifier or key column - these link the sheets together.
Green DERIVED. Do not type in these. They are LOCKED, so the sheet will refuse the
edit, and the column heading carries a note saying why. See below.
Yellow you must supply this value. The application cannot work it out.
Grey italic row an example, in the template only. Delete it before use.
DERIVED COLUMNS ARE LOCKED
Three columns are computed, not entered:
Project.total_period_months from start_date and end_date
Milestone.project_name looked up from Project
Assignment.person_name looked up from Person
Their cells are locked and every other cell on the sheet is not, so typing into one
is refused where it happens rather than going wrong later. There is NO PASSWORD:
Review > Unprotect Sheet turns it off if you genuinely need to paste a column.
Adding, deleting and sorting rows all still work with protection on; only adding or
removing COLUMNS is blocked, because the column set is the schema.
What the lock is protecting you from: a value typed into one of these is not
recalculated by anything, and the application recomputes the column on import in any
case - so a hand-typed one is discarded, and the disagreement is reported as V-13.
SHEETS
Project one row per project.
Milestone one row per milestone. Eight standard names.
ProjectPeriod the periods each project passes through, with their weights.
PeriodFTEStandard default weights per project type, clinical phase, WORK SCOPE and
period. Clinical trials only.
RoleFactor the relative burden of each role, per project type, clinical phase,
WORK SCOPE and period. Leave clinical_phase empty on the 'Others' rows.
Person one row per person.
Assignment one row per person + project + role.
PersonPeriodWeight optional windows where a person's weight differs.
Lists permitted values for every dropdown.
Config thresholds and settings.
FREE-TEXT NOTES
Every sheet carries at least one free-text column, so anything worth recording has a home:
Project note_1 .. note_5
Milestone note_1
ProjectPeriod note_1
PeriodFTEStandard note_1
RoleFactor role_note
Person note_1 .. note_5
Assignment note_1 .. note_3
PersonPeriodWeight reason
Lists note_1
Config note
Nothing in a note column affects the calculation. They are carried through import and export
unchanged, so they survive a round trip.
HOW THE CALCULATION USES THIS
monthly load = project period weight x role factor x person weight x month coverage
The result is FTE, where 1.00 FTE = 160 hours per month.
Over-allocated: a person's monthly total above 1.50 FTE.
Under-allocated: below 0.80 FTE for three or more consecutive months.
PERIODS
Clinical trial periods are derived from the milestone dates:
Before-Start-up project start, to the day before Start-up
Start-up one month before CTA submission, lasting four months
Conduct from the end of Start-up to the day before the next close-out
Close-out (interim) three months before the interim DB lock, to that lock
Conduct (again) from the interim DB lock to the day before Close-out (final)
Close-out (final) three months before the final DB lock, to that lock
After Close-out (final) the inspection activity that follows the final DB lock
Where 'Protocol (v1)' is recorded, Before-Start-up ends on it and Start-up begins the day after.
Where 'First SIV' (or 'FPI') is recorded, Start-up ends on it instead of running a fixed four
months. A recorded milestone always beats the month-offset fallback.
'Conduct' therefore appears TWICE where a trial has an interim DB lock. period_seq keeps
the two apart. A period squeezed to nothing by a tight timeline is simply omitted.
'Inspection' is the one milestone that may be recorded SEVERAL TIMES for a project. Only
inspections dated AFTER the final DB lock open the last period; an earlier one stays a marker.
'Others' projects have no milestones. Their period dates and weights are both typed in.
WORK SCOPE, AND THE NOTE BESIDE IT
work_scope_type is the field the CALCULATION reads: with the project type and the phase
it selects the standard weights and the role factors. It is a value list, so it has to be
one of a known set.
outsourcing_scope_det beside it is FREE TEXT and is read by people only. Write what is
actually outsourced and to whom - the detail the category cannot carry. Nothing you write
there changes a single figure.
It replaces outsourcing_type, which was a value list and is gone at schema 7. A workbook
still carrying that column is read: its values are moved across, and the application says
so once.
ASSIGNMENT DATES ARE OPTIONAL
Leave assign_start_date and assign_end_date BLANK for somebody who is on the project for
the whole of it - which is most people. A blank date means the project's own, so the two
never fall out of step when the project's dates move.
Fill them in only for a PARTIAL involvement: somebody who joins late, leaves early, or
covers one stretch of a longer study.
ADDING A PERMITTED VALUE
Insert a row inside that list's block on the Lists sheet, so the block stays contiguous -
the dropdowns read a range, not a scattered set of rows. work_scope_type is meant to be
extended this way: the three values supplied are a starting point, not a closed set.
WORK SCOPE, AND THE EMPTY ROW THAT COVERS EVERY SCOPE
PeriodFTEStandard and RoleFactor are keyed on work_scope_type as well as on the project
type, the phase and the period. A row with work_scope_type EMPTY applies to EVERY scope.
So fill the empty-scope rows first - they are your baseline - and add a scope-specific row
only where that scope really does change the number. A project looks for its own scope
first and falls back to the empty row, so nothing has to be entered three times to say
the same thing three times.
WHAT THIS FILE IS
A test bed, not a plan. 18 scenarios across 50 projects and 50 people.
Every project is ONE scenario and is named after it; the note on each row says what
it is for. Nothing here is random and nothing is filler.
50 projects ¦ 50 people ¦ 292 assignments ¦ 3 override windows ¦ 143 stated months
WHAT IT DELIBERATELY DOES NOT DO
It does not carry the ERROR-class problems that make the application reject a row -
an assignment pointing at a project that does not exist, a role with no factor, a
date that ends before it starts. Those need a file that is broken on purpose, and a
broken file cannot also be the one you click through to watch the application work.
The rules reported here are the ones that leave a usable plan behind.
The weights and role factors are ILLUSTRATIVE. Replace them before drawing any
conclusion from the output.
IF YOU ARE AN AI AGENT READING THIS FILE
docs/prap_contract.json is the machine-readable contract: every sheet, column,
value list and validation rule, with the severity each one carries. Read it before
writing to this workbook - it is what stops a plausible-looking column name being
silently ignored.
To check a file without a browser:
python tools/verify_source_workbook.py <file.xlsx> full validation + figures
python tools/prap_io.py validate <file> .xlsx or .prap.json
Every project note_1 says whether the row is a SCENARIO or portfolio filler, so the
interesting rows can be found without reading this sheet.
The figures are checked by four independent implementations that must agree - the
browser engine, tools/prap_io.py, tools/verify_source_workbook.py and the reference
inside tools/test_app.py. If your own arithmetic disagrees with all four, it is
probably yours; REQ-CAL-19 is the rule most often got wrong (a project-month IS its
standard, and the people on it DIVIDE it - they do not each add to it).
WHAT EACH PROJECT IS FOR
SCN-001 The baseline: every clinical period, every role staffed, all figures calculated.
Look at: Overall > Monthly demand by project. Source data (project) > Periods, to see the standard beside each weight.
SCN-002 A project STATED BY HAND, below what its own standard asks for. Trips V-34 short.
Look at: Overall > Standard vs staffed. The month is marked on the chart and in Resource by project; click it to open the figures behind it.
SCN-003 The same, stated ABOVE the standard. Trips V-34 over.
Look at: Overall > Standard vs staffed - the two directions are counted separately and never netted off.
SCN-004 A project figure stated by hand OVER an assignment figure also stated by hand. Trips V-33.
Look at: Source data (person) > PSN-004 > Monthly estimation. The stated figure and the one actually given are both shown.
SCN-005 An assignment on manual with a month that has NO figure. Trips V-31.
Look at: Source data (person) > PSN-005 > Monthly estimation, and the 'Fill the missing months' button.
SCN-006 A project figure for a month with NOBODY assigned. Trips V-32 - it cannot be shared out, so it is not applied.
Look at: The findings report, and Source data (project) > Monthly estimation.
SCN-007 An 'Others' project: three hand-entered periods, three 'Others' roles, no milestone derivation.
Look at: Source data (project) > Periods. The derivation button offers 'Standard periods' here, not 'Auto derivation'.
SCN-008 A role NOBODY holds, whose factor is picked up by another role (REQ-CAL-16).
Look at: Source data (project) > Utilisation. Clinical Data Associator is unstaffed; its factor lands on the Lead data manager.
SCN-009 One role held by THREE people at once, so each claims a third of what one would.
Look at: Source data (person) > Monthly estimation > 'Sharing this role'. The project's month does not move when a sharer is added.
SCN-010 A project with NO assignments at all.
Look at: Resource by project - it draws nothing, and says so rather than disappearing.
SCN-011 A derived column that DISAGREES with its master row. Trips V-13 - the file is read, then the master value wins.
Look at: The findings report. A milestone here records the wrong project_name; Project is the master and is used.
SCN-012 A clinical trial with NO product recorded. Trips V-04.
Look at: The findings report - a warning, not a refusal: the plan is still costed.
SCN-013 An Inspection BEFORE the final DB lock, which does not open the after-close-out period. Trips V-21, for information.
Look at: The findings report, and Overall > Project timeline (SCN-005).
SCN-014 A milestone name recorded TWICE on one project. Trips V-20.
Look at: The findings report, and Source data (project) > Milestones (SCN-009).
PSN-002/3 A capacity BELOW the under-allocation floor, so the person can never clear it however fully they are booked. Trips V-22.
Look at: The findings report. 0.50 and 0.00 are both legal capacities - V-35 bounds the column at 0.00 to 1.00 - and both are under the 0.60 floor.
PSN-001 A person over the 1.50 FTE ceiling, on four projects at once.
Look at: Overall > Resource by person, and Source data (person) > Utilisation: the bar is outlined where the month crosses a threshold.
BLK-xxx A milestone dated AFTER the project's own end, which extends the timeline rather than being dropped. Trips V-14, for information. (Large set only.)
Look at: The findings report, and Overall > Project timeline.
(several) A role that carries a factor and that NOBODY holds and nothing covers for. Trips V-29, for information - it is work not being counted.
Look at: The findings report. Distinct from SCN-008, where the unstaffed role IS covered and so is not reported.

## Project
project_id | project_name | project_type | project_category | clinical_phase | work_scope_type | outsourcing_scope_det | EDC_setup | DataReviewSystem_setup | RBQM_setup | DM_conduct | EDC_system | DataReviewSystem | RBQM_system | planned_member_count | start_date | end_date | total_period_months | status | estimation_type | note_1 | note_2 | note_3 | note_4 | note_5
SCN-001 | SCN-001 Baseline trial | NewDrug CT | Scenario product | Phase 3 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | automatic | SCENARIO. Nothing unusual - read this one first, the others are departures from it.
SCN-002 | SCN-002 Stated below standard | NewDrug CT | Scenario product | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | manual | SCENARIO. estimation_type = manual, with figures deliberately smaller than the standard - V-34 short.
SCN-003 | SCN-003 Stated above standard | Biosimilar CT (Healthy) | Scenario product | Phase 3 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | manual | SCENARIO. estimation_type = manual, figures above the standard - V-34 over.
SCN-004 | SCN-004 Two manual levels | Biosimilar CT (Patient) | Scenario product | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | manual | SCENARIO. Both levels manual. The project figure is the mother figure and the people on it are scaled to it (REQ-CAL-18) - V-33.
SCN-005 | SCN-005 Missing stated month | NewDrug CT | Scenario product | Phase 2 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | automatic | SCENARIO. One assignment here is manual with a month left unstated - V-31. Its Inspection is also early - V-21.
SCN-006 | SCN-006 Figure with nobody on it | NewDrug CT | Scenario product | Phase 4 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | manual | SCENARIO. Manual figures run the whole project; the staffing stops half way, so the later figures cannot be shared out - V-32.
SCN-007 | SCN-007 Internal project | Others |  |  | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-01-31 |  | Active | automatic | SCENARIO. An 'Others' project: no clinical phase, no product, and periods entered by hand.
SCN-008 | SCN-008 Unstaffed role absorbed | NewDrug CT | Scenario product | Phase 2 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | automatic | SCENARIO. No Clinical Data Associator is assigned; RoleFactor.absorbed_by sends that work to the Lead data manager.
SCN-009 | SCN-009 Three share one role | NewDrug CT | Scenario product | Phase 3 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | automatic | SCENARIO. Three people hold Clinical Data Associator, so each claims a third of the factor. A milestone is also duplicated - V-20.
SCN-010 | SCN-010 Nobody assigned | Others |  |  | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2026-10-31 |  | Planned | automatic | SCENARIO. No assignments at all - it draws nothing and says so rather than disappearing from the tables.
SCN-011 | SCN-011 Derived disagreement | NewDrug CT | Scenario product | Phase 3 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 | 99 | Active | automatic | SCENARIO. One milestone row carries a stale project_name - V-13. total_period_months also says 99; that one is recomputed in silence, because the file's value is never trusted for it.
SCN-012 | SCN-012 No product named | NewDrug CT |  | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-01-01 | 2027-12-31 |  | Active | automatic | SCENARIO. A clinical trial with no product recorded - V-04. A warning, not a refusal: the plan is still costed.
BLK-001 | BLK-001 NewDrug study | NewDrug CT | Compound A | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2026-09-01 | 2028-08-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-002 | BLK-002 Biosimilar study | Biosimilar CT (Healthy) | Compound B | Phase 3 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2032-04-01 | 2033-12-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-003 | BLK-003 Biosimilar study | Biosimilar CT (Patient) | Compound C | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2027-05-01 | 2029-02-28 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-004 | BLK-004 Others study | Others |  |  | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-10-01 | 2030-08-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-005 | BLK-005 NewDrug study | NewDrug CT | Compound E | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-01-01 | 2031-03-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-006 | BLK-006 Biosimilar study | Biosimilar CT (Healthy) | Compound F | Phase 3 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-04-01 | 2031-05-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-007 | BLK-007 Biosimilar study | Biosimilar CT (Patient) | Compound G | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-03-01 | 2030-12-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-008 | BLK-008 Others study | Others |  |  | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2031-10-01 | 2033-02-28 |  | On hold | automatic | Portfolio project - not a scenario.
BLK-009 | BLK-009 NewDrug study | NewDrug CT | Compound I | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2028-11-01 | 2030-09-30 |  | Active | automatic | Portfolio project - not a scenario.
BLK-010 | BLK-010 Biosimilar study | Biosimilar CT (Healthy) | Compound J | Phase 3 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2028-10-01 | 2030-10-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-011 | BLK-011 Biosimilar study | Biosimilar CT (Patient) | Compound K | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-09-01 | 2031-09-30 |  | Completed | automatic | Portfolio project - not a scenario.
BLK-012 | BLK-012 Others study | Others |  |  | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-04-01 | 2026-06-30 |  | Active | automatic | Portfolio project - not a scenario.
BLK-013 | BLK-013 NewDrug study | NewDrug CT | Compound M | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2030-11-01 | 2033-02-28 |  | Active | automatic | Portfolio project - not a scenario.
BLK-014 | BLK-014 Biosimilar study | Biosimilar CT (Healthy) | Compound N | Phase 3 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-07-01 | 2027-04-30 |  | Active | automatic | Portfolio project - not a scenario.
BLK-015 | BLK-015 Biosimilar study | Biosimilar CT (Patient) | Compound O | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2031-04-01 | 2033-06-30 |  | Active | automatic | Portfolio project - not a scenario.
BLK-016 | BLK-016 Others study | Others |  |  | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2027-11-01 | 2028-10-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-017 | BLK-017 NewDrug study | NewDrug CT | Compound Q | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2028-11-01 | 2031-03-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-018 | BLK-018 Biosimilar study | Biosimilar CT (Healthy) | Compound R | Phase 3 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2028-09-01 | 2030-05-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-019 | BLK-019 Biosimilar study | Biosimilar CT (Patient) | Compound S | Phase 1 | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-07-01 | 2027-03-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-020 | BLK-020 Others study | Others |  |  | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2030-06-01 | 2031-07-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-021 | BLK-021 NewDrug study | NewDrug CT | Compound U | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-10-01 | 2031-12-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-022 | BLK-022 Biosimilar study | Biosimilar CT (Healthy) | Compound V | Phase 3 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2030-12-01 | 2032-10-31 |  | On hold | automatic | Portfolio project - not a scenario.
BLK-023 | BLK-023 Biosimilar study | Biosimilar CT (Patient) | Compound W | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2032-10-01 | 2034-10-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-024 | BLK-024 Others study | Others |  |  | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2030-08-01 | 2031-10-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-025 | BLK-025 NewDrug study | NewDrug CT | Compound Y | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2027-10-01 | 2029-10-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-026 | BLK-026 Biosimilar study | Biosimilar CT (Healthy) | Compound Z | Phase 3 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-12-01 | 2032-02-29 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-027 | BLK-027 Biosimilar study | Biosimilar CT (Patient) | Compound A | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-04-01 | 2026-12-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-028 | BLK-028 Others study | Others |  |  | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2031-10-01 | 2032-10-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-029 | BLK-029 NewDrug study | NewDrug CT | Compound C | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-04-01 | 2027-06-30 |  | Completed | automatic | Portfolio project - not a scenario.
BLK-030 | BLK-030 Biosimilar study | Biosimilar CT (Healthy) | Compound D | Phase 3 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-03-01 | 2027-02-28 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-031 | BLK-031 Biosimilar study | Biosimilar CT (Patient) | Compound E | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2027-07-01 | 2029-06-30 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-032 | BLK-032 Others study | Others |  |  | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2032-01-01 | 2033-01-31 |  | Planned | automatic | Portfolio project - not a scenario.
BLK-033 | BLK-033 NewDrug study | NewDrug CT | Compound G | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2030-07-01 | 2032-02-29 |  | On hold | automatic | Portfolio project - not a scenario.
BLK-034 | BLK-034 Biosimilar study | Biosimilar CT (Healthy) | Compound H | Phase 3 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-05-01 | 2027-03-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-035 | BLK-035 Biosimilar study | Biosimilar CT (Patient) | Compound I | Phase 1 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2029-07-01 | 2031-02-28 |  | Active | automatic | Portfolio project - not a scenario.
BLK-036 | BLK-036 Others study | Others |  |  | fully in-housed |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2027-03-01 | 2028-05-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-037 | BLK-037 NewDrug study | NewDrug CT | Compound K | Phase 1 | fully outsourced |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2030-09-01 | 2032-05-31 |  | Active | automatic | Portfolio project - not a scenario.
BLK-038 | BLK-038 Biosimilar study | Biosimilar CT (Healthy) | Compound L | Phase 3 | Partially outsourced (in-house for EDC) |  | by SB | by SB | by SB | by SB | Veeva EDC | Veeva DQS | CluePoints |  | 2025-04-01 | 2026-12-31 |  | Active | automatic | Portfolio project - not a scenario.
Note on R1: total_period_months is DERIVED. DERIVED - formula, do not type. The cell is locked so it cannot be typed over by accident. Nothing is hidden: Review > Unprotect Sheet turns it off, there is no password. But a value typed here is not recalculated, and the application recomputes this column on import anyway - so a hand-typed one is silently discarded, and any disagreement is reported as V-13.

## Milestone
project_id | project_name | milestone_name | milestone_date | milestone_seq | note_1
SCN-001 |  | Protocol (v1) | 2026-01-01 | 1
SCN-001 |  | CTA submission | 2026-02-01 | 2
SCN-001 |  | First SIV | 2026-06-01 | 3
SCN-001 |  | FPI | 2026-07-01 | 4
SCN-001 |  | LPI | 2026-12-01 | 5
SCN-001 |  | interim DB lock cut-off | 2026-12-01 | 6
SCN-001 |  | interim DB lock | 2027-01-01 | 7
SCN-001 |  | final DB lock cut-off | 2027-08-01 | 8
SCN-001 |  | final DB lock | 2027-09-01 | 9
SCN-001 |  | Inspection | 2027-11-01 | 10
SCN-005 |  | Protocol (v1) | 2026-01-01 | 1
SCN-005 |  | CTA submission | 2026-02-01 | 2
SCN-005 |  | First SIV | 2026-06-01 | 3
SCN-005 |  | FPI | 2026-07-01 | 4
SCN-005 |  | Inspection | 2026-09-01 | 5
SCN-005 |  | LPI | 2026-12-01 | 6
SCN-005 |  | interim DB lock cut-off | 2026-12-01 | 7
SCN-005 |  | interim DB lock | 2027-01-01 | 8
SCN-005 |  | final DB lock cut-off | 2027-08-01 | 9
SCN-005 |  | final DB lock | 2027-09-01 | 10
SCN-009 |  | Protocol (v1) | 2026-01-01 | 1
SCN-009 |  | CTA submission | 2026-02-01 | 2
SCN-009 |  | First SIV | 2026-06-01 | 3
SCN-009 |  | FPI | 2026-07-01 | 4
SCN-009 |  | FPI | 2026-08-01 | 5 | DELIBERATE: a second FPI, which V-20 reports
SCN-009 |  | LPI | 2026-12-01 | 6
SCN-009 |  | interim DB lock cut-off | 2026-12-01 | 7
SCN-009 |  | interim DB lock | 2027-01-01 | 8
SCN-009 |  | final DB lock cut-off | 2027-08-01 | 9
SCN-009 |  | final DB lock | 2027-09-01 | 10
SCN-009 |  | Inspection | 2027-11-01 | 11
SCN-011 | SCN-011 under its OLD name | Protocol (v1) | 2026-01-01 | 1 | DELIBERATE: a stale project_name, which V-13 reports before the master value is used.
SCN-011 |  | CTA submission | 2026-02-01 | 2
SCN-011 |  | First SIV | 2026-06-01 | 3
SCN-011 |  | FPI | 2026-07-01 | 4
SCN-011 |  | LPI | 2026-12-01 | 5
SCN-011 |  | interim DB lock cut-off | 2026-12-01 | 6
SCN-011 |  | interim DB lock | 2027-01-01 | 7
SCN-011 |  | final DB lock cut-off | 2027-08-01 | 8
SCN-011 |  | final DB lock | 2027-09-01 | 9
SCN-011 |  | Inspection | 2027-11-01 | 10
BLK-001 |  | Protocol (v1) | 2026-09-01 | 1
BLK-001 |  | CTA submission | 2026-10-01 | 2
BLK-001 |  | First SIV | 2027-02-01 | 3
BLK-001 |  | FPI | 2027-03-01 | 4
BLK-001 |  | LPI | 2027-08-01 | 5
BLK-001 |  | interim DB lock cut-off | 2027-08-01 | 6
BLK-001 |  | interim DB lock | 2027-09-01 | 7
BLK-001 |  | final DB lock cut-off | 2028-04-01 | 8
BLK-001 |  | final DB lock | 2028-05-01 | 9
BLK-001 |  | Inspection | 2028-07-01 | 10
BLK-007 |  | Protocol (v1) | 2029-03-01 | 1
BLK-007 |  | CTA submission | 2029-04-01 | 2
BLK-007 |  | First SIV | 2029-08-01 | 3
BLK-007 |  | FPI | 2029-09-01 | 4
BLK-007 |  | LPI | 2030-02-01 | 5
BLK-007 |  | interim DB lock cut-off | 2030-02-01 | 6
BLK-007 |  | interim DB lock | 2030-03-01 | 7
BLK-007 |  | final DB lock cut-off | 2030-10-01 | 8
BLK-007 |  | final DB lock | 2030-11-01 | 9
BLK-007 |  | Inspection | 2031-01-01 | 10
BLK-010 |  | Protocol (v1) | 2028-10-01 | 1
BLK-010 |  | CTA submission | 2028-11-01 | 2
BLK-010 |  | First SIV | 2029-03-01 | 3
BLK-010 |  | FPI | 2029-04-01 | 4
BLK-010 |  | LPI | 2029-09-01 | 5
BLK-010 |  | interim DB lock cut-off | 2029-09-01 | 6
BLK-010 |  | interim DB lock | 2029-10-01 | 7
BLK-010 |  | final DB lock cut-off | 2030-05-01 | 8
BLK-010 |  | final DB lock | 2030-06-01 | 9
BLK-010 |  | Inspection | 2030-08-01 | 10
BLK-013 |  | Protocol (v1) | 2030-11-01 | 1
BLK-013 |  | CTA submission | 2030-12-01 | 2
BLK-013 |  | First SIV | 2031-04-01 | 3
BLK-013 |  | FPI | 2031-05-01 | 4
BLK-013 |  | LPI | 2031-10-01 | 5
BLK-013 |  | interim DB lock cut-off | 2031-10-01 | 6
BLK-013 |  | interim DB lock | 2031-11-01 | 7
BLK-013 |  | final DB lock cut-off | 2032-06-01 | 8
BLK-013 |  | final DB lock | 2032-07-01 | 9
BLK-013 |  | Inspection | 2032-09-01 | 10
BLK-019 |  | Protocol (v1) | 2025-07-01 | 1
BLK-019 |  | CTA submission | 2025-08-01 | 2
BLK-019 |  | First SIV | 2025-12-01 | 3
BLK-019 |  | FPI | 2026-01-01 | 4
BLK-019 |  | LPI | 2026-06-01 | 5
BLK-019 |  | interim DB lock cut-off | 2026-06-01 | 6
BLK-019 |  | interim DB lock | 2026-07-01 | 7
BLK-019 |  | final DB lock cut-off | 2027-02-01 | 8
BLK-019 |  | final DB lock | 2027-03-01 | 9
BLK-019 |  | Inspection | 2027-05-01 | 10
BLK-022 |  | Protocol (v1) | 2030-12-01 | 1
BLK-022 |  | CTA submission | 2031-01-01 | 2
BLK-022 |  | First SIV | 2031-05-01 | 3
BLK-022 |  | FPI | 2031-06-01 | 4
BLK-022 |  | LPI | 2031-11-01 | 5
BLK-022 |  | interim DB lock cut-off | 2031-11-01 | 6
BLK-022 |  | interim DB lock | 2031-12-01 | 7
BLK-022 |  | final DB lock cut-off | 2032-07-01 | 8
BLK-022 |  | final DB lock | 2032-08-01 | 9
BLK-022 |  | Inspection | 2032-10-01 | 10
BLK-025 |  | Protocol (v1) | 2027-10-01 | 1
BLK-025 |  | CTA submission | 2027-11-01 | 2
BLK-025 |  | First SIV | 2028-03-01 | 3
BLK-025 |  | FPI | 2028-04-01 | 4
BLK-025 |  | LPI | 2028-09-01 | 5
BLK-025 |  | interim DB lock cut-off | 2028-09-01 | 6
BLK-025 |  | interim DB lock | 2028-10-01 | 7
BLK-025 |  | final DB lock cut-off | 2029-05-01 | 8
BLK-025 |  | final DB lock | 2029-06-01 | 9
BLK-025 |  | Inspection | 2029-08-01 | 10
BLK-031 |  | Protocol (v1) | 2027-07-01 | 1
BLK-031 |  | CTA submission | 2027-08-01 | 2
BLK-031 |  | First SIV | 2027-12-01 | 3
BLK-031 |  | FPI | 2028-01-01 | 4
BLK-031 |  | LPI | 2028-06-01 | 5
BLK-031 |  | interim DB lock cut-off | 2028-06-01 | 6
BLK-031 |  | interim DB lock | 2028-07-01 | 7
BLK-031 |  | final DB lock cut-off | 2029-02-01 | 8
BLK-031 |  | final DB lock | 2029-03-01 | 9
BLK-031 |  | Inspection | 2029-05-01 | 10
BLK-034 |  | Protocol (v1) | 2025-05-01 | 1
BLK-034 |  | CTA submission | 2025-06-01 | 2
BLK-034 |  | First SIV | 2025-10-01 | 3
BLK-034 |  | FPI | 2025-11-01 | 4
BLK-034 |  | LPI | 2026-04-01 | 5
BLK-034 |  | interim DB lock cut-off | 2026-04-01 | 6
BLK-034 |  | interim DB lock | 2026-05-01 | 7
BLK-034 |  | final DB lock cut-off | 2026-12-01 | 8
BLK-034 |  | final DB lock | 2027-01-01 | 9
BLK-034 |  | Inspection | 2027-03-01 | 10
BLK-037 |  | Protocol (v1) | 2030-09-01 | 1
BLK-037 |  | CTA submission | 2030-10-01 | 2
BLK-037 |  | First SIV | 2031-02-01 | 3
BLK-037 |  | FPI | 2031-03-01 | 4
BLK-037 |  | LPI | 2031-08-01 | 5
BLK-037 |  | interim DB lock cut-off | 2031-08-01 | 6
BLK-037 |  | interim DB lock | 2031-09-01 | 7
BLK-037 |  | final DB lock cut-off | 2032-04-01 | 8
BLK-037 |  | final DB lock | 2032-05-01 | 9
BLK-037 |  | Inspection | 2032-07-01 | 10
Note on B1: project_name is DERIVED. DERIVED - looked up from Project, do not type. The cell is locked so it cannot be typed over by accident. Nothing is hidden: Review > Unprotect Sheet turns it off, there is no password. But a value typed here is not recalculated, and the application recomputes this column on import anyway - so a hand-typed one is silently discarded, and any disagreement is reported as V-13.

## ProjectPeriod
project_id | period_name | period_seq | period_start | period_end | weight | note_1
SCN-001 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-001 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-001 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-001 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-001 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-001 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-001 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-002 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-002 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-002 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-002 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-002 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-002 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-002 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-003 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-003 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-003 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-003 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-003 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-003 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-003 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-004 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-004 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-004 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-004 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-004 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-004 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-004 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-005 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-005 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-005 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-005 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-005 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-005 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-005 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-006 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-006 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-006 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-006 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-006 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-006 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-006 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-007 | Planning | 1 | 2026-01-01 | 2026-03-31 | 1
SCN-007 | Develop | 2 | 2026-04-01 | 2026-11-30 | 1
SCN-007 | Close | 3 | 2026-12-01 | 2027-01-31 | 1
SCN-008 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-008 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-008 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-008 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-008 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-008 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-008 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-009 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-009 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-009 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-009 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-009 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-009 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-009 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-010 | Planning | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-010 | Develop | 2 | 2026-03-01 | 2026-08-31 | 1
SCN-010 | Close | 3 | 2026-09-01 | 2026-10-31 | 1
SCN-011 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-011 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-011 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-011 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-011 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-011 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-011 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
SCN-012 | Before-Start-up | 1 | 2026-01-01 | 2026-02-28 | 1
SCN-012 | Start-up | 2 | 2026-03-01 | 2026-06-30 | 1
SCN-012 | Conduct (interim) | 3 | 2026-07-01 | 2026-12-31 | 1
SCN-012 | Close-out (interim) | 4 | 2027-01-01 | 2027-02-28 | 1
SCN-012 | Conduct (final) | 5 | 2027-03-01 | 2027-08-31 | 1
SCN-012 | Close-out (final) | 6 | 2027-09-01 | 2027-11-30 | 1
SCN-012 | After Close-out (final) | 7 | 2027-12-01 | 2027-12-31 | 1
BLK-001 | Before-Start-up | 1 | 2026-09-01 | 2026-11-30 | 1.06
BLK-001 | Start-up | 2 | 2026-12-01 | 2027-03-31 | 1.21
BLK-001 | Conduct (interim) | 3 | 2027-04-01 | 2027-12-31 | 0.85
BLK-001 | Close-out (interim) | 4 | 2028-01-01 | 2028-01-31 | 0.96
BLK-001 | Conduct (final) | 5 | 2028-02-01 | 2028-05-31 | 0.82
BLK-001 | Close-out (final) | 6 | 2028-06-01 | 2028-07-31 | 1.28
BLK-001 | After Close-out (final) | 7 | 2028-08-01 | 2028-08-31 | 1.17
BLK-002 | Before-Start-up | 1 | 2032-04-01 | 2032-05-31 | 1.17
BLK-002 | Start-up | 2 | 2032-06-01 | 2032-10-31 | 0.92
BLK-002 | Conduct (interim) | 3 | 2032-11-01 | 2033-03-31 | 1.26
BLK-002 | Close-out (interim) | 4 | 2033-04-01 | 2033-04-30 | 0.84
BLK-002 | Conduct (final) | 5 | 2033-05-01 | 2033-10-31 | 1.14
BLK-002 | Close-out (final) | 6 | 2033-11-01 | 2033-12-31 | 1.25
BLK-003 | Before-Start-up | 1 | 2027-05-01 | 2027-07-31 | 0.96
BLK-003 | Start-up | 2 | 2027-08-01 | 2027-10-31 | 1.02
BLK-003 | Conduct (interim) | 3 | 2027-11-01 | 2028-02-29 | 1.21
BLK-003 | Close-out (interim) | 4 | 2028-03-01 | 2028-03-31 | 1.26
BLK-003 | Conduct (final) | 5 | 2028-04-01 | 2028-10-31 | 0.83
BLK-003 | Close-out (final) | 6 | 2028-11-01 | 2029-02-28 | 0.97
BLK-004 | Planning | 1 | 2029-10-01 | 2029-11-30 | 0.87
BLK-004 | Develop | 2 | 2029-12-01 | 2030-06-30 | 0.91
BLK-004 | Close | 3 | 2030-07-01 | 2030-08-31 | 0.94
BLK-005 | Before-Start-up | 1 | 2029-01-01 | 2029-03-31 | 1.1
BLK-005 | Start-up | 2 | 2029-04-01 | 2029-08-31 | 0.99
BLK-005 | Conduct (interim) | 3 | 2029-09-01 | 2029-12-31 | 1.03
BLK-005 | Close-out (interim) | 4 | 2030-01-01 | 2030-02-28 | 1.3
BLK-005 | Conduct (final) | 5 | 2030-03-01 | 2030-10-31 | 0.97
BLK-005 | Close-out (final) | 6 | 2030-11-01 | 2031-02-28 | 0.86
BLK-005 | After Close-out (final) | 7 | 2031-03-01 | 2031-03-31 | 0.91
BLK-006 | Before-Start-up | 1 | 2029-04-01 | 2029-06-30 | 1.23
BLK-006 | Start-up | 2 | 2029-07-01 | 2029-09-30 | 1.14
BLK-006 | Conduct (interim) | 3 | 2029-10-01 | 2030-03-31 | 0.99
BLK-006 | Close-out (interim) | 4 | 2030-04-01 | 2030-05-31 | 1.28
BLK-006 | Conduct (final) | 5 | 2030-06-01 | 2031-03-31 | 0.97
BLK-006 | Close-out (final) | 6 | 2031-04-01 | 2031-05-31 | 0.84
BLK-007 | Before-Start-up | 1 | 2029-03-01 | 2029-04-30 | 0.86
BLK-007 | Start-up | 2 | 2029-05-01 | 2029-08-31 | 0.94
BLK-007 | Conduct (interim) | 3 | 2029-09-01 | 2030-01-31 | 1.16
BLK-007 | Close-out (interim) | 4 | 2030-02-01 | 2030-03-31 | 1.21
BLK-007 | Conduct (final) | 5 | 2030-04-01 | 2030-08-31 | 0.88
BLK-007 | Close-out (final) | 6 | 2030-09-01 | 2030-12-31 | 0.96
BLK-008 | Planning | 1 | 2031-10-01 | 2032-01-31 | 1.17
BLK-008 | Develop | 2 | 2032-02-01 | 2032-11-30 | 1.25
BLK-008 | Close | 3 | 2032-12-01 | 2033-02-28 | 0.87
BLK-009 | Before-Start-up | 1 | 2028-11-01 | 2028-11-30 | 0.99
BLK-009 | Start-up | 2 | 2028-12-01 | 2029-04-30 | 1.28
BLK-009 | Conduct (interim) | 3 | 2029-05-01 | 2029-08-31 | 0.93
BLK-009 | Close-out (interim) | 4 | 2029-09-01 | 2029-09-30 | 0.87
BLK-009 | Conduct (final) | 5 | 2029-10-01 | 2030-06-30 | 0.96
BLK-009 | Close-out (final) | 6 | 2030-07-01 | 2030-08-31 | 0.95
BLK-009 | After Close-out (final) | 7 | 2030-09-01 | 2030-09-30 | 1.05
BLK-010 | Before-Start-up | 1 | 2028-10-01 | 2028-12-31 | 1.12
BLK-010 | Start-up | 2 | 2029-01-01 | 2029-04-30 | 1.03
BLK-010 | Conduct (interim) | 3 | 2029-05-01 | 2029-12-31 | 0.93
BLK-010 | Close-out (interim) | 4 | 2030-01-01 | 2030-03-31 | 1.15
BLK-010 | Conduct (final) | 5 | 2030-04-01 | 2030-08-31 | 0.88
BLK-010 | Close-out (final) | 6 | 2030-09-01 | 2030-10-31 | 1.25
BLK-011 | Before-Start-up | 1 | 2029-09-01 | 2029-10-31 | 0.82
BLK-011 | Start-up | 2 | 2029-11-01 | 2030-03-31 | 1.19
BLK-011 | Conduct (interim) | 3 | 2030-04-01 | 2030-07-31 | 1.16
BLK-011 | Close-out (interim) | 4 | 2030-08-01 | 2030-08-31 | 0.84
BLK-011 | Conduct (final) | 5 | 2030-09-01 | 2031-06-30 | 1.12
BLK-011 | Close-out (final) | 6 | 2031-07-01 | 2031-09-30 | 0.9
BLK-012 | Planning | 1 | 2025-04-01 | 2025-05-31 | 0.82
BLK-012 | Develop | 2 | 2025-06-01 | 2026-03-31 | 1.27
BLK-012 | Close | 3 | 2026-04-01 | 2026-06-30 | 1.03
BLK-013 | Before-Start-up | 1 | 2030-11-01 | 2030-11-30 | 0.88
BLK-013 | Start-up | 2 | 2030-12-01 | 2031-03-31 | 1.29
BLK-013 | Conduct (interim) | 3 | 2031-04-01 | 2031-10-31 | 1.22
BLK-013 | Close-out (interim) | 4 | 2031-11-01 | 2031-11-30 | 0.83
BLK-013 | Conduct (final) | 5 | 2031-12-01 | 2032-09-30 | 0.92
BLK-013 | Close-out (final) | 6 | 2032-10-01 | 2033-01-31 | 0.89
BLK-013 | After Close-out (final) | 7 | 2033-02-01 | 2033-02-28 | 1.04
BLK-014 | Before-Start-up | 1 | 2025-07-01 | 2025-08-31 | 1.29
BLK-014 | Start-up | 2 | 2025-09-01 | 2025-11-30 | 1.29
BLK-014 | Conduct (interim) | 3 | 2025-12-01 | 2026-08-31 | 0.8
BLK-014 | Close-out (interim) | 4 | 2026-09-01 | 2026-10-31 | 1.1
BLK-014 | Conduct (final) | 5 | 2026-11-01 | 2027-02-28 | 1.27
BLK-014 | Close-out (final) | 6 | 2027-03-01 | 2027-04-30 | 0.88
BLK-015 | Before-Start-up | 1 | 2031-04-01 | 2031-04-30 | 1.26
BLK-015 | Start-up | 2 | 2031-05-01 | 2031-07-31 | 0.84
BLK-015 | Conduct (interim) | 3 | 2031-08-01 | 2032-04-30 | 1.16
BLK-015 | Close-out (interim) | 4 | 2032-05-01 | 2032-06-30 | 1.28
BLK-015 | Conduct (final) | 5 | 2032-07-01 | 2033-04-30 | 0.95
BLK-015 | Close-out (final) | 6 | 2033-05-01 | 2033-06-30 | 1.19
BLK-016 | Planning | 1 | 2027-11-01 | 2028-01-31 | 1.28
BLK-016 | Develop | 2 | 2028-02-01 | 2028-08-31 | 1.08
BLK-016 | Close | 3 | 2028-09-01 | 2028-10-31 | 1.24
BLK-017 | Before-Start-up | 1 | 2028-11-01 | 2029-01-31 | 0.92
BLK-017 | Start-up | 2 | 2029-02-01 | 2029-06-30 | 1.07
BLK-017 | Conduct (interim) | 3 | 2029-07-01 | 2030-03-31 | 1.27
BLK-017 | Close-out (interim) | 4 | 2030-04-01 | 2030-04-30 | 0.87
BLK-017 | Conduct (final) | 5 | 2030-05-01 | 2030-09-30 | 0.81
BLK-017 | Close-out (final) | 6 | 2030-10-01 | 2031-01-31 | 1.09
BLK-017 | After Close-out (final) | 7 | 2031-02-01 | 2031-03-31 | 1.19
BLK-018 | Before-Start-up | 1 | 2028-09-01 | 2028-09-30 | 1.29
BLK-018 | Start-up | 2 | 2028-10-01 | 2029-02-28 | 0.97
BLK-018 | Conduct (interim) | 3 | 2029-03-01 | 2029-07-31 | 1
BLK-018 | Close-out (interim) | 4 | 2029-08-01 | 2029-08-31 | 1
BLK-018 | Conduct (final) | 5 | 2029-09-01 | 2030-03-31 | 0.85
BLK-018 | Close-out (final) | 6 | 2030-04-01 | 2030-05-31 | 1.09
BLK-019 | Before-Start-up | 1 | 2025-07-01 | 2025-07-31 | 1.11
BLK-019 | Start-up | 2 | 2025-08-01 | 2025-11-30 | 0.89
BLK-019 | Conduct (interim) | 3 | 2025-12-01 | 2026-06-30 | 1.09
BLK-019 | Close-out (interim) | 4 | 2026-07-01 | 2026-08-31 | 1.21
BLK-019 | Conduct (final) | 5 | 2026-09-01 | 2027-01-31 | 1.17
BLK-019 | Close-out (final) | 6 | 2027-02-01 | 2027-03-31 | 1.12
BLK-020 | Planning | 1 | 2030-06-01 | 2030-07-31 | 1.26
BLK-020 | Develop | 2 | 2030-08-01 | 2031-05-31 | 0.85
BLK-020 | Close | 3 | 2031-06-01 | 2031-07-31 | 0.86
BLK-021 | Before-Start-up | 1 | 2029-10-01 | 2029-12-31 | 0.99
BLK-021 | Start-up | 2 | 2030-01-01 | 2030-04-30 | 0.89
BLK-021 | Conduct (interim) | 3 | 2030-05-01 | 2030-10-31 | 1.09
BLK-021 | Close-out (interim) | 4 | 2030-11-01 | 2030-12-31 | 1.03
BLK-021 | Conduct (final) | 5 | 2031-01-01 | 2031-06-30 | 0.8
BLK-021 | Close-out (final) | 6 | 2031-07-01 | 2031-10-31 | 0.93
BLK-021 | After Close-out (final) | 7 | 2031-11-01 | 2031-12-31 | 1.22
BLK-022 | Before-Start-up | 1 | 2030-12-01 | 2031-01-31 | 1.06
BLK-022 | Start-up | 2 | 2031-02-01 | 2031-06-30 | 1.19
BLK-022 | Conduct (interim) | 3 | 2031-07-01 | 2031-10-31 | 1.18
BLK-022 | Close-out (interim) | 4 | 2031-11-01 | 2031-11-30 | 1.25
BLK-022 | Conduct (final) | 5 | 2031-12-01 | 2032-08-31 | 1.1
BLK-022 | Close-out (final) | 6 | 2032-09-01 | 2032-10-31 | 1.05
BLK-023 | Before-Start-up | 1 | 2032-10-01 | 2032-11-30 | 1.13
BLK-023 | Start-up | 2 | 2032-12-01 | 2033-03-31 | 1.12
BLK-023 | Conduct (interim) | 3 | 2033-04-01 | 2033-12-31 | 1.24
BLK-023 | Close-out (interim) | 4 | 2034-01-01 | 2034-01-31 | 1.01
BLK-023 | Conduct (final) | 5 | 2034-02-01 | 2034-07-31 | 0.94
BLK-023 | Close-out (final) | 6 | 2034-08-01 | 2034-10-31 | 1.16
BLK-024 | Planning | 1 | 2030-08-01 | 2030-10-31 | 0.95
BLK-024 | Develop | 2 | 2030-11-01 | 2031-08-31 | 1.18
BLK-024 | Close | 3 | 2031-09-01 | 2031-10-31 | 0.98
BLK-025 | Before-Start-up | 1 | 2027-10-01 | 2027-10-31 | 1
BLK-025 | Start-up | 2 | 2027-11-01 | 2028-01-31 | 1.12
BLK-025 | Conduct (interim) | 3 | 2028-02-01 | 2028-05-31 | 0.82
BLK-025 | Close-out (interim) | 4 | 2028-06-01 | 2028-08-31 | 0.86
BLK-025 | Conduct (final) | 5 | 2028-09-01 | 2029-04-30 | 1.28
BLK-025 | Close-out (final) | 6 | 2029-05-01 | 2029-08-31 | 1
BLK-025 | After Close-out (final) | 7 | 2029-09-01 | 2029-10-31 | 1.28
BLK-026 | Before-Start-up | 1 | 2029-12-01 | 2030-02-28 | 0.98
BLK-026 | Start-up | 2 | 2030-03-01 | 2030-07-31 | 1.14
BLK-026 | Conduct (interim) | 3 | 2030-08-01 | 2031-01-31 | 1.23
BLK-026 | Close-out (interim) | 4 | 2031-02-01 | 2031-02-28 | 0.95
BLK-026 | Conduct (final) | 5 | 2031-03-01 | 2031-11-30 | 1.2
BLK-026 | Close-out (final) | 6 | 2031-12-01 | 2032-02-29 | 1.26
BLK-027 | Before-Start-up | 1 | 2025-04-01 | 2025-06-30 | 1.08
BLK-027 | Start-up | 2 | 2025-07-01 | 2025-09-30 | 0.96
BLK-027 | Conduct (interim) | 3 | 2025-10-01 | 2026-04-30 | 0.88
BLK-027 | Close-out (interim) | 4 | 2026-05-01 | 2026-06-30 | 0.83
BLK-027 | Conduct (final) | 5 | 2026-07-01 | 2026-10-31 | 0.93
BLK-027 | Close-out (final) | 6 | 2026-11-01 | 2026-12-31 | 1.03
BLK-028 | Planning | 1 | 2031-10-01 | 2031-11-30 | 1.29
BLK-028 | Develop | 2 | 2031-12-01 | 2032-09-30 | 0.98
BLK-028 | Close | 3 | 2032-10-01 | 2032-10-31 | 1.23
BLK-029 | Before-Start-up | 1 | 2025-04-01 | 2025-06-30 | 1.12
BLK-029 | Start-up | 2 | 2025-07-01 | 2025-09-30 | 1.24
BLK-029 | Conduct (interim) | 3 | 2025-10-01 | 2026-02-28 | 0.9
BLK-029 | Close-out (interim) | 4 | 2026-03-01 | 2026-05-31 | 0.99
BLK-029 | Conduct (final) | 5 | 2026-06-01 | 2027-01-31 | 1.04
BLK-029 | Close-out (final) | 6 | 2027-02-01 | 2027-04-30 | 1.12
BLK-029 | After Close-out (final) | 7 | 2027-05-01 | 2027-06-30 | 1.08
BLK-030 | Before-Start-up | 1 | 2025-03-01 | 2025-04-30 | 1.14
BLK-030 | Start-up | 2 | 2025-05-01 | 2025-07-31 | 0.82
BLK-030 | Conduct (interim) | 3 | 2025-08-01 | 2025-11-30 | 1.17
BLK-030 | Close-out (interim) | 4 | 2025-12-01 | 2026-01-31 | 0.9
BLK-030 | Conduct (final) | 5 | 2026-02-01 | 2026-10-31 | 1.09
BLK-030 | Close-out (final) | 6 | 2026-11-01 | 2027-02-28 | 1.25
BLK-031 | Before-Start-up | 1 | 2027-07-01 | 2027-07-31 | 1.02
BLK-031 | Start-up | 2 | 2027-08-01 | 2027-12-31 | 1.03
BLK-031 | Conduct (interim) | 3 | 2028-01-01 | 2028-05-31 | 1.04
BLK-031 | Close-out (interim) | 4 | 2028-06-01 | 2028-06-30 | 0.94
BLK-031 | Conduct (final) | 5 | 2028-07-01 | 2029-03-31 | 0.93
BLK-031 | Close-out (final) | 6 | 2029-04-01 | 2029-06-30 | 1.19
BLK-032 | Planning | 1 | 2032-01-01 | 2032-03-31 | 1.25
BLK-032 | Develop | 2 | 2032-04-01 | 2032-11-30 | 1.04
BLK-032 | Close | 3 | 2032-12-01 | 2033-01-31 | 1
BLK-033 | Before-Start-up | 1 | 2030-07-01 | 2030-08-31 | 0.85
BLK-033 | Start-up | 2 | 2030-09-01 | 2030-11-30 | 1.19
BLK-033 | Conduct (interim) | 3 | 2030-12-01 | 2031-03-31 | 1.24
BLK-033 | Close-out (interim) | 4 | 2031-04-01 | 2031-04-30 | 1.28
BLK-033 | Conduct (final) | 5 | 2031-05-01 | 2031-11-30 | 1.18
BLK-033 | Close-out (final) | 6 | 2031-12-01 | 2032-01-31 | 0.96
BLK-033 | After Close-out (final) | 7 | 2032-02-01 | 2032-02-29 | 0.85
BLK-034 | Before-Start-up | 1 | 2025-05-01 | 2025-05-31 | 0.95
BLK-034 | Start-up | 2 | 2025-06-01 | 2025-10-31 | 1.05
BLK-034 | Conduct (interim) | 3 | 2025-11-01 | 2026-02-28 | 1.11
BLK-034 | Close-out (interim) | 4 | 2026-03-01 | 2026-04-30 | 1.22
BLK-034 | Conduct (final) | 5 | 2026-05-01 | 2026-12-31 | 1.2
BLK-034 | Close-out (final) | 6 | 2027-01-01 | 2027-03-31 | 1.24
BLK-035 | Before-Start-up | 1 | 2029-07-01 | 2029-09-30 | 1.29
BLK-035 | Start-up | 2 | 2029-10-01 | 2029-12-31 | 0.94
BLK-035 | Conduct (interim) | 3 | 2030-01-01 | 2030-04-30 | 1.07
BLK-035 | Close-out (interim) | 4 | 2030-05-01 | 2030-06-30 | 1.04
BLK-035 | Conduct (final) | 5 | 2030-07-01 | 2030-10-31 | 1.25
BLK-035 | Close-out (final) | 6 | 2030-11-01 | 2031-02-28 | 0.92
BLK-036 | Planning | 1 | 2027-03-01 | 2027-04-30 | 0.83
BLK-036 | Develop | 2 | 2027-05-01 | 2028-02-29 | 1.04
BLK-036 | Close | 3 | 2028-03-01 | 2028-05-31 | 0.98
BLK-037 | Before-Start-up | 1 | 2030-09-01 | 2030-10-31 | 0.99
BLK-037 | Start-up | 2 | 2030-11-01 | 2031-01-31 | 1.23
BLK-037 | Conduct (interim) | 3 | 2031-02-01 | 2031-05-31 | 1.21
BLK-037 | Close-out (interim) | 4 | 2031-06-01 | 2031-06-30 | 0.9
BLK-037 | Conduct (final) | 5 | 2031-07-01 | 2031-12-31 | 0.8
BLK-037 | Close-out (final) | 6 | 2032-01-01 | 2032-03-31 | 1.26
BLK-037 | After Close-out (final) | 7 | 2032-04-01 | 2032-05-31 | 1.26
BLK-038 | Before-Start-up | 1 | 2025-04-01 | 2025-04-30 | 1.27
BLK-038 | Start-up | 2 | 2025-05-01 | 2025-09-30 | 0.9
BLK-038 | Conduct (interim) | 3 | 2025-10-01 | 2026-01-31 | 0.98
BLK-038 | Close-out (interim) | 4 | 2026-02-01 | 2026-02-28 | 0.99
BLK-038 | Conduct (final) | 5 | 2026-03-01 | 2026-08-31 | 1.3
BLK-038 | Close-out (final) | 6 | 2026-09-01 | 2026-12-31 | 1.2

## PeriodFTEStandard
project_type | clinical_phase | work_scope_type | period_name | standard_fte | note_1
NewDrug CT | Phase 1 |  | Before-Start-up | 1.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | 3.27 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | 2.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | 2.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | 3.52 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | 2.11 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | 1.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | 3.52 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | 2.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | 3.27 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | 2.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | 3.77 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | 2.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | 2.01 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | 4.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | 3.52 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | 4.27 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | 2.56 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | 1.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | 2.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | 2.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | 2.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | 2.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | 1.81 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | 1.28 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | 2.13 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | 2.13 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | 2.99 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | 1.79 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | 1.5 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | 2.99 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | 2.35 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | 2.35 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | 3.2 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | 1.92 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | 1.71 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | 3.42 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | 2.99 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | 3.63 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | 2.18 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | 1.07 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | 2.35 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | 1.92 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | 2.13 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | 1.92 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | 1.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | 1.39 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | 3.01 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | 2.31 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | 2.31 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | 3.24 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | 1.94 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | 1.62 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | 3.24 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | 2.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | 3.01 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | 2.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | 3.47 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | 2.08 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | 1.85 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | 3.7 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | 3.24 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | 3.93 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | 2.36 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | 1.16 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | 2.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | 2.08 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | 2.31 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | 2.08 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | 1.67 | Default assumption - replace with your own figure
Others |  |  | Planning | 1.21 | Default assumption - replace with your own figure
Others |  |  | Develop | 2.31 | Default assumption - replace with your own figure
Others |  |  | Close | 1.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 | fully in-housed | Before-Start-up | 1.74 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Start-up | 3.76 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Conduct (interim) | 2.89 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Close-out (interim) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Conduct (final) | 2.89 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Close-out (final) | 4.05 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | After Close-out (final) | 2.43 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Before-Start-up | 2.02 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Start-up | 4.05 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Conduct (interim) | 3.17 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Close-out (interim) | 3.76 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Conduct (final) | 3.17 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Close-out (final) | 4.34 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | After Close-out (final) | 2.6 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Before-Start-up | 2.31 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Start-up | 4.62 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Conduct (interim) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Close-out (interim) | 4.05 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Conduct (final) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Close-out (final) | 4.91 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | After Close-out (final) | 2.94 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Before-Start-up | 1.45 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Start-up | 3.17 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Conduct (interim) | 2.6 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Close-out (interim) | 2.89 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Conduct (final) | 2.6 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Close-out (final) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | After Close-out (final) | 2.08 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Before-Start-up | 1.47 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Start-up | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Conduct (interim) | 2.45 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Close-out (interim) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Conduct (final) | 2.45 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Close-out (final) | 3.44 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | After Close-out (final) | 2.06 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Before-Start-up | 1.72 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Start-up | 3.44 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Conduct (interim) | 2.7 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Close-out (interim) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Conduct (final) | 2.7 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Close-out (final) | 3.68 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | After Close-out (final) | 2.21 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Before-Start-up | 1.97 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Start-up | 3.93 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Conduct (interim) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Close-out (interim) | 3.44 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Conduct (final) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Close-out (final) | 4.17 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | After Close-out (final) | 2.51 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Before-Start-up | 1.23 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Start-up | 2.7 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Conduct (interim) | 2.21 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Close-out (interim) | 2.45 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Conduct (final) | 2.21 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Close-out (final) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | After Close-out (final) | 1.77 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Before-Start-up | 1.6 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Start-up | 3.46 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Conduct (interim) | 2.66 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Close-out (interim) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Conduct (final) | 2.66 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Close-out (final) | 3.73 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | After Close-out (final) | 2.23 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Before-Start-up | 1.86 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Start-up | 3.73 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Conduct (interim) | 2.92 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Close-out (interim) | 3.46 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Conduct (final) | 2.92 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Close-out (final) | 3.99 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | After Close-out (final) | 2.39 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Before-Start-up | 2.13 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Start-up | 4.25 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Conduct (interim) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Close-out (interim) | 3.73 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Conduct (final) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Close-out (final) | 4.52 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | After Close-out (final) | 2.71 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Before-Start-up | 1.33 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Start-up | 2.92 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Conduct (interim) | 2.39 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Close-out (interim) | 2.66 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Conduct (final) | 2.39 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Close-out (final) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | After Close-out (final) | 1.92 | Illustrative - fully in-housed
Others |  | fully in-housed | Planning | 1.39 | Illustrative - fully in-housed
Others |  | fully in-housed | Develop | 2.66 | Illustrative - fully in-housed
Others |  | fully in-housed | Close | 1.74 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | 1.21 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | 2.62 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | 2.01 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | 2.01 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | 2.82 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | 1.69 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | 1.41 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | 2.82 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | 2.21 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | 2.62 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | 2.21 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | 3.02 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | 1.81 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | 1.61 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | 3.22 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | 2.82 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | 3.42 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | 2.05 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | 1.01 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | 2.21 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | 1.81 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | 2.01 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | 1.81 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | 1.45 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | 1.02 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | 1.7 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | 1.7 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | 2.39 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | 1.43 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | 1.2 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | 2.39 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | 1.88 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | 1.88 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | 2.56 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | 1.54 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | 1.37 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | 2.74 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | 2.39 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | 2.9 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | 1.74 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | 0.86 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | 1.88 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | 1.54 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | 1.7 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | 1.54 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | 1.23 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | 1.11 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | 2.41 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | 1.85 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | 1.85 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | 2.59 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | 1.55 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | 1.3 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | 2.59 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | 2.03 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | 2.41 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | 2.03 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | 2.78 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | 1.66 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | 1.48 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | 2.96 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | 2.59 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | 3.14 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | 1.89 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | 0.93 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | 2.03 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | 1.66 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | 1.85 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | 1.66 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | 1.34 | Illustrative - fully outsourced
Others |  | fully outsourced | Planning | 0.97 | Illustrative - fully outsourced
Others |  | fully outsourced | Develop | 1.85 | Illustrative - fully outsourced
Others |  | fully outsourced | Close | 1.21 | Illustrative - fully outsourced

## RoleFactor
project_type | clinical_phase | work_scope_type | period_name | role_name | role_factor | absorbed_by | role_note
NewDrug CT | Phase 1 |  | Before-Start-up | Project oversight | 0.68 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Lead data manager | 0.91 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Clinical Database Programmer | 0.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Data Analyst | 0.34 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Clinical Data Associator | 0.76 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Clinical Database Programmer | 1.57 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Data Analyst | 0.51 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Lead data manager | 1.25 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Clinical Data Associator | 1.04 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Clinical Database Programmer | 1.04 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Data Analyst | 1.11 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Clinical Data Associator | 0.85 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Clinical Database Programmer | 1.15 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Data Analyst | 1.28 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Project oversight | 0.61 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Lead data manager | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Clinical Database Programmer | 0.42 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Lead data manager | 0.96 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Clinical Database Programmer | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Data Analyst | 0.36 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Clinical Data Associator | 0.8 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Clinical Database Programmer | 1.65 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Data Analyst | 0.54 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Lead data manager | 1.32 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Clinical Data Associator | 1.1 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Clinical Database Programmer | 1.1 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Data Analyst | 1.17 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Clinical Data Associator | 0.9 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Clinical Database Programmer | 1.21 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Data Analyst | 1.35 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Project oversight | 0.64 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Lead data manager | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Clinical Database Programmer | 0.44 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Lead data manager | 1.01 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Clinical Data Associator | 0.53 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Clinical Database Programmer | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Data Analyst | 0.38 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Lead data manager | 1.51 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Clinical Data Associator | 0.84 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Clinical Database Programmer | 1.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Data Analyst | 0.57 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Lead data manager | 1.26 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Clinical Data Associator | 1.37 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Clinical Database Programmer | 0.92 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Data Analyst | 0.85 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Lead data manager | 1.39 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Clinical Data Associator | 1.16 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Clinical Database Programmer | 1.16 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Data Analyst | 1.23 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Lead data manager | 1.26 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Clinical Data Associator | 1.37 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Clinical Database Programmer | 0.92 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Data Analyst | 0.85 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Lead data manager | 1.51 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Clinical Data Associator | 0.95 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Clinical Database Programmer | 1.27 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Data Analyst | 1.42 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Project oversight | 0.67 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Lead data manager | 0.88 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Clinical Data Associator | 0.53 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Clinical Database Programmer | 0.46 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Data Analyst | 0.85 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Project oversight | 0.65 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Lead data manager | 0.86 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Clinical Database Programmer | 0.69 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Data Analyst | 0.32 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Clinical Data Associator | 0.72 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Clinical Database Programmer | 1.49 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Data Analyst | 0.49 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Lead data manager | 1.19 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Clinical Data Associator | 0.99 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Clinical Database Programmer | 0.99 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Data Analyst | 1.05 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Clinical Data Associator | 0.81 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Clinical Database Programmer | 1.09 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Data Analyst | 1.22 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Project oversight | 0.58 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Lead data manager | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Clinical Database Programmer | 0.4 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Project oversight | 0.65 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Lead data manager | 0.87 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Clinical Database Programmer | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Data Analyst | 0.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Clinical Data Associator | 0.72 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Clinical Database Programmer | 1.49 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Data Analyst | 0.49 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Lead data manager | 1.19 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Clinical Data Associator | 0.99 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Clinical Database Programmer | 0.99 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Data Analyst | 1.06 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Clinical Data Associator | 0.81 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Clinical Database Programmer | 1.09 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Data Analyst | 1.22 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Project oversight | 0.58 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Lead data manager | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Clinical Database Programmer | 0.4 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Lead data manager | 0.91 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Clinical Database Programmer | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Data Analyst | 0.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Clinical Data Associator | 0.76 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Clinical Database Programmer | 1.57 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Data Analyst | 0.51 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Lead data manager | 1.25 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Clinical Data Associator | 1.04 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Clinical Database Programmer | 1.04 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Data Analyst | 1.11 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Clinical Data Associator | 0.85 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Clinical Database Programmer | 1.15 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Data Analyst | 1.28 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Project oversight | 0.61 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Lead data manager | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Clinical Database Programmer | 0.42 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Lead data manager | 0.96 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Clinical Database Programmer | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Data Analyst | 0.36 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Clinical Data Associator | 0.8 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Clinical Database Programmer | 1.65 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Data Analyst | 0.54 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Lead data manager | 1.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Clinical Data Associator | 1.1 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Clinical Database Programmer | 1.1 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Data Analyst | 1.17 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Clinical Data Associator | 0.9 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Clinical Database Programmer | 1.21 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Data Analyst | 1.35 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Project oversight | 0.64 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Lead data manager | 0.84 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Clinical Database Programmer | 0.44 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Project oversight | 0.62 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Lead data manager | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Clinical Data Associator | 0.43 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Clinical Database Programmer | 0.66 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Data Analyst | 0.31 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Clinical Data Associator | 0.68 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Clinical Database Programmer | 1.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Data Analyst | 0.46 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Lead data manager | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Clinical Data Associator | 1.11 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Clinical Database Programmer | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Data Analyst | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Lead data manager | 1.13 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Clinical Data Associator | 0.94 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Clinical Database Programmer | 0.94 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Data Analyst | 1 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Lead data manager | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Clinical Data Associator | 1.11 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Clinical Database Programmer | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Data Analyst | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Clinical Data Associator | 0.77 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Clinical Database Programmer | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Data Analyst | 1.15 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Project oversight | 0.55 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Lead data manager | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Clinical Data Associator | 0.43 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Clinical Database Programmer | 0.38 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Data Analyst | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Project oversight | 0.67 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Lead data manager | 0.89 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Clinical Database Programmer | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Data Analyst | 0.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Lead data manager | 1.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Clinical Data Associator | 0.74 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Clinical Database Programmer | 1.54 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Data Analyst | 0.5 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Lead data manager | 1.12 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Clinical Data Associator | 1.21 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Clinical Database Programmer | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Data Analyst | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Clinical Data Associator | 1.02 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Clinical Database Programmer | 1.02 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Data Analyst | 1.09 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Lead data manager | 1.12 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Clinical Data Associator | 1.21 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Clinical Database Programmer | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Data Analyst | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Lead data manager | 1.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Clinical Data Associator | 0.84 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Clinical Database Programmer | 1.13 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Data Analyst | 1.26 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Project oversight | 0.6 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Lead data manager | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Clinical Database Programmer | 0.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Data Analyst | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Lead data manager | 0.94 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Clinical Data Associator | 0.49 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Clinical Database Programmer | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Data Analyst | 0.35 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Lead data manager | 1.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Clinical Data Associator | 0.78 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Clinical Database Programmer | 1.62 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Data Analyst | 0.53 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Lead data manager | 1.18 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Clinical Data Associator | 1.27 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Clinical Database Programmer | 0.86 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Data Analyst | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Lead data manager | 1.29 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Clinical Data Associator | 1.08 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Clinical Database Programmer | 1.08 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Data Analyst | 1.15 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Lead data manager | 1.18 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Clinical Data Associator | 1.27 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Clinical Database Programmer | 0.86 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Data Analyst | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Lead data manager | 1.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Clinical Data Associator | 0.88 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Clinical Database Programmer | 1.19 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Data Analyst | 1.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Project oversight | 0.63 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Lead data manager | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Clinical Data Associator | 0.49 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Clinical Database Programmer | 0.43 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Data Analyst | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Lead data manager | 0.99 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Clinical Data Associator | 0.51 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Data Analyst | 0.37 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Lead data manager | 1.48 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Clinical Data Associator | 0.82 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Clinical Database Programmer | 1.7 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Data Analyst | 0.56 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Clinical Data Associator | 1.34 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Clinical Database Programmer | 0.91 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Data Analyst | 0.83 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Lead data manager | 1.36 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Clinical Data Associator | 1.13 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Clinical Database Programmer | 1.13 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Data Analyst | 1.2 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Clinical Data Associator | 1.34 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Clinical Database Programmer | 0.91 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Data Analyst | 0.83 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Lead data manager | 1.48 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Clinical Data Associator | 0.93 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Clinical Database Programmer | 1.25 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Data Analyst | 1.39 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Project oversight | 0.66 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Lead data manager | 0.86 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Clinical Data Associator | 0.51 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Clinical Database Programmer | 0.45 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Data Analyst | 0.83 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Project oversight | 0.64 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Lead data manager | 0.85 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Clinical Data Associator | 0.44 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Clinical Database Programmer | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Data Analyst | 0.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Lead data manager | 1.27 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Clinical Data Associator | 0.71 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Clinical Database Programmer | 1.46 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Data Analyst | 0.48 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Lead data manager | 1.06 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Clinical Data Associator | 1.15 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Clinical Database Programmer | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Data Analyst | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Lead data manager | 1.16 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Clinical Data Associator | 0.97 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Clinical Database Programmer | 0.97 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Data Analyst | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Lead data manager | 1.06 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Clinical Data Associator | 1.15 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Clinical Database Programmer | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Data Analyst | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Lead data manager | 1.27 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Clinical Data Associator | 0.79 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Clinical Database Programmer | 1.07 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Data Analyst | 1.19 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Project oversight | 0.56 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Lead data manager | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Clinical Data Associator | 0.44 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Clinical Database Programmer | 0.39 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Data Analyst | 0.71 |  | Default assumption - replace with your own figure
Others |  |  | Planning | Project lead | 1.1 |  | Default assumption - replace with your own figure
Others |  |  | Planning | Main staff | 0.63 |  | Default assumption - replace with your own figure
Others |  |  | Planning | Other staff | 0.42 | Project lead | Default assumption - replace with your own figure
Others |  |  | Develop | Project lead | 1 |  | Default assumption - replace with your own figure
Others |  |  | Develop | Main staff | 1.08 |  | Default assumption - replace with your own figure
Others |  |  | Develop | Other staff | 0.77 | Project lead | Default assumption - replace with your own figure
Others |  |  | Close | Project lead | 0.9 |  | Default assumption - replace with your own figure
Others |  |  | Close | Main staff | 0.81 |  | Default assumption - replace with your own figure
Others |  |  | Close | Other staff | 0.7 | Project lead | Default assumption - replace with your own figure
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Project oversight | 0.71 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Lead data manager | 0.86 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.4 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Data Analyst | 0.29 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Lead data manager | 1.3 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Clinical Data Associator | 0.46 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Clinical Database Programmer | 0.86 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Data Analyst | 0.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Lead data manager | 1.19 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.62 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.57 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Data Analyst | 0.94 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Lead data manager | 1.3 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.51 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.63 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Data Analyst | 1.09 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Project oversight | 0.64 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Lead data manager | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.23 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Lead data manager | 0.91 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.42 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Data Analyst | 0.31 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Lead data manager | 1.37 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Clinical Data Associator | 0.48 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Clinical Database Programmer | 0.91 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Data Analyst | 0.46 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Lead data manager | 1.25 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.66 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.61 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Data Analyst | 0.99 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Lead data manager | 1.37 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.54 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.67 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Data Analyst | 1.15 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Project oversight | 0.67 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Lead data manager | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.24 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Lead data manager | 0.96 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.32 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.45 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Data Analyst | 0.32 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Lead data manager | 1.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Clinical Data Associator | 0.5 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Clinical Database Programmer | 0.95 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Data Analyst | 0.48 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Lead data manager | 1.2 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.82 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.51 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Data Analyst | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Lead data manager | 1.32 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.64 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Data Analyst | 1.05 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Lead data manager | 1.2 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.82 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.51 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Data Analyst | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Lead data manager | 1.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.57 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.7 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Data Analyst | 1.21 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Project oversight | 0.7 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Lead data manager | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.32 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.25 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Data Analyst | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Project oversight | 0.68 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Lead data manager | 0.82 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.38 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Data Analyst | 0.27 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Lead data manager | 1.23 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Clinical Data Associator | 0.43 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Clinical Database Programmer | 0.82 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Data Analyst | 0.42 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Lead data manager | 1.13 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.59 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.54 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Data Analyst | 0.89 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Lead data manager | 1.23 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.49 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.6 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Data Analyst | 1.04 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Project oversight | 0.61 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Lead data manager | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.22 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Project oversight | 0.68 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Lead data manager | 0.83 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.38 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Data Analyst | 0.27 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Lead data manager | 1.23 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Clinical Data Associator | 0.43 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Clinical Database Programmer | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Data Analyst | 0.42 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Lead data manager | 1.13 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.59 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.54 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Data Analyst | 0.9 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Lead data manager | 1.23 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.49 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.6 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Data Analyst | 1.04 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Project oversight | 0.61 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Lead data manager | 0.72 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.22 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Lead data manager | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.4 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Data Analyst | 0.29 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Lead data manager | 1.3 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Clinical Data Associator | 0.46 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Clinical Database Programmer | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Data Analyst | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Lead data manager | 1.19 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.62 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.57 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Data Analyst | 0.94 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Lead data manager | 1.3 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.51 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.63 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Data Analyst | 1.09 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Project oversight | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Lead data manager | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.23 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Lead data manager | 0.91 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.42 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Data Analyst | 0.31 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Lead data manager | 1.37 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Clinical Data Associator | 0.48 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Clinical Database Programmer | 0.91 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Data Analyst | 0.46 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Lead data manager | 1.25 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.66 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.61 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Data Analyst | 0.99 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Lead data manager | 1.37 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.54 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Data Analyst | 1.15 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Project oversight | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Lead data manager | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.24 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Project oversight | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Lead data manager | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.36 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Data Analyst | 0.26 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Clinical Data Associator | 0.41 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Clinical Database Programmer | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Data Analyst | 0.39 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Lead data manager | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.67 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Data Analyst | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Lead data manager | 1.07 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.56 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.52 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Data Analyst | 0.85 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Lead data manager | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.67 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Data Analyst | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.46 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.57 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Data Analyst | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Project oversight | 0.58 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Lead data manager | 0.68 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.21 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Data Analyst | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Project oversight | 0.7 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Lead data manager | 0.85 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.4 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Data Analyst | 0.29 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Lead data manager | 1.27 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Clinical Data Associator | 0.44 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Clinical Database Programmer | 0.85 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Data Analyst | 0.42 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Lead data manager | 1.06 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.73 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.45 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Data Analyst | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.61 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.56 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Data Analyst | 0.93 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Lead data manager | 1.06 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.73 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.45 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Data Analyst | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Lead data manager | 1.27 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.5 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Data Analyst | 1.07 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Project oversight | 0.63 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Lead data manager | 0.74 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.23 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Data Analyst | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Lead data manager | 0.89 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.29 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Data Analyst | 0.3 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Lead data manager | 1.34 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Clinical Data Associator | 0.47 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Clinical Database Programmer | 0.89 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Data Analyst | 0.45 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Lead data manager | 1.12 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.76 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.47 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Data Analyst | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Lead data manager | 1.23 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.65 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Data Analyst | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Lead data manager | 1.12 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.76 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.47 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Data Analyst | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Lead data manager | 1.34 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.53 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Data Analyst | 1.12 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Project oversight | 0.66 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Lead data manager | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.29 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.24 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Data Analyst | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Lead data manager | 0.94 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.31 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Data Analyst | 0.31 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Lead data manager | 1.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Clinical Data Associator | 0.49 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Clinical Database Programmer | 0.94 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Data Analyst | 0.48 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.8 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.5 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Data Analyst | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Lead data manager | 1.29 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.68 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Data Analyst | 1.02 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.8 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.5 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Data Analyst | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Lead data manager | 1.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.56 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Data Analyst | 1.18 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Project oversight | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Lead data manager | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.31 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.25 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Data Analyst | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Project oversight | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Lead data manager | 0.81 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.37 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Data Analyst | 0.27 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Lead data manager | 1.21 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Clinical Data Associator | 0.43 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Clinical Database Programmer | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Data Analyst | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Lead data manager | 1.01 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.69 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Data Analyst | 0.6 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Lead data manager | 1.1 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.58 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.53 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Data Analyst | 0.88 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Lead data manager | 1.01 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.69 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Data Analyst | 0.6 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Lead data manager | 1.21 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Data Analyst | 1.01 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Project oversight | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Lead data manager | 0.7 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.21 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Data Analyst | 0.6 |  | Illustrative - fully outsourced

## Person
person_id | person_name | department | primary_role | capacity_fte | employment_start | employment_end | note_1 | note_2 | note_3 | note_4 | note_5
PSN-001 | Over Allocated | Data Management | Lead data manager | 1 |  |  | Deliberately on five projects at once - crosses the 1.50 ceiling.
PSN-002 | Half Timer | Data Management | Clinical Data Associator | 0.5 |  |  | capacity_fte 0.50. Capacity is context only - the thresholds are absolute.
PSN-003 | On The Books | Clinical Operations | Project oversight | 0 |  |  | capacity_fte 0.00 - on the books and not available. A legal value, and the bottom of the range V-35 enforces.
PSN-004 | Manual Figures | Data Management | Lead data manager | 1 |  |  | Carries an assignment-level manual estimate that the project figure overrides.
PSN-005 | Missing Month | Programming | Clinical Database Programmer | 1 |  |  | Manual, with one month left unstated.
PSN-006 | One Window | Biostatistics | Data Analyst | 1 |  |  | One PersonPeriodWeight window.
PSN-007 | Two Windows | Biostatistics | Data Analyst | 1 |  |  | TWO override windows on one assignment - which is why the override key includes the dates.
PSN-008 | Part Of Project | Clinical Operations | Project oversight | 1 |  |  | Assignment dates inside the project's own - joins late, leaves early.
PSN-009 | Whole Project | Clinical Operations | Project oversight | 1 |  |  | Both assignment dates BLANK, which means the project's own dates.
PSN-010 | Under Allocated | Programming | Data Analyst | 1 |  |  | One small assignment - a run below the 0.60 floor.
PSN-011 | Sharer Two | Data Management | Clinical Data Associator | 1 |  |  | Shares a role with PSN-012 and PSN-002.
PSN-012 | Sharer Three | Data Management | Clinical Data Associator | 1 |  |  | The third holder of that role.
PSN-013 | No Work | Business Systems | Data Analyst | 1 |  |  | No assignments at all - appears in the tables and draws nothing.
PSN-014 | Sun R. | Business Systems | Other staff | 1 |  |  | Portfolio staff - not a scenario.
PSN-015 | Pyo S. | Clinical Operations | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-016 | Wi T. | Data Management | Lead data manager | 1 |  |  | Portfolio staff - not a scenario.
PSN-017 | Ji W. | Programming | Clinical Data Associator | 1 |  |  | Portfolio staff - not a scenario.
PSN-018 | Nam Y. | Biostatistics | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-019 | Baek A. | Business Systems | Main staff | 0.6 |  |  | Portfolio staff - not a scenario.
PSN-020 | Shin B. | Clinical Operations | Clinical Data Associator | 0.6 |  |  | Portfolio staff - not a scenario.
PSN-021 | Koo C. | Data Management | Project oversight | 0.6 |  |  | Portfolio staff - not a scenario.
PSN-022 | Ryu D. | Programming | Lead data manager | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-023 | Moon E. | Biostatistics | Clinical Data Associator | 1 |  |  | Portfolio staff - not a scenario.
PSN-024 | Jang F. | Business Systems | Project lead | 1 |  |  | Portfolio staff - not a scenario.
PSN-025 | Hwang G. | Clinical Operations | Lead data manager | 1 |  |  | Portfolio staff - not a scenario.
PSN-026 | Cho H. | Data Management | Clinical Data Associator | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-027 | Song J. | Programming | Project oversight | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-028 | Yang K. | Biostatistics | Lead data manager | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-029 | Bae L. | Business Systems | Other staff | 0.6 |  |  | Portfolio staff - not a scenario.
PSN-030 | Noh M. | Clinical Operations | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-031 | Gil N. | Data Management | Lead data manager | 0.6 |  |  | Portfolio staff - not a scenario.
PSN-032 | Sun P. | Programming | Clinical Data Associator | 1 |  |  | Portfolio staff - not a scenario.
PSN-033 | Pyo R. | Biostatistics | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-034 | Wi S. | Business Systems | Main staff | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-035 | Ji T. | Clinical Operations | Clinical Data Associator | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-036 | Nam W. | Data Management | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-037 | Baek Y. | Programming | Lead data manager | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-038 | Shin A. | Biostatistics | Clinical Data Associator | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-039 | Koo B. | Business Systems | Project lead | 1 |  |  | Portfolio staff - not a scenario.
PSN-040 | Ryu C. | Clinical Operations | Lead data manager | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-041 | Moon D. | Data Management | Clinical Data Associator | 0.8 |  |  | Portfolio staff - not a scenario.
PSN-042 | Jang E. | Programming | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-043 | Hwang F. | Biostatistics | Lead data manager | 1 |  |  | Portfolio staff - not a scenario.
PSN-044 | Cho G. | Business Systems | Other staff | 1 |  |  | Portfolio staff - not a scenario.
PSN-045 | Song H. | Clinical Operations | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-046 | Yang J. | Data Management | Lead data manager | 0.6 |  |  | Portfolio staff - not a scenario.
PSN-047 | Bae K. | Programming | Clinical Data Associator | 1 |  |  | Portfolio staff - not a scenario.
PSN-048 | Noh L. | Biostatistics | Project oversight | 1 |  |  | Portfolio staff - not a scenario.
PSN-049 | Gil M. | Business Systems | Main staff | 1 |  |  | Portfolio staff - not a scenario.
PSN-050 | Sun N. | Clinical Operations | Clinical Data Associator | 1 |  |  | Portfolio staff - not a scenario.

## Assignment
assignment_id | person_id | person_name | project_id | role_name | assign_start_date | assign_end_date | person_weight | estimation_type | note_1 | note_2 | note_3
ASG-001 | PSN-006 |  | SCN-001 | Project oversight |  |  | 0.3 | automatic
ASG-002 | PSN-007 |  | SCN-001 | Lead data manager |  |  | 0.3 | automatic
ASG-003 | PSN-008 |  | SCN-001 | Clinical Data Associator |  |  | 0.3 | automatic
ASG-004 | PSN-009 |  | SCN-001 | Clinical Database Programmer |  |  | 0.3 | automatic
ASG-005 | PSN-010 |  | SCN-001 | Data Analyst |  |  | 0.3 | automatic
ASG-006 | PSN-011 |  | SCN-002 | Project oversight |  |  | 0.3 | automatic
ASG-007 | PSN-012 |  | SCN-002 | Lead data manager |  |  | 0.3 | automatic
ASG-008 | PSN-013 |  | SCN-002 | Clinical Data Associator |  |  | 0.3 | automatic
ASG-009 | PSN-006 |  | SCN-002 | Clinical Database Programmer |  |  | 0.3 | automatic
ASG-010 | PSN-007 |  | SCN-002 | Data Analyst |  |  | 0.3 | automatic
ASG-011 | PSN-008 |  | SCN-003 | Project oversight |  |  | 0.3 | automatic
ASG-012 | PSN-009 |  | SCN-003 | Lead data manager |  |  | 0.3 | automatic
ASG-013 | PSN-010 |  | SCN-003 | Clinical Data Associator |  |  | 0.3 | automatic
ASG-014 | PSN-011 |  | SCN-003 | Clinical Database Programmer |  |  | 0.3 | automatic
ASG-015 | PSN-012 |  | SCN-003 | Data Analyst |  |  | 0.3 | automatic
ASG-016 | PSN-004 |  | SCN-004 | Lead data manager |  |  | 0.4 | manual | Assignment-level manual. The project is manual too, so this figure is scaled to the project's month - V-33.
ASG-017 | PSN-013 |  | SCN-004 | Project oversight |  |  | 0.3 | automatic
ASG-018 | PSN-006 |  | SCN-004 | Clinical Data Associator |  |  | 0.3 | automatic
ASG-019 | PSN-007 |  | SCN-004 | Data Analyst |  |  | 0.3 | automatic
ASG-020 | PSN-005 |  | SCN-005 | Clinical Database Programmer |  |  | 0.4 | manual | One month of this assignment has no stated figure - V-31.
ASG-021 | PSN-008 |  | SCN-005 | Project oversight |  |  | 0.3 | automatic
ASG-022 | PSN-009 |  | SCN-005 | Lead data manager |  |  | 0.3 | automatic
ASG-023 | PSN-010 |  | SCN-005 | Data Analyst |  |  | 0.3 | automatic
ASG-024 | PSN-011 |  | SCN-006 | Lead data manager | 2026-01-01 | 2026-06-30 | 0.3 | automatic | Leaves half way through, which is what leaves the later project figures with nobody to share out to - V-32.
ASG-025 | PSN-012 |  | SCN-007 | Project lead |  |  | 0.3 | automatic
ASG-026 | PSN-013 |  | SCN-007 | Main staff |  |  | 0.3 | automatic
ASG-027 | PSN-006 |  | SCN-007 | Other staff |  |  | 0.3 | automatic
ASG-028 | PSN-007 |  | SCN-008 | Project oversight |  |  | 0.25 | automatic
ASG-029 | PSN-008 |  | SCN-008 | Lead data manager |  |  | 0.25 | automatic
ASG-030 | PSN-009 |  | SCN-008 | Clinical Database Programmer |  |  | 0.25 | automatic
ASG-031 | PSN-010 |  | SCN-008 | Data Analyst |  |  | 0.25 | automatic
ASG-032 | PSN-002 |  | SCN-009 | Clinical Data Associator |  |  | 0.4 | automatic | One of three holders of this role - the factor is divided by three.
ASG-033 | PSN-011 |  | SCN-009 | Clinical Data Associator |  |  | 0.4 | automatic | One of three holders of this role - the factor is divided by three.
ASG-034 | PSN-012 |  | SCN-009 | Clinical Data Associator |  |  | 0.4 | automatic | One of three holders of this role - the factor is divided by three.
ASG-035 | PSN-011 |  | SCN-009 | Project oversight |  |  | 0.3 | automatic
ASG-036 | PSN-012 |  | SCN-009 | Lead data manager |  |  | 0.3 | automatic
ASG-037 | PSN-013 |  | SCN-009 | Data Analyst |  |  | 0.3 | automatic
ASG-038 | PSN-006 |  | SCN-011 | Project oversight |  |  | 0.3 | automatic
ASG-039 | PSN-007 |  | SCN-011 | Lead data manager |  |  | 0.3 | automatic
ASG-040 | PSN-008 |  | SCN-011 | Clinical Data Associator |  |  | 0.3 | automatic
ASG-041 | PSN-009 |  | SCN-011 | Clinical Database Programmer |  |  | 0.3 | automatic
ASG-042 | PSN-010 |  | SCN-012 | Project oversight |  |  | 0.3 | automatic
ASG-043 | PSN-011 |  | SCN-012 | Lead data manager |  |  | 0.3 | automatic
ASG-044 | PSN-012 |  | SCN-012 | Clinical Data Associator |  |  | 0.3 | automatic
ASG-045 | PSN-013 |  | SCN-012 | Clinical Database Programmer |  |  | 0.3 | automatic
ASG-046 | PSN-006 |  | SCN-001 | Data Analyst |  |  | 0.6 | automatic | Carries ONE override window.
ASG-047 | PSN-007 |  | SCN-001 | Data Analyst |  |  | 0.6 | automatic | Carries TWO override windows, which is why the key includes the dates.
ASG-048 | PSN-008 |  | SCN-001 | Project oversight | 2026-05-01 | 2027-04-30 | 0.4 | automatic | Joins four months in and leaves early - a partial involvement.
ASG-049 | PSN-009 |  | SCN-001 | Project oversight |  |  | 0.4 | automatic | Both dates BLANK, so this is the project's own window (REQ-CAL-15).
ASG-050 | PSN-010 |  | SCN-007 | Other staff |  |  | 0.05 | automatic | One small commitment and nothing else - a run under the 0.60 floor.
ASG-051 | PSN-001 |  | SCN-001 | Lead data manager |  |  | 0.5 | automatic | One of four projects PSN-001 is on - together they cross the 1.50 FTE ceiling.
ASG-052 | PSN-001 |  | SCN-002 | Lead data manager |  |  | 0.5 | automatic | One of four projects PSN-001 is on - together they cross the 1.50 FTE ceiling.
ASG-053 | PSN-001 |  | SCN-003 | Lead data manager |  |  | 0.5 | automatic | One of four projects PSN-001 is on - together they cross the 1.50 FTE ceiling.
ASG-054 | PSN-001 |  | SCN-009 | Lead data manager |  |  | 0.5 | automatic | One of four projects PSN-001 is on - together they cross the 1.50 FTE ceiling.
ASG-055 | PSN-003 |  | SCN-007 | Project lead |  |  | 0.3 | automatic | capacity 0.00 and still assignable - capacity is context, not a limit.
ASG-056 | PSN-036 |  | BLK-001 | Project oversight |  |  | 0.56 | automatic | Portfolio assignment.
ASG-057 | PSN-015 |  | BLK-001 | Lead data manager |  |  | 0.37 | automatic | Portfolio assignment.
ASG-058 | PSN-017 |  | BLK-001 | Clinical Data Associator |  |  | 0.44 | automatic | Portfolio assignment.
ASG-059 | PSN-030 |  | BLK-001 | Clinical Database Programmer |  |  | 0.35 | automatic | Portfolio assignment.
ASG-060 | PSN-016 |  | BLK-001 | Data Analyst |  |  | 0.52 | automatic | Portfolio assignment.
ASG-061 | PSN-026 |  | BLK-002 | Project oversight |  |  | 0.24 | automatic | Portfolio assignment.
ASG-062 | PSN-045 |  | BLK-002 | Lead data manager |  |  | 0.35 | automatic | Portfolio assignment.
ASG-063 | PSN-022 |  | BLK-002 | Clinical Data Associator |  |  | 0.4 | automatic | Portfolio assignment.
ASG-064 | PSN-018 |  | BLK-002 | Clinical Database Programmer |  |  | 0.51 | automatic | Portfolio assignment.
ASG-065 | PSN-028 |  | BLK-002 | Data Analyst |  |  | 0.24 | automatic | Portfolio assignment.
ASG-066 | PSN-025 |  | BLK-002 | Data Analyst |  |  | 0.37 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-067 | PSN-023 |  | BLK-003 | Project oversight |  |  | 0.58 | automatic | Portfolio assignment.
ASG-068 | PSN-032 |  | BLK-003 | Lead data manager |  |  | 0.21 | automatic | Portfolio assignment.
ASG-069 | PSN-034 |  | BLK-003 | Clinical Data Associator |  |  | 0.54 | automatic | Portfolio assignment.
ASG-070 | PSN-035 |  | BLK-003 | Clinical Data Associator |  |  | 0.47 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-071 | PSN-037 |  | BLK-003 | Clinical Database Programmer | 2027-07-01 | 2028-12-31 | 0.41 | automatic | Portfolio assignment, joining late and leaving early.
ASG-072 | PSN-048 |  | BLK-003 | Data Analyst |  |  | 0.36 | automatic | Portfolio assignment.
ASG-073 | PSN-021 |  | BLK-003 | Data Analyst |  |  | 0.23 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-074 | PSN-031 |  | BLK-004 | Project lead |  |  | 0.34 | automatic | Portfolio assignment.
ASG-075 | PSN-047 |  | BLK-004 | Main staff | 2029-12-01 | 2030-06-30 | 0.46 | automatic | Portfolio assignment, joining late and leaving early.
ASG-076 | PSN-014 |  | BLK-004 | Other staff |  |  | 0.25 | automatic | Portfolio assignment.
ASG-077 | PSN-038 |  | BLK-005 | Project oversight | 2029-03-01 | 2031-01-31 | 0.5 | automatic | Portfolio assignment, joining late and leaving early.
ASG-078 | PSN-020 |  | BLK-005 | Project oversight |  |  | 0.35 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-079 | PSN-040 |  | BLK-005 | Lead data manager |  |  | 0.21 | automatic | Portfolio assignment.
ASG-080 | PSN-049 |  | BLK-005 | Clinical Data Associator |  |  | 0.51 | automatic | Portfolio assignment.
ASG-081 | PSN-043 |  | BLK-005 | Clinical Data Associator |  |  | 0.29 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-082 | PSN-024 |  | BLK-005 | Clinical Database Programmer |  |  | 0.33 | automatic | Portfolio assignment.
ASG-083 | PSN-039 |  | BLK-005 | Data Analyst |  |  | 0.25 | automatic | Portfolio assignment.
ASG-084 | PSN-019 |  | BLK-006 | Project oversight | 2029-06-01 | 2031-03-31 | 0.37 | automatic | Portfolio assignment, joining late and leaving early.
ASG-085 | PSN-029 |  | BLK-006 | Lead data manager |  |  | 0.47 | automatic | Portfolio assignment.
ASG-086 | PSN-042 |  | BLK-006 | Clinical Data Associator |  |  | 0.22 | automatic | Portfolio assignment.
ASG-087 | PSN-050 |  | BLK-006 | Clinical Data Associator |  |  | 0.24 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-088 | PSN-046 |  | BLK-006 | Clinical Database Programmer |  |  | 0.58 | automatic | Portfolio assignment.
ASG-089 | PSN-033 |  | BLK-006 | Data Analyst |  |  | 0.39 | automatic | Portfolio assignment.
ASG-090 | PSN-044 |  | BLK-006 | Data Analyst |  |  | 0.24 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-091 | PSN-041 |  | BLK-007 | Project oversight |  |  | 0.45 | automatic | Portfolio assignment.
ASG-092 | PSN-027 |  | BLK-007 | Project oversight |  |  | 0.23 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-093 | PSN-018 |  | BLK-007 | Lead data manager |  |  | 0.47 | automatic | Portfolio assignment.
ASG-094 | PSN-022 |  | BLK-007 | Clinical Data Associator |  |  | 0.46 | automatic | Portfolio assignment.
ASG-095 | PSN-050 |  | BLK-007 | Clinical Database Programmer | 2029-05-01 | 2030-10-31 | 0.41 | automatic | Portfolio assignment, joining late and leaving early.
ASG-096 | PSN-015 |  | BLK-007 | Clinical Database Programmer |  |  | 0.4 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-097 | PSN-048 |  | BLK-007 | Data Analyst |  |  | 0.5 | automatic | Portfolio assignment.
ASG-098 | PSN-035 |  | BLK-007 | Data Analyst |  |  | 0.46 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-099 | PSN-031 |  | BLK-008 | Project lead |  |  | 0.55 | automatic | Portfolio assignment.
ASG-100 | PSN-016 |  | BLK-008 | Project lead |  |  | 0.21 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-101 | PSN-025 |  | BLK-008 | Main staff |  |  | 0.29 | automatic | Portfolio assignment.
ASG-102 | PSN-033 |  | BLK-008 | Main staff |  |  | 0.29 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-103 | PSN-044 |  | BLK-008 | Other staff |  |  | 0.54 | automatic | Portfolio assignment.
ASG-104 | PSN-042 |  | BLK-008 | Other staff |  |  | 0.48 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-105 | PSN-023 |  | BLK-009 | Project oversight | 2029-01-01 | 2030-07-31 | 0.27 | automatic | Portfolio assignment, joining late and leaving early.
ASG-106 | PSN-024 |  | BLK-009 | Lead data manager | 2029-01-01 | 2030-07-31 | 0.28 | automatic | Portfolio assignment, joining late and leaving early.
ASG-107 | PSN-045 |  | BLK-009 | Lead data manager |  |  | 0.27 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-108 | PSN-034 |  | BLK-009 | Clinical Data Associator |  |  | 0.43 | automatic | Portfolio assignment.
ASG-109 | PSN-014 |  | BLK-009 | Clinical Data Associator |  |  | 0.46 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-110 | PSN-021 |  | BLK-009 | Clinical Database Programmer |  |  | 0.31 | automatic | Portfolio assignment.
ASG-111 | PSN-028 |  | BLK-009 | Clinical Database Programmer |  |  | 0.38 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-112 | PSN-041 |  | BLK-009 | Data Analyst |  |  | 0.53 | automatic | Portfolio assignment.
ASG-113 | PSN-017 |  | BLK-010 | Project oversight |  |  | 0.44 | automatic | Portfolio assignment.
ASG-114 | PSN-036 |  | BLK-010 | Project oversight |  |  | 0.43 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-115 | PSN-038 |  | BLK-010 | Lead data manager | 2028-12-01 | 2030-08-31 | 0.52 | automatic | Portfolio assignment, joining late and leaving early.
ASG-116 | PSN-019 |  | BLK-010 | Clinical Data Associator |  |  | 0.29 | automatic | Portfolio assignment.
ASG-117 | PSN-049 |  | BLK-010 | Clinical Database Programmer |  |  | 0.43 | automatic | Portfolio assignment.
ASG-118 | PSN-027 |  | BLK-010 | Data Analyst |  |  | 0.55 | automatic | Portfolio assignment.
ASG-119 | PSN-040 |  | BLK-011 | Project oversight |  |  | 0.43 | automatic | Portfolio assignment.
ASG-120 | PSN-037 |  | BLK-011 | Lead data manager |  |  | 0.41 | automatic | Portfolio assignment.
ASG-121 | PSN-043 |  | BLK-011 | Clinical Data Associator |  |  | 0.37 | automatic | Portfolio assignment.
ASG-122 | PSN-047 |  | BLK-011 | Clinical Database Programmer |  |  | 0.26 | automatic | Portfolio assignment.
ASG-123 | PSN-046 |  | BLK-011 | Data Analyst |  |  | 0.23 | automatic | Portfolio assignment.
ASG-124 | PSN-020 |  | BLK-011 | Data Analyst |  |  | 0.35 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-125 | PSN-030 |  | BLK-012 | Project lead |  |  | 0.58 | automatic | Portfolio assignment.
ASG-126 | PSN-029 |  | BLK-012 | Main staff |  |  | 0.42 | automatic | Portfolio assignment.
ASG-127 | PSN-039 |  | BLK-012 | Other staff | 2025-06-01 | 2026-04-30 | 0.53 | automatic | Portfolio assignment, joining late and leaving early.
ASG-128 | PSN-026 |  | BLK-012 | Other staff |  |  | 0.47 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-129 | PSN-032 |  | BLK-013 | Project oversight |  |  | 0.33 | automatic | Portfolio assignment.
ASG-130 | PSN-027 |  | BLK-013 | Project oversight |  |  | 0.45 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-131 | PSN-021 |  | BLK-013 | Lead data manager |  |  | 0.45 | automatic | Portfolio assignment.
ASG-132 | PSN-015 |  | BLK-013 | Clinical Data Associator |  |  | 0.28 | automatic | Portfolio assignment.
ASG-133 | PSN-031 |  | BLK-013 | Clinical Data Associator |  |  | 0.42 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-134 | PSN-023 |  | BLK-013 | Clinical Database Programmer |  |  | 0.21 | automatic | Portfolio assignment.
ASG-135 | PSN-032 |  | BLK-013 | Data Analyst |  |  | 0.52 | automatic | Portfolio assignment.
ASG-136 | PSN-022 |  | BLK-013 | Data Analyst |  |  | 0.23 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-137 | PSN-024 |  | BLK-014 | Project oversight |  |  | 0.22 | automatic | Portfolio assignment.
ASG-138 | PSN-020 |  | BLK-014 | Project oversight |  |  | 0.39 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-139 | PSN-046 |  | BLK-014 | Lead data manager |  |  | 0.6 | automatic | Portfolio assignment.
ASG-140 | PSN-042 |  | BLK-014 | Lead data manager |  |  | 0.22 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-141 | PSN-019 |  | BLK-014 | Clinical Data Associator |  |  | 0.29 | automatic | Portfolio assignment.
ASG-142 | PSN-017 |  | BLK-014 | Clinical Database Programmer |  |  | 0.29 | automatic | Portfolio assignment.
ASG-143 | PSN-048 |  | BLK-014 | Data Analyst |  |  | 0.55 | automatic | Portfolio assignment.
ASG-144 | PSN-047 |  | BLK-015 | Project oversight |  |  | 0.33 | automatic | Portfolio assignment.
ASG-145 | PSN-036 |  | BLK-015 | Project oversight |  |  | 0.42 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-146 | PSN-033 |  | BLK-015 | Lead data manager | 2031-06-01 | 2033-04-30 | 0.29 | automatic | Portfolio assignment, joining late and leaving early.
ASG-147 | PSN-049 |  | BLK-015 | Lead data manager |  |  | 0.39 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-148 | PSN-038 |  | BLK-015 | Clinical Data Associator |  |  | 0.29 | automatic | Portfolio assignment.
ASG-149 | PSN-018 |  | BLK-015 | Clinical Database Programmer |  |  | 0.22 | automatic | Portfolio assignment.
ASG-150 | PSN-043 |  | BLK-015 | Data Analyst | 2031-06-01 | 2033-04-30 | 0.59 | automatic | Portfolio assignment, joining late and leaving early.
ASG-151 | PSN-034 |  | BLK-015 | Data Analyst |  |  | 0.33 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-152 | PSN-037 |  | BLK-016 | Project lead |  |  | 0.43 | automatic | Portfolio assignment.
ASG-153 | PSN-026 |  | BLK-016 | Project lead |  |  | 0.45 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-154 | PSN-028 |  | BLK-016 | Main staff | 2028-01-01 | 2028-08-31 | 0.35 | automatic | Portfolio assignment, joining late and leaving early.
ASG-155 | PSN-050 |  | BLK-016 | Main staff |  |  | 0.37 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-156 | PSN-040 |  | BLK-016 | Other staff |  |  | 0.24 | automatic | Portfolio assignment.
ASG-157 | PSN-030 |  | BLK-016 | Other staff |  |  | 0.42 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-158 | PSN-045 |  | BLK-017 | Project oversight |  |  | 0.46 | automatic | Portfolio assignment.
ASG-159 | PSN-041 |  | BLK-017 | Lead data manager | 2029-01-01 | 2031-01-31 | 0.56 | automatic | Portfolio assignment, joining late and leaving early.
ASG-160 | PSN-035 |  | BLK-017 | Lead data manager |  |  | 0.21 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-161 | PSN-016 |  | BLK-017 | Clinical Data Associator |  |  | 0.52 | automatic | Portfolio assignment.
ASG-162 | PSN-029 |  | BLK-017 | Clinical Database Programmer |  |  | 0.21 | automatic | Portfolio assignment.
ASG-163 | PSN-044 |  | BLK-017 | Data Analyst |  |  | 0.34 | automatic | Portfolio assignment.
ASG-164 | PSN-025 |  | BLK-018 | Project oversight |  |  | 0.45 | automatic | Portfolio assignment.
ASG-165 | PSN-039 |  | BLK-018 | Lead data manager |  |  | 0.39 | automatic | Portfolio assignment.
ASG-166 | PSN-014 |  | BLK-018 | Clinical Data Associator | 2028-11-01 | 2030-03-31 | 0.31 | automatic | Portfolio assignment, joining late and leaving early.
ASG-167 | PSN-041 |  | BLK-018 | Clinical Database Programmer |  |  | 0.33 | automatic | Portfolio assignment.
ASG-168 | PSN-022 |  | BLK-018 | Data Analyst |  |  | 0.26 | automatic | Portfolio assignment.
ASG-169 | PSN-031 |  | BLK-018 | Data Analyst |  |  | 0.42 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-170 | PSN-018 |  | BLK-019 | Project oversight |  |  | 0.49 | automatic | Portfolio assignment.
ASG-171 | PSN-028 |  | BLK-019 | Lead data manager |  |  | 0.48 | automatic | Portfolio assignment.
ASG-172 | PSN-025 |  | BLK-019 | Lead data manager |  |  | 0.47 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-173 | PSN-042 |  | BLK-019 | Clinical Data Associator |  |  | 0.21 | automatic | Portfolio assignment.
ASG-174 | PSN-015 |  | BLK-019 | Clinical Database Programmer |  |  | 0.44 | automatic | Portfolio assignment.
ASG-175 | PSN-040 |  | BLK-019 | Data Analyst | 2025-09-01 | 2027-01-31 | 0.49 | automatic | Portfolio assignment, joining late and leaving early.
ASG-176 | PSN-027 |  | BLK-020 | Project lead | 2030-08-01 | 2031-05-31 | 0.44 | automatic | Portfolio assignment, joining late and leaving early.
ASG-177 | PSN-038 |  | BLK-020 | Project lead |  |  | 0.36 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-178 | PSN-023 |  | BLK-020 | Main staff |  |  | 0.48 | automatic | Portfolio assignment.
ASG-179 | PSN-044 |  | BLK-020 | Main staff |  |  | 0.25 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-180 | PSN-034 |  | BLK-020 | Other staff |  |  | 0.44 | automatic | Portfolio assignment.
ASG-181 | PSN-032 |  | BLK-020 | Other staff |  |  | 0.25 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-182 | PSN-021 |  | BLK-021 | Project oversight |  |  | 0.3 | automatic | Portfolio assignment.
ASG-183 | PSN-049 |  | BLK-021 | Lead data manager |  |  | 0.51 | automatic | Portfolio assignment.
ASG-184 | PSN-030 |  | BLK-021 | Lead data manager |  |  | 0.43 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-185 | PSN-036 |  | BLK-021 | Clinical Data Associator |  |  | 0.28 | automatic | Portfolio assignment.
ASG-186 | PSN-047 |  | BLK-021 | Clinical Database Programmer |  |  | 0.54 | automatic | Portfolio assignment.
ASG-187 | PSN-019 |  | BLK-021 | Data Analyst |  |  | 0.24 | automatic | Portfolio assignment.
ASG-188 | PSN-039 |  | BLK-022 | Project oversight |  |  | 0.28 | automatic | Portfolio assignment.
ASG-189 | PSN-045 |  | BLK-022 | Lead data manager |  |  | 0.38 | automatic | Portfolio assignment.
ASG-190 | PSN-016 |  | BLK-022 | Lead data manager |  |  | 0.34 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-191 | PSN-020 |  | BLK-022 | Clinical Data Associator |  |  | 0.42 | automatic | Portfolio assignment.
ASG-192 | PSN-035 |  | BLK-022 | Clinical Database Programmer |  |  | 0.24 | automatic | Portfolio assignment.
ASG-193 | PSN-037 |  | BLK-022 | Clinical Database Programmer |  |  | 0.34 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-194 | PSN-017 |  | BLK-022 | Data Analyst |  |  | 0.48 | automatic | Portfolio assignment.
ASG-195 | PSN-026 |  | BLK-023 | Project oversight |  |  | 0.42 | automatic | Portfolio assignment.
ASG-196 | PSN-050 |  | BLK-023 | Lead data manager |  |  | 0.2 | automatic | Portfolio assignment.
ASG-197 | PSN-024 |  | BLK-023 | Lead data manager |  |  | 0.35 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-198 | PSN-033 |  | BLK-023 | Clinical Data Associator | 2032-12-01 | 2034-08-31 | 0.22 | automatic | Portfolio assignment, joining late and leaving early.
ASG-199 | PSN-043 |  | BLK-023 | Clinical Database Programmer |  |  | 0.27 | automatic | Portfolio assignment.
ASG-200 | PSN-046 |  | BLK-023 | Data Analyst |  |  | 0.48 | automatic | Portfolio assignment.
ASG-201 | PSN-029 |  | BLK-024 | Project lead | 2030-10-01 | 2031-08-31 | 0.51 | automatic | Portfolio assignment, joining late and leaving early.
ASG-202 | PSN-014 |  | BLK-024 | Project lead |  |  | 0.47 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-203 | PSN-048 |  | BLK-024 | Main staff | 2030-10-01 | 2031-08-31 | 0.35 | automatic | Portfolio assignment, joining late and leaving early.
ASG-204 | PSN-030 |  | BLK-024 | Other staff |  |  | 0.43 | automatic | Portfolio assignment.
ASG-205 | PSN-021 |  | BLK-025 | Project oversight |  |  | 0.38 | automatic | Portfolio assignment.
ASG-206 | PSN-033 |  | BLK-025 | Project oversight |  |  | 0.26 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-207 | PSN-043 |  | BLK-025 | Lead data manager | 2027-12-01 | 2029-08-31 | 0.23 | automatic | Portfolio assignment, joining late and leaving early.
ASG-208 | PSN-015 |  | BLK-025 | Clinical Data Associator |  |  | 0.25 | automatic | Portfolio assignment.
ASG-209 | PSN-032 |  | BLK-025 | Clinical Database Programmer | 2027-12-01 | 2029-08-31 | 0.45 | automatic | Portfolio assignment, joining late and leaving early.
ASG-210 | PSN-025 |  | BLK-025 | Clinical Database Programmer |  |  | 0.41 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-211 | PSN-017 |  | BLK-025 | Data Analyst |  |  | 0.48 | automatic | Portfolio assignment.
ASG-212 | PSN-040 |  | BLK-026 | Project oversight |  |  | 0.25 | automatic | Portfolio assignment.
ASG-213 | PSN-041 |  | BLK-026 | Lead data manager |  |  | 0.32 | automatic | Portfolio assignment.
ASG-214 | PSN-028 |  | BLK-026 | Clinical Data Associator |  |  | 0.37 | automatic | Portfolio assignment.
ASG-215 | PSN-047 |  | BLK-026 | Clinical Database Programmer |  |  | 0.42 | automatic | Portfolio assignment.
ASG-216 | PSN-026 |  | BLK-026 | Clinical Database Programmer |  |  | 0.48 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-217 | PSN-018 |  | BLK-026 | Data Analyst |  |  | 0.46 | automatic | Portfolio assignment.
ASG-218 | PSN-034 |  | BLK-026 | Data Analyst |  |  | 0.47 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-219 | PSN-035 |  | BLK-027 | Project oversight |  |  | 0.43 | automatic | Portfolio assignment.
ASG-220 | PSN-029 |  | BLK-027 | Project oversight |  |  | 0.38 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-221 | PSN-049 |  | BLK-027 | Lead data manager |  |  | 0.31 | automatic | Portfolio assignment.
ASG-222 | PSN-019 |  | BLK-027 | Clinical Data Associator | 2025-06-01 | 2026-10-31 | 0.2 | automatic | Portfolio assignment, joining late and leaving early.
ASG-223 | PSN-016 |  | BLK-027 | Clinical Data Associator |  |  | 0.49 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-224 | PSN-050 |  | BLK-027 | Clinical Database Programmer |  |  | 0.47 | automatic | Portfolio assignment.
ASG-225 | PSN-024 |  | BLK-027 | Data Analyst |  |  | 0.27 | automatic | Portfolio assignment.
ASG-226 | PSN-045 |  | BLK-028 | Project lead | 2031-12-01 | 2032-08-31 | 0.45 | automatic | Portfolio assignment, joining late and leaving early.
ASG-227 | PSN-023 |  | BLK-028 | Project lead |  |  | 0.46 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-228 | PSN-031 |  | BLK-028 | Main staff |  |  | 0.33 | automatic | Portfolio assignment.
ASG-229 | PSN-020 |  | BLK-028 | Other staff | 2031-12-01 | 2032-08-31 | 0.52 | automatic | Portfolio assignment, joining late and leaving early.
ASG-230 | PSN-048 |  | BLK-029 | Project oversight |  |  | 0.46 | automatic | Portfolio assignment.
ASG-231 | PSN-027 |  | BLK-029 | Lead data manager | 2025-06-01 | 2027-04-30 | 0.39 | automatic | Portfolio assignment, joining late and leaving early.
ASG-232 | PSN-046 |  | BLK-029 | Clinical Data Associator | 2025-06-01 | 2027-04-30 | 0.35 | automatic | Portfolio assignment, joining late and leaving early.
ASG-233 | PSN-044 |  | BLK-029 | Clinical Data Associator |  |  | 0.27 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-234 | PSN-022 |  | BLK-029 | Clinical Database Programmer | 2025-06-01 | 2027-04-30 | 0.5 | automatic | Portfolio assignment, joining late and leaving early.
ASG-235 | PSN-039 |  | BLK-029 | Data Analyst |  |  | 0.28 | automatic | Portfolio assignment.
ASG-236 | PSN-014 |  | BLK-030 | Project oversight |  |  | 0.26 | automatic | Portfolio assignment.
ASG-237 | PSN-042 |  | BLK-030 | Lead data manager | 2025-05-01 | 2026-12-31 | 0.37 | automatic | Portfolio assignment, joining late and leaving early.
ASG-238 | PSN-036 |  | BLK-030 | Clinical Data Associator |  |  | 0.38 | automatic | Portfolio assignment.
ASG-239 | PSN-038 |  | BLK-030 | Clinical Database Programmer |  |  | 0.26 | automatic | Portfolio assignment.
ASG-240 | PSN-037 |  | BLK-030 | Data Analyst |  |  | 0.25 | automatic | Portfolio assignment.
ASG-241 | PSN-029 |  | BLK-030 | Data Analyst |  |  | 0.38 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-242 | PSN-020 |  | BLK-031 | Project oversight |  |  | 0.26 | automatic | Portfolio assignment.
ASG-243 | PSN-023 |  | BLK-031 | Project oversight |  |  | 0.39 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-244 | PSN-030 |  | BLK-031 | Lead data manager |  |  | 0.35 | automatic | Portfolio assignment.
ASG-245 | PSN-045 |  | BLK-031 | Lead data manager |  |  | 0.33 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-246 | PSN-032 |  | BLK-031 | Clinical Data Associator |  |  | 0.53 | automatic | Portfolio assignment.
ASG-247 | PSN-036 |  | BLK-031 | Clinical Database Programmer |  |  | 0.4 | automatic | Portfolio assignment.
ASG-248 | PSN-043 |  | BLK-031 | Data Analyst |  |  | 0.38 | automatic | Portfolio assignment.
ASG-249 | PSN-041 |  | BLK-032 | Project lead |  |  | 0.27 | automatic | Portfolio assignment.
ASG-250 | PSN-013 |  | BLK-032 | Project lead |  |  | 0.26 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-251 | PSN-024 |  | BLK-032 | Main staff |  |  | 0.42 | automatic | Portfolio assignment.
ASG-252 | PSN-035 |  | BLK-032 | Main staff |  |  | 0.47 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-253 | PSN-022 |  | BLK-032 | Other staff |  |  | 0.5 | automatic | Portfolio assignment.
ASG-254 | PSN-040 |  | BLK-032 | Other staff |  |  | 0.44 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-255 | PSN-044 |  | BLK-033 | Project oversight |  |  | 0.43 | automatic | Portfolio assignment.
ASG-256 | PSN-038 |  | BLK-033 | Lead data manager |  |  | 0.31 | automatic | Portfolio assignment.
ASG-257 | PSN-025 |  | BLK-033 | Clinical Data Associator | 2030-09-01 | 2031-12-31 | 0.56 | automatic | Portfolio assignment, joining late and leaving early.
ASG-258 | PSN-028 |  | BLK-033 | Clinical Database Programmer |  |  | 0.37 | automatic | Portfolio assignment.
ASG-259 | PSN-037 |  | BLK-033 | Data Analyst |  |  | 0.38 | automatic | Portfolio assignment.
ASG-260 | PSN-033 |  | BLK-033 | Data Analyst |  |  | 0.22 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-261 | PSN-050 |  | BLK-034 | Project oversight |  |  | 0.43 | automatic | Portfolio assignment.
ASG-262 | PSN-046 |  | BLK-034 | Lead data manager |  |  | 0.23 | automatic | Portfolio assignment.
ASG-263 | PSN-027 |  | BLK-034 | Clinical Data Associator | 2025-07-01 | 2027-01-31 | 0.48 | automatic | Portfolio assignment, joining late and leaving early.
ASG-264 | PSN-017 |  | BLK-034 | Clinical Database Programmer |  |  | 0.46 | automatic | Portfolio assignment.
ASG-265 | PSN-026 |  | BLK-034 | Data Analyst | 2025-07-01 | 2027-01-31 | 0.59 | automatic | Portfolio assignment, joining late and leaving early.
ASG-266 | PSN-039 |  | BLK-035 | Project oversight |  |  | 0.35 | automatic | Portfolio assignment.
ASG-267 | PSN-016 |  | BLK-035 | Project oversight |  |  | 0.48 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-268 | PSN-021 |  | BLK-035 | Lead data manager |  |  | 0.25 | automatic | Portfolio assignment.
ASG-269 | PSN-049 |  | BLK-035 | Lead data manager |  |  | 0.28 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-270 | PSN-015 |  | BLK-035 | Clinical Data Associator | 2029-09-01 | 2030-12-31 | 0.54 | automatic | Portfolio assignment, joining late and leaving early.
ASG-271 | PSN-019 |  | BLK-035 | Clinical Database Programmer |  |  | 0.25 | automatic | Portfolio assignment.
ASG-272 | PSN-031 |  | BLK-035 | Data Analyst |  |  | 0.4 | automatic | Portfolio assignment.
ASG-273 | PSN-042 |  | BLK-035 | Data Analyst |  |  | 0.29 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-274 | PSN-048 |  | BLK-036 | Project lead |  |  | 0.28 | automatic | Portfolio assignment.
ASG-275 | PSN-047 |  | BLK-036 | Main staff |  |  | 0.45 | automatic | Portfolio assignment.
ASG-276 | PSN-018 |  | BLK-036 | Other staff |  |  | 0.36 | automatic | Portfolio assignment.
ASG-277 | PSN-034 |  | BLK-037 | Project oversight | 2030-11-01 | 2032-03-31 | 0.32 | automatic | Portfolio assignment, joining late and leaving early.
ASG-278 | PSN-014 |  | BLK-037 | Lead data manager |  |  | 0.3 | automatic | Portfolio assignment.
ASG-279 | PSN-019 |  | BLK-037 | Clinical Data Associator |  |  | 0.22 | automatic | Portfolio assignment.
ASG-280 | PSN-007 |  | BLK-037 | Clinical Data Associator |  |  | 0.22 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-281 | PSN-049 |  | BLK-037 | Clinical Database Programmer |  |  | 0.42 | automatic | Portfolio assignment.
ASG-282 | PSN-043 |  | BLK-037 | Clinical Database Programmer |  |  | 0.42 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-283 | PSN-038 |  | BLK-037 | Data Analyst |  |  | 0.25 | automatic | Portfolio assignment.
ASG-284 | PSN-011 |  | BLK-038 | Project oversight |  |  | 0.35 | automatic | Portfolio assignment.
ASG-285 | PSN-045 |  | BLK-038 | Project oversight |  |  | 0.32 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-286 | PSN-034 |  | BLK-038 | Lead data manager |  |  | 0.48 | automatic | Portfolio assignment.
ASG-287 | PSN-014 |  | BLK-038 | Lead data manager |  |  | 0.21 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-288 | PSN-025 |  | BLK-038 | Clinical Data Associator | 2025-06-01 | 2026-10-31 | 0.46 | automatic | Portfolio assignment, joining late and leaving early.
ASG-289 | PSN-048 |  | BLK-038 | Clinical Data Associator |  |  | 0.36 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-290 | PSN-037 |  | BLK-038 | Clinical Database Programmer |  |  | 0.54 | automatic | Portfolio assignment.
ASG-291 | PSN-013 |  | BLK-038 | Clinical Database Programmer |  |  | 0.45 | automatic | Shares this role with a colleague - the factor is divided between them.
ASG-292 | PSN-039 |  | BLK-038 | Data Analyst |  |  | 0.38 | automatic | Portfolio assignment.
Note on C1: person_name is DERIVED. DERIVED - looked up from Person, do not type. The cell is locked so it cannot be typed over by accident. Nothing is hidden: Review > Unprotect Sheet turns it off, there is no password. But a value typed here is not recalculated, and the application recomputes this column on import anyway - so a hand-typed one is silently discarded, and any disagreement is reported as V-13.

## PersonPeriodWeight
assignment_id | period_start | period_end | weight_override | reason
ASG-046 | 2026-07-01 | 2026-09-30 | 0.2 | Part-time for a quarter - REPLACES person_weight, does not multiply it
ASG-047 | 2026-04-01 | 2026-06-30 | 0.15 | First window: reduced
ASG-047 | 2026-10-01 | 2026-12-31 | 0.9 | Second window on the SAME assignment: covering a peak

## MonthlyEstimate
scope | ref_id | month | fte | note_1
project | SCN-002 | 2026-01 | 0.96 | Stated at 55% of what this project's own standard asks for - V-34 short.
project | SCN-002 | 2026-02 | 0.96
project | SCN-002 | 2026-03 | 2.07
project | SCN-002 | 2026-04 | 2.07
project | SCN-002 | 2026-05 | 2.07
project | SCN-002 | 2026-06 | 2.07
project | SCN-002 | 2026-07 | 1.59
project | SCN-002 | 2026-08 | 1.59
project | SCN-002 | 2026-09 | 1.59
project | SCN-002 | 2026-10 | 1.59
project | SCN-002 | 2026-11 | 1.59
project | SCN-002 | 2026-12 | 1.59
project | SCN-002 | 2027-01 | 1.91
project | SCN-002 | 2027-02 | 1.91
project | SCN-002 | 2027-03 | 1.59
project | SCN-002 | 2027-04 | 1.59
project | SCN-002 | 2027-05 | 1.59
project | SCN-002 | 2027-06 | 1.59
project | SCN-002 | 2027-07 | 1.59
project | SCN-002 | 2027-08 | 1.59
project | SCN-002 | 2027-09 | 2.23
project | SCN-002 | 2027-10 | 2.23
project | SCN-002 | 2027-11 | 2.23
project | SCN-002 | 2027-12 | 1.34
project | SCN-003 | 2026-01 | 3.15 | Stated at 160% of the standard - V-34 over. The two directions are counted apart and never netted off.
project | SCN-003 | 2026-02 | 3.15
project | SCN-003 | 2026-03 | 6.29
project | SCN-003 | 2026-04 | 6.29
project | SCN-003 | 2026-05 | 6.29
project | SCN-003 | 2026-06 | 6.29
project | SCN-003 | 2026-07 | 4.74
project | SCN-003 | 2026-08 | 4.74
project | SCN-003 | 2026-09 | 4.74
project | SCN-003 | 2026-10 | 4.74
project | SCN-003 | 2026-11 | 4.74
project | SCN-003 | 2026-12 | 4.74
project | SCN-003 | 2027-01 | 5.5
project | SCN-003 | 2027-02 | 5.5
project | SCN-003 | 2027-03 | 4.74
project | SCN-003 | 2027-04 | 4.74
project | SCN-003 | 2027-05 | 4.74
project | SCN-003 | 2027-06 | 4.74
project | SCN-003 | 2027-07 | 4.74
project | SCN-003 | 2027-08 | 4.74
project | SCN-003 | 2027-09 | 6.67
project | SCN-003 | 2027-10 | 6.67
project | SCN-003 | 2027-11 | 6.67
project | SCN-003 | 2027-12 | 4.02
project | SCN-004 | 2026-01 | 1.6 | The project figure - the mother figure the people on it are scaled to.
project | SCN-004 | 2026-02 | 1.6
project | SCN-004 | 2026-03 | 3.46
project | SCN-004 | 2026-04 | 3.46
project | SCN-004 | 2026-05 | 3.46
project | SCN-004 | 2026-06 | 3.46
project | SCN-004 | 2026-07 | 2.66
project | SCN-004 | 2026-08 | 2.66
project | SCN-004 | 2026-09 | 2.66
project | SCN-004 | 2026-10 | 2.66
project | SCN-004 | 2026-11 | 2.66
project | SCN-004 | 2026-12 | 2.66
project | SCN-004 | 2027-01 | 3.2
project | SCN-004 | 2027-02 | 3.2
project | SCN-004 | 2027-03 | 2.66
project | SCN-004 | 2027-04 | 2.66
project | SCN-004 | 2027-05 | 2.66
project | SCN-004 | 2027-06 | 2.66
project | SCN-004 | 2027-07 | 2.66
project | SCN-004 | 2027-08 | 2.66
project | SCN-004 | 2027-09 | 3.73
project | SCN-004 | 2027-10 | 3.73
project | SCN-004 | 2027-11 | 3.73
project | SCN-004 | 2027-12 | 2.23
assignment | ASG-016 | 2026-01 | 2 | Stated 2.00 every month; the project figure scales it, which V-33 reports.
assignment | ASG-016 | 2026-02 | 2
assignment | ASG-016 | 2026-03 | 2
assignment | ASG-016 | 2026-04 | 2
assignment | ASG-016 | 2026-05 | 2
assignment | ASG-016 | 2026-06 | 2
assignment | ASG-016 | 2026-07 | 2
assignment | ASG-016 | 2026-08 | 2
assignment | ASG-016 | 2026-09 | 2
assignment | ASG-016 | 2026-10 | 2
assignment | ASG-016 | 2026-11 | 2
assignment | ASG-016 | 2026-12 | 2
assignment | ASG-016 | 2027-01 | 2
assignment | ASG-016 | 2027-02 | 2
assignment | ASG-016 | 2027-03 | 2
assignment | ASG-016 | 2027-04 | 2
assignment | ASG-016 | 2027-05 | 2
assignment | ASG-016 | 2027-06 | 2
assignment | ASG-016 | 2027-07 | 2
assignment | ASG-016 | 2027-08 | 2
assignment | ASG-016 | 2027-09 | 2
assignment | ASG-016 | 2027-10 | 2
assignment | ASG-016 | 2027-11 | 2
assignment | ASG-016 | 2027-12 | 2
assignment | ASG-020 | 2026-01 | 0.45 | Every month but one - the gap is deliberate, and V-31 reports it.
assignment | ASG-020 | 2026-02 | 0.45
assignment | ASG-020 | 2026-03 | 0.45
assignment | ASG-020 | 2026-04 | 0.45
assignment | ASG-020 | 2026-06 | 0.45
assignment | ASG-020 | 2026-07 | 0.45
assignment | ASG-020 | 2026-08 | 0.45
assignment | ASG-020 | 2026-09 | 0.45
assignment | ASG-020 | 2026-10 | 0.45
assignment | ASG-020 | 2026-11 | 0.45
assignment | ASG-020 | 2026-12 | 0.45
assignment | ASG-020 | 2027-01 | 0.45
assignment | ASG-020 | 2027-02 | 0.45
assignment | ASG-020 | 2027-03 | 0.45
assignment | ASG-020 | 2027-04 | 0.45
assignment | ASG-020 | 2027-05 | 0.45
assignment | ASG-020 | 2027-06 | 0.45
assignment | ASG-020 | 2027-07 | 0.45
assignment | ASG-020 | 2027-08 | 0.45
assignment | ASG-020 | 2027-09 | 0.45
assignment | ASG-020 | 2027-10 | 0.45
assignment | ASG-020 | 2027-11 | 0.45
assignment | ASG-020 | 2027-12 | 0.45
project | SCN-006 | 2026-01 | 1.45 | The later months have nobody assigned, so they cannot be shared out - V-32.
project | SCN-006 | 2026-02 | 1.45
project | SCN-006 | 2026-03 | 3.17
project | SCN-006 | 2026-04 | 3.17
project | SCN-006 | 2026-05 | 3.17
project | SCN-006 | 2026-06 | 3.17
project | SCN-006 | 2026-07 | 2.6
project | SCN-006 | 2026-08 | 2.6
project | SCN-006 | 2026-09 | 2.6
project | SCN-006 | 2026-10 | 2.6
project | SCN-006 | 2026-11 | 2.6
project | SCN-006 | 2026-12 | 2.6
project | SCN-006 | 2027-01 | 2.89
project | SCN-006 | 2027-02 | 2.89
project | SCN-006 | 2027-03 | 2.6
project | SCN-006 | 2027-04 | 2.6
project | SCN-006 | 2027-05 | 2.6
project | SCN-006 | 2027-06 | 2.6
project | SCN-006 | 2027-07 | 2.6
project | SCN-006 | 2027-08 | 2.6
project | SCN-006 | 2027-09 | 3.47
project | SCN-006 | 2027-10 | 3.47
project | SCN-006 | 2027-11 | 3.47
project | SCN-006 | 2027-12 | 2.08

## Lists
list_name | value | note_1
project_type | NewDrug CT
project_type | Biosimilar CT (Healthy)
project_type | Biosimilar CT (Patient)
project_type | Others
clinical_phase | Phase 1
clinical_phase | Phase 2
clinical_phase | Phase 3
clinical_phase | Phase 4
work_scope_type | fully in-housed
work_scope_type | fully outsourced
work_scope_type | Partially outsourced (in-house for EDC)
setup_party | by CRO
setup_party | by SB
EDC_system | Veeva EDC
EDC_system | Rave
EDC_system | eSOURCE
DataReviewSystem | Veeva DQS
DataReviewSystem | Medidata CDS
DataReviewSystem | No system (manual)
RBQM_system | CluePoints
RBQM_system | Medidata CDS
RBQM_system | No system (manual)
project_status | Planned
project_status | Active
project_status | On hold
project_status | Completed
milestone_name | Protocol (v1)
milestone_name | CTA submission
milestone_name | FPI
milestone_name | First SIV
milestone_name | LPI
milestone_name | interim DB lock cut-off
milestone_name | interim DB lock
milestone_name | final DB lock cut-off
milestone_name | final DB lock
milestone_name | Inspection
period_name_clinical | Before-Start-up
period_name_clinical | Start-up
period_name_clinical | Conduct (interim)
period_name_clinical | Close-out (interim)
period_name_clinical | Conduct (final)
period_name_clinical | Close-out (final)
period_name_clinical | After Close-out (final)
period_name_others | Planning
period_name_others | Develop
period_name_others | Close
role_clinical | Project oversight
role_clinical | Lead data manager
role_clinical | Clinical Data Associator
role_clinical | Clinical Database Programmer
role_clinical | Data Analyst
role_others | Project lead
role_others | Main staff
role_others | Other staff

## Config
parameter | value | note
schema_version | 12 | Structure version of this workbook. The application warns on a mismatch.
fte_hours_per_month | 160 | Hours equal to 1.00 FTE: 8 h/day x 5 days/week x 20 days/month.
over_allocation_fte | 1.5 | A person-month total above this is flagged as over-allocated. Absolute, not scaled by capacity (S2-01).
under_allocation_fte | 0.6 | A person-month total below this counts toward an under-allocated run. Absolute, not scaled by capacity (S2-01).
under_allocation_min_months | 3 | Consecutive months below the threshold before a run is flagged.
default_horizon_months | 24 | Months shown when the dashboard opens.
capacity_unit | FTE | Display unit for the figures on screen. 'FTE' shows a WEIGHT: 1.00 is one person working a full month on the project and 0.50 is half of one, so ordinary values run about 0.1 to 1.0. 'hours' shows that same weight multiplied by fte_hours_per_month. Display only - it changes nothing that is stored, and no figure the calculation produces.
absorb_unstaffed_role_factor | 1 | 1 = where nobody holds a role on a project, its factor is added to the role named in RoleFactor.absorbed_by, because the work still has to be done by whoever is there. 0 = an unstaffed role simply costs nothing, which is how versions before this one behaved.
split_shared_role_fte | 1 | 1 = when several people hold the same role on one project in a month, the role factor is divided between them. 0 = each is charged the whole factor, which is how versions before this one behaved.