## 00_README
PRAP source data - template
Schema version 3. Matches PRAP_Development_Plan_v1.0.xlsx, sheet 04_Data_Model.
COLOUR KEY
Blue identifier or key column - these link the sheets together.
Green derived by formula. Do not type in these; they recalculate.
Yellow you must supply this value. The application cannot work it out.
Grey italic row an example, in the template only. Delete it before use.
SHEETS
Project one row per project.
Milestone one row per milestone. Eight standard names.
ProjectPeriod the periods each project passes through, with their weights.
PeriodWeightStandard default weights per clinical phase. Clinical trials only.
RoleFactor the roles and their relative burden, per project type.
Person one row per person.
Assignment one row per person + project + role.
PersonPeriodWeight optional windows where a person's weight differs.
Lists permitted values for every dropdown.
Config thresholds and settings.
FREE-TEXT NOTES
Every sheet carries at least one free-text column, so anything worth recording has a home:
Project note_1 .. note_5
Milestone note_1
ProjectPeriod note_1
PeriodWeightStandard note_1
RoleFactor role_note
Person note_1 .. note_5
Assignment note_1 .. note_3
PersonPeriodWeight reason
Lists note_1
Config note
Nothing in a note column affects the calculation. They are carried through import and export
unchanged, so they survive a round trip.
HOW THE CALCULATION USES THIS
monthly load = project period weight x role factor x person weight x month coverage
The result is FTE, where 1.00 FTE = 160 hours per month.
Over-allocated: a person's monthly total above 1.50 FTE.
Under-allocated: below 0.80 FTE for three or more consecutive months.
PERIODS
Clinical trial periods are derived from the milestone dates:
Before-Start-up project start, to the day before Start-up
Start-up one month before CTA submission, lasting four months
Conduct from the end of Start-up to the day before the next close-out
Close-out (interim) three months before the interim DB lock, to that lock
Conduct (again) from the interim DB lock to the day before Close-out (final)
Close-out (final) three months before the final DB lock, to that lock
After Close-out (final) the inspection activity that follows the final DB lock
Where 'Protocol (v1)' is recorded, Before-Start-up ends on it and Start-up begins the day after.
Where 'First SIV' (or 'FPI') is recorded, Start-up ends on it instead of running a fixed four
months. A recorded milestone always beats the month-offset fallback.
'Conduct' therefore appears TWICE where a trial has an interim DB lock. period_seq keeps
the two apart. A period squeezed to nothing by a tight timeline is simply omitted.
'Inspection' is the one milestone that may be recorded SEVERAL TIMES for a project. Only
inspections dated AFTER the final DB lock open the last period; an earlier one stays a marker.
'Others' projects have no milestones. Their period dates and weights are both typed in.
ADDING A PERMITTED VALUE
Insert a row inside that list's block on the Lists sheet, so the block stays contiguous -
the dropdowns read a range, not a scattered set of rows.
BEFORE YOU USE THIS FILE
1. Delete the grey example row from every sheet.
2. Fill in the yellow columns: PeriodWeightStandard.weight and RoleFactor.role_factor.
Nothing simulates correctly until those are set.
3. Enter your projects, people and assignments.

## Project
project_id | project_name | project_type | project_category | clinical_phase | outsourcing_type | EDC_setup | DataReviewSystem_setup | RBQM_setup | DM_conduct | EDC_system | DataReviewSystem | RBQM_system | planned_member_count | start_date | end_date | total_period_months | status | note_1 | note_2 | note_3 | note_4 | note_5
PRJ-001 | ONV-101 First-in-human | NewDrug CT | Onvelaris | Phase 1 | Partial outsourcing | by SB | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 5 | 2025-10-01 | 2027-06-30 |  | Active | example row - delete before use

## Milestone
project_id | project_name | milestone_name | milestone_date | milestone_seq | note_1
PRJ-001 |  | CTA submission | 2026-01-15 | 2 | example row - delete before use

## ProjectPeriod
project_id | period_name | period_seq | period_start | period_end | weight | note_1
PRJ-001 | Start-up | 2 | 2025-12-15 | 2026-04-14 | 1.3 | example row - delete before use

## PeriodWeightStandard
project_type | clinical_phase | period_name | weight | note_1
NewDrug CT | Phase 1 | Start-up |  | example row - delete before use

## RoleFactor
project_type | role_name | role_factor | role_note
NewDrug CT | Lead data manager |  | example row - delete before use

## Person
person_id | person_name | department | primary_role | capacity_fte | employment_start | employment_end | note_1 | note_2 | note_3 | note_4 | note_5
PSN-001 | Kim S. | Data Management | Lead data manager | 1 |  |  | example row - delete before use

## Assignment
assignment_id | person_id | person_name | project_id | role_name | assign_start_date | assign_end_date | person_weight | note_1 | note_2 | note_3
ASG-001 | PSN-001 |  | PRJ-001 | Lead data manager | 2025-10-01 | 2027-06-30 | 0.45 | example row - delete before use

## PersonPeriodWeight
assignment_id | period_start | period_end | weight_override | reason
ASG-001 | 2026-07-01 | 2026-09-30 | 0.2 | Part-time - parental leave

## Lists
list_name | value | note_1
project_type | NewDrug CT
project_type | Biosimilar CT
project_type | Others
clinical_phase | Phase 1
clinical_phase | Phase 2
clinical_phase | Phase 3
clinical_phase | Phase 4
outsourcing_type | Full outsourcing
outsourcing_type | Partial outsourcing
outsourcing_type | Full In-house
setup_party | by CRO
setup_party | by SB
EDC_system | Veeva EDC
EDC_system | Rave
EDC_system | eSOURCE
DataReviewSystem | Veeva DQS
DataReviewSystem | Medidata CDS
DataReviewSystem | No system (manual)
RBQM_system | CluePoints
RBQM_system | Medidata CDS
RBQM_system | No system (manual)
project_status | Planned
project_status | Active
project_status | On hold
project_status | Completed
milestone_name | Protocol (v1)
milestone_name | CTA submission
milestone_name | FPI
milestone_name | First SIV
milestone_name | LPI
milestone_name | interim DB lock cut-off
milestone_name | interim DB lock
milestone_name | final DB lock cut-off
milestone_name | final DB lock
milestone_name | Inspection
period_name_clinical | Before-Start-up
period_name_clinical | Start-up
period_name_clinical | Conduct
period_name_clinical | Close-out (interim)
period_name_clinical | Close-out (final)
period_name_clinical | After Close-out (final)
period_name_others | Planning
period_name_others | Develop
period_name_others | Close
role_clinical | Project oversight
role_clinical | Lead data manager
role_clinical | Clinical Data Associator
role_clinical | Clinical Database Programmer
role_clinical | Data Analyst
role_others | Project lead
role_others | Main staff
role_others | Other staff

## Config
parameter | value | note
schema_version | 3 | Structure version of this workbook. The application warns on a mismatch.
fte_hours_per_month | 160 | Hours equal to 1.00 FTE: 8 h/day x 5 days/week x 20 days/month.
over_allocation_fte | 1.5 | A person-month total above this is flagged as over-allocated. Absolute, not scaled by capacity (S2-01).
under_allocation_fte | 0.6 | A person-month total below this counts toward an under-allocated run. Absolute, not scaled by capacity (S2-01).
under_allocation_min_months | 3 | Consecutive months below the threshold before a run is flagged.
default_horizon_months | 24 | Months shown when the dashboard opens.
capacity_unit | FTE | Display unit: 'FTE' or 'percent'.