## 00_Cover
PRAP — UI component list
Step 3, task 3.1 — review round 5: the PersonPeriodWeight key question
Version | v0.7
Date | 2026-08-01
Author | Claude Code
Reviewer | Dan — v0.3, v0.4 and v0.5 reviewed 2026-08-01 to 08-02
Prototype | app/PRAP_Prototype_v0.7.html
Governing plan | PRAP_Development_Plan_v1.9.xlsx (changes R-05..R-12, awaiting signature)
Specification | PRAP_Programming_Specification_v0.8.xlsx (draft)
What happened to your v0.3 review
All 15 design decisions accepted. Of the 38 components, 29 marked Keep and 9 marked Change.
Every one of the 9 is applied in the prototype named above - none is deferred, none is partial.
Sheet 01 carries your decision and your comment verbatim against each component, with a column
saying what was actually done. Six new components appeared as a result of your changes; they are
tinted green. The nine you changed are tinted amber.
Sheet 02 records the decisions. One needs your attention: you accepted D-06 (the timeline shades
bands by weight) and separately asked in O-10 for the timeline to be coloured by period name.
Those cannot both hold. O-10 is the more specific instruction and the later intent, so it wins -
D-06 is marked SUPERSEDED and weight now rides as a lightness step inside each period's hue,
so nothing that drove the simulation stopped being visible. Overturn that on sheet 02 if I have
read you backwards.
Sheet 04 lists what your review changed outside this document: two new requirements, two
reworded, and the plan and specification versions that carry them.
ROUND 3 (this issue) applied three further items you raised, listed in full on sheet 05:
the role factor is now keyed on role AND project type AND clinical phase AND period; every table
on the three data tabs scrolls inside its own panel; and the insert buttons missing from the
assumptions tab are fixed. You were right about the last one, and it was worse than reported -
the role-factor table had an 'insert' HEADER with no cells beneath it, so that table was a column
out of alignment, and the value-lists table had buttons it should never have had.
ROUND 4 (this issue) is on sheet 06. You named the two conduct stretches apart -
'Conduct (interim)' and 'Conduct (final)' - which makes period_name unique in a project and
gives ProjectPeriod a natural key again. That is the alternative D-15 offered and was not taken
at the time, so D-15 is now SUPERSEDED. It also retires the need for the display numbering that
REQ-DSH-10 introduced: the requirement is satisfied by the data model instead.
To review this round: open the prototype, then mark the YELLOW column on sheets 01 and 02 -
'OK' where the change landed, or 'Rework' with a note where it did not.

## 01_Components
Component list — your decisions and what was done
45 components. 27 Keep, 13 Change (amber), 5 added by those changes (green). Your comments are quoted exactly as written.
ID | Area | Component | What it does | REQ-IDs | Your decision | Your comment (verbatim) | What was done in v0.4 | Confirm
G-01 | Global | Header | Application name, version, expected schema version. | REQ-VC-02 | Keep |  | Unchanged.
G-02 | Global | Loaded-file line | Which workbook is loaded, and when it was read - now with the time zone. | REQ-IMP-05 | Change | Add GMT timezone for loaded date & time information. E.g. loaded 2026-08-01 09:14 (GMT+G6, KST) | Done. The stamp now reads 'loaded 2026-08-01 09:14 (GMT+9, KST)'. The offset and the zone abbreviation both show, because either alone is ambiguous to a reader in another country. Taken as GMT+9 / KST - your note says 'GMT+G6', which I have read as a typing slip for GMT+9 given KST beside it. Correct me if not.
G-03 | Global | Load workbook | File picker / drag-and-drop. Warns first if edits are unsaved. | REQ-IMP-01, REQ-IMP-08 | Keep |  | Unchanged.
G-04 | Global | Export | Writes all ten sheets back in template layout, edits included. | REQ-IMP-04, REQ-IMP-07 | Keep |  | Unchanged.
G-05 | Global | Findings banner | Summary of the last import; opens the full report. | REQ-IMP-02 | Keep |  | Unchanged.
G-06 | Global | Unsaved-edit counter | Always visible once anything is edited, and now states the validation standing of those edits. | REQ-IMP-08, REQ-IMP-09 | Change | When anything is changed, the update to be checked with validation rules and if no doubt on the updated all the changes to be included into the exported file when a use runs exporting. | Done, and it was already the specified behaviour - what was missing was any sign of it on screen. The counter now reads '3 unsaved edits · all 3 pass validation', and says outright that a failing edit is rejected at entry so nothing invalid can reach the export. The rule has not changed; it has become visible.
G-07 | Global | Tab bar | Overall ¦ Source data (project) ¦ Source data (person) ¦ General assumptions. | REQ-DSH-01..04, REQ-DSH-11 | Change | Add 'General assumtions' tab having other general information (e.g. 'PeriodWeightStandard' sheet, 'RoleFactor' sheet) | Done - a fourth tab, and the one gap in the design worth closing. Every figure on the Overall tab is the product of these two tables, yet they were reachable only by opening the workbook. See A-01 to A-04 for what the tab holds. This one needed a new requirement, REQ-DSH-11.
G-08 | Global | Empty state | With nothing loaded: one load panel and a template download link. | REQ-IMP-03 | Keep |  | Unchanged.
O-01 | Overall | Horizon control | From/to month, defaulting to 24 months. | REQ-CAL-01 | Keep |  | Unchanged.
O-02 | Overall | Expand to all projects | One click widens the horizon to the latest project end date. | REQ-DSH-07 | Keep |  | Unchanged.
O-03 | Overall | Filters (GLOBAL) | Project type, clinical phase, project, person, role, department. One setting drives every tab. | REQ-DSH-05 | Change | Filter for 'Unit' isn't needed because of no meaning. Instead, add 'Clinical trial phase' right side of 'Project type'. | Done both ways. 'Unit' is gone from the bar and moved to the new tab as configuration (see O-04) - you are right that it was never a filter: it changed how figures are written, not which are shown. 'Clinical phase' now sits immediately right of 'Project type', where the two type-ish controls read as a pair.
O-03b | Overall | Reset filters | Clears every filter and restores the 24-month default in one action. | REQ-DSH-05 | Keep |  | Unchanged.
O-04 | Overall | Unit toggle | FTE or hours. Now a setting on the General assumptions tab, not a filter. | REQ-CAL-08 | Change | Include configuration information into the new sheet (i.e. General assumptions). | Done. The whole Config sheet is on the new tab, and the display-unit control sits with it, under a line explaining why it is not in the filter bar.
O-05 | Overall | Summary tiles | Projects, people, total demand, over-allocated months, under-allocation runs. | REQ-DSH-08 | Keep |  | Unchanged.
O-06 | Overall | Demand chart | Stacked monthly demand, one band per project, largest on the baseline. No legend; hover pop-up instead. | REQ-DSH-02 | Change | In 'Monthly demand by project' section, remove legend information on the bottom. Instead, while hovering over each stack in the graph, provide pop-up information (e.g. project name, project's month FTE, acting people in the months). | Done. The legend is gone and a real hover pop-up replaces it, carrying project name and type, that month's FTE and its hour equivalent, the headcount, and every person on the project that month with their role. Note the knock-on: D-11 argued that identity came from the legend order because 62 hues cannot be told apart. The tooltip now carries that alone - which is stronger, since it names one band rather than asking you to match a colour against a list of 62.
O-07 | Overall | Resource by project (table) | Project x month heatmap. Sorted NewDrug CT, Biosimilar CT, Others, then earliest first. | REQ-DSH-01 | Keep |  | Unchanged.
O-07b | Overall | Project row expansion | Clicking a project name reveals a row per person and role, each with its own monthly figures. | REQ-DSH-01 | Keep |  | Unchanged.
O-08 | Overall | Mean load per person (chart) | One bar per person against both absolute thresholds; above the bar budget, a ranked subset. | REQ-DSH-02, REQ-DSH-08, REQ-DSH-09 | Keep |  | Unchanged.
O-09 | Overall | Resource by person (table) | Person x month, summed across projects, over/under flagged. | REQ-DSH-01, REQ-DSH-08 | Keep |  | Unchanged.
O-09b | Overall | Person row expansion | Clicking a person name reveals a row per project and role, in the same type-then-date order. | REQ-DSH-01 | Keep |  | Unchanged.
O-10 | Overall | Project timeline (Gantt) | First panel on the tab. Duration under each name, bands coloured by period, milestone markers. | REQ-DSH-02, REQ-PRJ-05, REQ-DSH-10 | Change | 1. Add project duration (start date, end date, total month) under individual project name. 2. Change color more intuitive. e.g. before start-up (Grey), Start-up (Red), Conduct (Green), Close-out (Orange), After close-out (Dark Grey). Information given when hovering over, should include monthly FTE for each period. 3. No need to seperate 'Inspection' because of that being one of milestones. Change the icon for milestone from circle to inverted triangle highlighted. 4. Location: as first section right after 'Horizon and filters' section. | All four done. (1) 'start -> end · n months' sits under each project name. (2) Your mapping is followed, with one departure: red beside green is the pair red-green colour blindness collapses, and you accepted D-04 making 'never colour alone' a floor - so the red is shifted slightly toward orange, every band wide enough carries its period name as text, and the tooltip names it outright. The two close-outs take a light and a deep orange so they are not one indistinguishable block. The tooltip carries dates, weight and the FTE per month the project draws across that period. (3) 'Inspection' now takes the same marker as every other milestone, and the marker is an inverted triangle in its own lane above the bands, so it never lands on a band label. (4) The timeline is now the first panel, above the summary tiles. This change supersedes D-06 - see sheet 02.
P-01 | Project tab | Project table | All 23 columns, sortable, filterable, editable, with an insert control on every row. | REQ-DSH-03, REQ-IMP-07, REQ-IMP-11 | Change | Add 'Insert new row' button for all rows and all sections. When clicking the button, new row to be added right after the row where a user clicks that button. | Done, and generalised - see X-06. Every row of every editable table now carries '+ row', and the new row lands directly below the row you pressed, not at the bottom of the table. This needed a new requirement, REQ-IMP-11: nothing in the plan said a row could be created at all.
P-02 | Project tab | Milestone sub-table | Milestones of the selected project in date order; Inspection may repeat. | REQ-PRJ-05, REQ-PRJ-13 | Keep |  | Unchanged except for gaining the insert control (X-06).
P-03 | Project tab | Period sub-table | Derived periods with seq, dates, weight and note; repeated names numbered. | REQ-PRJ-06, REQ-CAL-09, REQ-DSH-10 | Keep |  | Unchanged except for gaining the insert control (X-06).
P-04 | Project tab | Recompute periods | Re-derives from current milestones; warns before replacing hand-set dates. | decision C-10 | Keep |  | Unchanged.
P-05 | Project tab | Export visible table | Current table to .xlsx. | REQ-DSH-06 | Keep |  | Unchanged.
S-01 | Person tab | Person table | All 12 columns, sortable, filterable, editable, with an insert control on every row. | REQ-DSH-04, REQ-IMP-07, REQ-IMP-11 | Change | Add 'Insert new row' button for all rows and all sections. When clicking the button, new row to be added right after the row where a user clicks that button. | Done - same treatment as P-01, and the same generalisation to every section (X-06).
S-02 | Person tab | Utilisation strip | Selected person's monthly load with both absolute thresholds drawn. | REQ-DSH-08 | Keep |  | Unchanged.
S-03 | Person tab | Assignment sub-table | Project, role, dates and person weight. | REQ-PSN-02, REQ-PSN-03 | Keep |  | Unchanged except for gaining the insert control (X-06).
S-04 | Person tab | Override sub-table | PersonPeriodWeight windows for the selected assignment. | REQ-PSN-05 | Keep |  | Unchanged except for gaining the insert control (X-06).
S-05 | Person tab | Export visible table | Current table to .xlsx. | REQ-DSH-06 | Keep |  | Unchanged.
E-01 | Editing | Inline cell edit | Every field editable, validated at the point of entry. | REQ-IMP-09 | Keep |  | Unchanged.
E-02 | Editing | Cascade confirm | Changing an identifier states how many rows will follow, then rewrites them. | REQ-IMP-10, V-17 | Keep |  | Unchanged.
E-03 | Editing | Delete guard | Refuses to delete a row that is still referenced, naming what points at it. | V-17 | Keep |  | Unchanged.
X-01 | Layout | Scroll regions | Every chart and table scrolls inside its own panel - horizontally when wide, and within a bounded height when tall, with the header row staying visible. | REQ-NFR-02 | Change (round 3) | Apply scroll bar on the bottom of all sections of 'Source data (project)'/'Source data (person)'/'General assumptions'. Some sections have problems that table size over the fixed section site. (e.g. Periods of 'Source data (project)', Assignments and Weight overrides of 'Source data (person)') | Done. Six tables were rendering outside their panels: the milestone and period sub-tables, assignments, weight overrides, and both assumptions tables. Each now sits in a scroll region that is bounded in BOTH directions - the earlier rule only covered width, which is why a long sub-table still grew the page and pushed the panels below it down. Verified by measuring the document's scroll width against the viewport: they match, so nothing overflows sideways.
X-02 | Layout | Type and phase pills | Project type and clinical phase as labelled pills; text carries the meaning, colour only speeds recognition. | REQ-PRJ-01, REQ-PRJ-09 | Keep |  | Unchanged.
X-03 | Layout | Numbered repeated periods — now a guard only | Retained, but it never fires: since R-11 no period name repeats, so a name alone identifies a period on screen. | REQ-DSH-10 | Change (round 4) | Change period name for conduct as 'Conduct (interim)' and 'Conduct (final)' in order to distinguish multiple periods. | Done - see sheet 06. This component is what REQ-DSH-10 asked for, and your change satisfies that requirement structurally instead. The numbering code is kept as a guard: V-18 now rejects a repeated name on import, but a hand-built model could still reach the renderer, and a silent collision there would be worse than a redundant ten lines.
X-04 | Layout | Row virtualisation | Both Overall tables render only the rows in the viewport plus overscan. | REQ-DSH-09, REQ-NFR-03 | Keep |  | Unchanged.
A-01 | Assumptions tab | Standard period weights | PeriodWeightStandard as a matrix - phase down the side, period across, shaded by magnitude. | REQ-DSH-11 |  |  | Added for G-07. Shown as a matrix, not 48 flat rows: it is a standard, and a standard is read across. 'Others' projects are absent by design - their weights are hand-entered per project.
A-02 | Assumptions tab | Role factors — clinical trials | RoleFactor as a matrix: type + phase + role down the side, the six periods across. | REQ-DSH-11 | Change (round 3) | Weight of Role factors should be given by Role & Project type & Clinical phase & Periods. | Done - see sheet 05. The key is now all four columns and the sheet grows from 13 rows to 249, so it is shown as a matrix: 40 rows of six periods each. Reading a role ACROSS the periods is the point of the change - the database programmer peaks at start-up, the analyst at lock. Also fixed here: this table had an 'insert' header with no cells beneath it, so every row was a column out of alignment. It is a reference matrix now, and reference matrices carry no insert control.
A-02b | Assumptions tab | Role factors — Others | The same matrix for non-trial projects: role down the side, the three 'Others' periods across. | REQ-DSH-11 |  |  | Split out because 'Others' projects carry no clinical phase and run a different period set, so they cannot share a matrix with the trials without a column of blanks.
A-03 | Assumptions tab | Configuration | Config: thresholds and settings, plus the display-unit control moved here from the filter bar. | REQ-DSH-11, REQ-CAL-08 |  |  | Added for G-07 and O-04. The thresholds that colour the tables now sit next to a note saying what they mean.
A-04 | Assumptions tab | Value lists | Lists: what each list-typed column will accept, and how many values each list holds. Read-only. | REQ-DSH-11 | Change (round 3) | Insert row button ... Check all tables of the 'General assumptions'. | Fixed. This table had insert BUTTONS it should never have had - the header carried no insert column, so it too was out of alignment, the opposite way round from A-02. It is now explicitly read-only: a value added here with nothing referring to it is noise, and the note says so.
X-05 | Layout | Hover pop-up layer | A real tooltip - follows the cursor, flips at the screen edge, carries formatted multi-line content. | REQ-DSH-02 |  |  | Added for O-06 and O-10. The native SVG tooltip cannot show a list of people and waits half a second to appear, so it could not do what you asked for. This moves off the deferred list, where v0.3 had it.
X-06 | Layout | Insert-row control | '+ row' leading every row of every editable table; the new row lands directly below that row. | REQ-IMP-11 |  |  | Added for P-01 and S-01, generalised to 'all sections' as you asked: both source-data tables, all four sub-tables, and the role-factor and config tables on the new tab. The control leads the row - see D-18 for why.
Count | Keep | Changed | Added
| 27 | 9 | 5
Green = added by this review. Amber = changed by this review.

## 02_Design_Decisions
Design decisions — all 15 accepted, one now superseded
You accepted every decision. D-06 is nonetheless overturned, because O-10 asks for the opposite; that conflict is the one thing on this sheet needing your eye.
ID | Decision | Why | Your decision | State after your review | Confirm
D-01 | SUPERSEDED at the v0.2 review - the demand chart stacks by individual project. | You asked for per-project bands, so that is what the chart does: ordered by total resource with the largest on the baseline, 'Others' grey. | Accept | Stands. No change.
D-06 | SUPERSEDED by your own O-10 - the timeline now colours bands by PERIOD NAME. | D-06 said the timeline shades by weight, because weight is what drives the simulation and naming periods by colour would spend the palette on labels already in the tooltip. You accepted that, and then asked in O-10 for exactly the opposite - grey, red, green, orange, dark grey by period. | Accept (conflicts with O-10) | O-10 wins: it is the more specific instruction and the clearer statement of what you want to see. But D-06's point was real, so weight was not thrown away - it rides as a lightness step inside each period's hue, deliberately over a narrow range so it never competes with the hue, and it stays exact in the tooltip. If you did mean to keep weight as the colour, mark this Rework and O-10.2 goes back.
D-11 | Beyond seven projects, colour comes from an EXTENDED palette, not the validated one. | The validated set caps at eight hues; per-project colour needs ~50, so the seven validated hues are stepped in lightness. Hue alone no longer identifies a band. | Accept | Stands, but its safety net changed. D-11 said identity came from 'the legend order, the tooltip and the table below'. O-06 removed the legend, so the tooltip now carries it alone - which is the stronger half of that pair anyway, since it names one band rather than asking you to match a hue against 62.
D-12 | The project table samples the head of each type rather than listing a flat top-14. | Your sort puts all 34 NewDrug CT projects first, so a flat top-14 would never reach the other types and the ordering could not be seen working. | Accept | Stands. No change.
D-13 | The global filter bar is not sticky. | A sticky bar 110px tall covered panel headings as soon as the page scrolled. | Accept | Stands. No change.
D-02 | The project table lists the ten busiest projects plus an aggregate row. | 62 rows x 12 months does not fit on screen; the real table lists all 62 with sort and filter. | Accept | Stands. No change.
D-03 | Heat shading in the tables is one blue ramp, light to dark. | Magnitude is a sequential quantity, so it takes one hue. The aggregate row is deliberately not shaded. | Accept | Stands, and now also carries the period-weight matrix on the new tab, so the same ramp means the same thing everywhere.
D-04 | Over- and under-allocation carry an icon and a value, never colour alone. | Red-green colour blindness affects around 8% of men; a cell that says only 'red' is unreadable to them and unprintable in mono. | Accept | Stands, and it is what shaped the O-10 palette: your red/green pair is exactly the collapse this decision guards against, so the bands carry text labels and the red sits slightly toward orange.
D-05 | Both thresholds are drawn on the person chart and the utilisation strip. | A ceiling without a floor makes under-use invisible, and under-use is half of what the tool is for. | Accept | Stands. No change.
D-07 | Editing is inline in the tables, not in a separate form or dialog. | A dialog per row would make bulk correction - the common case after a timeline slips - slow enough that people would go back to editing the workbook by hand. | Accept | Stands, and extends naturally to X-06: a row is inserted in place, where the user is looking.
D-08 | The findings banner persists until dismissed rather than fading. | A toast that disappears is a finding nobody read. | Accept | Stands. No change.
D-09 | Dark mode is supported, with its own selected colour steps. | Not a flip of the light palette: the ramp, the categorical hues and the status inks are each re-stepped for the dark surface. | Accept | Stands, and it caught a real fault in the new period palette: your 'dark grey' for After Close-out vanished against the dark surface. Both greys were re-picked to a pair that separates on either background.
D-10 | The page is one scrolling column per tab, not a fixed dashboard grid. | It prints, it works on a laptop screen, and it needs no layout engine. | Accept | Stands, and the fourth tab follows the same pattern.
D-14 | At the target volume the person chart shows the 20 most loaded people, not all 1,000. | 1,000 bars across a 1,200px panel is 1.2px each - narrower than the gap between them. | Accept | Stands. No change.
D-15 | SUPERSEDED — the conduct stretches are RENAMED, not numbered. | D-15 argued for numbering because renaming would break the PeriodWeightStandard lookup, which is keyed on the period name. Its stated alternative was to label them by what separates them - 'Conduct (pre-interim)' and 'Conduct (post-interim)'. You took that alternative in round 4. | Accept, then superseded | The objection was answered rather than ignored: the lookup does not break because the new names were added to the standard period set, so PeriodWeightStandard and RoleFactor are keyed on them like any other period. The cost is the one D-15 named - the set grows from six names to seven, and both weight tables grow with it. The gain is larger: period_name is unique within a project, so ProjectPeriod has a natural key and the display numbering is no longer needed at all.
D-16 | The two 'Close-out' periods take a light and a deep orange, not one shared orange. | Your mapping gave 'Close-out' a single colour, but a trial with an interim DB lock shows both in the same row, adjacent to each other. One shared hue made them read as a single interrupted band. |  | Light amber for interim, deep orange for final. Both still read as 'the close-out family', which is what your mapping intended.
D-19 | PeriodWeightStandard and RoleFactor are kept as two tables, not collapsed into one. | Keying the role factor on phase and period means both tables now vary over (type, phase, period), and the calculation multiplies them - so they are mathematically collapsible into a single table keyed on all four columns. They are kept apart because they answer different questions: one is how busy the PROJECT is in a period, the other how much of that falls on a ROLE. |  | Kept separate. But the separation is a maintenance convention, not something the arithmetic enforces: raising a project's Conduct load by editing all five role rows gives the right answer today and double-counts the next time the period weight moves. If that distinction is not kept in practice, the honest fix is to collapse them - a schema change, so flagged rather than done.
D-18 | The insert control leads each row rather than trailing it. | Placed at the end of the row, '+ row' sat off-screen on the 23-column project table and needed a horizontal scroll every time. Leading, it is always in view and reads as a row-action gutter. |  | Applies to every editable table, so the control is in the same place everywhere. Alternative: trailing but pinned to the viewport edge, which costs a sticky column.
D-17 | Milestone markers sit in their own lane above the bands, not on them. | Inverted triangles drawn on the bands landed on top of the period labels, and on a busy row the two fought for the same pixels. |  | The markers occupy a thin lane above each row's band. Alternative: draw them on the bands and drop the in-band labels, which trades one legibility problem for another.

## 03_Deferred
Deliberately not in the prototype
So their absence is not read as an oversight.
Not shown | Why
Any loading, calculation, filtering or export behaviour | Task 3.1 is design only. The figures shown are a fixed snapshot computed in Python and baked into the markup. The controls are real controls; nothing is wired behind them.
Exact spacing, type scale and final colour values | Fixed at task 3.3, once the components are agreed. The period hues are the exception - they now carry meaning, so they were settled here.
Keyboard shortcuts and full accessibility pass | Reviewed against the working prototype at task 3.3, where they can be tried rather than described.
Row virtualisation at the target volume | Specified (X-04, REQ-DSH-09) but not built: the prototype shows 9 rows of 62, where virtualisation would be invisible. It is a Step 4 concern.
The validation findings report itself | Specified on sheet 04 of the specification; the banner that opens it is in the prototype.
NO LONGER DEFERRED - hover tooltips | v0.3 deferred the tooltip layer to code generation. O-06 and O-10 both depend on it, so it is built and reviewable now (X-05).

## 04_Change_Log
What your review changed outside this document
Two components could not be satisfied by design alone - they asked for behaviour the plan did not require. Those became requirements.
Item | Change | Raised by | What it says now | Priority | Carried in
REQ-DSH-11 | NEW | G-07 | The application presents the standing assumptions - standard period weights, role factors, configuration and value lists - on their own tab, without the user opening the workbook. | Must | Plan v1.6, change R-09
REQ-IMP-11 | NEW | P-01, S-01 | A new row can be inserted into any editable table, immediately below the row the user acts on, and is validated on entry like any other edit. | Must | Plan v1.6, change R-09
REQ-DSH-05 | REWORDED | O-03 | The filter set now names clinical phase, and no longer implies the display unit is a filter. | Must | Plan v1.6, change R-09
REQ-IMP-05 | REWORDED | G-02 | The loaded-file stamp carries its time zone. | Should | Plan v1.6, change R-09
Specification sheet 06 | UPDATED | all nine | Tab 4 specified; filter set, load stamp, insert-row behaviour, timeline colour rule, tooltip content and edit-counter wording all restated. | - | Specification v0.5
Design decision D-06 | SUPERSEDED | O-10 | Timeline colour moves from weight to period name; weight becomes a lightness step within the hue. | - | Sheet 02 of this document
Nothing else in the plan or specification moved. Everything else you asked for was a design change the existing requirements already permitted.

## 05_Round3
Review round 3 — three items
Raised after prototype v0.4. All three applied in v0.5.
# | Area | What you raised (verbatim) | What was done | Carried in
1 | Data model | Weight of Role factors should be given by Role & Project type & Clinical phase & Periods. Update all relevant outputs (plan, specification, sourcedata template, dummy test sourcedata file, prototype, UI_Component_List). | Applied as plan change R-10, and it is a genuine gain: a role's burden is not flat across a project, and the dummy data now shows the database programmer peaking at start-up and the analyst at lock. RoleFactor gains clinical_phase and period_name; the key becomes all four columns; the sheet grows from 13 rows to 249; schema version steps 3 to 4. Every output listed was regenerated. TWO COSTS, both stated rather than hidden. (a) 249 rows is a large table to maintain by hand. (b) RoleFactor now varies over the same three dimensions as PeriodWeightStandard and the two multiply, so editing both for the same reason double-counts - see D-19 and specification sheet 05. A new rule, V-23, catches a factor missing for a period an assignment actually spans, which would otherwise drop that stretch silently to 1.00. | Plan v1.7 (R-10), spec v0.6, template v1.5, dummy v1.6, prototype v0.5
2 | Layout | Apply scroll bar on the bottom of all sections of 'Source data (project)' / 'Source data (person)' / 'General assumptions'. Some sections have problems that table size over the fixed section site. (e.g. Periods of 'Source data (project)', Assignments and Weight overrides of 'Source data (person)') | Applied. Six tables were rendering outside their panels. The v0.4 rule bounded WIDTH only, which is why the ones you named still overflowed - Periods is too wide for a half-width panel, Assignments and Weight overrides are too tall. Each table now sits in a region bounded in both directions, and keeps its header row visible while scrolled. Checked by measuring the document scroll width against the viewport width: equal, so nothing overflows sideways. | Prototype v0.5, component X-01, spec v0.6 sheet 06
3 | Layout | Insert row button should be added, however only column is added now but no button to add new row is added under 'Insert' column. It looks like wrong information. Check all tables of the 'General assumptions'. | Fixed, and it was worse than you saw. The role-factor table had an 'insert' HEADER with no cells beneath it, so every row of that table was a column out of alignment - the note you read as wrong information was wrong. The value-lists table had the opposite fault: insert buttons with no header. Both came from one careless edit in v0.4 that moved the control to the front of the row and missed these two tables. Now: role factors are reference matrices with no insert control at all, value lists are explicitly read-only, and Config keeps its per-row control. | Prototype v0.5, components A-02, A-02b, A-04
Item 3 is the kind of fault a rendered screenshot catches and a code diff does not. The prototype is now rendered and inspected on every build for exactly that reason.

## 06_Round4
Review round 4 — two items
Raised after prototype v0.5. Both applied in v0.6. The second follows from the first.
# | Area | What you raised (verbatim) | What was done | Carried in
1 | Data model | Change period name for conduct as 'Conduct (interim)' and 'Conduct (final)' in order to distinguish multiple periods. Conduct (interim): if the milestone has interim DB lock and is before interim DB lock then use this period name. Conduct (final): if the milestone is after interim DB lock or the project has only final DB lock without interim DB lock, use this period name. | Applied as plan change R-11. Your rule maps exactly onto the derivation already in the specification: the split branch runs only when an interim DB lock exists, so 'Conduct (interim)' is emitted only there, and every other conduct stretch - including the single one of a project with no interim lock - is 'Conduct (final)'. The clinical period set grows from six names to seven. PeriodWeightStandard grows 48 to 56 rows and RoleFactor 249 to 289; both new entries carry the same weights the single 'Conduct' did, so this RENAMES without reweighting - the dummy dataset returns 189 over-allocated person-months before and after, which is the evidence. Schema 4 to 5: no column changed, but the period_name value set did, so a v4 file's 'Conduct' rows would now fail V-15. | Plan v1.8 (R-11), spec v0.7, template v1.6, dummy v1.7, prototype v0.6
2 | Data model | Change key of ProjectPeriod to 'project_id + period_name' because now the period table has a unique period name list. Use the changed key to map relative information. | Applied, and this is the payoff of item 1. period_name is now unique within a project, so (project_id, period_name) is a natural key and period_seq goes back to carrying ORDER rather than identity. V-18 becomes a plain uniqueness check on the name - proved by renaming one row in a copy of the dummy file and confirming the error. Three things simplify as a result: the ProjectPeriod key loses period_start, which was only ever there to tell two identically-named rows apart; decision D-15 is superseded; and REQ-DSH-10's display numbering becomes unnecessary, since a name alone now identifies a period on screen. The numbering code is kept as a guard, not as the mechanism. | Plan v1.8 (R-11), spec v0.7 sheets 03 and 04, component X-03, decision D-15
A note on what this change is worth: the previous design carried the repeated name through four places - a composite key, a validation rule, a display numbering rule and a requirement. Naming the two stretches apart removes the need for all four. It is the cheaper design and it was available from the start; D-15 argued against it on a lookup objection that turned out to be answerable.

## 07_Round5
Review round 5 — a question, not a change
The key was right. Checking it found two rules that were not implemented.
# | Area | What you raised (verbatim) | What was done | Carried in
1 | Data model | In the programming specification, key setting of 'PersonPeriodWeight' is 'assignment_id + period_start'. My opinion is why period_start is needed as key. 'assignment_id' is unique in the 'PersonPeriodWeight' and 'Assignment' sheets. Explain me that point. If my opinion isn't hurting other data consistency then change the key setting of 'PersonPeriodWeight' as 'assignment_id' only. | NOT CHANGED, and here is why. assignment_id is unique in Assignment - it is that sheet's primary key. It was also unique in PersonPeriodWeight, but only because the dummy file happened to carry one window per assignment; that is a property of the sample, not of the schema. PersonPeriodWeight is a CHILD of Assignment and one assignment may carry SEVERAL non-overlapping windows - a spell of leave, back to normal, then a peak - which is what REQ-PSN-05's 'overrides' (plural), V-06's assignment-window clause and the data model's 'periods within one assignment must not overlap' all assume. Keying on assignment_id alone would cap it at one window, and the second spell would need a second Assignment row, fragmenting one person-project-role across rows that are not really different assignments. Your condition - 'if it isn't hurting other data consistency' - is therefore not met, so the key stays as it is. Say the word if you want the single-window model anyway; it is a small change and the cost is exactly the one described above. | Specification v0.8 sheet 03 now carries this reasoning
2 | Validation | (not raised - found while answering item 1) | Two rules were specified but never implemented, and the question is what exposed them. (a) V-06 says periods within one project AND within one assignment must not overlap. Only the project half ran, so two overlapping override windows passed silently and the weight that applied in the shared months depended on the order the rows happened to sit in the file. (b) Nothing checked that a PersonPeriodWeight row pointed at a real assignment, so an orphan override was accepted and then ignored without a word - the typed weight simply never applied. Both are now in the reference implementation, the second as new rule V-24, and both were proved to fire against deliberately broken copies of the dummy file. The fixture itself is the root cause: it only ever had one window per assignment, so the multi-window path was never exercised. It now carries an assignment with two. | Plan v1.9 (R-12), spec v0.8, dummy v1.8
Worth noting for its own sake: a question about a key found two silent-wrong-answer bugs. Neither was reachable by reading the code, because both were absences - a rule that was written down and never built.