## Slide 1
PRAP · how the numbers are made
Anatomy of an FTE
Every figure the application draws is a sum of one small multiplication, done once per assignment per month. This is that multiplication, where each of its numbers comes from, and what happens when one is missing.
FTE = period weight × (role factor ÷ sharers) × person weight × coverage
Engine core/06_calculate.js
Schema 8
1.00 FTE 160 h / month
Notes: Every number in PRAP comes from one multiplication per assignment per month. Everything else on screen is those numbers added up.

## Slide 2
One multiplication, four numbers
Worked out once for every assignment, in every month that assignment touches.
FTE =
period weight
×
role factor ÷ sharers
×
person weight
×
coverage
period weight
How heavy this stretch of the project is.
ProjectPeriod
role factor ÷ sharers
What the role costs, split between its holders.
RoleFactor
person weight
How much of that person this project has.
Assignment / override
coverage
How much of the calendar month is covered.
computed
Nothing else enters it. There is no fifth hidden factor and no rounding step — and capacity_fte is not in the multiplication at all. It is what a person’s load is later compared against, never something it is scaled by.
Notes: All four terms are resolved for the month, not once per assignment. That is what lets figures move on their own when a period boundary is crossed or a second person joins a role.

## Slide 3
First: which months does this assignment touch?
Resolved before any of the four terms — it decides which months exist at all.
00
Both assignment dates are optional
A blank date means the project’s own, so an assignment with neither runs for the whole project — which is what most assignments are. Fill them in only for a partial involvement.
The project’s own window is its PERIODS
Earliest period_start to latest period_end. Not its milestones — several of those mark moments inside the run rather than its edges, and taking the window from them stretched projects across months belonging to no period.
If it finds nothing the project keeps its own typed start and end dates, and V-12 reports that it has no periods.
Coverage, once the window is known
The fraction of that calendar month’s days the window actually covers.
A full month
1.0000
Ends 1 June
1 ÷ 30 = 0.0333
This is what makes a part-month sharer contribute less with no special case anywhere: their coverage is already smaller.
Notes: REQ-CAL-15 and REQ-CAL-17. The periods are the project.

## Slide 4
Period weight
How heavy this stretch of the project is.
FTE =
period weight
×
role factor ÷ sharers
×
person weight
×
coverage
01
The period whose span contains the 1st of that month supplies its weight.
ProjectPeriod.weight
A project’s periods are its own rows — derived from its milestones for a clinical trial, entered by hand for an ‘Others’ project.
If it finds nothing weight 1.00, and V-12 reports the gap. 1.00 is not a neutral choice — it silently costs that month at full rate.
The one that surprises people
PeriodWeightStandard is not read here.
It is the assumption table the derivation uses to fill in ProjectPeriod.weight. Once a period row exists, the calculation reads that row.
Which is why an ‘Others’ project calculates perfectly well with no standard rows anywhere.
Notes: Standards fill in the period rows; the calculation reads the period rows.

## Slide 5
Role factor
What the ROLE costs the project — not what each person holding it costs.
FTE =
period weight
×
role factor ÷ sharers
×
person weight
×
coverage
02
Looked up on the full composition, in two steps: the project’s own work scope first, then the row whose work_scope_type is empty, which stands for every scope.
project_type · clinical_phase · work_scope_type · period_name · role_name
If it finds nothing factor 1.00, and V-23 names the exact combination and counts the person-months it affected.
Then: absorption
If another role names this one in absorbed_by and nobody at all holds it that month, its factor is added here. One hop only.
Lead data manager, alone on a trial
1.23 + 0.49 = 1.72
own factor, plus the absent Clinical Data Associator’s
Delivered as ROWS, not as names in the program — empty the column and nothing is absorbed.
Notes: REQ-CAL-16. A trial run without a CDA still has the data to handle, and it lands on the lead data manager.

## Slide 6
Sharers, and person weight
One divides the role’s cost; the other says how much of the person there is.
FTE =
period weight
×
role factor ÷ sharers
×
person weight
×
coverage
03
Sharers
How many distinct people hold that same role, on that same project, in that month. The factor is divided between them.
0.78 ÷ 2 = 0.39 each
Per month, so one of two sharers leaving in June returns July to a full share by itself. By people, so one person on two rows is one person and does not halve their own load.
04
Person weight
If a PersonPeriodWeight window covers the 1st of the month, its weight_override is used; otherwise the assignment’s own person_weight.
The override REPLACES the weight for its months — it does not multiply it. That is the single thing about this sheet most often got wrong.
If it finds nothing a blank weight is 0.00 — the row contributes nothing.
Notes: A weight is a fact only the planner knows; guessing 1.00 would invent load.

## Slide 7
Worked through: Kim S., February 2027
PSN-001 is on six projects that month. Each row is one assignment’s multiplication.
Project | Period that month | Period wt | Role factor | ÷ sharers | Person wt | Cov. | FTE
PRJ-001 Biosimilar (Healthy) Ph1 | Close-out (final) | 0.95 | 0.76 | 1 | 0.31 | 1.00 | 0.2238
PRJ-002 Biosimilar (Patient) Ph2 | Conduct (interim) | 1.01 | 0.78 | 2 | 0.75 | 1.00 | 0.2954
PRJ-003 NewDrug CT Ph3 | Conduct (final) | 1.38 | 0.84 | 1 | 0.31 | 1.00 | 0.3594
PRJ-005 Biosimilar (Patient) Ph1 | Conduct (interim) | 0.92 | 0.74 | 1 | 0.26 | 1.00 | 0.1770
PRJ-007 Biosimilar (Healthy) Ph3 | Conduct (interim) | 0.82 | 0.84 | 1 | 0.29 | 1.00 | 0.1998
PRJ-009 Others — CDISC migration | Planning (hand-entered) | 0.80 | 1.10 | 1 | 0.39 | 1.00 | 0.3432
Monthly personal FTE — PSN-001, Feb 2027
1.5986
Read one row across. PRJ-002 is 1.01 × (0.78 ÷ 2) × 0.75 × 1.00 = 0.2954. Its factor is halved because a second person holds Project oversight on that project that month, and its person weight comes from a PersonPeriodWeight row rather than the assignment.
PRJ-009 is an ‘Others’ project: its 0.80 was typed into ProjectPeriod, and no PeriodWeightStandard row exists for it anywhere.
Notes: Read out of the running application over the 10x10 dummy set.

## Slide 8
The two totals you actually read
The same person-months, added along different axes — which is why they can never disagree.
Monthly personal FTE
1.5986 FTE
PSN-001, Feb 2027 — the six rows on the last slide
Sum of that person’s assignments for the month, across every project. This is what the person utilisation chart plots, and what the over- and under-allocation flags are measured against — the only place capacity_fte is used.
Monthly project FTE
2.1095 FTE
PRJ-003, Feb 2027 — five people, of whom PSN-001 gave 0.3594
Sum of that project’s assignments for the month, across every person. This is what the project utilisation chart plots, stacked by person, and what the timeline band tooltips report.
Everything else is these two, filtered. Total demand is every person-month in the current filter and horizon added up. Change a filter and all of it is recomputed — none of it is stored, and none is written to the workbook.
Notes: Across its whole timeline the ten-project set comes to 346.59 FTE-months.

## Slide 9
What can move a figure
Five settings on the Config sheet. Two change the arithmetic itself.
split_shared_role_fte
default 1
moves figures
Set to 0 and each holder of a shared role is charged the whole factor instead of a share. Term 03 disappears.
absorb_unstaffed_role_factor
default 1
moves figures
Set to 0 and an unstaffed role simply costs nothing. On, its factor lands on whoever covers for it.
over_allocation_fte
default 1.50
The monthly personal FTE above which a month is flagged. Absolute — not scaled by anyone’s capacity.
under_allocation_fte / _min_months
default 0.60 / 3
The floor, and how many consecutive months below it before a run is reported. Also absolute.
fte_hours_per_month
default 160
Display only. The FTE figure times this is the hours figure; the person-months do not move.
Notes: An import takes the file's Config with it, which is why the application now names any setting an import changed.

## Slide 10
Where a figure can be quietly wrong
Three lookups fall back to 1.00 — exactly the value that makes a term vanish from a product.
V-12
A month in no period
The month is costed at full weight, 1.00, as though the period plan covered it.
V-23
A role with no factor
Names the exact composition, and counts the person-months that came out at 1.00.
V-30
A setting missing from Config
A built-in default is in force rather than the plan’s own value.
None of the three refuses your data. They are reported at full severity and the rows are kept, because a missing assumption is a fact about a document somebody else maintains — not a fault in the row you just typed. A convenient fallback is dangerous precisely because the resulting number looks exactly like an answer.
Notes: Must / conditional / incomplete: only 'must' errors refuse a row.

## Slide 11
In one line
Four numbers, once per assignment per month. Everything else is a sum.
FTE = period weight × (role factor ÷ sharers) × person weight × coverage
Every figure in this deck was read out of the running application over PRAP_SourceData_Dummy_10x10_v1.5.xlsx. The same numbers are produced independently by two Python implementations, and all 1,227 person-months of the 62-project set are compared between the four on every test run.
Notes: Four implementations: the browser engine, prap_io.py, verify_source_workbook.py, and test_app.py's own reference.