## 00_README
PRAP source data - dummy
Schema version 3. Matches PRAP_Development_Plan_v1.0.xlsx, sheet 04_Data_Model.
COLOUR KEY
Blue identifier or key column - these link the sheets together.
Green derived by formula. Do not type in these; they recalculate.
Yellow you must supply this value. The application cannot work it out.
Grey italic row an example, in the template only. Delete it before use.
SHEETS
Project one row per project.
Milestone one row per milestone. Eight standard names.
ProjectPeriod the periods each project passes through, with their weights.
PeriodWeightStandard default weights per clinical phase. Clinical trials only.
RoleFactor the roles and their relative burden, per project type.
Person one row per person.
Assignment one row per person + project + role.
PersonPeriodWeight optional windows where a person's weight differs.
Lists permitted values for every dropdown.
Config thresholds and settings.
FREE-TEXT NOTES
Every sheet carries at least one free-text column, so anything worth recording has a home:
Project note_1 .. note_5
Milestone note_1
ProjectPeriod note_1
PeriodWeightStandard note_1
RoleFactor role_note
Person note_1 .. note_5
Assignment note_1 .. note_3
PersonPeriodWeight reason
Lists note_1
Config note
Nothing in a note column affects the calculation. They are carried through import and export
unchanged, so they survive a round trip.
HOW THE CALCULATION USES THIS
monthly load = project period weight x role factor x person weight x month coverage
The result is FTE, where 1.00 FTE = 160 hours per month.
Over-allocated: a person's monthly total above 1.50 FTE.
Under-allocated: below 0.80 FTE for three or more consecutive months.
PERIODS
Clinical trial periods are derived from the milestone dates:
Before-Start-up project start, to the day before Start-up
Start-up one month before CTA submission, lasting four months
Conduct from the end of Start-up to the day before the next close-out
Close-out (interim) three months before the interim DB lock, to that lock
Conduct (again) from the interim DB lock to the day before Close-out (final)
Close-out (final) three months before the final DB lock, to that lock
After Close-out (final) the inspection activity that follows the final DB lock
Where 'Protocol (v1)' is recorded, Before-Start-up ends on it and Start-up begins the day after.
Where 'First SIV' (or 'FPI') is recorded, Start-up ends on it instead of running a fixed four
months. A recorded milestone always beats the month-offset fallback.
'Conduct' therefore appears TWICE where a trial has an interim DB lock. period_seq keeps
the two apart. A period squeezed to nothing by a tight timeline is simply omitted.
'Inspection' is the one milestone that may be recorded SEVERAL TIMES for a project. Only
inspections dated AFTER the final DB lock open the last period; an earlier one stays a marker.
'Others' projects have no milestones. Their period dates and weights are both typed in.
ADDING A PERMITTED VALUE
Insert a row inside that list's block on the Lists sheet, so the block stays contiguous -
the dropdowns read a range, not a scattered set of rows.
WHAT IS IN THIS FILE
62 projects 50 clinical trials (PRJ-001..050) + 12 'Others' (PRJ-051..062)
20 people PSN-001..020, including two part-timers (PSN-004 at 0.80,
PSN-020 at 0.60 capacity)
289 assignments, 372 milestones, 308 periods, spanning 73 months
Trials are spread evenly across Phase 1-4 and staggered from 2025 to 2031.
WHAT IT DEMONSTRATES
- 30 trials carry an interim DB lock, so each has TWO 'Conduct' stretches and two
close-out periods. The other 20 run Conduct once.
- 12 trials record an 'Inspection' after the final DB lock and so carry the seventh
period, 'After Close-out (final)'.
- The 12 'Others' projects have hand-entered periods and no milestones.
- PSN-001 is pushed above the 1.50 FTE ceiling for a stretch in 2026-27.
- PSN-020 is a part-timer (0.60 FTE) carrying one light assignment, so an under-allocation run
is raised. With the floor now at 0.60 (S2-05) they CAN clear it, but only at full
utilisation - V-22 warns if anyone is recorded below the floor and so could never clear it.
- Two assignments carry PersonPeriodWeight overrides.
Typical load is around 0.93 FTE per person-month (median). Months at the very start
and end of the 73-month span are naturally light, since few projects overlap there.
The weights and role factors here are ILLUSTRATIVE, so the numbers can be exercised.
Replace them with your own before drawing any conclusion from the output.

## Project
project_id | project_name | project_type | project_category | clinical_phase | outsourcing_type | EDC_setup | DataReviewSystem_setup | RBQM_setup | DM_conduct | EDC_system | DataReviewSystem | RBQM_system | planned_member_count | start_date | end_date | total_period_months | status | note_1 | note_2 | note_3 | note_4 | note_5
PRJ-001 | ONV-101 Phase 1 | NewDrug CT | Onvelaris | Phase 1 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2027-12-01 | 2030-05-31 |  | Active
PRJ-002 | CAR-102 Phase 2 | NewDrug CT | Cardexa | Phase 2 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 8 | 2025-10-01 | 2027-03-31 |  | Active
PRJ-003 | NEU-103 Phase 3 | Biosimilar CT | Neurexa | Phase 3 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 4 | 2026-03-01 | 2028-08-31 |  | Active
PRJ-004 | REN-104 Phase 4 | NewDrug CT | Renvia | Phase 4 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 7 | 2026-12-01 | 2028-05-31 |  | On hold
PRJ-005 | HEP-105 Phase 1 | NewDrug CT | Hepatiq | Phase 1 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 7 | 2025-05-01 | 2027-04-30 |  | Completed
PRJ-006 | IMM-106 Phase 2 | Biosimilar CT | Immunex | Phase 2 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 7 | 2027-05-01 | 2029-04-30 |  | Planned
PRJ-007 | OST-107 Phase 3 | NewDrug CT | Osteva | Phase 3 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2027-11-01 | 2030-04-30 |  | Active
PRJ-008 | PUL-108 Phase 4 | NewDrug CT | Pulmora | Phase 4 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 8 | 2026-11-01 | 2028-10-31 |  | Active
PRJ-009 | DER-109 Phase 1 | Biosimilar CT | Dermaline | Phase 1 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 3 | 2026-04-01 | 2028-03-31 |  | Active
PRJ-010 | GLY-110 Phase 2 | NewDrug CT | Glycora | Phase 2 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 7 | 2026-09-01 | 2028-08-31 |  | On hold
PRJ-011 | ONV-111 Phase 3 | NewDrug CT | Onvelaris | Phase 3 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 6 | 2026-03-01 | 2027-08-31 |  | Completed
PRJ-012 | CAR-112 Phase 4 | Biosimilar CT | Cardexa | Phase 4 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 3 | 2027-12-01 | 2030-11-30 |  | Planned
PRJ-013 | NEU-113 Phase 1 | NewDrug CT | Neurexa | Phase 1 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 6 | 2025-11-01 | 2027-04-30 |  | Active
PRJ-014 | REN-114 Phase 2 | NewDrug CT | Renvia | Phase 2 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 5 | 2026-06-01 | 2027-11-30 |  | Active
PRJ-015 | HEP-115 Phase 3 | Biosimilar CT | Hepatiq | Phase 3 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 6 | 2027-07-01 | 2030-06-30 |  | Active
PRJ-016 | IMM-116 Phase 4 | NewDrug CT | Immunex | Phase 4 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 6 | 2026-08-01 | 2028-01-31 |  | On hold
PRJ-017 | OST-117 Phase 1 | NewDrug CT | Osteva | Phase 1 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 3 | 2028-03-01 | 2031-02-28 |  | Completed
PRJ-018 | PUL-118 Phase 2 | Biosimilar CT | Pulmora | Phase 2 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 6 | 2025-11-01 | 2028-04-30 |  | Planned
PRJ-019 | DER-119 Phase 3 | NewDrug CT | Dermaline | Phase 3 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2026-03-01 | 2029-08-31 |  | Active
PRJ-020 | GLY-120 Phase 4 | NewDrug CT | Glycora | Phase 4 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 3 | 2025-06-01 | 2028-11-30 |  | Active
PRJ-021 | ONV-121 Phase 1 | Biosimilar CT | Onvelaris | Phase 1 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 5 | 2025-09-01 | 2027-02-28 |  | Active
PRJ-022 | CAR-122 Phase 2 | NewDrug CT | Cardexa | Phase 2 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 6 | 2026-02-01 | 2028-01-31 |  | On hold
PRJ-023 | NEU-123 Phase 3 | NewDrug CT | Neurexa | Phase 3 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 5 | 2026-12-01 | 2028-05-31 |  | Completed
PRJ-024 | REN-124 Phase 4 | Biosimilar CT | Renvia | Phase 4 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 7 | 2025-12-01 | 2028-05-31 |  | Planned
PRJ-025 | HEP-125 Phase 1 | NewDrug CT | Hepatiq | Phase 1 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2027-10-01 | 2030-03-31 |  | Active
PRJ-026 | IMM-126 Phase 2 | NewDrug CT | Immunex | Phase 2 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 4 | 2027-03-01 | 2030-02-28 |  | Active
PRJ-027 | OST-127 Phase 3 | Biosimilar CT | Osteva | Phase 3 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 8 | 2027-07-01 | 2029-12-31 |  | Active
PRJ-028 | PUL-128 Phase 4 | NewDrug CT | Pulmora | Phase 4 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 4 | 2025-12-01 | 2029-05-31 |  | On hold
PRJ-029 | DER-129 Phase 1 | NewDrug CT | Dermaline | Phase 1 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 5 | 2027-07-01 | 2030-06-30 |  | Completed
PRJ-030 | GLY-130 Phase 2 | Biosimilar CT | Glycora | Phase 2 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 4 | 2025-09-01 | 2027-08-31 |  | Planned
PRJ-031 | ONV-131 Phase 3 | NewDrug CT | Onvelaris | Phase 3 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 4 | 2027-04-01 | 2029-03-31 |  | Active
PRJ-032 | CAR-132 Phase 4 | NewDrug CT | Cardexa | Phase 4 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 3 | 2028-05-01 | 2029-10-31 |  | Active
PRJ-033 | NEU-133 Phase 1 | Biosimilar CT | Neurexa | Phase 1 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 5 | 2027-02-01 | 2028-07-31 |  | Active
PRJ-034 | REN-134 Phase 2 | NewDrug CT | Renvia | Phase 2 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 6 | 2027-10-01 | 2030-09-30 |  | On hold
PRJ-035 | HEP-135 Phase 3 | NewDrug CT | Hepatiq | Phase 3 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 4 | 2025-01-01 | 2028-06-30 |  | Completed
PRJ-036 | IMM-136 Phase 4 | Biosimilar CT | Immunex | Phase 4 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 5 | 2025-10-01 | 2028-03-31 |  | Planned
PRJ-037 | OST-137 Phase 1 | NewDrug CT | Osteva | Phase 1 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2026-02-01 | 2028-07-31 |  | Active
PRJ-038 | PUL-138 Phase 2 | NewDrug CT | Pulmora | Phase 2 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 6 | 2025-11-01 | 2028-10-31 |  | Active
PRJ-039 | DER-139 Phase 3 | Biosimilar CT | Dermaline | Phase 3 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 6 | 2026-09-01 | 2030-02-28 |  | Active
PRJ-040 | GLY-140 Phase 4 | NewDrug CT | Glycora | Phase 4 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 6 | 2025-08-01 | 2027-01-31 |  | On hold
PRJ-041 | ONV-141 Phase 1 | NewDrug CT | Onvelaris | Phase 1 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 8 | 2027-01-01 | 2030-06-30 |  | Completed
PRJ-042 | CAR-142 Phase 2 | Biosimilar CT | Cardexa | Phase 2 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 6 | 2027-04-01 | 2029-09-30 |  | Planned
PRJ-043 | NEU-143 Phase 3 | NewDrug CT | Neurexa | Phase 3 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2027-07-01 | 2030-06-30 |  | Active
PRJ-044 | REN-144 Phase 4 | NewDrug CT | Renvia | Phase 4 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 4 | 2025-12-01 | 2027-05-31 |  | Active
PRJ-045 | HEP-145 Phase 1 | Biosimilar CT | Hepatiq | Phase 1 | Full outsourcing | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 5 | 2026-03-01 | 2027-08-31 |  | Active
PRJ-046 | IMM-146 Phase 2 | NewDrug CT | Immunex | Phase 2 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 7 | 2026-05-01 | 2028-10-31 |  | On hold
PRJ-047 | OST-147 Phase 3 | NewDrug CT | Osteva | Phase 3 | Full In-house | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 6 | 2026-12-01 | 2029-11-30 |  | Completed
PRJ-048 | PUL-148 Phase 4 | Biosimilar CT | Pulmora | Phase 4 | Full outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 7 | 2027-10-01 | 2030-09-30 |  | Planned
PRJ-049 | DER-149 Phase 1 | NewDrug CT | Dermaline | Phase 1 | Partial outsourcing | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 4 | 2027-12-01 | 2029-11-30 |  | Active
PRJ-050 | GLY-150 Phase 2 | NewDrug CT | Glycora | Phase 2 | Full In-house | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 8 | 2025-03-01 | 2027-08-31 |  | Active
PRJ-051 | CDISC library migration | Others |  |  | Full outsourcing | [7 empty] | 3 | 2027-11-01 | 2029-04-30 |  | Completed
PRJ-052 | eTMF rollout | Others |  |  | Partial outsourcing | [7 empty] | 4 | 2027-12-01 | 2028-08-31 |  | Planned
PRJ-053 | EDC vendor evaluation | Others |  |  | Full In-house | [7 empty] | 3 | 2027-01-01 | 2027-12-31 |  | Active
PRJ-054 | SDTM automation | Others |  |  | Full outsourcing | [7 empty] | 3 | 2027-04-01 | 2028-09-30 |  | Active
PRJ-055 | Risk dashboard build | Others |  |  | Partial outsourcing | [7 empty] | 5 | 2027-05-01 | 2028-01-31 |  | Completed
PRJ-056 | Archive remediation | Others |  |  | Full In-house | [7 empty] | 3 | 2025-10-01 | 2027-03-31 |  | Planned
PRJ-057 | CDR pilot | Others |  |  | Full outsourcing | [7 empty] | 4 | 2027-12-01 | 2028-05-31 |  | Active
PRJ-058 | Metadata repository | Others |  |  | Partial outsourcing | [7 empty] | 4 | 2025-08-01 | 2027-01-31 |  | Active
PRJ-059 | eConsent rollout | Others |  |  | Full In-house | [7 empty] | 5 | 2028-01-01 | 2028-12-31 |  | Completed
PRJ-060 | Query analytics | Others |  |  | Full outsourcing | [7 empty] | 3 | 2028-06-01 | 2029-02-28 |  | Planned
PRJ-061 | Training refresh | Others |  |  | Partial outsourcing | [7 empty] | 2 | 2026-07-01 | 2027-12-31 |  | Active
PRJ-062 | SOP revision | Others |  |  | Full In-house | [7 empty] | 4 | 2027-02-01 | 2028-07-31 |  | Active

## Milestone
project_id | project_name | milestone_name | milestone_date | milestone_seq | note_1
PRJ-001 |  | Protocol (v1) | 2028-01-01 | 1
PRJ-001 |  | CTA submission | 2028-03-01 | 2
PRJ-001 |  | First SIV | 2028-07-01 | 3
PRJ-001 |  | LPI | 2029-06-01 | 4
PRJ-001 |  | interim DB lock cut-off | 2029-06-01 | 5
PRJ-001 |  | interim DB lock | 2029-08-01 | 6
PRJ-001 |  | final DB lock cut-off | 2030-02-01 | 7
PRJ-001 |  | final DB lock | 2030-04-01 | 8
PRJ-002 |  | Protocol (v1) | 2025-11-01 | 1
PRJ-002 |  | CTA submission | 2026-01-01 | 2
PRJ-002 |  | First SIV | 2026-05-01 | 3
PRJ-002 |  | LPI | 2026-08-01 | 4
PRJ-002 |  | interim DB lock cut-off | 2026-09-01 | 5
PRJ-002 |  | interim DB lock | 2026-10-01 | 6
PRJ-002 |  | final DB lock cut-off | 2026-12-01 | 7
PRJ-002 |  | final DB lock | 2027-02-01 | 8
PRJ-003 |  | Protocol (v1) | 2026-04-01 | 1
PRJ-003 |  | CTA submission | 2026-06-01 | 2
PRJ-003 |  | First SIV | 2026-10-01 | 3
PRJ-003 |  | LPI | 2027-09-01 | 4
PRJ-003 |  | final DB lock cut-off | 2028-05-01 | 5
PRJ-003 |  | final DB lock | 2028-07-01 | 6
PRJ-004 |  | Protocol (v1) | 2027-01-01 | 1
PRJ-004 |  | CTA submission | 2027-03-01 | 2
PRJ-004 |  | First SIV | 2027-07-01 | 3
PRJ-004 |  | LPI | 2027-10-01 | 4
PRJ-004 |  | final DB lock cut-off | 2028-02-01 | 5
PRJ-004 |  | final DB lock | 2028-04-01 | 6
PRJ-004 |  | Inspection | 2028-06-01 | 7 | Regulatory inspection
PRJ-005 |  | Protocol (v1) | 2025-06-01 | 1
PRJ-005 |  | CTA submission | 2025-08-01 | 2
PRJ-005 |  | First SIV | 2025-12-01 | 3
PRJ-005 |  | LPI | 2026-07-01 | 4
PRJ-005 |  | interim DB lock cut-off | 2026-07-01 | 5
PRJ-005 |  | interim DB lock | 2026-09-01 | 6
PRJ-005 |  | final DB lock cut-off | 2027-01-01 | 7
PRJ-005 |  | final DB lock | 2027-03-01 | 8
PRJ-006 |  | Protocol (v1) | 2027-06-01 | 1
PRJ-006 |  | CTA submission | 2027-08-01 | 2
PRJ-006 |  | First SIV | 2027-12-01 | 3
PRJ-006 |  | LPI | 2028-07-01 | 4
PRJ-006 |  | interim DB lock cut-off | 2028-07-01 | 5
PRJ-006 |  | interim DB lock | 2028-09-01 | 6
PRJ-006 |  | final DB lock cut-off | 2029-01-01 | 7
PRJ-006 |  | final DB lock | 2029-03-01 | 8
PRJ-007 |  | Protocol (v1) | 2027-12-01 | 1
PRJ-007 |  | CTA submission | 2028-02-01 | 2
PRJ-007 |  | First SIV | 2028-06-01 | 3
PRJ-007 |  | LPI | 2029-05-01 | 4
PRJ-007 |  | interim DB lock cut-off | 2029-05-01 | 5
PRJ-007 |  | interim DB lock | 2029-07-01 | 6
PRJ-007 |  | final DB lock cut-off | 2030-01-01 | 7
PRJ-007 |  | final DB lock | 2030-03-01 | 8
PRJ-008 |  | Protocol (v1) | 2026-12-01 | 1
PRJ-008 |  | CTA submission | 2027-02-01 | 2
PRJ-008 |  | First SIV | 2027-06-01 | 3
PRJ-008 |  | LPI | 2028-01-01 | 4
PRJ-008 |  | final DB lock cut-off | 2028-07-01 | 5
PRJ-008 |  | final DB lock | 2028-09-01 | 6
PRJ-008 |  | Inspection | 2028-11-01 | 7 | Regulatory inspection
PRJ-009 |  | Protocol (v1) | 2026-05-01 | 1
PRJ-009 |  | CTA submission | 2026-07-01 | 2
PRJ-009 |  | First SIV | 2026-11-01 | 3
PRJ-009 |  | LPI | 2027-06-01 | 4
PRJ-009 |  | final DB lock cut-off | 2027-12-01 | 5
PRJ-009 |  | final DB lock | 2028-02-01 | 6
PRJ-010 |  | Protocol (v1) | 2026-10-01 | 1
PRJ-010 |  | CTA submission | 2026-12-01 | 2
PRJ-010 |  | First SIV | 2027-04-01 | 3
PRJ-010 |  | LPI | 2027-11-01 | 4
PRJ-010 |  | interim DB lock cut-off | 2027-11-01 | 5
PRJ-010 |  | interim DB lock | 2028-01-01 | 6
PRJ-010 |  | final DB lock cut-off | 2028-05-01 | 7
PRJ-010 |  | final DB lock | 2028-07-01 | 8
PRJ-011 |  | Protocol (v1) | 2026-04-01 | 1
PRJ-011 |  | CTA submission | 2026-06-01 | 2
PRJ-011 |  | First SIV | 2026-10-01 | 3
PRJ-011 |  | LPI | 2027-01-01 | 4
PRJ-011 |  | interim DB lock cut-off | 2027-02-01 | 5
PRJ-011 |  | interim DB lock | 2027-03-01 | 6
PRJ-011 |  | final DB lock cut-off | 2027-05-01 | 7
PRJ-011 |  | final DB lock | 2027-07-01 | 8
PRJ-012 |  | Protocol (v1) | 2028-01-01 | 1
PRJ-012 |  | CTA submission | 2028-03-01 | 2
PRJ-012 |  | First SIV | 2028-07-01 | 3
PRJ-012 |  | LPI | 2029-09-01 | 4
PRJ-012 |  | interim DB lock cut-off | 2029-10-01 | 5
PRJ-012 |  | interim DB lock | 2029-12-01 | 6
PRJ-012 |  | final DB lock cut-off | 2030-08-01 | 7
PRJ-012 |  | final DB lock | 2030-10-01 | 8
PRJ-012 |  | Inspection | 2030-12-01 | 9 | Regulatory inspection
PRJ-013 |  | Protocol (v1) | 2025-12-01 | 1
PRJ-013 |  | CTA submission | 2026-02-01 | 2
PRJ-013 |  | First SIV | 2026-06-01 | 3
PRJ-013 |  | LPI | 2026-09-01 | 4
PRJ-013 |  | final DB lock cut-off | 2027-01-01 | 5
PRJ-013 |  | final DB lock | 2027-03-01 | 6
PRJ-014 |  | Protocol (v1) | 2026-07-01 | 1
PRJ-014 |  | CTA submission | 2026-09-01 | 2
PRJ-014 |  | First SIV | 2027-01-01 | 3
PRJ-014 |  | LPI | 2027-04-01 | 4
PRJ-014 |  | final DB lock cut-off | 2027-08-01 | 5
PRJ-014 |  | final DB lock | 2027-10-01 | 6
PRJ-015 |  | Protocol (v1) | 2027-08-01 | 1
PRJ-015 |  | CTA submission | 2027-10-01 | 2
PRJ-015 |  | First SIV | 2028-02-01 | 3
PRJ-015 |  | LPI | 2029-04-01 | 4
PRJ-015 |  | interim DB lock cut-off | 2029-05-01 | 5
PRJ-015 |  | interim DB lock | 2029-07-01 | 6
PRJ-015 |  | final DB lock cut-off | 2030-03-01 | 7
PRJ-015 |  | final DB lock | 2030-05-01 | 8
PRJ-016 |  | Protocol (v1) | 2026-09-01 | 1
PRJ-016 |  | CTA submission | 2026-11-01 | 2
PRJ-016 |  | First SIV | 2027-03-01 | 3
PRJ-016 |  | LPI | 2027-06-01 | 4
PRJ-016 |  | interim DB lock cut-off | 2027-07-01 | 5
PRJ-016 |  | interim DB lock | 2027-08-01 | 6
PRJ-016 |  | final DB lock cut-off | 2027-10-01 | 7
PRJ-016 |  | final DB lock | 2027-12-01 | 8
PRJ-016 |  | Inspection | 2028-02-01 | 9 | Regulatory inspection
PRJ-017 |  | Protocol (v1) | 2028-04-01 | 1
PRJ-017 |  | CTA submission | 2028-06-01 | 2
PRJ-017 |  | First SIV | 2028-10-01 | 3
PRJ-017 |  | LPI | 2029-12-01 | 4
PRJ-017 |  | interim DB lock cut-off | 2030-01-01 | 5
PRJ-017 |  | interim DB lock | 2030-03-01 | 6
PRJ-017 |  | final DB lock cut-off | 2030-11-01 | 7
PRJ-017 |  | final DB lock | 2031-01-01 | 8
PRJ-018 |  | Protocol (v1) | 2025-12-01 | 1
PRJ-018 |  | CTA submission | 2026-02-01 | 2
PRJ-018 |  | First SIV | 2026-06-01 | 3
PRJ-018 |  | LPI | 2027-05-01 | 4
PRJ-018 |  | final DB lock cut-off | 2028-01-01 | 5
PRJ-018 |  | final DB lock | 2028-03-01 | 6
PRJ-019 |  | Protocol (v1) | 2026-04-01 | 1
PRJ-019 |  | CTA submission | 2026-06-01 | 2
PRJ-019 |  | First SIV | 2026-10-01 | 3
PRJ-019 |  | LPI | 2028-04-01 | 4
PRJ-019 |  | final DB lock cut-off | 2029-05-01 | 5
PRJ-019 |  | final DB lock | 2029-07-01 | 6
PRJ-020 |  | Protocol (v1) | 2025-07-01 | 1
PRJ-020 |  | CTA submission | 2025-09-01 | 2
PRJ-020 |  | First SIV | 2026-01-01 | 3
PRJ-020 |  | LPI | 2027-07-01 | 4
PRJ-020 |  | interim DB lock cut-off | 2027-08-01 | 5
PRJ-020 |  | interim DB lock | 2027-10-01 | 6
PRJ-020 |  | final DB lock cut-off | 2028-08-01 | 7
PRJ-020 |  | final DB lock | 2028-10-01 | 8
PRJ-020 |  | Inspection | 2028-12-01 | 9 | Regulatory inspection
PRJ-021 |  | Protocol (v1) | 2025-10-01 | 1
PRJ-021 |  | CTA submission | 2025-12-01 | 2
PRJ-021 |  | First SIV | 2026-04-01 | 3
PRJ-021 |  | LPI | 2026-07-01 | 4
PRJ-021 |  | interim DB lock cut-off | 2026-08-01 | 5
PRJ-021 |  | interim DB lock | 2026-09-01 | 6
PRJ-021 |  | final DB lock cut-off | 2026-11-01 | 7
PRJ-021 |  | final DB lock | 2027-01-01 | 8
PRJ-022 |  | Protocol (v1) | 2026-03-01 | 1
PRJ-022 |  | CTA submission | 2026-05-01 | 2
PRJ-022 |  | First SIV | 2026-09-01 | 3
PRJ-022 |  | LPI | 2027-04-01 | 4
PRJ-022 |  | interim DB lock cut-off | 2027-04-01 | 5
PRJ-022 |  | interim DB lock | 2027-06-01 | 6
PRJ-022 |  | final DB lock cut-off | 2027-10-01 | 7
PRJ-022 |  | final DB lock | 2027-12-01 | 8
PRJ-023 |  | Protocol (v1) | 2027-01-01 | 1
PRJ-023 |  | CTA submission | 2027-03-01 | 2
PRJ-023 |  | First SIV | 2027-07-01 | 3
PRJ-023 |  | LPI | 2027-10-01 | 4
PRJ-023 |  | final DB lock cut-off | 2028-02-01 | 5
PRJ-023 |  | final DB lock | 2028-04-01 | 6
PRJ-024 |  | Protocol (v1) | 2026-01-01 | 1
PRJ-024 |  | CTA submission | 2026-03-01 | 2
PRJ-024 |  | First SIV | 2026-07-01 | 3
PRJ-024 |  | LPI | 2027-06-01 | 4
PRJ-024 |  | final DB lock cut-off | 2028-02-01 | 5
PRJ-024 |  | final DB lock | 2028-04-01 | 6
PRJ-024 |  | Inspection | 2028-06-01 | 7 | Regulatory inspection
PRJ-025 |  | Protocol (v1) | 2027-11-01 | 1
PRJ-025 |  | CTA submission | 2028-01-01 | 2
PRJ-025 |  | First SIV | 2028-05-01 | 3
PRJ-025 |  | LPI | 2029-04-01 | 4
PRJ-025 |  | interim DB lock cut-off | 2029-04-01 | 5
PRJ-025 |  | interim DB lock | 2029-06-01 | 6
PRJ-025 |  | final DB lock cut-off | 2029-12-01 | 7
PRJ-025 |  | final DB lock | 2030-02-01 | 8
PRJ-026 |  | Protocol (v1) | 2027-04-01 | 1
PRJ-026 |  | CTA submission | 2027-06-01 | 2
PRJ-026 |  | First SIV | 2027-10-01 | 3
PRJ-026 |  | LPI | 2028-12-01 | 4
PRJ-026 |  | interim DB lock cut-off | 2029-01-01 | 5
PRJ-026 |  | interim DB lock | 2029-03-01 | 6
PRJ-026 |  | final DB lock cut-off | 2029-11-01 | 7
PRJ-026 |  | final DB lock | 2030-01-01 | 8
PRJ-027 |  | Protocol (v1) | 2027-08-01 | 1
PRJ-027 |  | CTA submission | 2027-10-01 | 2
PRJ-027 |  | First SIV | 2028-02-01 | 3
PRJ-027 |  | LPI | 2029-01-01 | 4
PRJ-027 |  | interim DB lock cut-off | 2029-01-01 | 5
PRJ-027 |  | interim DB lock | 2029-03-01 | 6
PRJ-027 |  | final DB lock cut-off | 2029-09-01 | 7
PRJ-027 |  | final DB lock | 2029-11-01 | 8
PRJ-028 |  | Protocol (v1) | 2026-01-01 | 1
PRJ-028 |  | CTA submission | 2026-03-01 | 2
PRJ-028 |  | First SIV | 2026-07-01 | 3
PRJ-028 |  | LPI | 2028-01-01 | 4
PRJ-028 |  | final DB lock cut-off | 2029-02-01 | 5
PRJ-028 |  | final DB lock | 2029-04-01 | 6
PRJ-028 |  | Inspection | 2029-06-01 | 7 | Regulatory inspection
PRJ-029 |  | Protocol (v1) | 2027-08-01 | 1
PRJ-029 |  | CTA submission | 2027-10-01 | 2
PRJ-029 |  | First SIV | 2028-02-01 | 3
PRJ-029 |  | LPI | 2029-04-01 | 4
PRJ-029 |  | final DB lock cut-off | 2030-03-01 | 5
PRJ-029 |  | final DB lock | 2030-05-01 | 6
PRJ-030 |  | Protocol (v1) | 2025-10-01 | 1
PRJ-030 |  | CTA submission | 2025-12-01 | 2
PRJ-030 |  | First SIV | 2026-04-01 | 3
PRJ-030 |  | LPI | 2026-11-01 | 4
PRJ-030 |  | interim DB lock cut-off | 2026-11-01 | 5
PRJ-030 |  | interim DB lock | 2027-01-01 | 6
PRJ-030 |  | final DB lock cut-off | 2027-05-01 | 7
PRJ-030 |  | final DB lock | 2027-07-01 | 8
PRJ-031 |  | Protocol (v1) | 2027-05-01 | 1
PRJ-031 |  | CTA submission | 2027-07-01 | 2
PRJ-031 |  | First SIV | 2027-11-01 | 3
PRJ-031 |  | LPI | 2028-06-01 | 4
PRJ-031 |  | interim DB lock cut-off | 2028-06-01 | 5
PRJ-031 |  | interim DB lock | 2028-08-01 | 6
PRJ-031 |  | final DB lock cut-off | 2028-12-01 | 7
PRJ-031 |  | final DB lock | 2029-02-01 | 8
PRJ-032 |  | Protocol (v1) | 2028-06-01 | 1
PRJ-032 |  | CTA submission | 2028-08-01 | 2
PRJ-032 |  | First SIV | 2028-12-01 | 3
PRJ-032 |  | LPI | 2029-03-01 | 4
PRJ-032 |  | interim DB lock cut-off | 2029-04-01 | 5
PRJ-032 |  | interim DB lock | 2029-05-01 | 6
PRJ-032 |  | final DB lock cut-off | 2029-07-01 | 7
PRJ-032 |  | final DB lock | 2029-09-01 | 8
PRJ-032 |  | Inspection | 2029-11-01 | 9 | Regulatory inspection
PRJ-033 |  | Protocol (v1) | 2027-03-01 | 1
PRJ-033 |  | CTA submission | 2027-05-01 | 2
PRJ-033 |  | First SIV | 2027-09-01 | 3
PRJ-033 |  | LPI | 2027-12-01 | 4
PRJ-033 |  | final DB lock cut-off | 2028-04-01 | 5
PRJ-033 |  | final DB lock | 2028-06-01 | 6
PRJ-034 |  | Protocol (v1) | 2027-11-01 | 1
PRJ-034 |  | CTA submission | 2028-01-01 | 2
PRJ-034 |  | First SIV | 2028-05-01 | 3
PRJ-034 |  | LPI | 2029-07-01 | 4
PRJ-034 |  | final DB lock cut-off | 2030-06-01 | 5
PRJ-034 |  | final DB lock | 2030-08-01 | 6
PRJ-035 |  | Protocol (v1) | 2025-02-01 | 1
PRJ-035 |  | CTA submission | 2025-04-01 | 2
PRJ-035 |  | First SIV | 2025-08-01 | 3
PRJ-035 |  | LPI | 2027-02-01 | 4
PRJ-035 |  | interim DB lock cut-off | 2027-03-01 | 5
PRJ-035 |  | interim DB lock | 2027-05-01 | 6
PRJ-035 |  | final DB lock cut-off | 2028-03-01 | 7
PRJ-035 |  | final DB lock | 2028-05-01 | 8
PRJ-036 |  | Protocol (v1) | 2025-11-01 | 1
PRJ-036 |  | CTA submission | 2026-01-01 | 2
PRJ-036 |  | First SIV | 2026-05-01 | 3
PRJ-036 |  | LPI | 2027-04-01 | 4
PRJ-036 |  | interim DB lock cut-off | 2027-04-01 | 5
PRJ-036 |  | interim DB lock | 2027-06-01 | 6
PRJ-036 |  | final DB lock cut-off | 2027-12-01 | 7
PRJ-036 |  | final DB lock | 2028-02-01 | 8
PRJ-036 |  | Inspection | 2028-04-01 | 9 | Regulatory inspection
PRJ-037 |  | Protocol (v1) | 2026-03-01 | 1
PRJ-037 |  | CTA submission | 2026-05-01 | 2
PRJ-037 |  | First SIV | 2026-09-01 | 3
PRJ-037 |  | LPI | 2027-08-01 | 4
PRJ-037 |  | interim DB lock cut-off | 2027-08-01 | 5
PRJ-037 |  | interim DB lock | 2027-10-01 | 6
PRJ-037 |  | final DB lock cut-off | 2028-04-01 | 7
PRJ-037 |  | final DB lock | 2028-06-01 | 8
PRJ-038 |  | Protocol (v1) | 2025-12-01 | 1
PRJ-038 |  | CTA submission | 2026-02-01 | 2
PRJ-038 |  | First SIV | 2026-06-01 | 3
PRJ-038 |  | LPI | 2027-08-01 | 4
PRJ-038 |  | final DB lock cut-off | 2028-07-01 | 5
PRJ-038 |  | final DB lock | 2028-09-01 | 6
PRJ-039 |  | Protocol (v1) | 2026-10-01 | 1
PRJ-039 |  | CTA submission | 2026-12-01 | 2
PRJ-039 |  | First SIV | 2027-04-01 | 3
PRJ-039 |  | LPI | 2028-10-01 | 4
PRJ-039 |  | final DB lock cut-off | 2029-11-01 | 5
PRJ-039 |  | final DB lock | 2030-01-01 | 6
PRJ-040 |  | Protocol (v1) | 2025-09-01 | 1
PRJ-040 |  | CTA submission | 2025-11-01 | 2
PRJ-040 |  | First SIV | 2026-03-01 | 3
PRJ-040 |  | LPI | 2026-06-01 | 4
PRJ-040 |  | interim DB lock cut-off | 2026-07-01 | 5
PRJ-040 |  | interim DB lock | 2026-08-01 | 6
PRJ-040 |  | final DB lock cut-off | 2026-10-01 | 7
PRJ-040 |  | final DB lock | 2026-12-01 | 8
PRJ-040 |  | Inspection | 2027-02-01 | 9 | Regulatory inspection
PRJ-041 |  | Protocol (v1) | 2027-02-01 | 1
PRJ-041 |  | CTA submission | 2027-04-01 | 2
PRJ-041 |  | First SIV | 2027-08-01 | 3
PRJ-041 |  | LPI | 2029-02-01 | 4
PRJ-041 |  | interim DB lock cut-off | 2029-03-01 | 5
PRJ-041 |  | interim DB lock | 2029-05-01 | 6
PRJ-041 |  | final DB lock cut-off | 2030-03-01 | 7
PRJ-041 |  | final DB lock | 2030-05-01 | 8
PRJ-042 |  | Protocol (v1) | 2027-05-01 | 1
PRJ-042 |  | CTA submission | 2027-07-01 | 2
PRJ-042 |  | First SIV | 2027-11-01 | 3
PRJ-042 |  | LPI | 2028-10-01 | 4
PRJ-042 |  | interim DB lock cut-off | 2028-10-01 | 5
PRJ-042 |  | interim DB lock | 2028-12-01 | 6
PRJ-042 |  | final DB lock cut-off | 2029-06-01 | 7
PRJ-042 |  | final DB lock | 2029-08-01 | 8
PRJ-043 |  | Protocol (v1) | 2027-08-01 | 1
PRJ-043 |  | CTA submission | 2027-10-01 | 2
PRJ-043 |  | First SIV | 2028-02-01 | 3
PRJ-043 |  | LPI | 2029-04-01 | 4
PRJ-043 |  | final DB lock cut-off | 2030-03-01 | 5
PRJ-043 |  | final DB lock | 2030-05-01 | 6
PRJ-044 |  | Protocol (v1) | 2026-01-01 | 1
PRJ-044 |  | CTA submission | 2026-03-01 | 2
PRJ-044 |  | First SIV | 2026-07-01 | 3
PRJ-044 |  | LPI | 2026-10-01 | 4
PRJ-044 |  | final DB lock cut-off | 2027-02-01 | 5
PRJ-044 |  | final DB lock | 2027-04-01 | 6
PRJ-044 |  | Inspection | 2027-06-01 | 7 | Regulatory inspection
PRJ-045 |  | Protocol (v1) | 2026-04-01 | 1
PRJ-045 |  | CTA submission | 2026-06-01 | 2
PRJ-045 |  | First SIV | 2026-10-01 | 3
PRJ-045 |  | LPI | 2027-01-01 | 4
PRJ-045 |  | interim DB lock cut-off | 2027-02-01 | 5
PRJ-045 |  | interim DB lock | 2027-03-01 | 6
PRJ-045 |  | final DB lock cut-off | 2027-05-01 | 7
PRJ-045 |  | final DB lock | 2027-07-01 | 8
PRJ-046 |  | Protocol (v1) | 2026-06-01 | 1
PRJ-046 |  | CTA submission | 2026-08-01 | 2
PRJ-046 |  | First SIV | 2026-12-01 | 3
PRJ-046 |  | LPI | 2027-11-01 | 4
PRJ-046 |  | interim DB lock cut-off | 2027-11-01 | 5
PRJ-046 |  | interim DB lock | 2028-01-01 | 6
PRJ-046 |  | final DB lock cut-off | 2028-07-01 | 7
PRJ-046 |  | final DB lock | 2028-09-01 | 8
PRJ-047 |  | Protocol (v1) | 2027-01-01 | 1
PRJ-047 |  | CTA submission | 2027-03-01 | 2
PRJ-047 |  | First SIV | 2027-07-01 | 3
PRJ-047 |  | LPI | 2028-09-01 | 4
PRJ-047 |  | interim DB lock cut-off | 2028-10-01 | 5
PRJ-047 |  | interim DB lock | 2028-12-01 | 6
PRJ-047 |  | final DB lock cut-off | 2029-08-01 | 7
PRJ-047 |  | final DB lock | 2029-10-01 | 8
PRJ-048 |  | Protocol (v1) | 2027-11-01 | 1
PRJ-048 |  | CTA submission | 2028-01-01 | 2
PRJ-048 |  | First SIV | 2028-05-01 | 3
PRJ-048 |  | LPI | 2029-07-01 | 4
PRJ-048 |  | final DB lock cut-off | 2030-06-01 | 5
PRJ-048 |  | final DB lock | 2030-08-01 | 6
PRJ-048 |  | Inspection | 2030-10-01 | 7 | Regulatory inspection
PRJ-049 |  | Protocol (v1) | 2028-01-01 | 1
PRJ-049 |  | CTA submission | 2028-03-01 | 2
PRJ-049 |  | First SIV | 2028-07-01 | 3
PRJ-049 |  | LPI | 2029-02-01 | 4
PRJ-049 |  | final DB lock cut-off | 2029-08-01 | 5
PRJ-049 |  | final DB lock | 2029-10-01 | 6
PRJ-050 |  | Protocol (v1) | 2025-04-01 | 1
PRJ-050 |  | CTA submission | 2025-06-01 | 2
PRJ-050 |  | First SIV | 2025-10-01 | 3
PRJ-050 |  | LPI | 2026-09-01 | 4
PRJ-050 |  | interim DB lock cut-off | 2026-09-01 | 5
PRJ-050 |  | interim DB lock | 2026-11-01 | 6
PRJ-050 |  | final DB lock cut-off | 2027-05-01 | 7
PRJ-050 |  | final DB lock | 2027-07-01 | 8

## ProjectPeriod
project_id | period_name | period_seq | period_start | period_end | weight | note_1
PRJ-001 | Before-Start-up | 1 | 2027-12-01 | 2028-01-01 | 0.6 | Derived from milestones
PRJ-001 | Start-up | 2 | 2028-01-02 | 2028-07-01 | 1.3 | Derived from milestones
PRJ-001 | Conduct | 3 | 2028-07-02 | 2029-04-30 | 1 | Derived from milestones
PRJ-001 | Close-out (interim) | 4 | 2029-05-01 | 2029-08-01 | 1.2 | Derived from milestones
PRJ-001 | Conduct | 5 | 2029-08-02 | 2029-12-31 | 1 | Derived from milestones
PRJ-001 | Close-out (final) | 6 | 2030-01-01 | 2030-05-31 | 1.4 | Derived from milestones
PRJ-002 | Before-Start-up | 1 | 2025-10-01 | 2025-11-01 | 0.7 | Derived from milestones
PRJ-002 | Start-up | 2 | 2025-11-02 | 2026-05-01 | 1.4 | Derived from milestones
PRJ-002 | Conduct | 3 | 2026-05-02 | 2026-06-30 | 1.1 | Derived from milestones
PRJ-002 | Close-out (interim) | 4 | 2026-07-01 | 2026-10-01 | 1.3 | Derived from milestones
PRJ-002 | Conduct | 5 | 2026-10-02 | 2026-10-31 | 1.1 | Derived from milestones
PRJ-002 | Close-out (final) | 6 | 2026-11-01 | 2027-03-31 | 1.5 | Derived from milestones
PRJ-003 | Before-Start-up | 1 | 2026-03-01 | 2026-04-01 | 0.68 | Derived from milestones
PRJ-003 | Start-up | 2 | 2026-04-02 | 2026-10-01 | 1.36 | Derived from milestones
PRJ-003 | Conduct | 3 | 2026-10-02 | 2028-03-31 | 1.02 | Derived from milestones
PRJ-003 | Close-out (final) | 4 | 2028-04-01 | 2028-08-31 | 1.44 | Derived from milestones
PRJ-004 | Before-Start-up | 1 | 2026-12-01 | 2027-01-01 | 0.5 | Derived from milestones
PRJ-004 | Start-up | 2 | 2027-01-02 | 2027-07-01 | 1.1 | Derived from milestones
PRJ-004 | Conduct | 3 | 2027-07-02 | 2027-12-31 | 0.9 | Derived from milestones
PRJ-004 | Close-out (final) | 4 | 2028-01-01 | 2028-05-31 | 1.2 | Derived from milestones
PRJ-004 | After Close-out (final) | 5 | 2028-06-01 | 2028-06-01 | 0.72 | Derived from milestones
PRJ-005 | Before-Start-up | 1 | 2025-05-01 | 2025-06-01 | 0.6 | Derived from milestones
PRJ-005 | Start-up | 2 | 2025-06-02 | 2025-12-01 | 1.3 | Derived from milestones
PRJ-005 | Conduct | 3 | 2025-12-02 | 2026-05-31 | 1 | Derived from milestones
PRJ-005 | Close-out (interim) | 4 | 2026-06-01 | 2026-09-01 | 1.2 | Derived from milestones
PRJ-005 | Conduct | 5 | 2026-09-02 | 2026-11-30 | 1 | Derived from milestones
PRJ-005 | Close-out (final) | 6 | 2026-12-01 | 2027-04-30 | 1.4 | Derived from milestones
PRJ-006 | Before-Start-up | 1 | 2027-05-01 | 2027-06-01 | 0.59 | Derived from milestones
PRJ-006 | Start-up | 2 | 2027-06-02 | 2027-12-01 | 1.19 | Derived from milestones
PRJ-006 | Conduct | 3 | 2027-12-02 | 2028-05-31 | 0.94 | Derived from milestones
PRJ-006 | Close-out (interim) | 4 | 2028-06-01 | 2028-09-01 | 1.1 | Derived from milestones
PRJ-006 | Conduct | 5 | 2028-09-02 | 2028-11-30 | 0.94 | Derived from milestones
PRJ-006 | Close-out (final) | 6 | 2028-12-01 | 2029-04-30 | 1.27 | Derived from milestones
PRJ-007 | Before-Start-up | 1 | 2027-11-01 | 2027-12-01 | 0.8 | Derived from milestones
PRJ-007 | Start-up | 2 | 2027-12-02 | 2028-06-01 | 1.6 | Derived from milestones
PRJ-007 | Conduct | 3 | 2028-06-02 | 2029-03-31 | 1.2 | Derived from milestones
PRJ-007 | Close-out (interim) | 4 | 2029-04-01 | 2029-07-01 | 1.4 | Derived from milestones
PRJ-007 | Conduct | 5 | 2029-07-02 | 2029-11-30 | 1.2 | Derived from milestones
PRJ-007 | Close-out (final) | 6 | 2029-12-01 | 2030-04-30 | 1.7 | Derived from milestones
PRJ-008 | Before-Start-up | 1 | 2026-11-01 | 2026-12-01 | 0.5 | Derived from milestones
PRJ-008 | Start-up | 2 | 2026-12-02 | 2027-06-01 | 1.1 | Derived from milestones
PRJ-008 | Conduct | 3 | 2027-06-02 | 2028-05-31 | 0.9 | Derived from milestones
PRJ-008 | Close-out (final) | 4 | 2028-06-01 | 2028-10-31 | 1.2 | Derived from milestones
PRJ-008 | After Close-out (final) | 5 | 2028-11-01 | 2028-11-01 | 0.72 | Derived from milestones
PRJ-009 | Before-Start-up | 1 | 2026-04-01 | 2026-05-01 | 0.51 | Derived from milestones
PRJ-009 | Start-up | 2 | 2026-05-02 | 2026-11-01 | 1.1 | Derived from milestones
PRJ-009 | Conduct | 3 | 2026-11-02 | 2027-10-31 | 0.85 | Derived from milestones
PRJ-009 | Close-out (final) | 4 | 2027-11-01 | 2028-03-31 | 1.19 | Derived from milestones
PRJ-010 | Before-Start-up | 1 | 2026-09-01 | 2026-10-01 | 0.7 | Derived from milestones
PRJ-010 | Start-up | 2 | 2026-10-02 | 2027-04-01 | 1.4 | Derived from milestones
PRJ-010 | Conduct | 3 | 2027-04-02 | 2027-09-30 | 1.1 | Derived from milestones
PRJ-010 | Close-out (interim) | 4 | 2027-10-01 | 2028-01-01 | 1.3 | Derived from milestones
PRJ-010 | Conduct | 5 | 2028-01-02 | 2028-03-31 | 1.1 | Derived from milestones
PRJ-010 | Close-out (final) | 6 | 2028-04-01 | 2028-08-31 | 1.5 | Derived from milestones
PRJ-011 | Before-Start-up | 1 | 2026-03-01 | 2026-04-01 | 0.8 | Derived from milestones
PRJ-011 | Start-up | 2 | 2026-04-02 | 2026-10-01 | 1.6 | Derived from milestones
PRJ-011 | Conduct | 3 | 2026-10-02 | 2026-11-30 | 1.2 | Derived from milestones
PRJ-011 | Close-out (interim) | 4 | 2026-12-01 | 2027-03-01 | 1.4 | Derived from milestones
PRJ-011 | Conduct | 5 | 2027-03-02 | 2027-03-31 | 1.2 | Derived from milestones
PRJ-011 | Close-out (final) | 6 | 2027-04-01 | 2027-08-31 | 1.7 | Derived from milestones
PRJ-012 | Before-Start-up | 1 | 2027-12-01 | 2028-01-01 | 0.42 | Derived from milestones
PRJ-012 | Start-up | 2 | 2028-01-02 | 2028-07-01 | 0.94 | Derived from milestones
PRJ-012 | Conduct | 3 | 2028-07-02 | 2029-08-31 | 0.77 | Derived from milestones
PRJ-012 | Close-out (interim) | 4 | 2029-09-01 | 2029-12-01 | 0.85 | Derived from milestones
PRJ-012 | Conduct | 5 | 2029-12-02 | 2030-06-30 | 0.77 | Derived from milestones
PRJ-012 | Close-out (final) | 6 | 2030-07-01 | 2030-11-30 | 1.02 | Derived from milestones
PRJ-012 | After Close-out (final) | 7 | 2030-12-01 | 2030-12-01 | 0.61 | Derived from milestones
PRJ-013 | Before-Start-up | 1 | 2025-11-01 | 2025-12-01 | 0.6 | Derived from milestones
PRJ-013 | Start-up | 2 | 2025-12-02 | 2026-06-01 | 1.3 | Derived from milestones
PRJ-013 | Conduct | 3 | 2026-06-02 | 2026-11-30 | 1 | Derived from milestones
PRJ-013 | Close-out (final) | 4 | 2026-12-01 | 2027-04-30 | 1.4 | Derived from milestones
PRJ-014 | Before-Start-up | 1 | 2026-06-01 | 2026-07-01 | 0.7 | Derived from milestones
PRJ-014 | Start-up | 2 | 2026-07-02 | 2027-01-01 | 1.4 | Derived from milestones
PRJ-014 | Conduct | 3 | 2027-01-02 | 2027-06-30 | 1.1 | Derived from milestones
PRJ-014 | Close-out (final) | 4 | 2027-07-01 | 2027-11-30 | 1.5 | Derived from milestones
PRJ-015 | Before-Start-up | 1 | 2027-07-01 | 2027-08-01 | 0.68 | Derived from milestones
PRJ-015 | Start-up | 2 | 2027-08-02 | 2028-02-01 | 1.36 | Derived from milestones
PRJ-015 | Conduct | 3 | 2028-02-02 | 2029-03-31 | 1.02 | Derived from milestones
PRJ-015 | Close-out (interim) | 4 | 2029-04-01 | 2029-07-01 | 1.19 | Derived from milestones
PRJ-015 | Conduct | 5 | 2029-07-02 | 2030-01-31 | 1.02 | Derived from milestones
PRJ-015 | Close-out (final) | 6 | 2030-02-01 | 2030-06-30 | 1.44 | Derived from milestones
PRJ-016 | Before-Start-up | 1 | 2026-08-01 | 2026-09-01 | 0.5 | Derived from milestones
PRJ-016 | Start-up | 2 | 2026-09-02 | 2027-03-01 | 1.1 | Derived from milestones
PRJ-016 | Conduct | 3 | 2027-03-02 | 2027-04-30 | 0.9 | Derived from milestones
PRJ-016 | Close-out (interim) | 4 | 2027-05-01 | 2027-08-01 | 1 | Derived from milestones
PRJ-016 | Conduct | 5 | 2027-08-02 | 2027-08-31 | 0.9 | Derived from milestones
PRJ-016 | Close-out (final) | 6 | 2027-09-01 | 2028-01-31 | 1.2 | Derived from milestones
PRJ-016 | After Close-out (final) | 7 | 2028-02-01 | 2028-02-01 | 0.72 | Derived from milestones
PRJ-017 | Before-Start-up | 1 | 2028-03-01 | 2028-04-01 | 0.6 | Derived from milestones
PRJ-017 | Start-up | 2 | 2028-04-02 | 2028-10-01 | 1.3 | Derived from milestones
PRJ-017 | Conduct | 3 | 2028-10-02 | 2029-11-30 | 1 | Derived from milestones
PRJ-017 | Close-out (interim) | 4 | 2029-12-01 | 2030-03-01 | 1.2 | Derived from milestones
PRJ-017 | Conduct | 5 | 2030-03-02 | 2030-09-30 | 1 | Derived from milestones
PRJ-017 | Close-out (final) | 6 | 2030-10-01 | 2031-02-28 | 1.4 | Derived from milestones
PRJ-018 | Before-Start-up | 1 | 2025-11-01 | 2025-12-01 | 0.59 | Derived from milestones
PRJ-018 | Start-up | 2 | 2025-12-02 | 2026-06-01 | 1.19 | Derived from milestones
PRJ-018 | Conduct | 3 | 2026-06-02 | 2027-11-30 | 0.94 | Derived from milestones
PRJ-018 | Close-out (final) | 4 | 2027-12-01 | 2028-04-30 | 1.27 | Derived from milestones
PRJ-019 | Before-Start-up | 1 | 2026-03-01 | 2026-04-01 | 0.8 | Derived from milestones
PRJ-019 | Start-up | 2 | 2026-04-02 | 2026-10-01 | 1.6 | Derived from milestones
PRJ-019 | Conduct | 3 | 2026-10-02 | 2029-03-31 | 1.2 | Derived from milestones
PRJ-019 | Close-out (final) | 4 | 2029-04-01 | 2029-08-31 | 1.7 | Derived from milestones
PRJ-020 | Before-Start-up | 1 | 2025-06-01 | 2025-07-01 | 0.5 | Derived from milestones
PRJ-020 | Start-up | 2 | 2025-07-02 | 2026-01-01 | 1.1 | Derived from milestones
PRJ-020 | Conduct | 3 | 2026-01-02 | 2027-06-30 | 0.9 | Derived from milestones
PRJ-020 | Close-out (interim) | 4 | 2027-07-01 | 2027-10-01 | 1 | Derived from milestones
PRJ-020 | Conduct | 5 | 2027-10-02 | 2028-06-30 | 0.9 | Derived from milestones
PRJ-020 | Close-out (final) | 6 | 2028-07-01 | 2028-11-30 | 1.2 | Derived from milestones
PRJ-020 | After Close-out (final) | 7 | 2028-12-01 | 2028-12-01 | 0.72 | Derived from milestones
PRJ-021 | Before-Start-up | 1 | 2025-09-01 | 2025-10-01 | 0.51 | Derived from milestones
PRJ-021 | Start-up | 2 | 2025-10-02 | 2026-04-01 | 1.1 | Derived from milestones
PRJ-021 | Conduct | 3 | 2026-04-02 | 2026-05-31 | 0.85 | Derived from milestones
PRJ-021 | Close-out (interim) | 4 | 2026-06-01 | 2026-09-01 | 1.02 | Derived from milestones
PRJ-021 | Conduct | 5 | 2026-09-02 | 2026-09-30 | 0.85 | Derived from milestones
PRJ-021 | Close-out (final) | 6 | 2026-10-01 | 2027-02-28 | 1.19 | Derived from milestones
PRJ-022 | Before-Start-up | 1 | 2026-02-01 | 2026-03-01 | 0.7 | Derived from milestones
PRJ-022 | Start-up | 2 | 2026-03-02 | 2026-09-01 | 1.4 | Derived from milestones
PRJ-022 | Conduct | 3 | 2026-09-02 | 2027-02-28 | 1.1 | Derived from milestones
PRJ-022 | Close-out (interim) | 4 | 2027-03-01 | 2027-06-01 | 1.3 | Derived from milestones
PRJ-022 | Conduct | 5 | 2027-06-02 | 2027-08-31 | 1.1 | Derived from milestones
PRJ-022 | Close-out (final) | 6 | 2027-09-01 | 2028-01-31 | 1.5 | Derived from milestones
PRJ-023 | Before-Start-up | 1 | 2026-12-01 | 2027-01-01 | 0.8 | Derived from milestones
PRJ-023 | Start-up | 2 | 2027-01-02 | 2027-07-01 | 1.6 | Derived from milestones
PRJ-023 | Conduct | 3 | 2027-07-02 | 2027-12-31 | 1.2 | Derived from milestones
PRJ-023 | Close-out (final) | 4 | 2028-01-01 | 2028-05-31 | 1.7 | Derived from milestones
PRJ-024 | Before-Start-up | 1 | 2025-12-01 | 2026-01-01 | 0.42 | Derived from milestones
PRJ-024 | Start-up | 2 | 2026-01-02 | 2026-07-01 | 0.94 | Derived from milestones
PRJ-024 | Conduct | 3 | 2026-07-02 | 2027-12-31 | 0.77 | Derived from milestones
PRJ-024 | Close-out (final) | 4 | 2028-01-01 | 2028-05-31 | 1.02 | Derived from milestones
PRJ-024 | After Close-out (final) | 5 | 2028-06-01 | 2028-06-01 | 0.61 | Derived from milestones
PRJ-025 | Before-Start-up | 1 | 2027-10-01 | 2027-11-01 | 0.6 | Derived from milestones
PRJ-025 | Start-up | 2 | 2027-11-02 | 2028-05-01 | 1.3 | Derived from milestones
PRJ-025 | Conduct | 3 | 2028-05-02 | 2029-02-28 | 1 | Derived from milestones
PRJ-025 | Close-out (interim) | 4 | 2029-03-01 | 2029-06-01 | 1.2 | Derived from milestones
PRJ-025 | Conduct | 5 | 2029-06-02 | 2029-10-31 | 1 | Derived from milestones
PRJ-025 | Close-out (final) | 6 | 2029-11-01 | 2030-03-31 | 1.4 | Derived from milestones
PRJ-026 | Before-Start-up | 1 | 2027-03-01 | 2027-04-01 | 0.7 | Derived from milestones
PRJ-026 | Start-up | 2 | 2027-04-02 | 2027-10-01 | 1.4 | Derived from milestones
PRJ-026 | Conduct | 3 | 2027-10-02 | 2028-11-30 | 1.1 | Derived from milestones
PRJ-026 | Close-out (interim) | 4 | 2028-12-01 | 2029-03-01 | 1.3 | Derived from milestones
PRJ-026 | Conduct | 5 | 2029-03-02 | 2029-09-30 | 1.1 | Derived from milestones
PRJ-026 | Close-out (final) | 6 | 2029-10-01 | 2030-02-28 | 1.5 | Derived from milestones
PRJ-027 | Before-Start-up | 1 | 2027-07-01 | 2027-08-01 | 0.68 | Derived from milestones
PRJ-027 | Start-up | 2 | 2027-08-02 | 2028-02-01 | 1.36 | Derived from milestones
PRJ-027 | Conduct | 3 | 2028-02-02 | 2028-11-30 | 1.02 | Derived from milestones
PRJ-027 | Close-out (interim) | 4 | 2028-12-01 | 2029-03-01 | 1.19 | Derived from milestones
PRJ-027 | Conduct | 5 | 2029-03-02 | 2029-07-31 | 1.02 | Derived from milestones
PRJ-027 | Close-out (final) | 6 | 2029-08-01 | 2029-12-31 | 1.44 | Derived from milestones
PRJ-028 | Before-Start-up | 1 | 2025-12-01 | 2026-01-01 | 0.5 | Derived from milestones
PRJ-028 | Start-up | 2 | 2026-01-02 | 2026-07-01 | 1.1 | Derived from milestones
PRJ-028 | Conduct | 3 | 2026-07-02 | 2028-12-31 | 0.9 | Derived from milestones
PRJ-028 | Close-out (final) | 4 | 2029-01-01 | 2029-05-31 | 1.2 | Derived from milestones
PRJ-028 | After Close-out (final) | 5 | 2029-06-01 | 2029-06-01 | 0.72 | Derived from milestones
PRJ-029 | Before-Start-up | 1 | 2027-07-01 | 2027-08-01 | 0.6 | Derived from milestones
PRJ-029 | Start-up | 2 | 2027-08-02 | 2028-02-01 | 1.3 | Derived from milestones
PRJ-029 | Conduct | 3 | 2028-02-02 | 2030-01-31 | 1 | Derived from milestones
PRJ-029 | Close-out (final) | 4 | 2030-02-01 | 2030-06-30 | 1.4 | Derived from milestones
PRJ-030 | Before-Start-up | 1 | 2025-09-01 | 2025-10-01 | 0.59 | Derived from milestones
PRJ-030 | Start-up | 2 | 2025-10-02 | 2026-04-01 | 1.19 | Derived from milestones
PRJ-030 | Conduct | 3 | 2026-04-02 | 2026-09-30 | 0.94 | Derived from milestones
PRJ-030 | Close-out (interim) | 4 | 2026-10-01 | 2027-01-01 | 1.1 | Derived from milestones
PRJ-030 | Conduct | 5 | 2027-01-02 | 2027-03-31 | 0.94 | Derived from milestones
PRJ-030 | Close-out (final) | 6 | 2027-04-01 | 2027-08-31 | 1.27 | Derived from milestones
PRJ-031 | Before-Start-up | 1 | 2027-04-01 | 2027-05-01 | 0.8 | Derived from milestones
PRJ-031 | Start-up | 2 | 2027-05-02 | 2027-11-01 | 1.6 | Derived from milestones
PRJ-031 | Conduct | 3 | 2027-11-02 | 2028-04-30 | 1.2 | Derived from milestones
PRJ-031 | Close-out (interim) | 4 | 2028-05-01 | 2028-08-01 | 1.4 | Derived from milestones
PRJ-031 | Conduct | 5 | 2028-08-02 | 2028-10-31 | 1.2 | Derived from milestones
PRJ-031 | Close-out (final) | 6 | 2028-11-01 | 2029-03-31 | 1.7 | Derived from milestones
PRJ-032 | Before-Start-up | 1 | 2028-05-01 | 2028-06-01 | 0.5 | Derived from milestones
PRJ-032 | Start-up | 2 | 2028-06-02 | 2028-12-01 | 1.1 | Derived from milestones
PRJ-032 | Conduct | 3 | 2028-12-02 | 2029-01-31 | 0.9 | Derived from milestones
PRJ-032 | Close-out (interim) | 4 | 2029-02-01 | 2029-05-01 | 1 | Derived from milestones
PRJ-032 | Conduct | 5 | 2029-05-02 | 2029-05-31 | 0.9 | Derived from milestones
PRJ-032 | Close-out (final) | 6 | 2029-06-01 | 2029-10-31 | 1.2 | Derived from milestones
PRJ-032 | After Close-out (final) | 7 | 2029-11-01 | 2029-11-01 | 0.72 | Derived from milestones
PRJ-033 | Before-Start-up | 1 | 2027-02-01 | 2027-03-01 | 0.51 | Derived from milestones
PRJ-033 | Start-up | 2 | 2027-03-02 | 2027-09-01 | 1.1 | Derived from milestones
PRJ-033 | Conduct | 3 | 2027-09-02 | 2028-02-29 | 0.85 | Derived from milestones
PRJ-033 | Close-out (final) | 4 | 2028-03-01 | 2028-07-31 | 1.19 | Derived from milestones
PRJ-034 | Before-Start-up | 1 | 2027-10-01 | 2027-11-01 | 0.7 | Derived from milestones
PRJ-034 | Start-up | 2 | 2027-11-02 | 2028-05-01 | 1.4 | Derived from milestones
PRJ-034 | Conduct | 3 | 2028-05-02 | 2030-04-30 | 1.1 | Derived from milestones
PRJ-034 | Close-out (final) | 4 | 2030-05-01 | 2030-09-30 | 1.5 | Derived from milestones
PRJ-035 | Before-Start-up | 1 | 2025-01-01 | 2025-02-01 | 0.8 | Derived from milestones
PRJ-035 | Start-up | 2 | 2025-02-02 | 2025-08-01 | 1.6 | Derived from milestones
PRJ-035 | Conduct | 3 | 2025-08-02 | 2027-01-31 | 1.2 | Derived from milestones
PRJ-035 | Close-out (interim) | 4 | 2027-02-01 | 2027-05-01 | 1.4 | Derived from milestones
PRJ-035 | Conduct | 5 | 2027-05-02 | 2028-01-31 | 1.2 | Derived from milestones
PRJ-035 | Close-out (final) | 6 | 2028-02-01 | 2028-06-30 | 1.7 | Derived from milestones
PRJ-036 | Before-Start-up | 1 | 2025-10-01 | 2025-11-01 | 0.42 | Derived from milestones
PRJ-036 | Start-up | 2 | 2025-11-02 | 2026-05-01 | 0.94 | Derived from milestones
PRJ-036 | Conduct | 3 | 2026-05-02 | 2027-02-28 | 0.77 | Derived from milestones
PRJ-036 | Close-out (interim) | 4 | 2027-03-01 | 2027-06-01 | 0.85 | Derived from milestones
PRJ-036 | Conduct | 5 | 2027-06-02 | 2027-10-31 | 0.77 | Derived from milestones
PRJ-036 | Close-out (final) | 6 | 2027-11-01 | 2028-03-31 | 1.02 | Derived from milestones
PRJ-036 | After Close-out (final) | 7 | 2028-04-01 | 2028-04-01 | 0.61 | Derived from milestones
PRJ-037 | Before-Start-up | 1 | 2026-02-01 | 2026-03-01 | 0.6 | Derived from milestones
PRJ-037 | Start-up | 2 | 2026-03-02 | 2026-09-01 | 1.3 | Derived from milestones
PRJ-037 | Conduct | 3 | 2026-09-02 | 2027-06-30 | 1 | Derived from milestones
PRJ-037 | Close-out (interim) | 4 | 2027-07-01 | 2027-10-01 | 1.2 | Derived from milestones
PRJ-037 | Conduct | 5 | 2027-10-02 | 2028-02-29 | 1 | Derived from milestones
PRJ-037 | Close-out (final) | 6 | 2028-03-01 | 2028-07-31 | 1.4 | Derived from milestones
PRJ-038 | Before-Start-up | 1 | 2025-11-01 | 2025-12-01 | 0.7 | Derived from milestones
PRJ-038 | Start-up | 2 | 2025-12-02 | 2026-06-01 | 1.4 | Derived from milestones
PRJ-038 | Conduct | 3 | 2026-06-02 | 2028-05-31 | 1.1 | Derived from milestones
PRJ-038 | Close-out (final) | 4 | 2028-06-01 | 2028-10-31 | 1.5 | Derived from milestones
PRJ-039 | Before-Start-up | 1 | 2026-09-01 | 2026-10-01 | 0.68 | Derived from milestones
PRJ-039 | Start-up | 2 | 2026-10-02 | 2027-04-01 | 1.36 | Derived from milestones
PRJ-039 | Conduct | 3 | 2027-04-02 | 2029-09-30 | 1.02 | Derived from milestones
PRJ-039 | Close-out (final) | 4 | 2029-10-01 | 2030-02-28 | 1.44 | Derived from milestones
PRJ-040 | Before-Start-up | 1 | 2025-08-01 | 2025-09-01 | 0.5 | Derived from milestones
PRJ-040 | Start-up | 2 | 2025-09-02 | 2026-03-01 | 1.1 | Derived from milestones
PRJ-040 | Conduct | 3 | 2026-03-02 | 2026-04-30 | 0.9 | Derived from milestones
PRJ-040 | Close-out (interim) | 4 | 2026-05-01 | 2026-08-01 | 1 | Derived from milestones
PRJ-040 | Conduct | 5 | 2026-08-02 | 2026-08-31 | 0.9 | Derived from milestones
PRJ-040 | Close-out (final) | 6 | 2026-09-01 | 2027-01-31 | 1.2 | Derived from milestones
PRJ-040 | After Close-out (final) | 7 | 2027-02-01 | 2027-02-01 | 0.72 | Derived from milestones
PRJ-041 | Before-Start-up | 1 | 2027-01-01 | 2027-02-01 | 0.6 | Derived from milestones
PRJ-041 | Start-up | 2 | 2027-02-02 | 2027-08-01 | 1.3 | Derived from milestones
PRJ-041 | Conduct | 3 | 2027-08-02 | 2029-01-31 | 1 | Derived from milestones
PRJ-041 | Close-out (interim) | 4 | 2029-02-01 | 2029-05-01 | 1.2 | Derived from milestones
PRJ-041 | Conduct | 5 | 2029-05-02 | 2030-01-31 | 1 | Derived from milestones
PRJ-041 | Close-out (final) | 6 | 2030-02-01 | 2030-06-30 | 1.4 | Derived from milestones
PRJ-042 | Before-Start-up | 1 | 2027-04-01 | 2027-05-01 | 0.59 | Derived from milestones
PRJ-042 | Start-up | 2 | 2027-05-02 | 2027-11-01 | 1.19 | Derived from milestones
PRJ-042 | Conduct | 3 | 2027-11-02 | 2028-08-31 | 0.94 | Derived from milestones
PRJ-042 | Close-out (interim) | 4 | 2028-09-01 | 2028-12-01 | 1.1 | Derived from milestones
PRJ-042 | Conduct | 5 | 2028-12-02 | 2029-04-30 | 0.94 | Derived from milestones
PRJ-042 | Close-out (final) | 6 | 2029-05-01 | 2029-09-30 | 1.27 | Derived from milestones
PRJ-043 | Before-Start-up | 1 | 2027-07-01 | 2027-08-01 | 0.8 | Derived from milestones
PRJ-043 | Start-up | 2 | 2027-08-02 | 2028-02-01 | 1.6 | Derived from milestones
PRJ-043 | Conduct | 3 | 2028-02-02 | 2030-01-31 | 1.2 | Derived from milestones
PRJ-043 | Close-out (final) | 4 | 2030-02-01 | 2030-06-30 | 1.7 | Derived from milestones
PRJ-044 | Before-Start-up | 1 | 2025-12-01 | 2026-01-01 | 0.5 | Derived from milestones
PRJ-044 | Start-up | 2 | 2026-01-02 | 2026-07-01 | 1.1 | Derived from milestones
PRJ-044 | Conduct | 3 | 2026-07-02 | 2026-12-31 | 0.9 | Derived from milestones
PRJ-044 | Close-out (final) | 4 | 2027-01-01 | 2027-05-31 | 1.2 | Derived from milestones
PRJ-044 | After Close-out (final) | 5 | 2027-06-01 | 2027-06-01 | 0.72 | Derived from milestones
PRJ-045 | Before-Start-up | 1 | 2026-03-01 | 2026-04-01 | 0.51 | Derived from milestones
PRJ-045 | Start-up | 2 | 2026-04-02 | 2026-10-01 | 1.1 | Derived from milestones
PRJ-045 | Conduct | 3 | 2026-10-02 | 2026-11-30 | 0.85 | Derived from milestones
PRJ-045 | Close-out (interim) | 4 | 2026-12-01 | 2027-03-01 | 1.02 | Derived from milestones
PRJ-045 | Conduct | 5 | 2027-03-02 | 2027-03-31 | 0.85 | Derived from milestones
PRJ-045 | Close-out (final) | 6 | 2027-04-01 | 2027-08-31 | 1.19 | Derived from milestones
PRJ-046 | Before-Start-up | 1 | 2026-05-01 | 2026-06-01 | 0.7 | Derived from milestones
PRJ-046 | Start-up | 2 | 2026-06-02 | 2026-12-01 | 1.4 | Derived from milestones
PRJ-046 | Conduct | 3 | 2026-12-02 | 2027-09-30 | 1.1 | Derived from milestones
PRJ-046 | Close-out (interim) | 4 | 2027-10-01 | 2028-01-01 | 1.3 | Derived from milestones
PRJ-046 | Conduct | 5 | 2028-01-02 | 2028-05-31 | 1.1 | Derived from milestones
PRJ-046 | Close-out (final) | 6 | 2028-06-01 | 2028-10-31 | 1.5 | Derived from milestones
PRJ-047 | Before-Start-up | 1 | 2026-12-01 | 2027-01-01 | 0.8 | Derived from milestones
PRJ-047 | Start-up | 2 | 2027-01-02 | 2027-07-01 | 1.6 | Derived from milestones
PRJ-047 | Conduct | 3 | 2027-07-02 | 2028-08-31 | 1.2 | Derived from milestones
PRJ-047 | Close-out (interim) | 4 | 2028-09-01 | 2028-12-01 | 1.4 | Derived from milestones
PRJ-047 | Conduct | 5 | 2028-12-02 | 2029-06-30 | 1.2 | Derived from milestones
PRJ-047 | Close-out (final) | 6 | 2029-07-01 | 2029-11-30 | 1.7 | Derived from milestones
PRJ-048 | Before-Start-up | 1 | 2027-10-01 | 2027-11-01 | 0.42 | Derived from milestones
PRJ-048 | Start-up | 2 | 2027-11-02 | 2028-05-01 | 0.94 | Derived from milestones
PRJ-048 | Conduct | 3 | 2028-05-02 | 2030-04-30 | 0.77 | Derived from milestones
PRJ-048 | Close-out (final) | 4 | 2030-05-01 | 2030-09-30 | 1.02 | Derived from milestones
PRJ-048 | After Close-out (final) | 5 | 2030-10-01 | 2030-10-01 | 0.61 | Derived from milestones
PRJ-049 | Before-Start-up | 1 | 2027-12-01 | 2028-01-01 | 0.6 | Derived from milestones
PRJ-049 | Start-up | 2 | 2028-01-02 | 2028-07-01 | 1.3 | Derived from milestones
PRJ-049 | Conduct | 3 | 2028-07-02 | 2029-06-30 | 1 | Derived from milestones
PRJ-049 | Close-out (final) | 4 | 2029-07-01 | 2029-11-30 | 1.4 | Derived from milestones
PRJ-050 | Before-Start-up | 1 | 2025-03-01 | 2025-04-01 | 0.7 | Derived from milestones
PRJ-050 | Start-up | 2 | 2025-04-02 | 2025-10-01 | 1.4 | Derived from milestones
PRJ-050 | Conduct | 3 | 2025-10-02 | 2026-07-31 | 1.1 | Derived from milestones
PRJ-050 | Close-out (interim) | 4 | 2026-08-01 | 2026-11-01 | 1.3 | Derived from milestones
PRJ-050 | Conduct | 5 | 2026-11-02 | 2027-03-31 | 1.1 | Derived from milestones
PRJ-050 | Close-out (final) | 6 | 2027-04-01 | 2027-08-31 | 1.5 | Derived from milestones
PRJ-051 | Planning | 1 | 2027-11-01 | 2028-03-16 | 0.8 | Entered by hand - no milestone mapping
PRJ-051 | Develop | 2 | 2028-03-17 | 2029-01-10 | 1.2 | Entered by hand - no milestone mapping
PRJ-051 | Close | 3 | 2029-01-11 | 2029-04-30 | 0.9 | Entered by hand - no milestone mapping
PRJ-052 | Planning | 1 | 2027-12-01 | 2028-02-07 | 0.8 | Entered by hand - no milestone mapping
PRJ-052 | Develop | 2 | 2028-02-08 | 2028-07-07 | 1.2 | Entered by hand - no milestone mapping
PRJ-052 | Close | 3 | 2028-07-08 | 2028-08-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-053 | Planning | 1 | 2027-01-01 | 2027-04-02 | 0.8 | Entered by hand - no milestone mapping
PRJ-053 | Develop | 2 | 2027-04-03 | 2027-10-19 | 1.2 | Entered by hand - no milestone mapping
PRJ-053 | Close | 3 | 2027-10-20 | 2027-12-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-054 | Planning | 1 | 2027-04-01 | 2027-08-16 | 0.8 | Entered by hand - no milestone mapping
PRJ-054 | Develop | 2 | 2027-08-17 | 2028-06-12 | 1.2 | Entered by hand - no milestone mapping
PRJ-054 | Close | 3 | 2028-06-13 | 2028-09-30 | 0.9 | Entered by hand - no milestone mapping
PRJ-055 | Planning | 1 | 2027-05-01 | 2027-07-08 | 0.8 | Entered by hand - no milestone mapping
PRJ-055 | Develop | 2 | 2027-07-09 | 2027-12-07 | 1.2 | Entered by hand - no milestone mapping
PRJ-055 | Close | 3 | 2027-12-08 | 2028-01-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-056 | Planning | 1 | 2025-10-01 | 2026-02-14 | 0.8 | Entered by hand - no milestone mapping
PRJ-056 | Develop | 2 | 2026-02-15 | 2026-12-11 | 1.2 | Entered by hand - no milestone mapping
PRJ-056 | Close | 3 | 2026-12-12 | 2027-03-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-057 | Planning | 1 | 2027-12-01 | 2028-01-15 | 0.8 | Entered by hand - no milestone mapping
PRJ-057 | Develop | 2 | 2028-01-16 | 2028-04-24 | 1.2 | Entered by hand - no milestone mapping
PRJ-057 | Close | 3 | 2028-04-25 | 2028-05-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-058 | Planning | 1 | 2025-08-01 | 2025-12-16 | 0.8 | Entered by hand - no milestone mapping
PRJ-058 | Develop | 2 | 2025-12-17 | 2026-10-13 | 1.2 | Entered by hand - no milestone mapping
PRJ-058 | Close | 3 | 2026-10-14 | 2027-01-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-059 | Planning | 1 | 2028-01-01 | 2028-04-01 | 0.8 | Entered by hand - no milestone mapping
PRJ-059 | Develop | 2 | 2028-04-02 | 2028-10-19 | 1.2 | Entered by hand - no milestone mapping
PRJ-059 | Close | 3 | 2028-10-20 | 2028-12-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-060 | Planning | 1 | 2028-06-01 | 2028-08-08 | 0.8 | Entered by hand - no milestone mapping
PRJ-060 | Develop | 2 | 2028-08-09 | 2029-01-04 | 1.2 | Entered by hand - no milestone mapping
PRJ-060 | Close | 3 | 2029-01-05 | 2029-02-28 | 0.9 | Entered by hand - no milestone mapping
PRJ-061 | Planning | 1 | 2026-07-01 | 2026-11-15 | 0.8 | Entered by hand - no milestone mapping
PRJ-061 | Develop | 2 | 2026-11-16 | 2027-09-12 | 1.2 | Entered by hand - no milestone mapping
PRJ-061 | Close | 3 | 2027-09-13 | 2027-12-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-062 | Planning | 1 | 2027-02-01 | 2027-06-17 | 0.8 | Entered by hand - no milestone mapping
PRJ-062 | Develop | 2 | 2027-06-18 | 2028-04-12 | 1.2 | Entered by hand - no milestone mapping
PRJ-062 | Close | 3 | 2028-04-13 | 2028-07-31 | 0.9 | Entered by hand - no milestone mapping

## PeriodWeightStandard
project_type | clinical_phase | period_name | weight | note_1
NewDrug CT | Phase 1 | Before-Start-up | 0.6 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 1 | Start-up | 1.3 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 1 | Conduct | 1 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 1 | Close-out (interim) | 1.2 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 1 | Close-out (final) | 1.4 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 1 | After Close-out (final) | 0.84 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 2 | Before-Start-up | 0.7 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 2 | Start-up | 1.4 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 2 | Conduct | 1.1 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 2 | Close-out (interim) | 1.3 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 2 | Close-out (final) | 1.5 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 2 | After Close-out (final) | 0.9 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 3 | Before-Start-up | 0.8 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 3 | Start-up | 1.6 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 3 | Conduct | 1.2 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 3 | Close-out (interim) | 1.4 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 3 | Close-out (final) | 1.7 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 3 | After Close-out (final) | 1.02 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 4 | Before-Start-up | 0.5 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 4 | Start-up | 1.1 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 4 | Conduct | 0.9 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 4 | Close-out (interim) | 1 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 4 | Close-out (final) | 1.2 | Illustrative - replace with your figure | Illustrative - replace with your figure
NewDrug CT | Phase 4 | After Close-out (final) | 0.72 | Illustrative - replace with your figure | Illustrative - replace with your figure
Biosimilar CT | Phase 1 | Before-Start-up | 0.51 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 1 | Start-up | 1.1 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 1 | Conduct | 0.85 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 1 | Close-out (interim) | 1.02 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 1 | Close-out (final) | 1.19 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 1 | After Close-out (final) | 0.71 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 2 | Before-Start-up | 0.59 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 2 | Start-up | 1.19 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 2 | Conduct | 0.94 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 2 | Close-out (interim) | 1.1 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 2 | Close-out (final) | 1.27 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 2 | After Close-out (final) | 0.77 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 3 | Before-Start-up | 0.68 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 3 | Start-up | 1.36 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 3 | Conduct | 1.02 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 3 | Close-out (interim) | 1.19 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 3 | Close-out (final) | 1.44 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 3 | After Close-out (final) | 0.87 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 4 | Before-Start-up | 0.42 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 4 | Start-up | 0.94 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 4 | Conduct | 0.77 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 4 | Close-out (interim) | 0.85 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 4 | Close-out (final) | 1.02 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure
Biosimilar CT | Phase 4 | After Close-out (final) | 0.61 | Illustrative - lighter than new-drug at the same phase | Illustrative - replace with your figure

## RoleFactor
project_type | role_name | role_factor | role_note
NewDrug CT | Project oversight | 0.8 | Illustrative - replace with your figure
NewDrug CT | Lead data manager | 1.2 | Illustrative - replace with your figure
NewDrug CT | Clinical Data Associator | 1 | Illustrative - replace with your figure
NewDrug CT | Clinical Database Programmer | 1.1 | Illustrative - replace with your figure
NewDrug CT | Data Analyst | 0.9 | Illustrative - replace with your figure
Biosimilar CT | Project oversight | 0.8 | Illustrative - replace with your figure
Biosimilar CT | Lead data manager | 1.2 | Illustrative - replace with your figure
Biosimilar CT | Clinical Data Associator | 1 | Illustrative - replace with your figure
Biosimilar CT | Clinical Database Programmer | 1.1 | Illustrative - replace with your figure
Biosimilar CT | Data Analyst | 0.9 | Illustrative - replace with your figure
Others | Project lead | 1 | Illustrative
Others | Main staff | 0.9 | Illustrative
Others | Other staff | 0.7 | Illustrative

## Person
person_id | person_name | department | primary_role | capacity_fte | employment_start | employment_end | note_1 | note_2 | note_3 | note_4 | note_5
PSN-001 | Kim S. | Clinical Operations | Project oversight | 1
PSN-002 | Park J. | Clinical Operations | Project oversight | 1
PSN-003 | Lee H. | Clinical Operations | Project oversight | 1
PSN-004 | Choi M. | Data Management | Lead data manager | 0.8
PSN-005 | Jung Y. | Data Management | Lead data manager | 1
PSN-006 | Han B. | Data Management | Lead data manager | 1
PSN-007 | Oh K. | Data Management | Lead data manager | 1
PSN-008 | Seo W. | Data Management | Clinical Data Associator | 1
PSN-009 | Yoon T. | Data Management | Clinical Data Associator | 1
PSN-010 | Nam R. | Data Management | Clinical Data Associator | 1
PSN-011 | Ahn D. | Data Management | Clinical Data Associator | 1
PSN-012 | Baek C. | Data Management | Clinical Data Associator | 1
PSN-013 | Shin E. | Programming | Clinical Database Programmer | 1
PSN-014 | Koo J. | Programming | Clinical Database Programmer | 1
PSN-015 | Ryu P. | Programming | Clinical Database Programmer | 1
PSN-016 | Moon A. | Programming | Clinical Database Programmer | 1
PSN-017 | Jang L. | Biostatistics | Data Analyst | 1
PSN-018 | Hwang N. | Biostatistics | Data Analyst | 1
PSN-019 | Cho V. | Biostatistics | Data Analyst | 1
PSN-020 | Song G. | Business Systems | Other staff | 0.6

## Assignment
assignment_id | person_id | person_name | project_id | role_name | assign_start_date | assign_end_date | person_weight | note_1 | note_2 | note_3
ASG-001 | PSN-001 |  | PRJ-001 | Project oversight | 2028-01-01 | 2030-05-31 | 0.16
ASG-002 | PSN-004 |  | PRJ-001 | Lead data manager | 2028-01-01 | 2030-05-31 | 0.18
ASG-003 | PSN-008 |  | PRJ-001 | Clinical Data Associator | 2028-01-01 | 2030-04-30 | 0.11
ASG-004 | PSN-013 |  | PRJ-001 | Clinical Database Programmer | 2027-12-01 | 2030-04-30 | 0.13
ASG-005 | PSN-017 |  | PRJ-001 | Data Analyst | 2027-12-01 | 2030-05-31 | 0.12
ASG-006 | PSN-002 |  | PRJ-002 | Project oversight | 2025-11-01 | 2027-01-31 | 0.1
ASG-007 | PSN-005 |  | PRJ-002 | Lead data manager | 2025-12-01 | 2027-03-31 | 0.16
ASG-008 | PSN-009 |  | PRJ-002 | Clinical Data Associator | 2025-11-01 | 2027-03-31 | 0.14
ASG-009 | PSN-014 |  | PRJ-002 | Clinical Database Programmer | 2025-11-01 | 2027-02-28 | 0.16
ASG-010 | PSN-018 |  | PRJ-002 | Data Analyst | 2025-12-01 | 2027-02-28 | 0.13
ASG-011 | PSN-003 |  | PRJ-003 | Project oversight | 2026-04-01 | 2028-06-30 | 0.15
ASG-012 | PSN-006 |  | PRJ-003 | Lead data manager | 2026-04-01 | 2028-06-30 | 0.18
ASG-013 | PSN-010 |  | PRJ-003 | Clinical Data Associator | 2026-05-01 | 2028-07-31 | 0.11
ASG-014 | PSN-015 |  | PRJ-003 | Clinical Database Programmer | 2026-03-01 | 2028-06-30 | 0.17
ASG-015 | PSN-019 |  | PRJ-003 | Data Analyst | 2026-03-01 | 2028-06-30 | 0.12
ASG-016 | PSN-001 |  | PRJ-004 | Project oversight | 2027-02-01 | 2028-03-31 | 0.12
ASG-017 | PSN-007 |  | PRJ-004 | Lead data manager | 2027-01-01 | 2028-05-31 | 0.19
ASG-018 | PSN-011 |  | PRJ-004 | Clinical Data Associator | 2026-12-01 | 2028-03-31 | 0.11
ASG-019 | PSN-016 |  | PRJ-004 | Clinical Database Programmer | 2027-01-01 | 2028-03-31 | 0.17
ASG-020 | PSN-017 |  | PRJ-004 | Data Analyst | 2027-01-01 | 2028-05-31 | 0.16
ASG-021 | PSN-002 |  | PRJ-005 | Project oversight | 2025-06-01 | 2027-03-30 | 0.15
ASG-022 | PSN-004 |  | PRJ-005 | Lead data manager | 2025-07-01 | 2027-02-28 | 0.2
ASG-023 | PSN-012 |  | PRJ-005 | Clinical Data Associator | 2025-05-01 | 2027-02-28 | 0.12
ASG-024 | PSN-013 |  | PRJ-005 | Clinical Database Programmer | 2025-07-01 | 2027-03-30 | 0.13
ASG-025 | PSN-018 |  | PRJ-005 | Data Analyst | 2025-05-01 | 2027-04-30 | 0.12
ASG-026 | PSN-003 |  | PRJ-006 | Project oversight | 2027-06-01 | 2029-03-30 | 0.11
ASG-027 | PSN-005 |  | PRJ-006 | Lead data manager | 2027-05-01 | 2029-03-30 | 0.17
ASG-028 | PSN-008 |  | PRJ-006 | Clinical Data Associator | 2027-06-01 | 2029-02-28 | 0.12
ASG-029 | PSN-014 |  | PRJ-006 | Clinical Database Programmer | 2027-07-01 | 2029-02-28 | 0.15
ASG-030 | PSN-019 |  | PRJ-006 | Data Analyst | 2027-07-01 | 2029-02-28 | 0.11
ASG-031 | PSN-001 |  | PRJ-007 | Project oversight | 2028-01-01 | 2030-02-28 | 0.1
ASG-032 | PSN-006 |  | PRJ-007 | Lead data manager | 2027-12-01 | 2030-02-28 | 0.16
ASG-033 | PSN-009 |  | PRJ-007 | Clinical Data Associator | 2027-11-01 | 2030-04-30 | 0.12
ASG-034 | PSN-015 |  | PRJ-007 | Clinical Database Programmer | 2027-11-01 | 2030-02-28 | 0.14
ASG-035 | PSN-017 |  | PRJ-007 | Data Analyst | 2027-11-01 | 2030-03-30 | 0.12
ASG-036 | PSN-002 |  | PRJ-008 | Project oversight | 2026-11-01 | 2028-08-31 | 0.12
ASG-037 | PSN-007 |  | PRJ-008 | Lead data manager | 2026-11-01 | 2028-09-30 | 0.14
ASG-038 | PSN-010 |  | PRJ-008 | Clinical Data Associator | 2026-11-01 | 2028-10-31 | 0.14
ASG-039 | PSN-016 |  | PRJ-008 | Clinical Database Programmer | 2027-01-01 | 2028-08-31 | 0.17
ASG-040 | PSN-018 |  | PRJ-008 | Data Analyst | 2027-01-01 | 2028-08-31 | 0.16
ASG-041 | PSN-003 |  | PRJ-009 | Project oversight | 2026-04-01 | 2028-01-31 | 0.13
ASG-042 | PSN-004 |  | PRJ-009 | Lead data manager | 2026-04-01 | 2028-02-29 | 0.17
ASG-043 | PSN-011 |  | PRJ-009 | Clinical Data Associator | 2026-06-01 | 2028-01-31 | 0.15
ASG-044 | PSN-013 |  | PRJ-009 | Clinical Database Programmer | 2026-05-01 | 2028-02-29 | 0.12
ASG-045 | PSN-019 |  | PRJ-009 | Data Analyst | 2026-06-01 | 2028-02-29 | 0.1
ASG-046 | PSN-001 |  | PRJ-010 | Project oversight | 2026-09-01 | 2028-07-31 | 0.12
ASG-047 | PSN-005 |  | PRJ-010 | Lead data manager | 2026-09-01 | 2028-06-30 | 0.17
ASG-048 | PSN-012 |  | PRJ-010 | Clinical Data Associator | 2026-09-01 | 2028-07-31 | 0.17
ASG-049 | PSN-014 |  | PRJ-010 | Clinical Database Programmer | 2026-11-01 | 2028-08-31 | 0.1
ASG-050 | PSN-017 |  | PRJ-010 | Data Analyst | 2026-09-01 | 2028-08-31 | 0.11
ASG-051 | PSN-002 |  | PRJ-011 | Project oversight | 2026-04-01 | 2027-07-31 | 0.1
ASG-052 | PSN-006 |  | PRJ-011 | Lead data manager | 2026-04-01 | 2027-06-30 | 0.18
ASG-053 | PSN-008 |  | PRJ-011 | Clinical Data Associator | 2026-04-01 | 2027-07-31 | 0.16
ASG-054 | PSN-015 |  | PRJ-011 | Clinical Database Programmer | 2026-04-01 | 2027-08-31 | 0.1
ASG-055 | PSN-018 |  | PRJ-011 | Data Analyst | 2026-03-01 | 2027-06-30 | 0.13
ASG-056 | PSN-003 |  | PRJ-012 | Project oversight | 2028-02-01 | 2030-10-30 | 0.14
ASG-057 | PSN-007 |  | PRJ-012 | Lead data manager | 2027-12-01 | 2030-11-30 | 0.16
ASG-058 | PSN-009 |  | PRJ-012 | Clinical Data Associator | 2027-12-01 | 2030-11-30 | 0.13
ASG-059 | PSN-016 |  | PRJ-012 | Clinical Database Programmer | 2027-12-01 | 2030-09-30 | 0.16
ASG-060 | PSN-019 |  | PRJ-012 | Data Analyst | 2028-02-01 | 2030-11-30 | 0.12
ASG-061 | PSN-001 |  | PRJ-013 | Project oversight | 2026-01-01 | 2027-02-28 | 0.15
ASG-062 | PSN-004 |  | PRJ-013 | Lead data manager | 2025-11-01 | 2027-03-30 | 0.14
ASG-063 | PSN-010 |  | PRJ-013 | Clinical Data Associator | 2026-01-01 | 2027-02-28 | 0.16
ASG-064 | PSN-013 |  | PRJ-013 | Clinical Database Programmer | 2026-01-01 | 2027-02-28 | 0.17
ASG-065 | PSN-017 |  | PRJ-013 | Data Analyst | 2025-12-01 | 2027-02-28 | 0.13
ASG-066 | PSN-002 |  | PRJ-014 | Project oversight | 2026-08-01 | 2027-10-30 | 0.1
ASG-067 | PSN-005 |  | PRJ-014 | Lead data manager | 2026-07-01 | 2027-11-30 | 0.15
ASG-068 | PSN-011 |  | PRJ-014 | Clinical Data Associator | 2026-06-01 | 2027-11-30 | 0.14
ASG-069 | PSN-014 |  | PRJ-014 | Clinical Database Programmer | 2026-07-01 | 2027-11-30 | 0.16
ASG-070 | PSN-018 |  | PRJ-014 | Data Analyst | 2026-06-01 | 2027-11-30 | 0.16
ASG-071 | PSN-003 |  | PRJ-015 | Project oversight | 2027-09-01 | 2030-05-30 | 0.15
ASG-072 | PSN-006 |  | PRJ-015 | Lead data manager | 2027-08-01 | 2030-06-30 | 0.16
ASG-073 | PSN-012 |  | PRJ-015 | Clinical Data Associator | 2027-08-01 | 2030-06-30 | 0.13
ASG-074 | PSN-015 |  | PRJ-015 | Clinical Database Programmer | 2027-09-01 | 2030-05-30 | 0.11
ASG-075 | PSN-019 |  | PRJ-015 | Data Analyst | 2027-09-01 | 2030-06-30 | 0.15
ASG-076 | PSN-001 |  | PRJ-016 | Project oversight | 2026-10-01 | 2027-12-31 | 0.17
ASG-077 | PSN-007 |  | PRJ-016 | Lead data manager | 2026-08-01 | 2027-11-30 | 0.15
ASG-078 | PSN-008 |  | PRJ-016 | Clinical Data Associator | 2026-10-01 | 2028-01-31 | 0.14
ASG-079 | PSN-016 |  | PRJ-016 | Clinical Database Programmer | 2026-08-01 | 2027-11-30 | 0.12
ASG-080 | PSN-017 |  | PRJ-016 | Data Analyst | 2026-10-01 | 2027-11-30 | 0.11
ASG-081 | PSN-002 |  | PRJ-017 | Project oversight | 2028-04-01 | 2031-01-28 | 0.14
ASG-082 | PSN-004 |  | PRJ-017 | Lead data manager | 2028-04-01 | 2031-01-28 | 0.16
ASG-083 | PSN-009 |  | PRJ-017 | Clinical Data Associator | 2028-04-01 | 2031-01-28 | 0.1
ASG-084 | PSN-013 |  | PRJ-017 | Clinical Database Programmer | 2028-03-01 | 2030-12-28 | 0.15
ASG-085 | PSN-018 |  | PRJ-017 | Data Analyst | 2028-05-01 | 2031-01-28 | 0.17
ASG-086 | PSN-003 |  | PRJ-018 | Project oversight | 2026-01-01 | 2028-04-30 | 0.14
ASG-087 | PSN-005 |  | PRJ-018 | Lead data manager | 2025-12-01 | 2028-02-29 | 0.16
ASG-088 | PSN-010 |  | PRJ-018 | Clinical Data Associator | 2025-12-01 | 2028-02-29 | 0.15
ASG-089 | PSN-014 |  | PRJ-018 | Clinical Database Programmer | 2025-12-01 | 2028-04-30 | 0.16
ASG-090 | PSN-019 |  | PRJ-018 | Data Analyst | 2025-12-01 | 2028-03-30 | 0.14
ASG-091 | PSN-001 |  | PRJ-019 | Project oversight | 2026-04-01 | 2029-06-30 | 0.14
ASG-092 | PSN-006 |  | PRJ-019 | Lead data manager | 2026-03-01 | 2029-08-31 | 0.2
ASG-093 | PSN-011 |  | PRJ-019 | Clinical Data Associator | 2026-04-01 | 2029-08-31 | 0.12
ASG-094 | PSN-015 |  | PRJ-019 | Clinical Database Programmer | 2026-05-01 | 2029-07-31 | 0.12
ASG-095 | PSN-017 |  | PRJ-019 | Data Analyst | 2026-05-01 | 2029-08-31 | 0.16
ASG-096 | PSN-002 |  | PRJ-020 | Project oversight | 2025-08-01 | 2028-11-30 | 0.13
ASG-097 | PSN-007 |  | PRJ-020 | Lead data manager | 2025-06-01 | 2028-09-30 | 0.16
ASG-098 | PSN-012 |  | PRJ-020 | Clinical Data Associator | 2025-08-01 | 2028-09-30 | 0.13
ASG-099 | PSN-016 |  | PRJ-020 | Clinical Database Programmer | 2025-06-01 | 2028-11-30 | 0.13
ASG-100 | PSN-018 |  | PRJ-020 | Data Analyst | 2025-07-01 | 2028-10-30 | 0.15
ASG-101 | PSN-003 |  | PRJ-021 | Project oversight | 2025-10-01 | 2027-01-28 | 0.12
ASG-102 | PSN-004 |  | PRJ-021 | Lead data manager | 2025-11-01 | 2027-02-28 | 0.17
ASG-103 | PSN-008 |  | PRJ-021 | Clinical Data Associator | 2025-10-01 | 2027-02-28 | 0.15
ASG-104 | PSN-013 |  | PRJ-021 | Clinical Database Programmer | 2025-11-01 | 2027-01-28 | 0.11
ASG-105 | PSN-019 |  | PRJ-021 | Data Analyst | 2025-11-01 | 2027-01-28 | 0.15
ASG-106 | PSN-001 |  | PRJ-022 | Project oversight | 2026-03-01 | 2028-01-31 | 0.12
ASG-107 | PSN-005 |  | PRJ-022 | Lead data manager | 2026-04-01 | 2027-12-31 | 0.17
ASG-108 | PSN-009 |  | PRJ-022 | Clinical Data Associator | 2026-03-01 | 2027-12-31 | 0.12
ASG-109 | PSN-014 |  | PRJ-022 | Clinical Database Programmer | 2026-04-01 | 2027-11-30 | 0.15
ASG-110 | PSN-017 |  | PRJ-022 | Data Analyst | 2026-02-01 | 2027-12-31 | 0.17
ASG-111 | PSN-002 |  | PRJ-023 | Project oversight | 2027-02-01 | 2028-04-30 | 0.15
ASG-112 | PSN-006 |  | PRJ-023 | Lead data manager | 2027-02-01 | 2028-05-31 | 0.16
ASG-113 | PSN-010 |  | PRJ-023 | Clinical Data Associator | 2027-02-01 | 2028-04-30 | 0.12
ASG-114 | PSN-015 |  | PRJ-023 | Clinical Database Programmer | 2027-01-01 | 2028-04-30 | 0.15
ASG-115 | PSN-018 |  | PRJ-023 | Data Analyst | 2027-02-01 | 2028-03-31 | 0.16
ASG-116 | PSN-003 |  | PRJ-024 | Project oversight | 2026-01-01 | 2028-05-31 | 0.14
ASG-117 | PSN-007 |  | PRJ-024 | Lead data manager | 2026-01-01 | 2028-05-31 | 0.15
ASG-118 | PSN-011 |  | PRJ-024 | Clinical Data Associator | 2025-12-01 | 2028-05-31 | 0.15
ASG-119 | PSN-016 |  | PRJ-024 | Clinical Database Programmer | 2026-01-01 | 2028-03-31 | 0.12
ASG-120 | PSN-019 |  | PRJ-024 | Data Analyst | 2025-12-01 | 2028-03-31 | 0.17
ASG-121 | PSN-001 |  | PRJ-025 | Project oversight | 2027-10-01 | 2030-03-31 | 0.1
ASG-122 | PSN-004 |  | PRJ-025 | Lead data manager | 2027-11-01 | 2030-01-31 | 0.16
ASG-123 | PSN-012 |  | PRJ-025 | Clinical Data Associator | 2027-10-01 | 2030-03-31 | 0.15
ASG-124 | PSN-013 |  | PRJ-025 | Clinical Database Programmer | 2027-10-01 | 2030-03-31 | 0.15
ASG-125 | PSN-017 |  | PRJ-025 | Data Analyst | 2027-10-01 | 2030-01-31 | 0.14
ASG-126 | PSN-002 |  | PRJ-026 | Project oversight | 2027-05-01 | 2029-12-28 | 0.16
ASG-127 | PSN-005 |  | PRJ-026 | Lead data manager | 2027-05-01 | 2029-12-28 | 0.18
ASG-128 | PSN-008 |  | PRJ-026 | Clinical Data Associator | 2027-05-01 | 2029-12-28 | 0.14
ASG-129 | PSN-014 |  | PRJ-026 | Clinical Database Programmer | 2027-05-01 | 2030-01-28 | 0.16
ASG-130 | PSN-018 |  | PRJ-026 | Data Analyst | 2027-03-01 | 2029-12-28 | 0.15
ASG-131 | PSN-003 |  | PRJ-027 | Project oversight | 2027-07-01 | 2029-12-31 | 0.12
ASG-132 | PSN-006 |  | PRJ-027 | Lead data manager | 2027-09-01 | 2029-11-30 | 0.16
ASG-133 | PSN-009 |  | PRJ-027 | Clinical Data Associator | 2027-09-01 | 2029-10-31 | 0.11
ASG-134 | PSN-015 |  | PRJ-027 | Clinical Database Programmer | 2027-09-01 | 2029-10-31 | 0.16
ASG-135 | PSN-019 |  | PRJ-027 | Data Analyst | 2027-09-01 | 2029-11-30 | 0.16
ASG-136 | PSN-001 |  | PRJ-028 | Project oversight | 2026-02-01 | 2029-03-31 | 0.12
ASG-137 | PSN-007 |  | PRJ-028 | Lead data manager | 2026-02-01 | 2029-03-31 | 0.15
ASG-138 | PSN-010 |  | PRJ-028 | Clinical Data Associator | 2025-12-01 | 2029-04-30 | 0.12
ASG-139 | PSN-016 |  | PRJ-028 | Clinical Database Programmer | 2026-02-01 | 2029-05-31 | 0.17
ASG-140 | PSN-017 |  | PRJ-028 | Data Analyst | 2025-12-01 | 2029-05-31 | 0.17
ASG-141 | PSN-002 |  | PRJ-029 | Project oversight | 2027-09-01 | 2030-05-30 | 0.15
ASG-142 | PSN-004 |  | PRJ-029 | Lead data manager | 2027-09-01 | 2030-06-30 | 0.14
ASG-143 | PSN-011 |  | PRJ-029 | Clinical Data Associator | 2027-09-01 | 2030-05-30 | 0.16
ASG-144 | PSN-013 |  | PRJ-029 | Clinical Database Programmer | 2027-09-01 | 2030-06-30 | 0.1
ASG-145 | PSN-018 |  | PRJ-029 | Data Analyst | 2027-08-01 | 2030-04-30 | 0.12
ASG-146 | PSN-003 |  | PRJ-030 | Project oversight | 2025-09-01 | 2027-07-31 | 0.15
ASG-147 | PSN-005 |  | PRJ-030 | Lead data manager | 2025-11-01 | 2027-08-31 | 0.19
ASG-148 | PSN-012 |  | PRJ-030 | Clinical Data Associator | 2025-09-01 | 2027-08-31 | 0.15
ASG-149 | PSN-014 |  | PRJ-030 | Clinical Database Programmer | 2025-11-01 | 2027-06-30 | 0.17
ASG-150 | PSN-019 |  | PRJ-030 | Data Analyst | 2025-10-01 | 2027-08-31 | 0.15
ASG-151 | PSN-001 |  | PRJ-031 | Project oversight | 2027-06-01 | 2029-03-31 | 0.11
ASG-152 | PSN-006 |  | PRJ-031 | Lead data manager | 2027-05-01 | 2029-02-28 | 0.2
ASG-153 | PSN-008 |  | PRJ-031 | Clinical Data Associator | 2027-04-01 | 2029-02-28 | 0.12
ASG-154 | PSN-015 |  | PRJ-031 | Clinical Database Programmer | 2027-05-01 | 2029-02-28 | 0.1
ASG-155 | PSN-017 |  | PRJ-031 | Data Analyst | 2027-05-01 | 2029-02-28 | 0.15
ASG-156 | PSN-002 |  | PRJ-032 | Project oversight | 2028-05-01 | 2029-09-30 | 0.15
ASG-157 | PSN-007 |  | PRJ-032 | Lead data manager | 2028-06-01 | 2029-08-31 | 0.16
ASG-158 | PSN-009 |  | PRJ-032 | Clinical Data Associator | 2028-05-01 | 2029-08-31 | 0.15
ASG-159 | PSN-016 |  | PRJ-032 | Clinical Database Programmer | 2028-06-01 | 2029-08-31 | 0.16
ASG-160 | PSN-018 |  | PRJ-032 | Data Analyst | 2028-05-01 | 2029-10-31 | 0.15
ASG-161 | PSN-003 |  | PRJ-033 | Project oversight | 2027-02-01 | 2028-06-30 | 0.1
ASG-162 | PSN-004 |  | PRJ-033 | Lead data manager | 2027-02-01 | 2028-07-31 | 0.16
ASG-163 | PSN-010 |  | PRJ-033 | Clinical Data Associator | 2027-03-01 | 2028-07-31 | 0.14
ASG-164 | PSN-013 |  | PRJ-033 | Clinical Database Programmer | 2027-02-01 | 2028-05-31 | 0.15
ASG-165 | PSN-019 |  | PRJ-033 | Data Analyst | 2027-03-01 | 2028-05-31 | 0.13
ASG-166 | PSN-001 |  | PRJ-034 | Project oversight | 2027-10-01 | 2030-07-30 | 0.13
ASG-167 | PSN-005 |  | PRJ-034 | Lead data manager | 2027-10-01 | 2030-09-30 | 0.15
ASG-168 | PSN-011 |  | PRJ-034 | Clinical Data Associator | 2027-11-01 | 2030-08-30 | 0.11
ASG-169 | PSN-014 |  | PRJ-034 | Clinical Database Programmer | 2027-10-01 | 2030-09-30 | 0.13
ASG-170 | PSN-017 |  | PRJ-034 | Data Analyst | 2027-11-01 | 2030-09-30 | 0.17
ASG-171 | PSN-002 |  | PRJ-035 | Project oversight | 2025-03-01 | 2028-05-30 | 0.15
ASG-172 | PSN-006 |  | PRJ-035 | Lead data manager | 2025-01-01 | 2028-06-30 | 0.18
ASG-173 | PSN-012 |  | PRJ-035 | Clinical Data Associator | 2025-03-01 | 2028-04-30 | 0.11
ASG-174 | PSN-015 |  | PRJ-035 | Clinical Database Programmer | 2025-02-01 | 2028-04-30 | 0.13
ASG-175 | PSN-018 |  | PRJ-035 | Data Analyst | 2025-01-01 | 2028-05-30 | 0.11
ASG-176 | PSN-003 |  | PRJ-036 | Project oversight | 2025-11-01 | 2028-03-31 | 0.11
ASG-177 | PSN-007 |  | PRJ-036 | Lead data manager | 2025-12-01 | 2028-01-31 | 0.15
ASG-178 | PSN-008 |  | PRJ-036 | Clinical Data Associator | 2025-11-01 | 2028-02-29 | 0.11
ASG-179 | PSN-016 |  | PRJ-036 | Clinical Database Programmer | 2025-11-01 | 2028-01-31 | 0.15
ASG-180 | PSN-019 |  | PRJ-036 | Data Analyst | 2025-10-01 | 2028-01-31 | 0.13
ASG-181 | PSN-001 |  | PRJ-037 | Project oversight | 2026-04-01 | 2028-07-31 | 0.15
ASG-182 | PSN-004 |  | PRJ-037 | Lead data manager | 2026-02-01 | 2028-07-31 | 0.21
ASG-183 | PSN-009 |  | PRJ-037 | Clinical Data Associator | 2026-03-01 | 2028-06-30 | 0.11
ASG-184 | PSN-013 |  | PRJ-037 | Clinical Database Programmer | 2026-03-01 | 2028-06-30 | 0.12
ASG-185 | PSN-017 |  | PRJ-037 | Data Analyst | 2026-04-01 | 2028-05-31 | 0.17
ASG-186 | PSN-002 |  | PRJ-038 | Project oversight | 2026-01-01 | 2028-08-31 | 0.17
ASG-187 | PSN-005 |  | PRJ-038 | Lead data manager | 2025-11-01 | 2028-08-31 | 0.14
ASG-188 | PSN-010 |  | PRJ-038 | Clinical Data Associator | 2026-01-01 | 2028-09-30 | 0.13
ASG-189 | PSN-014 |  | PRJ-038 | Clinical Database Programmer | 2025-11-01 | 2028-08-31 | 0.12
ASG-190 | PSN-018 |  | PRJ-038 | Data Analyst | 2026-01-01 | 2028-10-31 | 0.12
ASG-191 | PSN-003 |  | PRJ-039 | Project oversight | 2026-09-01 | 2030-02-28 | 0.1
ASG-192 | PSN-006 |  | PRJ-039 | Lead data manager | 2026-09-01 | 2029-12-28 | 0.2
ASG-193 | PSN-011 |  | PRJ-039 | Clinical Data Associator | 2026-09-01 | 2030-02-28 | 0.11
ASG-194 | PSN-015 |  | PRJ-039 | Clinical Database Programmer | 2026-09-01 | 2030-01-28 | 0.16
ASG-195 | PSN-019 |  | PRJ-039 | Data Analyst | 2026-11-01 | 2029-12-28 | 0.12
ASG-196 | PSN-001 |  | PRJ-040 | Project oversight | 2025-09-01 | 2027-01-31 | 0.11
ASG-197 | PSN-007 |  | PRJ-040 | Lead data manager | 2025-09-01 | 2026-12-31 | 0.2
ASG-198 | PSN-012 |  | PRJ-040 | Clinical Data Associator | 2025-09-01 | 2026-11-30 | 0.15
ASG-199 | PSN-016 |  | PRJ-040 | Clinical Database Programmer | 2025-09-01 | 2026-12-31 | 0.12
ASG-200 | PSN-017 |  | PRJ-040 | Data Analyst | 2025-10-01 | 2027-01-31 | 0.11
ASG-201 | PSN-002 |  | PRJ-041 | Project oversight | 2027-02-01 | 2030-05-30 | 0.1
ASG-202 | PSN-004 |  | PRJ-041 | Lead data manager | 2027-02-01 | 2030-06-30 | 0.18
ASG-203 | PSN-008 |  | PRJ-041 | Clinical Data Associator | 2027-02-01 | 2030-04-30 | 0.15
ASG-204 | PSN-013 |  | PRJ-041 | Clinical Database Programmer | 2027-03-01 | 2030-04-30 | 0.11
ASG-205 | PSN-018 |  | PRJ-041 | Data Analyst | 2027-02-01 | 2030-06-30 | 0.15
ASG-206 | PSN-003 |  | PRJ-042 | Project oversight | 2027-05-01 | 2029-07-30 | 0.17
ASG-207 | PSN-005 |  | PRJ-042 | Lead data manager | 2027-04-01 | 2029-08-30 | 0.15
ASG-208 | PSN-009 |  | PRJ-042 | Clinical Data Associator | 2027-05-01 | 2029-07-30 | 0.11
ASG-209 | PSN-014 |  | PRJ-042 | Clinical Database Programmer | 2027-04-01 | 2029-08-30 | 0.13
ASG-210 | PSN-019 |  | PRJ-042 | Data Analyst | 2027-05-01 | 2029-09-30 | 0.12
ASG-211 | PSN-001 |  | PRJ-043 | Project oversight | 2027-08-01 | 2030-06-30 | 0.16
ASG-212 | PSN-006 |  | PRJ-043 | Lead data manager | 2027-07-01 | 2030-05-30 | 0.18
ASG-213 | PSN-010 |  | PRJ-043 | Clinical Data Associator | 2027-07-01 | 2030-06-30 | 0.12
ASG-214 | PSN-015 |  | PRJ-043 | Clinical Database Programmer | 2027-07-01 | 2030-06-30 | 0.15
ASG-215 | PSN-017 |  | PRJ-043 | Data Analyst | 2027-08-01 | 2030-06-30 | 0.11
ASG-216 | PSN-002 |  | PRJ-044 | Project oversight | 2026-02-01 | 2027-05-31 | 0.12
ASG-217 | PSN-007 |  | PRJ-044 | Lead data manager | 2025-12-01 | 2027-04-30 | 0.16
ASG-218 | PSN-011 |  | PRJ-044 | Clinical Data Associator | 2025-12-01 | 2027-04-30 | 0.11
ASG-219 | PSN-016 |  | PRJ-044 | Clinical Database Programmer | 2026-02-01 | 2027-04-30 | 0.13
ASG-220 | PSN-018 |  | PRJ-044 | Data Analyst | 2026-02-01 | 2027-04-30 | 0.15
ASG-221 | PSN-003 |  | PRJ-045 | Project oversight | 2026-04-01 | 2027-08-31 | 0.12
ASG-222 | PSN-004 |  | PRJ-045 | Lead data manager | 2026-04-01 | 2027-08-31 | 0.16
ASG-223 | PSN-012 |  | PRJ-045 | Clinical Data Associator | 2026-04-01 | 2027-06-30 | 0.14
ASG-224 | PSN-013 |  | PRJ-045 | Clinical Database Programmer | 2026-05-01 | 2027-06-30 | 0.16
ASG-225 | PSN-019 |  | PRJ-045 | Data Analyst | 2026-03-01 | 2027-06-30 | 0.16
ASG-226 | PSN-001 |  | PRJ-046 | Project oversight | 2026-06-01 | 2028-08-31 | 0.12
ASG-227 | PSN-005 |  | PRJ-046 | Lead data manager | 2026-07-01 | 2028-08-31 | 0.2
ASG-228 | PSN-008 |  | PRJ-046 | Clinical Data Associator | 2026-05-01 | 2028-08-31 | 0.13
ASG-229 | PSN-014 |  | PRJ-046 | Clinical Database Programmer | 2026-05-01 | 2028-08-31 | 0.16
ASG-230 | PSN-017 |  | PRJ-046 | Data Analyst | 2026-07-01 | 2028-08-31 | 0.1
ASG-231 | PSN-002 |  | PRJ-047 | Project oversight | 2027-02-01 | 2029-09-30 | 0.15
ASG-232 | PSN-006 |  | PRJ-047 | Lead data manager | 2026-12-01 | 2029-09-30 | 0.16
ASG-233 | PSN-009 |  | PRJ-047 | Clinical Data Associator | 2026-12-01 | 2029-09-30 | 0.16
ASG-234 | PSN-015 |  | PRJ-047 | Clinical Database Programmer | 2027-01-01 | 2029-09-30 | 0.1
ASG-235 | PSN-018 |  | PRJ-047 | Data Analyst | 2027-01-01 | 2029-11-30 | 0.14
ASG-236 | PSN-003 |  | PRJ-048 | Project oversight | 2027-10-01 | 2030-08-30 | 0.16
ASG-237 | PSN-007 |  | PRJ-048 | Lead data manager | 2027-11-01 | 2030-07-30 | 0.15
ASG-238 | PSN-010 |  | PRJ-048 | Clinical Data Associator | 2027-12-01 | 2030-07-30 | 0.11
ASG-239 | PSN-016 |  | PRJ-048 | Clinical Database Programmer | 2027-12-01 | 2030-08-30 | 0.16
ASG-240 | PSN-019 |  | PRJ-048 | Data Analyst | 2027-12-01 | 2030-08-30 | 0.14
ASG-241 | PSN-001 |  | PRJ-049 | Project oversight | 2028-02-01 | 2029-09-30 | 0.12
ASG-242 | PSN-004 |  | PRJ-049 | Lead data manager | 2028-01-01 | 2029-11-30 | 0.15
ASG-243 | PSN-011 |  | PRJ-049 | Clinical Data Associator | 2028-02-01 | 2029-09-30 | 0.12
ASG-244 | PSN-013 |  | PRJ-049 | Clinical Database Programmer | 2027-12-01 | 2029-09-30 | 0.16
ASG-245 | PSN-017 |  | PRJ-049 | Data Analyst | 2027-12-01 | 2029-09-30 | 0.12
ASG-246 | PSN-002 |  | PRJ-050 | Project oversight | 2025-05-01 | 2027-07-31 | 0.15
ASG-247 | PSN-005 |  | PRJ-050 | Lead data manager | 2025-04-01 | 2027-06-30 | 0.15
ASG-248 | PSN-012 |  | PRJ-050 | Clinical Data Associator | 2025-05-01 | 2027-07-31 | 0.17
ASG-249 | PSN-014 |  | PRJ-050 | Clinical Database Programmer | 2025-05-01 | 2027-06-30 | 0.11
ASG-250 | PSN-018 |  | PRJ-050 | Data Analyst | 2025-05-01 | 2027-06-30 | 0.15
ASG-251 | PSN-001 |  | PRJ-051 | Project lead | 2027-11-01 | 2029-03-30 | 0.21
ASG-252 | PSN-008 |  | PRJ-051 | Main staff | 2028-01-01 | 2029-03-30 | 0.12
ASG-253 | PSN-011 |  | PRJ-051 | Other staff | 2027-12-01 | 2029-02-28 | 0.13
ASG-254 | PSN-004 |  | PRJ-052 | Project lead | 2027-12-01 | 2028-06-30 | 0.16
ASG-255 | PSN-013 |  | PRJ-052 | Main staff | 2027-12-01 | 2028-08-31 | 0.14
ASG-256 | PSN-016 |  | PRJ-052 | Other staff | 2028-01-01 | 2028-06-30 | 0.15
ASG-257 | PSN-001 |  | PRJ-053 | Project lead | 2027-03-01 | 2027-12-31 | 0.2
ASG-258 | PSN-017 |  | PRJ-053 | Main staff | 2027-03-01 | 2027-12-31 | 0.12
ASG-259 | PSN-011 |  | PRJ-053 | Other staff | 2027-02-01 | 2027-11-30 | 0.17
ASG-260 | PSN-004 |  | PRJ-054 | Project lead | 2027-04-01 | 2028-07-30 | 0.19
ASG-261 | PSN-008 |  | PRJ-054 | Main staff | 2027-06-01 | 2028-07-30 | 0.16
ASG-262 | PSN-016 |  | PRJ-054 | Other staff | 2027-05-01 | 2028-09-30 | 0.12
ASG-263 | PSN-001 |  | PRJ-055 | Project lead | 2027-07-01 | 2027-12-31 | 0.19
ASG-264 | PSN-013 |  | PRJ-055 | Main staff | 2027-06-01 | 2028-01-31 | 0.11
ASG-265 | PSN-011 |  | PRJ-055 | Other staff | 2027-06-01 | 2027-12-31 | 0.12
ASG-266 | PSN-004 |  | PRJ-056 | Project lead | 2025-11-01 | 2027-01-31 | 0.17
ASG-267 | PSN-017 |  | PRJ-056 | Main staff | 2025-12-01 | 2027-03-31 | 0.15
ASG-268 | PSN-016 |  | PRJ-056 | Other staff | 2025-12-01 | 2027-01-31 | 0.15
ASG-269 | PSN-001 |  | PRJ-057 | Project lead | 2028-02-01 | 2028-03-31 | 0.15
ASG-270 | PSN-008 |  | PRJ-057 | Main staff | 2028-01-01 | 2028-03-31 | 0.16
ASG-271 | PSN-011 |  | PRJ-057 | Other staff | 2027-12-01 | 2028-04-30 | 0.14
ASG-272 | PSN-004 |  | PRJ-058 | Project lead | 2025-09-01 | 2027-01-31 | 0.19
ASG-273 | PSN-013 |  | PRJ-058 | Main staff | 2025-10-01 | 2026-12-31 | 0.17
ASG-274 | PSN-016 |  | PRJ-058 | Other staff | 2025-08-01 | 2027-01-31 | 0.16
ASG-275 | PSN-001 |  | PRJ-059 | Project lead | 2028-02-01 | 2028-10-31 | 0.16
ASG-276 | PSN-017 |  | PRJ-059 | Main staff | 2028-02-01 | 2028-11-30 | 0.11
ASG-277 | PSN-011 |  | PRJ-059 | Other staff | 2028-02-01 | 2028-10-31 | 0.12
ASG-278 | PSN-004 |  | PRJ-060 | Project lead | 2028-07-01 | 2028-12-28 | 0.2
ASG-279 | PSN-008 |  | PRJ-060 | Main staff | 2028-08-01 | 2029-01-28 | 0.14
ASG-280 | PSN-016 |  | PRJ-060 | Other staff | 2028-08-01 | 2028-12-28 | 0.12
ASG-281 | PSN-001 |  | PRJ-061 | Project lead | 2026-08-01 | 2027-12-31 | 0.2
ASG-282 | PSN-013 |  | PRJ-061 | Main staff | 2026-07-01 | 2027-10-31 | 0.12
ASG-283 | PSN-011 |  | PRJ-061 | Other staff | 2026-09-01 | 2027-12-31 | 0.16
ASG-284 | PSN-004 |  | PRJ-062 | Project lead | 2027-02-01 | 2028-06-30 | 0.16
ASG-285 | PSN-017 |  | PRJ-062 | Main staff | 2027-03-01 | 2028-07-31 | 0.13
ASG-286 | PSN-016 |  | PRJ-062 | Other staff | 2027-04-01 | 2028-06-30 | 0.15
ASG-901 | PSN-020 |  | PRJ-051 | Other staff | 2026-01-01 | 2027-06-30 | 0.18
ASG-902 | PSN-001 |  | PRJ-002 | Project oversight | 2026-04-01 | 2027-03-31 | 0.35
ASG-903 | PSN-001 |  | PRJ-006 | Project oversight | 2026-04-01 | 2027-03-31 | 0.35

## PersonPeriodWeight
assignment_id | period_start | period_end | weight_override | reason
ASG-902 | 2026-07-01 | 2026-09-30 | 0.2 | Part-time - parental leave
ASG-903 | 2026-10-01 | 2026-12-31 | 0.45 | Covering interim analysis peak

## Lists
list_name | value | note_1
project_type | NewDrug CT
project_type | Biosimilar CT
project_type | Others
clinical_phase | Phase 1
clinical_phase | Phase 2
clinical_phase | Phase 3
clinical_phase | Phase 4
outsourcing_type | Full outsourcing
outsourcing_type | Partial outsourcing
outsourcing_type | Full In-house
setup_party | by CRO
setup_party | by SB
EDC_system | Veeva EDC
EDC_system | Rave
EDC_system | eSOURCE
DataReviewSystem | Veeva DQS
DataReviewSystem | Medidata CDS
DataReviewSystem | No system (manual)
RBQM_system | CluePoints
RBQM_system | Medidata CDS
RBQM_system | No system (manual)
project_status | Planned
project_status | Active
project_status | On hold
project_status | Completed
milestone_name | Protocol (v1)
milestone_name | CTA submission
milestone_name | FPI
milestone_name | First SIV
milestone_name | LPI
milestone_name | interim DB lock cut-off
milestone_name | interim DB lock
milestone_name | final DB lock cut-off
milestone_name | final DB lock
milestone_name | Inspection
period_name_clinical | Before-Start-up
period_name_clinical | Start-up
period_name_clinical | Conduct
period_name_clinical | Close-out (interim)
period_name_clinical | Close-out (final)
period_name_clinical | After Close-out (final)
period_name_others | Planning
period_name_others | Develop
period_name_others | Close
role_clinical | Project oversight
role_clinical | Lead data manager
role_clinical | Clinical Data Associator
role_clinical | Clinical Database Programmer
role_clinical | Data Analyst
role_others | Project lead
role_others | Main staff
role_others | Other staff

## Config
parameter | value | note
schema_version | 3 | Structure version of this workbook. The application warns on a mismatch.
fte_hours_per_month | 160 | Hours equal to 1.00 FTE: 8 h/day x 5 days/week x 20 days/month.
over_allocation_fte | 1.5 | A person-month total above this is flagged as over-allocated. Absolute, not scaled by capacity (S2-01).
under_allocation_fte | 0.6 | A person-month total below this counts toward an under-allocated run. Absolute, not scaled by capacity (S2-01).
under_allocation_min_months | 3 | Consecutive months below the threshold before a run is flagged.
default_horizon_months | 24 | Months shown when the dashboard opens.
capacity_unit | FTE | Display unit: 'FTE' or 'percent'.