## 00_README
PRAP source data - dummy
Schema version 2. Matches PRAP_Development_Plan_v1.0.xlsx, sheet 04_Data_Model.
COLOUR KEY
Blue identifier or key column - these link the sheets together.
Green derived by formula. Do not type in these; they recalculate.
Yellow you must supply this value. The application cannot work it out.
Grey italic row an example, in the template only. Delete it before use.
SHEETS
Project one row per project.
Milestone one row per milestone. Eight standard names.
ProjectPeriod the periods each project passes through, with their weights.
PeriodWeightStandard default weights per clinical phase. Clinical trials only.
RoleFactor the roles and their relative burden, per project type.
Person one row per person.
Assignment one row per person + project + role.
PersonPeriodWeight optional windows where a person's weight differs.
Lists permitted values for every dropdown.
Config thresholds and settings.
FREE-TEXT NOTES
Every sheet carries at least one free-text column, so anything worth recording has a home:
Project note_1 .. note_5
Milestone note_1
ProjectPeriod note_1
PeriodWeightStandard note_1
RoleFactor role_note
Person note_1 .. note_5
Assignment note_1 .. note_3
PersonPeriodWeight reason
Lists note_1
Config note
Nothing in a note column affects the calculation. They are carried through import and export
unchanged, so they survive a round trip.
HOW THE CALCULATION USES THIS
monthly load = project period weight x role factor x person weight x month coverage
The result is FTE, where 1.00 FTE = 160 hours per month.
Over-allocated: a person's monthly total above 1.50 FTE.
Under-allocated: below 0.80 FTE for three or more consecutive months.
PERIODS
Clinical trial periods are derived from the milestone dates:
Before-Start-up project start, to the day before Start-up
Start-up one month before CTA submission, lasting four months
Conduct from the end of Start-up to the day before the next close-out
Close-out (interim) three months before the interim DB lock, to that lock
Conduct (again) from the interim DB lock to the day before Close-out (final)
Close-out (final) three months before the final DB lock, to that lock
After Close-out (final) the inspection activity that follows the final DB lock
Where 'Protocol (v1)' is recorded, Before-Start-up ends on it and Start-up begins the day after.
Where 'First SIV' (or 'FPI') is recorded, Start-up ends on it instead of running a fixed four
months. A recorded milestone always beats the month-offset fallback.
'Conduct' therefore appears TWICE where a trial has an interim DB lock. period_seq keeps
the two apart. A period squeezed to nothing by a tight timeline is simply omitted.
'Inspection' is the one milestone that may be recorded SEVERAL TIMES for a project. Only
inspections dated AFTER the final DB lock open the last period; an earlier one stays a marker.
'Others' projects have no milestones. Their period dates and weights are both typed in.
ADDING A PERMITTED VALUE
Insert a row inside that list's block on the Lists sheet, so the block stays contiguous -
the dropdowns read a range, not a scattered set of rows.
WHAT THIS DUMMY FILE DEMONSTRATES
- PSN-001 is loaded across three projects and breaches the 1.50 FTE over-allocation
threshold in several months.
- PSN-004 sits below 0.80 FTE for well over three consecutive months, so an
under-allocation run is raised.
- PRJ-002, PRJ-003 and PRJ-005 have an interim DB lock, so each has TWO Conduct
stretches and two close-out periods.
- PRJ-001 and PRJ-004 have no interim lock, so Conduct runs once.
- PRJ-006 and PRJ-007 are 'Others' projects with hand-entered periods.
- ASG-001 and ASG-004 carry PersonPeriodWeight overrides.
- PRJ-003 records THREE 'Inspection' events after its final DB lock, so it carries the
seventh period. PRJ-001 records one. PRJ-002 records one dated BEFORE its final lock,
which stays a marker and opens no period - the case raised as R-03 in the plan.
The weights and role factors here are ILLUSTRATIVE, so the numbers can be exercised.
Replace them with your own before drawing any conclusion from the output.

## Project
project_id | project_name | project_type | project_category | clinical_phase | outsourcing_type | EDC_setup | DataReviewSystem_setup | RBQM_setup | DM_conduct | EDC_system | DataReviewSystem | RBQM_system | planned_member_count | start_date | end_date | total_period_months | status | note_1 | note_2 | note_3 | note_4 | note_5
PRJ-001 | ONV-101 First-in-human | Clinical Trial | Onvelaris | Phase 1 | Partial outsourcing | by SB | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 5 | 2025-10-01 | 2027-09-30 |  | Active
PRJ-002 | ONV-205 Dose expansion | Clinical Trial | Onvelaris | Phase 2 | Full outsourcing | by CRO | by CRO | by CRO | by CRO | Rave | Medidata CDS | Medidata CDS | 6 | 2026-01-01 | 2028-09-30 |  | Active
PRJ-003 | CDX-310 Pivotal | Clinical Trial | Cardexa | Phase 3 | Partial outsourcing | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 8 | 2025-07-01 | 2029-10-31 |  | Active
PRJ-004 | NRX-410 Post-marketing | Clinical Trial | Neurexa | Phase 4 | Full In-house | by SB | by SB | by SB | by SB | eSOURCE | No system (manual) | No system (manual) | 3 | 2026-04-01 | 2028-03-31 |  | Planned
PRJ-005 | ONV-302 Confirmatory | Clinical Trial | Onvelaris | Phase 3 | Full outsourcing | by CRO | by CRO | by CRO | by CRO | Rave | Medidata CDS | CluePoints | 7 | 2026-06-01 | 2029-06-30 |  | Planned
PRJ-006 | CDISC library migration | Others |  |  | Full In-house | [7 empty] | 4 | 2026-01-01 | 2026-12-31 |  | Active
PRJ-007 | eTMF rollout | Others |  |  | Partial outsourcing | [7 empty] | 3 | 2026-03-01 | 2027-02-28 |  | Active

## Milestone
project_id | project_name | milestone_name | milestone_date | milestone_seq | note_1
PRJ-001 |  | Protocol (v1) | 2025-10-15 | 1
PRJ-001 |  | CTA submission | 2026-01-15 | 2
PRJ-001 |  | First SIV | 2026-04-01 | 3
PRJ-001 |  | LPI | 2026-11-30 | 4
PRJ-001 |  | final DB lock cut-off | 2027-03-31 | 5
PRJ-001 |  | final DB lock | 2027-05-31 | 6
PRJ-001 |  | Inspection | 2027-08-15 | 7 | Regulatory inspection
PRJ-002 |  | Protocol (v1) | 2026-01-20 | 1
PRJ-002 |  | CTA submission | 2026-04-01 | 2
PRJ-002 |  | First SIV | 2026-07-01 | 3
PRJ-002 |  | LPI | 2027-06-30 | 4
PRJ-002 |  | interim DB lock cut-off | 2027-09-30 | 5
PRJ-002 |  | interim DB lock | 2027-11-30 | 6
PRJ-002 |  | Inspection | 2028-05-20 | 7 | Regulatory inspection
PRJ-002 |  | final DB lock cut-off | 2028-06-30 | 8
PRJ-002 |  | final DB lock | 2028-08-31 | 9
PRJ-003 |  | Protocol (v1) | 2025-07-15 | 1
PRJ-003 |  | CTA submission | 2025-10-01 | 2
PRJ-003 |  | First SIV | 2026-01-15 | 3
PRJ-003 |  | LPI | 2027-09-30 | 4
PRJ-003 |  | interim DB lock cut-off | 2027-12-31 | 5
PRJ-003 |  | interim DB lock | 2028-02-29 | 6
PRJ-003 |  | final DB lock cut-off | 2028-12-31 | 7
PRJ-003 |  | final DB lock | 2029-02-28 | 8
PRJ-003 |  | Inspection | 2029-05-10 | 9 | Regulatory inspection
PRJ-003 |  | Inspection | 2029-07-22 | 10 | Regulatory inspection
PRJ-003 |  | Inspection | 2029-09-30 | 11 | Regulatory inspection
PRJ-004 |  | Protocol (v1) | 2026-04-10 | 1
PRJ-004 |  | CTA submission | 2026-06-01 | 2
PRJ-004 |  | First SIV | 2026-09-01 | 3
PRJ-004 |  | LPI | 2027-06-30 | 4
PRJ-004 |  | final DB lock cut-off | 2027-12-31 | 5
PRJ-004 |  | final DB lock | 2028-02-29 | 6
PRJ-005 |  | Protocol (v1) | 2026-06-15 | 1
PRJ-005 |  | CTA submission | 2026-09-01 | 2
PRJ-005 |  | First SIV | 2026-12-01 | 3
PRJ-005 |  | LPI | 2028-03-31 | 4
PRJ-005 |  | interim DB lock cut-off | 2028-06-30 | 5
PRJ-005 |  | interim DB lock | 2028-08-31 | 6
PRJ-005 |  | final DB lock cut-off | 2029-03-31 | 7
PRJ-005 |  | final DB lock | 2029-05-31 | 8

## ProjectPeriod
project_id | period_name | period_seq | period_start | period_end | weight | note_1
PRJ-001 | Before-Start-up | 1 | 2025-10-01 | 2025-10-15 | 0.6 | Derived from milestones
PRJ-001 | Start-up | 2 | 2025-10-16 | 2026-04-01 | 1.3 | Derived from milestones
PRJ-001 | Conduct | 3 | 2026-04-02 | 2027-02-27 | 1 | Derived from milestones
PRJ-001 | Close-out (final) | 4 | 2027-02-28 | 2027-08-14 | 1.4 | Derived from milestones
PRJ-001 | After Close-out (final) | 5 | 2027-08-15 | 2027-09-30 | 0.84 | Derived from milestones
PRJ-002 | Before-Start-up | 1 | 2026-01-01 | 2026-01-20 | 0.7 | Derived from milestones
PRJ-002 | Start-up | 2 | 2026-01-21 | 2026-07-01 | 1.4 | Derived from milestones
PRJ-002 | Conduct | 3 | 2026-07-02 | 2027-08-29 | 1.1 | Derived from milestones
PRJ-002 | Close-out (interim) | 4 | 2027-08-30 | 2027-11-30 | 1.3 | Derived from milestones
PRJ-002 | Conduct | 5 | 2027-12-01 | 2028-05-30 | 1.1 | Derived from milestones
PRJ-002 | Close-out (final) | 6 | 2028-05-31 | 2028-09-30 | 1.5 | Derived from milestones
PRJ-003 | Before-Start-up | 1 | 2025-07-01 | 2025-07-15 | 0.8 | Derived from milestones
PRJ-003 | Start-up | 2 | 2025-07-16 | 2026-01-15 | 1.6 | Derived from milestones
PRJ-003 | Conduct | 3 | 2026-01-16 | 2027-11-28 | 1.2 | Derived from milestones
PRJ-003 | Close-out (interim) | 4 | 2027-11-29 | 2028-02-29 | 1.4 | Derived from milestones
PRJ-003 | Conduct | 5 | 2028-03-01 | 2028-11-27 | 1.2 | Derived from milestones
PRJ-003 | Close-out (final) | 6 | 2028-11-28 | 2029-05-09 | 1.7 | Derived from milestones
PRJ-003 | After Close-out (final) | 7 | 2029-05-10 | 2029-10-31 | 1.02 | Derived from milestones
PRJ-004 | Before-Start-up | 1 | 2026-04-01 | 2026-04-10 | 0.5 | Derived from milestones
PRJ-004 | Start-up | 2 | 2026-04-11 | 2026-09-01 | 1.1 | Derived from milestones
PRJ-004 | Conduct | 3 | 2026-09-02 | 2027-11-28 | 0.9 | Derived from milestones
PRJ-004 | Close-out (final) | 4 | 2027-11-29 | 2028-03-31 | 1.2 | Derived from milestones
PRJ-005 | Before-Start-up | 1 | 2026-06-01 | 2026-06-15 | 0.8 | Derived from milestones
PRJ-005 | Start-up | 2 | 2026-06-16 | 2026-12-01 | 1.6 | Derived from milestones
PRJ-005 | Conduct | 3 | 2026-12-02 | 2028-05-30 | 1.2 | Derived from milestones
PRJ-005 | Close-out (interim) | 4 | 2028-05-31 | 2028-08-31 | 1.4 | Derived from milestones
PRJ-005 | Conduct | 5 | 2028-09-01 | 2029-02-27 | 1.2 | Derived from milestones
PRJ-005 | Close-out (final) | 6 | 2029-02-28 | 2029-06-30 | 1.7 | Derived from milestones
PRJ-006 | Planning | 1 | 2026-01-01 | 2026-04-02 | 0.8 | Entered by hand - no milestone mapping
PRJ-006 | Develop | 2 | 2026-04-03 | 2026-10-19 | 1.2 | Entered by hand - no milestone mapping
PRJ-006 | Close | 3 | 2026-10-20 | 2026-12-31 | 0.9 | Entered by hand - no milestone mapping
PRJ-007 | Planning | 1 | 2026-03-01 | 2026-05-31 | 0.8 | Entered by hand - no milestone mapping
PRJ-007 | Develop | 2 | 2026-06-01 | 2026-12-17 | 1.2 | Entered by hand - no milestone mapping
PRJ-007 | Close | 3 | 2026-12-18 | 2027-02-28 | 0.9 | Entered by hand - no milestone mapping

## PeriodWeightStandard
project_type | clinical_phase | period_name | weight | note_1
Clinical Trial | Phase 1 | Before-Start-up | 0.6 | Illustrative - replace with your figure
Clinical Trial | Phase 1 | Start-up | 1.3 | Illustrative - replace with your figure
Clinical Trial | Phase 1 | Conduct | 1 | Illustrative - replace with your figure
Clinical Trial | Phase 1 | Close-out (interim) | 1.2 | Illustrative - replace with your figure
Clinical Trial | Phase 1 | Close-out (final) | 1.4 | Illustrative - replace with your figure
Clinical Trial | Phase 1 | After Close-out (final) | 0.84 | Illustrative - replace with your figure
Clinical Trial | Phase 2 | Before-Start-up | 0.7 | Illustrative - replace with your figure
Clinical Trial | Phase 2 | Start-up | 1.4 | Illustrative - replace with your figure
Clinical Trial | Phase 2 | Conduct | 1.1 | Illustrative - replace with your figure
Clinical Trial | Phase 2 | Close-out (interim) | 1.3 | Illustrative - replace with your figure
Clinical Trial | Phase 2 | Close-out (final) | 1.5 | Illustrative - replace with your figure
Clinical Trial | Phase 2 | After Close-out (final) | 0.9 | Illustrative - replace with your figure
Clinical Trial | Phase 3 | Before-Start-up | 0.8 | Illustrative - replace with your figure
Clinical Trial | Phase 3 | Start-up | 1.6 | Illustrative - replace with your figure
Clinical Trial | Phase 3 | Conduct | 1.2 | Illustrative - replace with your figure
Clinical Trial | Phase 3 | Close-out (interim) | 1.4 | Illustrative - replace with your figure
Clinical Trial | Phase 3 | Close-out (final) | 1.7 | Illustrative - replace with your figure
Clinical Trial | Phase 3 | After Close-out (final) | 1.02 | Illustrative - replace with your figure
Clinical Trial | Phase 4 | Before-Start-up | 0.5 | Illustrative - replace with your figure
Clinical Trial | Phase 4 | Start-up | 1.1 | Illustrative - replace with your figure
Clinical Trial | Phase 4 | Conduct | 0.9 | Illustrative - replace with your figure
Clinical Trial | Phase 4 | Close-out (interim) | 1 | Illustrative - replace with your figure
Clinical Trial | Phase 4 | Close-out (final) | 1.2 | Illustrative - replace with your figure
Clinical Trial | Phase 4 | After Close-out (final) | 0.72 | Illustrative - replace with your figure

## RoleFactor
project_type | role_name | role_factor | role_note
Clinical Trial | Project oversight | 0.8 | Illustrative - replace with your figure
Clinical Trial | Lead data manager | 1.2 | Illustrative
Clinical Trial | Clinical Data Associator | 1 | Illustrative
Clinical Trial | Clinical Database Programmer | 1.1 | Illustrative
Clinical Trial | Data Analyst | 0.9 | Illustrative
Others | Project lead | 1 | Illustrative
Others | Main staff | 0.9 | Illustrative
Others | Other staff | 0.7 | Illustrative

## Person
person_id | person_name | department | primary_role | capacity_fte | employment_start | employment_end | note_1 | note_2 | note_3 | note_4 | note_5
PSN-001 | Kim S. | Data Management | Lead data manager | 1
PSN-002 | Park J. | Data Management | Lead data manager | 1
PSN-003 | Lee H. | Data Management | Clinical Data Associator | 1
PSN-004 | Choi M. | Data Management | Clinical Data Associator | 0.6
PSN-005 | Jung Y. | Programming | Clinical Database Programmer | 1
PSN-006 | Han B. | Programming | Clinical Database Programmer | 1
PSN-007 | Oh K. | Biostatistics | Data Analyst | 1
PSN-008 | Seo W. | Biostatistics | Data Analyst | 0.8
PSN-009 | Yoon T. | Clinical Operations | Project oversight | 1
PSN-010 | Nam R. | Clinical Operations | Project oversight | 1
PSN-011 | Ahn D. | Business Systems | Project lead | 1
PSN-012 | Baek C. | Business Systems | Main staff | 1

## Assignment
assignment_id | person_id | person_name | project_id | role_name | assign_start_date | assign_end_date | person_weight | note_1 | note_2 | note_3
ASG-001 | PSN-001 |  | PRJ-001 | Lead data manager | 2025-10-01 | 2027-06-30 | 0.5
ASG-002 | PSN-001 |  | PRJ-002 | Lead data manager | 2026-01-01 | 2028-09-30 | 0.5
ASG-003 | PSN-001 |  | PRJ-006 | Project lead | 2026-01-01 | 2026-12-31 | 0.4
ASG-004 | PSN-002 |  | PRJ-003 | Lead data manager | 2025-07-01 | 2029-03-31 | 0.55
ASG-005 | PSN-002 |  | PRJ-005 | Lead data manager | 2026-06-01 | 2029-06-30 | 0.45
ASG-006 | PSN-003 |  | PRJ-001 | Clinical Data Associator | 2026-01-01 | 2027-06-30 | 0.55
ASG-007 | PSN-003 |  | PRJ-003 | Clinical Data Associator | 2026-01-01 | 2029-03-31 | 0.55
ASG-024 | PSN-003 |  | PRJ-005 | Clinical Data Associator | 2027-07-01 | 2029-06-30 | 0.35
ASG-008 | PSN-004 |  | PRJ-004 | Clinical Data Associator | 2026-04-01 | 2028-03-31 | 0.3
ASG-009 | PSN-005 |  | PRJ-001 | Clinical Database Programmer | 2025-11-01 | 2026-12-31 | 0.45
ASG-010 | PSN-005 |  | PRJ-002 | Clinical Database Programmer | 2026-02-01 | 2028-09-30 | 0.45
ASG-025 | PSN-005 |  | PRJ-004 | Clinical Database Programmer | 2026-06-01 | 2028-03-31 | 0.3
ASG-011 | PSN-006 |  | PRJ-003 | Clinical Database Programmer | 2025-09-01 | 2029-03-31 | 0.5
ASG-012 | PSN-006 |  | PRJ-005 | Clinical Database Programmer | 2026-09-01 | 2029-06-30 | 0.4
ASG-026 | PSN-006 |  | PRJ-006 | Main staff | 2026-01-01 | 2026-12-31 | 0.3
ASG-013 | PSN-007 |  | PRJ-002 | Data Analyst | 2026-06-01 | 2028-09-30 | 0.55
ASG-014 | PSN-007 |  | PRJ-003 | Data Analyst | 2026-06-01 | 2029-03-31 | 0.55
ASG-015 | PSN-008 |  | PRJ-005 | Data Analyst | 2026-09-01 | 2029-06-30 | 0.5
ASG-027 | PSN-008 |  | PRJ-001 | Data Analyst | 2026-01-01 | 2027-06-30 | 0.4
ASG-016 | PSN-009 |  | PRJ-001 | Project oversight | 2025-10-01 | 2027-06-30 | 0.35
ASG-017 | PSN-009 |  | PRJ-002 | Project oversight | 2026-01-01 | 2028-09-30 | 0.35
ASG-018 | PSN-009 |  | PRJ-004 | Project oversight | 2026-04-01 | 2028-03-31 | 0.35
ASG-028 | PSN-009 |  | PRJ-006 | Project lead | 2026-01-01 | 2026-12-31 | 0.3
ASG-019 | PSN-010 |  | PRJ-003 | Project oversight | 2025-07-01 | 2029-03-31 | 0.45
ASG-020 | PSN-010 |  | PRJ-005 | Project oversight | 2026-06-01 | 2029-06-30 | 0.45
ASG-029 | PSN-010 |  | PRJ-007 | Project lead | 2026-03-01 | 2027-02-28 | 0.35
ASG-021 | PSN-011 |  | PRJ-007 | Project lead | 2026-03-01 | 2027-02-28 | 0.6
ASG-030 | PSN-011 |  | PRJ-006 | Main staff | 2026-01-01 | 2026-12-31 | 0.5
ASG-022 | PSN-012 |  | PRJ-006 | Main staff | 2026-01-01 | 2026-12-31 | 0.7
ASG-023 | PSN-012 |  | PRJ-007 | Other staff | 2026-03-01 | 2027-02-28 | 0.6

## PersonPeriodWeight
assignment_id | period_start | period_end | weight_override | reason
ASG-001 | 2026-07-01 | 2026-09-30 | 0.2 | Part-time - parental leave
ASG-004 | 2027-01-01 | 2027-03-31 | 0.7 | Covering interim analysis peak

## Lists
list_name | value | note_1
project_type | Clinical Trial
project_type | Others
clinical_phase | Phase 1
clinical_phase | Phase 2
clinical_phase | Phase 3
clinical_phase | Phase 4
outsourcing_type | Full outsourcing
outsourcing_type | Partial outsourcing
outsourcing_type | Full In-house
setup_party | by CRO
setup_party | by SB
EDC_system | Veeva EDC
EDC_system | Rave
EDC_system | eSOURCE
DataReviewSystem | Veeva DQS
DataReviewSystem | Medidata CDS
DataReviewSystem | No system (manual)
RBQM_system | CluePoints
RBQM_system | Medidata CDS
RBQM_system | No system (manual)
project_status | Planned
project_status | Active
project_status | On hold
project_status | Completed
milestone_name | Protocol (v1)
milestone_name | CTA submission
milestone_name | FPI
milestone_name | First SIV
milestone_name | LPI
milestone_name | interim DB lock cut-off
milestone_name | interim DB lock
milestone_name | final DB lock cut-off
milestone_name | final DB lock
milestone_name | Inspection
period_name_clinical | Before-Start-up
period_name_clinical | Start-up
period_name_clinical | Conduct
period_name_clinical | Close-out (interim)
period_name_clinical | Close-out (final)
period_name_clinical | After Close-out (final)
period_name_others | Planning
period_name_others | Develop
period_name_others | Close
role_clinical | Project oversight
role_clinical | Lead data manager
role_clinical | Clinical Data Associator
role_clinical | Clinical Database Programmer
role_clinical | Data Analyst
role_others | Project lead
role_others | Main staff
role_others | Other staff

## Config
parameter | value | note
schema_version | 2 | Structure version of this workbook. The application warns on a mismatch.
fte_hours_per_month | 160 | Hours equal to 1.00 FTE: 8 h/day x 5 days/week x 20 days/month.
over_allocation_fte | 1.5 | A person-month total above this is flagged as over-allocated.
under_allocation_fte | 0.8 | A person-month total below this counts toward an under-allocated run.
under_allocation_min_months | 3 | Consecutive months below the threshold before a run is flagged.
default_horizon_months | 24 | Months shown when the dashboard opens.
capacity_unit | FTE | Display unit: 'FTE' or 'percent'.