## 00_README
PRAP source data - dummy
Schema version 12. Matches PRAP_Development_Plan_v1.0.xlsx, sheet 04_Data_Model.
COLOUR KEY
Blue identifier or key column - these link the sheets together.
Green DERIVED. Do not type in these. They are LOCKED, so the sheet will refuse the
edit, and the column heading carries a note saying why. See below.
Yellow you must supply this value. The application cannot work it out.
Grey italic row an example, in the template only. Delete it before use.
DERIVED COLUMNS ARE LOCKED
Three columns are computed, not entered:
Project.total_period_months from start_date and end_date
Milestone.project_name looked up from Project
Assignment.person_name looked up from Person
Their cells are locked and every other cell on the sheet is not, so typing into one
is refused where it happens rather than going wrong later. There is NO PASSWORD:
Review > Unprotect Sheet turns it off if you genuinely need to paste a column.
Adding, deleting and sorting rows all still work with protection on; only adding or
removing COLUMNS is blocked, because the column set is the schema.
What the lock is protecting you from: a value typed into one of these is not
recalculated by anything, and the application recomputes the column on import in any
case - so a hand-typed one is discarded, and the disagreement is reported as V-13.
SHEETS
Project one row per project.
Milestone one row per milestone. Eight standard names.
ProjectPeriod the periods each project passes through, with their weights.
PeriodFTEStandard default weights per project type, clinical phase, WORK SCOPE and
period. Clinical trials only.
RoleFactor the relative burden of each role, per project type, clinical phase,
WORK SCOPE and period. Leave clinical_phase empty on the 'Others' rows.
Person one row per person.
Assignment one row per person + project + role.
PersonPeriodWeight optional windows where a person's weight differs.
Lists permitted values for every dropdown.
Config thresholds and settings.
FREE-TEXT NOTES
Every sheet carries at least one free-text column, so anything worth recording has a home:
Project note_1 .. note_5
Milestone note_1
ProjectPeriod note_1
PeriodFTEStandard note_1
RoleFactor role_note
Person note_1 .. note_5
Assignment note_1 .. note_3
PersonPeriodWeight reason
Lists note_1
Config note
Nothing in a note column affects the calculation. They are carried through import and export
unchanged, so they survive a round trip.
HOW THE CALCULATION USES THIS
monthly load = project period weight x role factor x person weight x month coverage
The result is FTE, where 1.00 FTE = 160 hours per month.
Over-allocated: a person's monthly total above 1.50 FTE.
Under-allocated: below 0.80 FTE for three or more consecutive months.
PERIODS
Clinical trial periods are derived from the milestone dates:
Before-Start-up project start, to the day before Start-up
Start-up one month before CTA submission, lasting four months
Conduct from the end of Start-up to the day before the next close-out
Close-out (interim) three months before the interim DB lock, to that lock
Conduct (again) from the interim DB lock to the day before Close-out (final)
Close-out (final) three months before the final DB lock, to that lock
After Close-out (final) the inspection activity that follows the final DB lock
Where 'Protocol (v1)' is recorded, Before-Start-up ends on it and Start-up begins the day after.
Where 'First SIV' (or 'FPI') is recorded, Start-up ends on it instead of running a fixed four
months. A recorded milestone always beats the month-offset fallback.
'Conduct' therefore appears TWICE where a trial has an interim DB lock. period_seq keeps
the two apart. A period squeezed to nothing by a tight timeline is simply omitted.
'Inspection' is the one milestone that may be recorded SEVERAL TIMES for a project. Only
inspections dated AFTER the final DB lock open the last period; an earlier one stays a marker.
'Others' projects have no milestones. Their period dates and weights are both typed in.
WORK SCOPE, AND THE NOTE BESIDE IT
work_scope_type is the field the CALCULATION reads: with the project type and the phase
it selects the standard weights and the role factors. It is a value list, so it has to be
one of a known set.
outsourcing_scope_det beside it is FREE TEXT and is read by people only. Write what is
actually outsourced and to whom - the detail the category cannot carry. Nothing you write
there changes a single figure.
It replaces outsourcing_type, which was a value list and is gone at schema 7. A workbook
still carrying that column is read: its values are moved across, and the application says
so once.
ASSIGNMENT DATES ARE OPTIONAL
Leave assign_start_date and assign_end_date BLANK for somebody who is on the project for
the whole of it - which is most people. A blank date means the project's own, so the two
never fall out of step when the project's dates move.
Fill them in only for a PARTIAL involvement: somebody who joins late, leaves early, or
covers one stretch of a longer study.
ADDING A PERMITTED VALUE
Insert a row inside that list's block on the Lists sheet, so the block stays contiguous -
the dropdowns read a range, not a scattered set of rows. work_scope_type is meant to be
extended this way: the three values supplied are a starting point, not a closed set.
WORK SCOPE, AND THE EMPTY ROW THAT COVERS EVERY SCOPE
PeriodFTEStandard and RoleFactor are keyed on work_scope_type as well as on the project
type, the phase and the period. A row with work_scope_type EMPTY applies to EVERY scope.
So fill the empty-scope rows first - they are your baseline - and add a scope-specific row
only where that scope really does change the number. A project looks for its own scope
first and falls back to the empty row, so nothing has to be entered three times to say
the same thing three times.
WHAT IS IN THIS FILE
10 projects 8 clinical trials (PRJ-001..008) + 2 'Others' (PRJ-009..010)
10 people PSN-001..010, including PSN-004 at 0.80, PSN-010 at 0.60 capacity
48 assignments, 60 milestones, 50 periods, spanning 50 months (Feb 2025 to Mar 2029)
Types: Biosimilar CT (Healthy), Biosimilar CT (Patient), NewDrug CT. Phases: Phase 1, Phase 2, Phase 3, Phase 4.
WHAT IT DEMONSTRATES
- 5 of the 8 trials carry an interim DB lock, so each has TWO 'Conduct'
stretches and two close-outs. The other 3 run Conduct once.
- 2 trials record an 'Inspection' after the final DB lock and so carry the
seventh period, 'After Close-out (final)'.
- The 2 'Others' projects have hand-entered periods and no milestones.
- PSN-001 carries two extra oversight assignments on top of a full round-robin
share, and so crosses the 1.50 FTE ceiling at the peaks.
- PSN-009 is the busiest by row count, at 8 assignments - every trial, as the only
Data Analyst. Their share of each is set lower to match.
- PSN-010 is a part-timer carrying 2 light assignments, so an under-allocation
run is raised. With the floor at 0.60 they CAN clear it, but only at full utilisation -
V-22 warns if anyone is recorded below the floor and so could never clear it.
- 2 assignments carry PersonPeriodWeight overrides, one of them with 2 separate
windows, which is why that sheet is keyed on assignment_id AND period_start.
- The months at either end of the span are naturally light: with few projects
overlapping there, most under-allocation runs sit in the ramp-up and wind-down.
The weights and role factors here are ILLUSTRATIVE, so the numbers can be exercised.
Replace them with your own before drawing any conclusion from the output.

## Project
project_id | project_name | project_type | project_category | clinical_phase | work_scope_type | outsourcing_scope_det | EDC_setup | DataReviewSystem_setup | RBQM_setup | DM_conduct | EDC_system | DataReviewSystem | RBQM_system | planned_member_count | start_date | end_date | total_period_months | status | estimation_type | note_1 | note_2 | note_3 | note_4 | note_5
PRJ-001 | ONV-101 Phase 1 | Biosimilar CT (Healthy) | Onvelaris | Phase 1 | fully outsourced | Everything with the CRO: EDC build, data review and reporting. | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 7 | 2025-03-01 | 2027-02-28 |  | Active | automatic
PRJ-002 | CAR-102 Phase 2 | Biosimilar CT (Patient) | Cardexa | Phase 2 | Partially outsourced (in-house for EDC) | EDC built and maintained in-house; data review and listings with the CRO. | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 3 | 2025-11-01 | 2028-04-30 |  | Active | automatic
PRJ-003 | NEU-103 Phase 3 | NewDrug CT | Neurexa | Phase 3 | fully in-housed | All data management in-house. No CRO on this study. | by SB | by CRO | by SB | by CRO | Veeva EDC | Veeva DQS | CluePoints | 8 | 2026-01-01 | 2028-06-30 |  | Active | automatic
PRJ-004 | REN-104 Phase 4 | Biosimilar CT (Healthy) | Renvia | Phase 4 | fully outsourced | Everything with the CRO: EDC build, data review and reporting. | by CRO | by SB | by CRO | by SB | Rave | Medidata CDS | Medidata CDS | 8 | 2025-06-01 | 2027-11-30 |  | On hold | automatic
PRJ-005 | HEP-105 Phase 1 | Biosimilar CT (Patient) | Hepatiq | Phase 1 | Partially outsourced (in-house for EDC) | EDC built and maintained in-house; data review and listings with the CRO. | by SB | by CRO | by SB | by CRO | eSOURCE | No system (manual) | No system (manual) | 4 | 2026-01-01 | 2028-06-30 |  | Completed | automatic
PRJ-006 | IMM-106 Phase 2 | NewDrug CT | Immunex | Phase 2 | fully in-housed | All data management in-house. No CRO on this study. | by CRO | by SB | by CRO | by SB | Veeva EDC | Veeva DQS | CluePoints | 4 | 2025-02-01 | 2027-01-31 |  | Planned | automatic
PRJ-007 | OST-107 Phase 3 | Biosimilar CT (Healthy) | Osteva | Phase 3 | fully outsourced | Everything with the CRO: EDC build, data review and reporting. | by SB | by CRO | by SB | by CRO | Rave | Medidata CDS | Medidata CDS | 5 | 2025-10-01 | 2029-03-31 |  | Active | manual
PRJ-008 | PUL-108 Phase 4 | Biosimilar CT (Patient) | Pulmora | Phase 4 | Partially outsourced (in-house for EDC) | EDC built and maintained in-house; data review and listings with the CRO. | by CRO | by SB | by CRO | by SB | eSOURCE | No system (manual) | No system (manual) | 3 | 2025-10-01 | 2029-03-31 |  | Active | automatic
PRJ-009 | CDISC library migration | Others |  |  | fully in-housed | All data management in-house. No CRO on this study. | [7 empty] | 5 | 2027-02-01 | 2027-07-31 |  | Active | automatic
PRJ-010 | eTMF rollout | Others |  |  | fully outsourced | Everything with the CRO: EDC build, data review and reporting. | [7 empty] | 2 | 2027-01-01 | 2027-09-30 |  | Active | automatic
Note on R1: total_period_months is DERIVED. DERIVED - formula, do not type. The cell is locked so it cannot be typed over by accident. Nothing is hidden: Review > Unprotect Sheet turns it off, there is no password. But a value typed here is not recalculated, and the application recomputes this column on import anyway - so a hand-typed one is silently discarded, and any disagreement is reported as V-13.

## Milestone
project_id | project_name | milestone_name | milestone_date | milestone_seq | note_1
PRJ-001 |  | Protocol (v1) | 2025-04-01 | 1
PRJ-001 |  | CTA submission | 2025-06-01 | 2
PRJ-001 |  | First SIV | 2025-10-01 | 3
PRJ-001 |  | LPI | 2026-05-01 | 4
PRJ-001 |  | interim DB lock cut-off | 2026-05-01 | 5
PRJ-001 |  | interim DB lock | 2026-07-01 | 6
PRJ-001 |  | final DB lock cut-off | 2026-11-01 | 7
PRJ-001 |  | final DB lock | 2027-01-01 | 8
PRJ-002 |  | Protocol (v1) | 2025-12-01 | 1
PRJ-002 |  | CTA submission | 2026-02-01 | 2
PRJ-002 |  | First SIV | 2026-06-01 | 3
PRJ-002 |  | LPI | 2027-05-01 | 4
PRJ-002 |  | interim DB lock cut-off | 2027-05-01 | 5
PRJ-002 |  | interim DB lock | 2027-07-01 | 6
PRJ-002 |  | final DB lock cut-off | 2028-01-01 | 7
PRJ-002 |  | final DB lock | 2028-03-01 | 8
PRJ-003 |  | Protocol (v1) | 2026-02-01 | 1
PRJ-003 |  | CTA submission | 2026-04-01 | 2
PRJ-003 |  | First SIV | 2026-08-01 | 3
PRJ-003 |  | LPI | 2027-07-01 | 4
PRJ-003 |  | final DB lock cut-off | 2028-03-01 | 5
PRJ-003 |  | final DB lock | 2028-05-01 | 6
PRJ-004 |  | Protocol (v1) | 2025-07-01 | 1
PRJ-004 |  | CTA submission | 2025-09-01 | 2
PRJ-004 |  | First SIV | 2026-01-01 | 3
PRJ-004 |  | LPI | 2026-12-01 | 4
PRJ-004 |  | final DB lock cut-off | 2027-08-01 | 5
PRJ-004 |  | final DB lock | 2027-10-01 | 6
PRJ-004 |  | Inspection | 2027-12-01 | 7 | Regulatory inspection
PRJ-005 |  | Protocol (v1) | 2026-02-01 | 1
PRJ-005 |  | CTA submission | 2026-04-01 | 2
PRJ-005 |  | First SIV | 2026-08-01 | 3
PRJ-005 |  | LPI | 2027-07-01 | 4
PRJ-005 |  | interim DB lock cut-off | 2027-07-01 | 5
PRJ-005 |  | interim DB lock | 2027-09-01 | 6
PRJ-005 |  | final DB lock cut-off | 2028-03-01 | 7
PRJ-005 |  | final DB lock | 2028-05-01 | 8
PRJ-006 |  | Protocol (v1) | 2025-03-01 | 1
PRJ-006 |  | CTA submission | 2025-05-01 | 2
PRJ-006 |  | First SIV | 2025-09-01 | 3
PRJ-006 |  | LPI | 2026-04-01 | 4
PRJ-006 |  | interim DB lock cut-off | 2026-04-01 | 5
PRJ-006 |  | interim DB lock | 2026-06-01 | 6
PRJ-006 |  | final DB lock cut-off | 2026-10-01 | 7
PRJ-006 |  | final DB lock | 2026-12-01 | 8
PRJ-007 |  | Protocol (v1) | 2025-11-01 | 1
PRJ-007 |  | CTA submission | 2026-01-01 | 2
PRJ-007 |  | First SIV | 2026-05-01 | 3
PRJ-007 |  | LPI | 2027-11-01 | 4
PRJ-007 |  | interim DB lock cut-off | 2027-12-01 | 5
PRJ-007 |  | interim DB lock | 2028-02-01 | 6
PRJ-007 |  | final DB lock cut-off | 2028-12-01 | 7
PRJ-007 |  | final DB lock | 2029-02-01 | 8
PRJ-008 |  | Protocol (v1) | 2025-11-01 | 1
PRJ-008 |  | CTA submission | 2026-01-01 | 2
PRJ-008 |  | First SIV | 2026-05-01 | 3
PRJ-008 |  | LPI | 2027-11-01 | 4
PRJ-008 |  | final DB lock cut-off | 2028-12-01 | 5
PRJ-008 |  | final DB lock | 2029-02-01 | 6
PRJ-008 |  | Inspection | 2029-04-01 | 7 | Regulatory inspection
Note on B1: project_name is DERIVED. DERIVED - looked up from Project, do not type. The cell is locked so it cannot be typed over by accident. Nothing is hidden: Review > Unprotect Sheet turns it off, there is no password. But a value typed here is not recalculated, and the application recomputes this column on import anyway - so a hand-typed one is silently discarded, and any disagreement is reported as V-13.

## ProjectPeriod
project_id | period_name | period_seq | period_start | period_end | weight | note_1
PRJ-001 | Before-Start-up | 1 | 2025-03-01 | 2025-04-01 | 0.84 | Derived from milestones
PRJ-001 | Start-up | 2 | 2025-04-02 | 2025-10-01 | 0.78 | Derived from milestones
PRJ-001 | Conduct (interim) | 3 | 2025-10-02 | 2026-03-31 | 0.84 | Derived from milestones
PRJ-001 | Close-out (interim) | 4 | 2026-04-01 | 2026-07-01 | 0.81 | Derived from milestones
PRJ-001 | Conduct (final) | 5 | 2026-07-02 | 2026-09-30 | 0.83 | Derived from milestones
PRJ-001 | Close-out (final) | 6 | 2026-10-01 | 2027-02-28 | 0.78 | Derived from milestones
PRJ-002 | Before-Start-up | 1 | 2025-11-01 | 2025-12-01 | 1.11 | Derived from milestones
PRJ-002 | Start-up | 2 | 2025-12-02 | 2026-06-01 | 1.1 | Derived from milestones
PRJ-002 | Conduct (interim) | 3 | 2026-06-02 | 2027-03-31 | 0.96 | Derived from milestones
PRJ-002 | Close-out (interim) | 4 | 2027-04-01 | 2027-07-01 | 1.05 | Derived from milestones
PRJ-002 | Conduct (final) | 5 | 2027-07-02 | 2027-11-30 | 1.1 | Derived from milestones
PRJ-002 | Close-out (final) | 6 | 2027-12-01 | 2028-04-30 | 1.04 | Derived from milestones
PRJ-003 | Before-Start-up | 1 | 2026-01-01 | 2026-02-01 | 1.12 | Derived from milestones
PRJ-003 | Start-up | 2 | 2026-02-02 | 2026-08-01 | 1.14 | Derived from milestones
PRJ-003 | Conduct (final) | 3 | 2026-08-02 | 2028-01-31 | 1.23 | Derived from milestones
PRJ-003 | Close-out (final) | 4 | 2028-02-01 | 2028-06-30 | 1.26 | Derived from milestones
PRJ-004 | Before-Start-up | 1 | 2025-06-01 | 2025-07-01 | 0.83 | Derived from milestones
PRJ-004 | Start-up | 2 | 2025-07-02 | 2026-01-01 | 0.85 | Derived from milestones
PRJ-004 | Conduct (final) | 3 | 2026-01-02 | 2027-06-30 | 0.87 | Derived from milestones
PRJ-004 | Close-out (final) | 4 | 2027-07-01 | 2027-11-30 | 0.87 | Derived from milestones
PRJ-004 | After Close-out (final) | 5 | 2027-12-01 | 2027-12-01 | 0.86 | Derived from milestones
PRJ-005 | Before-Start-up | 1 | 2026-01-01 | 2026-02-01 | 0.99 | Derived from milestones
PRJ-005 | Start-up | 2 | 2026-02-02 | 2026-08-01 | 0.93 | Derived from milestones
PRJ-005 | Conduct (interim) | 3 | 2026-08-02 | 2027-05-31 | 1.07 | Derived from milestones
PRJ-005 | Close-out (interim) | 4 | 2027-06-01 | 2027-09-01 | 1.06 | Derived from milestones
PRJ-005 | Conduct (final) | 5 | 2027-09-02 | 2028-01-31 | 1.05 | Derived from milestones
PRJ-005 | Close-out (final) | 6 | 2028-02-01 | 2028-06-30 | 1.02 | Derived from milestones
PRJ-006 | Before-Start-up | 1 | 2025-02-01 | 2025-03-01 | 1.12 | Derived from milestones
PRJ-006 | Start-up | 2 | 2025-03-02 | 2025-09-01 | 1.29 | Derived from milestones
PRJ-006 | Conduct (interim) | 3 | 2025-09-02 | 2026-02-28 | 1.22 | Derived from milestones
PRJ-006 | Close-out (interim) | 4 | 2026-03-01 | 2026-06-01 | 1.19 | Derived from milestones
PRJ-006 | Conduct (final) | 5 | 2026-06-02 | 2026-08-31 | 1.21 | Derived from milestones
PRJ-006 | Close-out (final) | 6 | 2026-09-01 | 2027-01-31 | 1.18 | Derived from milestones
PRJ-007 | Before-Start-up | 1 | 2025-10-01 | 2025-11-01 | 0.79 | Derived from milestones
PRJ-007 | Start-up | 2 | 2025-11-02 | 2026-05-01 | 0.89 | Derived from milestones
PRJ-007 | Conduct (interim) | 3 | 2026-05-02 | 2027-10-31 | 0.89 | Derived from milestones
PRJ-007 | Close-out (interim) | 4 | 2027-11-01 | 2028-02-01 | 0.82 | Derived from milestones
PRJ-007 | Conduct (final) | 5 | 2028-02-02 | 2028-10-31 | 0.76 | Derived from milestones
PRJ-007 | Close-out (final) | 6 | 2028-11-01 | 2029-03-31 | 0.82 | Derived from milestones
PRJ-008 | Before-Start-up | 1 | 2025-10-01 | 2025-11-01 | 0.96 | Derived from milestones
PRJ-008 | Start-up | 2 | 2025-11-02 | 2026-05-01 | 1.12 | Derived from milestones
PRJ-008 | Conduct (final) | 3 | 2026-05-02 | 2028-10-31 | 1.05 | Derived from milestones
PRJ-008 | Close-out (final) | 4 | 2028-11-01 | 2029-03-31 | 1.04 | Derived from milestones
PRJ-008 | After Close-out (final) | 5 | 2029-04-01 | 2029-04-01 | 1.07 | Derived from milestones
PRJ-009 | Planning | 1 | 2027-02-01 | 2027-03-18 | 0.93 | Entered by hand - no milestone mapping
PRJ-009 | Develop | 2 | 2027-03-19 | 2027-06-25 | 0.93 | Entered by hand - no milestone mapping
PRJ-009 | Close | 3 | 2027-06-26 | 2027-07-31 | 0.96 | Entered by hand - no milestone mapping
PRJ-010 | Planning | 1 | 2027-01-01 | 2027-03-10 | 1.11 | Entered by hand - no milestone mapping
PRJ-010 | Develop | 2 | 2027-03-11 | 2027-08-06 | 1.09 | Entered by hand - no milestone mapping
PRJ-010 | Close | 3 | 2027-08-07 | 2027-09-30 | 1.02 | Entered by hand - no milestone mapping

## PeriodFTEStandard
project_type | clinical_phase | work_scope_type | period_name | standard_fte | note_1
NewDrug CT | Phase 1 |  | Before-Start-up | 1.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | 3.27 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | 2.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | 2.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | 3.52 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | 2.11 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | 1.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | 3.52 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | 2.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | 3.27 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | 2.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | 3.77 | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | 2.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | 2.01 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | 4.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | 3.52 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | 4.27 | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | 2.56 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | 1.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | 2.76 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | 2.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | 2.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | 2.26 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | 3.02 | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | 1.81 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | 1.28 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | 2.13 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | 2.13 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | 2.99 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | 1.79 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | 1.5 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | 2.99 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | 2.35 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | 2.35 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | 3.2 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | 1.92 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | 1.71 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | 3.42 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | 2.99 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | 3.63 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | 2.18 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | 1.07 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | 2.35 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | 1.92 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | 2.13 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | 1.92 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | 2.57 | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | 1.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | 1.39 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | 3.01 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | 2.31 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | 2.31 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | 3.24 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | 1.94 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | 1.62 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | 3.24 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | 2.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | 3.01 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | 2.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | 3.47 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | 2.08 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | 1.85 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | 3.7 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | 3.24 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | 3.93 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | 2.36 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | 1.16 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | 2.54 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | 2.08 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | 2.31 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | 2.08 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | 2.78 | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | 1.67 | Default assumption - replace with your own figure
Others |  |  | Planning | 1.21 | Default assumption - replace with your own figure
Others |  |  | Develop | 2.31 | Default assumption - replace with your own figure
Others |  |  | Close | 1.51 | Default assumption - replace with your own figure
NewDrug CT | Phase 1 | fully in-housed | Before-Start-up | 1.74 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Start-up | 3.76 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Conduct (interim) | 2.89 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Close-out (interim) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Conduct (final) | 2.89 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | Close-out (final) | 4.05 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully in-housed | After Close-out (final) | 2.43 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Before-Start-up | 2.02 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Start-up | 4.05 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Conduct (interim) | 3.17 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Close-out (interim) | 3.76 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Conduct (final) | 3.17 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | Close-out (final) | 4.34 | Illustrative - fully in-housed
NewDrug CT | Phase 2 | fully in-housed | After Close-out (final) | 2.6 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Before-Start-up | 2.31 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Start-up | 4.62 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Conduct (interim) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Close-out (interim) | 4.05 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Conduct (final) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | Close-out (final) | 4.91 | Illustrative - fully in-housed
NewDrug CT | Phase 3 | fully in-housed | After Close-out (final) | 2.94 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Before-Start-up | 1.45 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Start-up | 3.17 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Conduct (interim) | 2.6 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Close-out (interim) | 2.89 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Conduct (final) | 2.6 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | Close-out (final) | 3.47 | Illustrative - fully in-housed
NewDrug CT | Phase 4 | fully in-housed | After Close-out (final) | 2.08 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Before-Start-up | 1.47 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Start-up | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Conduct (interim) | 2.45 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Close-out (interim) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Conduct (final) | 2.45 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | Close-out (final) | 3.44 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 1 | fully in-housed | After Close-out (final) | 2.06 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Before-Start-up | 1.72 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Start-up | 3.44 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Conduct (interim) | 2.7 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Close-out (interim) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Conduct (final) | 2.7 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | Close-out (final) | 3.68 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 2 | fully in-housed | After Close-out (final) | 2.21 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Before-Start-up | 1.97 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Start-up | 3.93 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Conduct (interim) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Close-out (interim) | 3.44 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Conduct (final) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | Close-out (final) | 4.17 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 3 | fully in-housed | After Close-out (final) | 2.51 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Before-Start-up | 1.23 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Start-up | 2.7 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Conduct (interim) | 2.21 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Close-out (interim) | 2.45 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Conduct (final) | 2.21 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | Close-out (final) | 2.96 | Illustrative - fully in-housed
Biosimilar CT (Healthy) | Phase 4 | fully in-housed | After Close-out (final) | 1.77 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Before-Start-up | 1.6 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Start-up | 3.46 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Conduct (interim) | 2.66 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Close-out (interim) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Conduct (final) | 2.66 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | Close-out (final) | 3.73 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 1 | fully in-housed | After Close-out (final) | 2.23 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Before-Start-up | 1.86 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Start-up | 3.73 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Conduct (interim) | 2.92 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Close-out (interim) | 3.46 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Conduct (final) | 2.92 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | Close-out (final) | 3.99 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 2 | fully in-housed | After Close-out (final) | 2.39 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Before-Start-up | 2.13 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Start-up | 4.25 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Conduct (interim) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Close-out (interim) | 3.73 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Conduct (final) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | Close-out (final) | 4.52 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 3 | fully in-housed | After Close-out (final) | 2.71 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Before-Start-up | 1.33 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Start-up | 2.92 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Conduct (interim) | 2.39 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Close-out (interim) | 2.66 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Conduct (final) | 2.39 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | Close-out (final) | 3.2 | Illustrative - fully in-housed
Biosimilar CT (Patient) | Phase 4 | fully in-housed | After Close-out (final) | 1.92 | Illustrative - fully in-housed
Others |  | fully in-housed | Planning | 1.39 | Illustrative - fully in-housed
Others |  | fully in-housed | Develop | 2.66 | Illustrative - fully in-housed
Others |  | fully in-housed | Close | 1.74 | Illustrative - fully in-housed
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | 1.21 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | 2.62 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | 2.01 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | 2.01 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | 2.82 | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | 1.69 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | 1.41 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | 2.82 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | 2.21 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | 2.62 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | 2.21 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | 3.02 | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | 1.81 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | 1.61 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | 3.22 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | 2.82 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | 3.42 | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | 2.05 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | 1.01 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | 2.21 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | 1.81 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | 2.01 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | 1.81 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | 2.42 | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | 1.45 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | 1.02 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | 1.7 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | 1.7 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | 2.39 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | 1.43 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | 1.2 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | 2.39 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | 1.88 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | 1.88 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | 2.56 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | 1.54 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | 1.37 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | 2.74 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | 2.39 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | 2.9 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | 1.74 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | 0.86 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | 1.88 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | 1.54 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | 1.7 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | 1.54 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | 2.06 | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | 1.23 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | 1.11 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | 2.41 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | 1.85 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | 1.85 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | 2.59 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | 1.55 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | 1.3 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | 2.59 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | 2.03 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | 2.41 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | 2.03 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | 2.78 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | 1.66 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | 1.48 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | 2.96 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | 2.59 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | 3.14 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | 1.89 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | 0.93 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | 2.03 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | 1.66 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | 1.85 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | 1.66 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | 2.22 | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | 1.34 | Illustrative - fully outsourced
Others |  | fully outsourced | Planning | 0.97 | Illustrative - fully outsourced
Others |  | fully outsourced | Develop | 1.85 | Illustrative - fully outsourced
Others |  | fully outsourced | Close | 1.21 | Illustrative - fully outsourced

## RoleFactor
project_type | clinical_phase | work_scope_type | period_name | role_name | role_factor | absorbed_by | role_note
NewDrug CT | Phase 1 |  | Before-Start-up | Project oversight | 0.68 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Lead data manager | 0.91 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Clinical Database Programmer | 0.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Before-Start-up | Data Analyst | 0.34 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Clinical Data Associator | 0.76 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Clinical Database Programmer | 1.57 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Start-up | Data Analyst | 0.51 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (interim) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Lead data manager | 1.25 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Clinical Data Associator | 1.04 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Clinical Database Programmer | 1.04 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (interim) | Data Analyst | 1.11 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Conduct (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Clinical Data Associator | 0.85 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Clinical Database Programmer | 1.15 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | Close-out (final) | Data Analyst | 1.28 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Project oversight | 0.61 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Lead data manager | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Clinical Database Programmer | 0.42 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 1 |  | After Close-out (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Lead data manager | 0.96 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Clinical Database Programmer | 0.77 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Before-Start-up | Data Analyst | 0.36 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Clinical Data Associator | 0.8 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Clinical Database Programmer | 1.65 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Start-up | Data Analyst | 0.54 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (interim) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Lead data manager | 1.32 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Clinical Data Associator | 1.1 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Clinical Database Programmer | 1.1 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (interim) | Data Analyst | 1.17 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Conduct (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Clinical Data Associator | 0.9 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Clinical Database Programmer | 1.21 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | Close-out (final) | Data Analyst | 1.35 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Project oversight | 0.64 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Lead data manager | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Clinical Database Programmer | 0.44 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 2 |  | After Close-out (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Project oversight | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Lead data manager | 1.01 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Clinical Data Associator | 0.53 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Clinical Database Programmer | 0.81 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Before-Start-up | Data Analyst | 0.38 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Lead data manager | 1.51 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Clinical Data Associator | 0.84 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Clinical Database Programmer | 1.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Start-up | Data Analyst | 0.57 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Lead data manager | 1.26 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Clinical Data Associator | 1.37 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Clinical Database Programmer | 0.92 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (interim) | Data Analyst | 0.85 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Lead data manager | 1.39 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Clinical Data Associator | 1.16 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Clinical Database Programmer | 1.16 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (interim) | Data Analyst | 1.23 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Lead data manager | 1.26 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Clinical Data Associator | 1.37 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Clinical Database Programmer | 0.92 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Conduct (final) | Data Analyst | 0.85 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Project oversight | 0.84 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Lead data manager | 1.51 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Clinical Data Associator | 0.95 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Clinical Database Programmer | 1.27 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | Close-out (final) | Data Analyst | 1.42 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Project oversight | 0.67 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Lead data manager | 0.88 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Clinical Data Associator | 0.53 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Clinical Database Programmer | 0.46 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 3 |  | After Close-out (final) | Data Analyst | 0.85 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Project oversight | 0.65 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Lead data manager | 0.86 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Clinical Database Programmer | 0.69 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Before-Start-up | Data Analyst | 0.32 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Clinical Data Associator | 0.72 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Clinical Database Programmer | 1.49 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Start-up | Data Analyst | 0.49 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (interim) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Lead data manager | 1.19 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Clinical Data Associator | 0.99 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Clinical Database Programmer | 0.99 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (interim) | Data Analyst | 1.05 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Conduct (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Clinical Data Associator | 0.81 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Clinical Database Programmer | 1.09 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | Close-out (final) | Data Analyst | 1.22 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Project oversight | 0.58 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Lead data manager | 0.76 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Clinical Database Programmer | 0.4 |  | Default assumption - replace with your own figure
NewDrug CT | Phase 4 |  | After Close-out (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Project oversight | 0.65 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Lead data manager | 0.87 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Clinical Database Programmer | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Before-Start-up | Data Analyst | 0.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Clinical Data Associator | 0.72 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Clinical Database Programmer | 1.49 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Start-up | Data Analyst | 0.49 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (interim) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Lead data manager | 1.19 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Clinical Data Associator | 0.99 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Clinical Database Programmer | 0.99 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (interim) | Data Analyst | 1.06 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Lead data manager | 1.08 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Clinical Data Associator | 1.17 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Conduct (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Lead data manager | 1.3 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Clinical Data Associator | 0.81 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Clinical Database Programmer | 1.09 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | Close-out (final) | Data Analyst | 1.22 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Project oversight | 0.58 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Lead data manager | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Clinical Data Associator | 0.45 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Clinical Database Programmer | 0.4 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 1 |  | After Close-out (final) | Data Analyst | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Lead data manager | 0.91 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Clinical Database Programmer | 0.73 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Before-Start-up | Data Analyst | 0.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Clinical Data Associator | 0.76 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Clinical Database Programmer | 1.57 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Start-up | Data Analyst | 0.51 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (interim) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Lead data manager | 1.25 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Clinical Data Associator | 1.04 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Clinical Database Programmer | 1.04 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (interim) | Data Analyst | 1.11 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Lead data manager | 1.14 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Clinical Data Associator | 1.23 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Clinical Database Programmer | 0.84 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Conduct (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Project oversight | 0.76 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Lead data manager | 1.37 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Clinical Data Associator | 0.85 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Clinical Database Programmer | 1.15 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | Close-out (final) | Data Analyst | 1.28 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Project oversight | 0.61 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Lead data manager | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Clinical Database Programmer | 0.42 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 2 |  | After Close-out (final) | Data Analyst | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Project oversight | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Lead data manager | 0.96 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Clinical Database Programmer | 0.77 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Before-Start-up | Data Analyst | 0.36 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Clinical Data Associator | 0.8 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Clinical Database Programmer | 1.65 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Start-up | Data Analyst | 0.54 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (interim) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Lead data manager | 1.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Clinical Data Associator | 1.1 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Clinical Database Programmer | 1.1 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (interim) | Data Analyst | 1.17 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Lead data manager | 1.2 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Clinical Data Associator | 1.3 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Clinical Database Programmer | 0.88 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Conduct (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Project oversight | 0.8 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Lead data manager | 1.44 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Clinical Data Associator | 0.9 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Clinical Database Programmer | 1.21 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | Close-out (final) | Data Analyst | 1.35 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Project oversight | 0.64 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Lead data manager | 0.84 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Clinical Data Associator | 0.5 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Clinical Database Programmer | 0.44 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 3 |  | After Close-out (final) | Data Analyst | 0.81 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Project oversight | 0.62 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Lead data manager | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Clinical Data Associator | 0.43 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Clinical Database Programmer | 0.66 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Before-Start-up | Data Analyst | 0.31 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Clinical Data Associator | 0.68 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Clinical Database Programmer | 1.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Start-up | Data Analyst | 0.46 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Lead data manager | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Clinical Data Associator | 1.11 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Clinical Database Programmer | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (interim) | Data Analyst | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Lead data manager | 1.13 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Clinical Data Associator | 0.94 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Clinical Database Programmer | 0.94 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (interim) | Data Analyst | 1 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Lead data manager | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Clinical Data Associator | 1.11 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Clinical Database Programmer | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Conduct (final) | Data Analyst | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Project oversight | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Clinical Data Associator | 0.77 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Clinical Database Programmer | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | Close-out (final) | Data Analyst | 1.15 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Project oversight | 0.55 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Lead data manager | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Clinical Data Associator | 0.43 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Clinical Database Programmer | 0.38 |  | Default assumption - replace with your own figure
Biosimilar CT (Healthy) | Phase 4 |  | After Close-out (final) | Data Analyst | 0.69 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Project oversight | 0.67 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Lead data manager | 0.89 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Clinical Database Programmer | 0.72 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Before-Start-up | Data Analyst | 0.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Lead data manager | 1.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Clinical Data Associator | 0.74 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Clinical Database Programmer | 1.54 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Start-up | Data Analyst | 0.5 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Lead data manager | 1.12 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Clinical Data Associator | 1.21 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Clinical Database Programmer | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (interim) | Data Analyst | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Clinical Data Associator | 1.02 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Clinical Database Programmer | 1.02 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (interim) | Data Analyst | 1.09 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Lead data manager | 1.12 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Clinical Data Associator | 1.21 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Clinical Database Programmer | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Conduct (final) | Data Analyst | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Lead data manager | 1.34 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Clinical Data Associator | 0.84 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Clinical Database Programmer | 1.13 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | Close-out (final) | Data Analyst | 1.26 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Project oversight | 0.6 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Lead data manager | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Clinical Database Programmer | 0.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 1 |  | After Close-out (final) | Data Analyst | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Lead data manager | 0.94 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Clinical Data Associator | 0.49 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Clinical Database Programmer | 0.75 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Before-Start-up | Data Analyst | 0.35 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Lead data manager | 1.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Clinical Data Associator | 0.78 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Clinical Database Programmer | 1.62 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Start-up | Data Analyst | 0.53 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Lead data manager | 1.18 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Clinical Data Associator | 1.27 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Clinical Database Programmer | 0.86 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (interim) | Data Analyst | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Lead data manager | 1.29 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Clinical Data Associator | 1.08 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Clinical Database Programmer | 1.08 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (interim) | Data Analyst | 1.15 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Lead data manager | 1.18 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Clinical Data Associator | 1.27 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Clinical Database Programmer | 0.86 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Conduct (final) | Data Analyst | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Project oversight | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Lead data manager | 1.41 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Clinical Data Associator | 0.88 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Clinical Database Programmer | 1.19 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | Close-out (final) | Data Analyst | 1.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Project oversight | 0.63 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Lead data manager | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Clinical Data Associator | 0.49 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Clinical Database Programmer | 0.43 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 2 |  | After Close-out (final) | Data Analyst | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Project oversight | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Lead data manager | 0.99 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Clinical Data Associator | 0.51 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Clinical Database Programmer | 0.79 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Before-Start-up | Data Analyst | 0.37 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Lead data manager | 1.48 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Clinical Data Associator | 0.82 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Clinical Database Programmer | 1.7 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Start-up | Data Analyst | 0.56 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Clinical Data Associator | 1.34 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Clinical Database Programmer | 0.91 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (interim) | Data Analyst | 0.83 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Lead data manager | 1.36 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Clinical Data Associator | 1.13 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Clinical Database Programmer | 1.13 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (interim) | Data Analyst | 1.2 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Lead data manager | 1.23 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Clinical Data Associator | 1.34 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Clinical Database Programmer | 0.91 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Conduct (final) | Data Analyst | 0.83 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Project oversight | 0.82 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Lead data manager | 1.48 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Clinical Data Associator | 0.93 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Clinical Database Programmer | 1.25 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | Close-out (final) | Data Analyst | 1.39 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Project oversight | 0.66 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Lead data manager | 0.86 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Clinical Data Associator | 0.51 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Clinical Database Programmer | 0.45 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 3 |  | After Close-out (final) | Data Analyst | 0.83 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Project oversight | 0.64 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Lead data manager | 0.85 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Clinical Data Associator | 0.44 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Clinical Database Programmer | 0.68 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Before-Start-up | Data Analyst | 0.32 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Lead data manager | 1.27 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Clinical Data Associator | 0.71 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Clinical Database Programmer | 1.46 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Start-up | Data Analyst | 0.48 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Lead data manager | 1.06 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Clinical Data Associator | 1.15 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Clinical Database Programmer | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (interim) | Data Analyst | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Lead data manager | 1.16 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Clinical Data Associator | 0.97 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Clinical Database Programmer | 0.97 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (interim) | Data Analyst | 1.03 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Lead data manager | 1.06 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Clinical Data Associator | 1.15 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Clinical Database Programmer | 0.78 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Conduct (final) | Data Analyst | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Project oversight | 0.71 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Lead data manager | 1.27 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Clinical Data Associator | 0.79 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Clinical Database Programmer | 1.07 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | Close-out (final) | Data Analyst | 1.19 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Project oversight | 0.56 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Lead data manager | 0.74 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Clinical Data Associator | 0.44 | Lead data manager | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Clinical Database Programmer | 0.39 |  | Default assumption - replace with your own figure
Biosimilar CT (Patient) | Phase 4 |  | After Close-out (final) | Data Analyst | 0.71 |  | Default assumption - replace with your own figure
Others |  |  | Planning | Project lead | 1.1 |  | Default assumption - replace with your own figure
Others |  |  | Planning | Main staff | 0.63 |  | Default assumption - replace with your own figure
Others |  |  | Planning | Other staff | 0.42 | Project lead | Default assumption - replace with your own figure
Others |  |  | Develop | Project lead | 1 |  | Default assumption - replace with your own figure
Others |  |  | Develop | Main staff | 1.08 |  | Default assumption - replace with your own figure
Others |  |  | Develop | Other staff | 0.77 | Project lead | Default assumption - replace with your own figure
Others |  |  | Close | Project lead | 0.9 |  | Default assumption - replace with your own figure
Others |  |  | Close | Main staff | 0.81 |  | Default assumption - replace with your own figure
Others |  |  | Close | Other staff | 0.7 | Project lead | Default assumption - replace with your own figure
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Project oversight | 0.71 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Lead data manager | 0.86 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.4 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Before-Start-up | Data Analyst | 0.29 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Lead data manager | 1.3 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Clinical Data Associator | 0.46 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Clinical Database Programmer | 0.86 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Start-up | Data Analyst | 0.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (interim) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Lead data manager | 1.19 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.62 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.57 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (interim) | Data Analyst | 0.94 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Conduct (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Lead data manager | 1.3 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.51 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.63 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | Close-out (final) | Data Analyst | 1.09 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Project oversight | 0.64 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Lead data manager | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.23 |  | Illustrative - fully outsourced
NewDrug CT | Phase 1 | fully outsourced | After Close-out (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Lead data manager | 0.91 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.42 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Before-Start-up | Data Analyst | 0.31 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Lead data manager | 1.37 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Clinical Data Associator | 0.48 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Clinical Database Programmer | 0.91 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Start-up | Data Analyst | 0.46 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (interim) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Lead data manager | 1.25 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.66 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.61 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (interim) | Data Analyst | 0.99 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Conduct (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Lead data manager | 1.37 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.54 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.67 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | Close-out (final) | Data Analyst | 1.15 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Project oversight | 0.67 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Lead data manager | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.24 |  | Illustrative - fully outsourced
NewDrug CT | Phase 2 | fully outsourced | After Close-out (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Project oversight | 0.8 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Lead data manager | 0.96 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.32 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.45 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Before-Start-up | Data Analyst | 0.32 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Lead data manager | 1.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Clinical Data Associator | 0.5 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Clinical Database Programmer | 0.95 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Start-up | Data Analyst | 0.48 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Lead data manager | 1.2 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.82 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.51 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (interim) | Data Analyst | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Lead data manager | 1.32 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.64 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (interim) | Data Analyst | 1.05 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Lead data manager | 1.2 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.82 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.51 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Conduct (final) | Data Analyst | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Project oversight | 0.88 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Lead data manager | 1.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.57 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.7 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | Close-out (final) | Data Analyst | 1.21 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Project oversight | 0.7 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Lead data manager | 0.84 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.32 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.25 |  | Illustrative - fully outsourced
NewDrug CT | Phase 3 | fully outsourced | After Close-out (final) | Data Analyst | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Project oversight | 0.68 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Lead data manager | 0.82 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.38 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Before-Start-up | Data Analyst | 0.27 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Lead data manager | 1.23 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Clinical Data Associator | 0.43 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Clinical Database Programmer | 0.82 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Start-up | Data Analyst | 0.42 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (interim) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Lead data manager | 1.13 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.59 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.54 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (interim) | Data Analyst | 0.89 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Conduct (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Lead data manager | 1.23 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.49 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.6 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | Close-out (final) | Data Analyst | 1.04 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Project oversight | 0.61 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Lead data manager | 0.72 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.22 |  | Illustrative - fully outsourced
NewDrug CT | Phase 4 | fully outsourced | After Close-out (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Project oversight | 0.68 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Lead data manager | 0.83 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.38 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Before-Start-up | Data Analyst | 0.27 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Lead data manager | 1.23 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Clinical Data Associator | 0.43 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Clinical Database Programmer | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Start-up | Data Analyst | 0.42 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (interim) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Lead data manager | 1.13 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.59 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.54 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (interim) | Data Analyst | 0.9 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Lead data manager | 1.03 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.7 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Conduct (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Lead data manager | 1.23 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.49 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.6 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | Close-out (final) | Data Analyst | 1.04 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Project oversight | 0.61 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Lead data manager | 0.72 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.27 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.22 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 1 | fully outsourced | After Close-out (final) | Data Analyst | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Lead data manager | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.4 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Before-Start-up | Data Analyst | 0.29 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Lead data manager | 1.3 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Clinical Data Associator | 0.46 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Clinical Database Programmer | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Start-up | Data Analyst | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (interim) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Lead data manager | 1.19 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.62 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.57 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (interim) | Data Analyst | 0.94 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Lead data manager | 1.08 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.74 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.46 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Conduct (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Project oversight | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Lead data manager | 1.3 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.51 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.63 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | Close-out (final) | Data Analyst | 1.09 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Project oversight | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Lead data manager | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.23 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 2 | fully outsourced | After Close-out (final) | Data Analyst | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Project oversight | 0.76 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Lead data manager | 0.91 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.42 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Before-Start-up | Data Analyst | 0.31 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Lead data manager | 1.37 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Clinical Data Associator | 0.48 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Clinical Database Programmer | 0.91 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Start-up | Data Analyst | 0.46 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (interim) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Lead data manager | 1.25 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.66 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.61 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (interim) | Data Analyst | 0.99 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Lead data manager | 1.14 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.78 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.48 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Conduct (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Project oversight | 0.84 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Lead data manager | 1.37 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.54 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | Close-out (final) | Data Analyst | 1.15 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Project oversight | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Lead data manager | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.3 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.24 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 3 | fully outsourced | After Close-out (final) | Data Analyst | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Project oversight | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Lead data manager | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.36 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Before-Start-up | Data Analyst | 0.26 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Clinical Data Associator | 0.41 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Clinical Database Programmer | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Start-up | Data Analyst | 0.39 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Lead data manager | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.67 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (interim) | Data Analyst | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Lead data manager | 1.07 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.56 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.52 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (interim) | Data Analyst | 0.85 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Lead data manager | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.67 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Conduct (final) | Data Analyst | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Project oversight | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.46 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.57 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | Close-out (final) | Data Analyst | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Project oversight | 0.58 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Lead data manager | 0.68 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.21 |  | Illustrative - fully outsourced
Biosimilar CT (Healthy) | Phase 4 | fully outsourced | After Close-out (final) | Data Analyst | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Project oversight | 0.7 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Lead data manager | 0.85 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.4 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Before-Start-up | Data Analyst | 0.29 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Lead data manager | 1.27 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Clinical Data Associator | 0.44 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Clinical Database Programmer | 0.85 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Start-up | Data Analyst | 0.42 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Lead data manager | 1.06 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.73 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.45 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (interim) | Data Analyst | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.61 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.56 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (interim) | Data Analyst | 0.93 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Lead data manager | 1.06 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.73 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.45 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Conduct (final) | Data Analyst | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Lead data manager | 1.27 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.5 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | Close-out (final) | Data Analyst | 1.07 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Project oversight | 0.63 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Lead data manager | 0.74 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.28 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.23 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 1 | fully outsourced | After Close-out (final) | Data Analyst | 0.64 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Lead data manager | 0.89 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.29 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Before-Start-up | Data Analyst | 0.3 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Lead data manager | 1.34 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Clinical Data Associator | 0.47 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Clinical Database Programmer | 0.89 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Start-up | Data Analyst | 0.45 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Lead data manager | 1.12 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.76 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.47 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (interim) | Data Analyst | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Lead data manager | 1.23 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.65 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (interim) | Data Analyst | 0.98 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Lead data manager | 1.12 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.76 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.47 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Conduct (final) | Data Analyst | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Project oversight | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Lead data manager | 1.34 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.53 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.65 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | Close-out (final) | Data Analyst | 1.12 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Project oversight | 0.66 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Lead data manager | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.29 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.24 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 2 | fully outsourced | After Close-out (final) | Data Analyst | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Project oversight | 0.78 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Lead data manager | 0.94 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.31 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Before-Start-up | Data Analyst | 0.31 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Lead data manager | 1.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Clinical Data Associator | 0.49 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Clinical Database Programmer | 0.94 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Start-up | Data Analyst | 0.48 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.8 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.5 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (interim) | Data Analyst | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Lead data manager | 1.29 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.68 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.62 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (interim) | Data Analyst | 1.02 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Lead data manager | 1.17 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.8 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.5 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Conduct (final) | Data Analyst | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Project oversight | 0.86 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Lead data manager | 1.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.56 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | Close-out (final) | Data Analyst | 1.18 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Project oversight | 0.69 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Lead data manager | 0.82 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.31 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.25 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 3 | fully outsourced | After Close-out (final) | Data Analyst | 0.71 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Project oversight | 0.67 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Lead data manager | 0.81 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Clinical Database Programmer | 0.37 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Before-Start-up | Data Analyst | 0.27 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Lead data manager | 1.21 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Clinical Data Associator | 0.43 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Clinical Database Programmer | 0.8 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Start-up | Data Analyst | 0.41 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Lead data manager | 1.01 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Data Associator | 0.69 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (interim) | Data Analyst | 0.6 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Lead data manager | 1.1 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Data Associator | 0.58 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Clinical Database Programmer | 0.53 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (interim) | Data Analyst | 0.88 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Lead data manager | 1.01 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Clinical Data Associator | 0.69 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Clinical Database Programmer | 0.43 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Conduct (final) | Data Analyst | 0.6 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Project oversight | 0.75 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Lead data manager | 1.21 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Clinical Data Associator | 0.47 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Clinical Database Programmer | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | Close-out (final) | Data Analyst | 1.01 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Project oversight | 0.59 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Lead data manager | 0.7 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Data Associator | 0.26 | Lead data manager | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Clinical Database Programmer | 0.21 |  | Illustrative - fully outsourced
Biosimilar CT (Patient) | Phase 4 | fully outsourced | After Close-out (final) | Data Analyst | 0.6 |  | Illustrative - fully outsourced

## Person
person_id | person_name | department | primary_role | capacity_fte | employment_start | employment_end | note_1 | note_2 | note_3 | note_4 | note_5
PSN-001 | Kim S. | Clinical Operations | Project oversight | 1
PSN-002 | Park J. | Clinical Operations | Project oversight | 1
PSN-003 | Lee H. | Data Management | Lead data manager | 1
PSN-004 | Choi M. | Data Management | Lead data manager | 0.8
PSN-005 | Jung Y. | Data Management | Clinical Data Associator | 1
PSN-006 | Han B. | Data Management | Clinical Data Associator | 1
PSN-007 | Oh K. | Programming | Clinical Database Programmer | 1
PSN-008 | Seo W. | Programming | Clinical Database Programmer | 1
PSN-009 | Yoon T. | Biostatistics | Data Analyst | 1
PSN-010 | Nam R. | Business Systems | Other staff | 0.6

## Assignment
assignment_id | person_id | person_name | project_id | role_name | assign_start_date | assign_end_date | person_weight | estimation_type | note_1 | note_2 | note_3
ASG-001 | PSN-001 |  | PRJ-001 | Project oversight |  |  | 0.31 | manual
ASG-002 | PSN-003 |  | PRJ-001 | Lead data manager | 2025-05-01 | 2027-02-28 | 0.38 | automatic
ASG-003 | PSN-005 |  | PRJ-001 | Clinical Data Associator | 2025-05-01 | 2027-02-28 | 0.27 | automatic
ASG-004 | PSN-007 |  | PRJ-001 | Clinical Database Programmer |  |  | 0.28 | automatic
ASG-005 | PSN-009 |  | PRJ-001 | Data Analyst | 2025-05-01 | 2027-01-28 | 0.13 | automatic
ASG-006 | PSN-002 |  | PRJ-002 | Project oversight | 2026-01-01 | 2028-02-29 | 0.31 | automatic
ASG-007 | PSN-004 |  | PRJ-002 | Lead data manager |  |  | 0.36 | automatic
ASG-008 | PSN-006 |  | PRJ-002 | Clinical Data Associator | 2026-01-01 | 2028-04-30 | 0.33 | automatic
ASG-009 | PSN-008 |  | PRJ-002 | Clinical Database Programmer | 2025-12-01 | 2028-04-30 | 0.23 | automatic
ASG-010 | PSN-009 |  | PRJ-002 | Data Analyst |  |  | 0.17 | automatic
ASG-011 | PSN-001 |  | PRJ-003 | Project oversight | 2026-01-01 | 2028-05-30 | 0.31 | automatic
ASG-012 | PSN-003 |  | PRJ-003 | Lead data manager | 2026-03-01 | 2028-05-30 | 0.32 | automatic
ASG-013 | PSN-005 |  | PRJ-003 | Clinical Data Associator |  |  | 0.31 | automatic
ASG-014 | PSN-007 |  | PRJ-003 | Clinical Database Programmer | 2026-03-01 | 2028-04-30 | 0.34 | automatic
ASG-015 | PSN-009 |  | PRJ-003 | Data Analyst | 2026-03-01 | 2028-06-30 | 0.15 | automatic
ASG-016 | PSN-002 |  | PRJ-004 | Project oversight |  |  | 0.28 | automatic
ASG-017 | PSN-004 |  | PRJ-004 | Lead data manager | 2025-06-01 | 2027-11-30 | 0.28 | automatic
ASG-018 | PSN-006 |  | PRJ-004 | Clinical Data Associator | 2025-07-01 | 2027-11-30 | 0.31 | automatic
ASG-019 | PSN-008 |  | PRJ-004 | Clinical Database Programmer |  |  | 0.28 | automatic
ASG-020 | PSN-009 |  | PRJ-004 | Data Analyst | 2025-06-01 | 2027-10-30 | 0.13 | automatic
ASG-021 | PSN-001 |  | PRJ-005 | Project oversight | 2026-02-01 | 2028-05-30 | 0.26 | automatic
ASG-022 | PSN-003 |  | PRJ-005 | Lead data manager |  |  | 0.38 | automatic
ASG-023 | PSN-007 |  | PRJ-005 | Clinical Database Programmer | 2026-03-01 | 2028-05-30 | 0.3 | automatic
ASG-024 | PSN-009 |  | PRJ-005 | Data Analyst | 2026-01-01 | 2028-06-30 | 0.18 | automatic
ASG-025 | PSN-002 |  | PRJ-006 | Project oversight |  |  | 0.25 | automatic
ASG-026 | PSN-004 |  | PRJ-006 | Lead data manager | 2025-02-01 | 2026-11-30 | 0.37 | automatic
ASG-027 | PSN-005 |  | PRJ-006 | Clinical Data Associator | 2025-04-01 | 2027-01-31 | 0.29 | automatic
ASG-028 | PSN-008 |  | PRJ-006 | Clinical Database Programmer |  |  | 0.28 | automatic
ASG-029 | PSN-009 |  | PRJ-006 | Data Analyst | 2025-02-01 | 2026-12-31 | 0.14 | automatic
ASG-030 | PSN-001 |  | PRJ-007 | Project oversight | 2025-11-01 | 2029-01-31 | 0.29 | automatic
ASG-031 | PSN-003 |  | PRJ-007 | Lead data manager |  |  | 0.3 | automatic
ASG-032 | PSN-006 |  | PRJ-007 | Clinical Data Associator | 2025-12-01 | 2029-02-28 | 0.24 | automatic
ASG-033 | PSN-007 |  | PRJ-007 | Clinical Database Programmer | 2025-10-01 | 2029-01-31 | 0.31 | automatic
ASG-034 | PSN-009 |  | PRJ-007 | Data Analyst |  |  | 0.14 | automatic
ASG-035 | PSN-002 |  | PRJ-008 | Project oversight | 2025-12-01 | 2029-02-28 | 0.34 | automatic
ASG-036 | PSN-004 |  | PRJ-008 | Lead data manager | 2025-12-01 | 2029-03-31 | 0.37 | automatic
ASG-037 | PSN-005 |  | PRJ-008 | Clinical Data Associator |  |  | 0.34 | automatic
ASG-038 | PSN-008 |  | PRJ-008 | Clinical Database Programmer | 2025-12-01 | 2029-03-31 | 0.28 | automatic
ASG-039 | PSN-009 |  | PRJ-008 | Data Analyst | 2025-10-01 | 2029-01-31 | 0.13 | automatic
ASG-040 | PSN-001 |  | PRJ-009 | Project lead |  |  | 0.39 | automatic
ASG-041 | PSN-005 |  | PRJ-009 | Main staff | 2027-04-01 | 2027-06-30 | 0.28 | automatic
ASG-042 | PSN-006 |  | PRJ-009 | Other staff | 2027-02-01 | 2027-05-31 | 0.28 | automatic
ASG-043 | PSN-003 |  | PRJ-010 | Project lead |  |  | 0.32 | automatic
ASG-044 | PSN-007 |  | PRJ-010 | Main staff | 2027-02-01 | 2027-09-30 | 0.23 | automatic
ASG-901 | PSN-010 |  | PRJ-009 | Other staff | 2027-02-01 | 2027-06-30 | 0.18 | automatic
ASG-902 | PSN-001 |  | PRJ-002 | Project oversight | 2026-01-01 | 2027-04-30 | 0.35 | automatic
ASG-903 | PSN-001 |  | PRJ-006 | Project oversight | 2025-04-01 | 2026-03-31 | 0.35 | automatic
ASG-904 | PSN-010 |  | PRJ-010 | Other staff | 2027-01-01 | 2027-08-31 | 0.22 | automatic
Note on C1: person_name is DERIVED. DERIVED - looked up from Person, do not type. The cell is locked so it cannot be typed over by accident. Nothing is hidden: Review > Unprotect Sheet turns it off, there is no password. But a value typed here is not recalculated, and the application recomputes this column on import anyway - so a hand-typed one is silently discarded, and any disagreement is reported as V-13.

## PersonPeriodWeight
assignment_id | period_start | period_end | weight_override | reason
ASG-902 | 2026-01-01 | 2026-05-31 | 0.2 | Part-time - parental leave
ASG-902 | 2026-11-01 | 2027-03-31 | 0.75 | Covering start-up peak
ASG-903 | 2025-08-01 | 2025-11-30 | 0.45 | Covering interim analysis peak

## MonthlyEstimate
scope | ref_id | month | fte | note_1
project | PRJ-007 | 2025-10 | 1.2 |  | Manager's own estimate - the assumptions understate this study
project | PRJ-007 | 2025-11 | 1.23
project | PRJ-007 | 2025-12 | 1.28
project | PRJ-007 | 2026-01 | 1.34
project | PRJ-007 | 2026-02 | 1.4
project | PRJ-007 | 2026-03 | 1.48
project | PRJ-007 | 2026-04 | 1.56
project | PRJ-007 | 2026-05 | 1.65
project | PRJ-007 | 2026-06 | 1.74
project | PRJ-007 | 2026-07 | 1.84
project | PRJ-007 | 2026-08 | 1.94
project | PRJ-007 | 2026-09 | 2.04
project | PRJ-007 | 2026-10 | 2.15
project | PRJ-007 | 2026-11 | 2.26
project | PRJ-007 | 2026-12 | 2.38
project | PRJ-007 | 2027-01 | 2.5
project | PRJ-007 | 2027-02 | 2.62
project | PRJ-007 | 2027-03 | 2.75
project | PRJ-007 | 2027-04 | 2.88
project | PRJ-007 | 2027-05 | 3.01
project | PRJ-007 | 2027-06 | 3.14
project | PRJ-007 | 2027-07 | 3.28
project | PRJ-007 | 2027-08 | 3.42
project | PRJ-007 | 2027-09 | 3.44
project | PRJ-007 | 2027-10 | 3.3
project | PRJ-007 | 2027-11 | 3.16
project | PRJ-007 | 2027-12 | 3.02
project | PRJ-007 | 2028-01 | 2.89
project | PRJ-007 | 2028-02 | 2.76
project | PRJ-007 | 2028-03 | 2.64
project | PRJ-007 | 2028-04 | 2.51
project | PRJ-007 | 2028-05 | 2.39
project | PRJ-007 | 2028-06 | 2.28
project | PRJ-007 | 2028-07 | 2.16
project | PRJ-007 | 2028-08 | 2.05
project | PRJ-007 | 2028-09 | 1.95
project | PRJ-007 | 2028-10 | 1.85
project | PRJ-007 | 2028-11 | 1.75
project | PRJ-007 | 2028-12 | 1.66
project | PRJ-007 | 2029-01 | 1.57
project | PRJ-007 | 2029-02 | 1.49
project | PRJ-007 | 2029-03 | 1.41
assignment | ASG-001 | 2025-03 | 0.35 |  | Agreed with the study lead
assignment | ASG-001 | 2025-04 | 0.4
assignment | ASG-001 | 2025-05 | 0.45
assignment | ASG-001 | 2025-06 | 0.5
assignment | ASG-001 | 2025-07 | 0.35
assignment | ASG-001 | 2025-08 | 0.4
assignment | ASG-001 | 2025-09 | 0.45
assignment | ASG-001 | 2025-10 | 0.5
assignment | ASG-001 | 2025-11 | 0.35
assignment | ASG-001 | 2025-12 | 0.4
assignment | ASG-001 | 2026-01 | 0.45
assignment | ASG-001 | 2026-02 | 0.5
assignment | ASG-001 | 2026-03 | 0.35
assignment | ASG-001 | 2026-04 | 0.4
assignment | ASG-001 | 2026-05 | 0.45
assignment | ASG-001 | 2026-06 | 0.5
assignment | ASG-001 | 2026-07 | 0.35
assignment | ASG-001 | 2026-08 | 0.4
assignment | ASG-001 | 2026-09 | 0.45
assignment | ASG-001 | 2026-10 | 0.5
assignment | ASG-001 | 2026-11 | 0.35
assignment | ASG-001 | 2026-12 | 0.4
assignment | ASG-001 | 2027-01 | 0.45
assignment | ASG-001 | 2027-02 | 0.5

## Lists
list_name | value | note_1
project_type | NewDrug CT
project_type | Biosimilar CT (Healthy)
project_type | Biosimilar CT (Patient)
project_type | Others
clinical_phase | Phase 1
clinical_phase | Phase 2
clinical_phase | Phase 3
clinical_phase | Phase 4
work_scope_type | fully in-housed
work_scope_type | fully outsourced
work_scope_type | Partially outsourced (in-house for EDC)
setup_party | by CRO
setup_party | by SB
EDC_system | Veeva EDC
EDC_system | Rave
EDC_system | eSOURCE
DataReviewSystem | Veeva DQS
DataReviewSystem | Medidata CDS
DataReviewSystem | No system (manual)
RBQM_system | CluePoints
RBQM_system | Medidata CDS
RBQM_system | No system (manual)
project_status | Planned
project_status | Active
project_status | On hold
project_status | Completed
milestone_name | Protocol (v1)
milestone_name | CTA submission
milestone_name | FPI
milestone_name | First SIV
milestone_name | LPI
milestone_name | interim DB lock cut-off
milestone_name | interim DB lock
milestone_name | final DB lock cut-off
milestone_name | final DB lock
milestone_name | Inspection
period_name_clinical | Before-Start-up
period_name_clinical | Start-up
period_name_clinical | Conduct (interim)
period_name_clinical | Close-out (interim)
period_name_clinical | Conduct (final)
period_name_clinical | Close-out (final)
period_name_clinical | After Close-out (final)
period_name_others | Planning
period_name_others | Develop
period_name_others | Close
role_clinical | Project oversight
role_clinical | Lead data manager
role_clinical | Clinical Data Associator
role_clinical | Clinical Database Programmer
role_clinical | Data Analyst
role_others | Project lead
role_others | Main staff
role_others | Other staff

## Config
parameter | value | note
schema_version | 12 | Structure version of this workbook. The application warns on a mismatch.
fte_hours_per_month | 160 | Hours equal to 1.00 FTE: 8 h/day x 5 days/week x 20 days/month.
over_allocation_fte | 1.5 | A person-month total above this is flagged as over-allocated. Absolute, not scaled by capacity (S2-01).
under_allocation_fte | 0.6 | A person-month total below this counts toward an under-allocated run. Absolute, not scaled by capacity (S2-01).
under_allocation_min_months | 3 | Consecutive months below the threshold before a run is flagged.
default_horizon_months | 24 | Months shown when the dashboard opens.
capacity_unit | FTE | Display unit for the figures on screen. 'FTE' shows a WEIGHT: 1.00 is one person working a full month on the project and 0.50 is half of one, so ordinary values run about 0.1 to 1.0. 'hours' shows that same weight multiplied by fte_hours_per_month. Display only - it changes nothing that is stored, and no figure the calculation produces.
absorb_unstaffed_role_factor | 1 | 1 = where nobody holds a role on a project, its factor is added to the role named in RoleFactor.absorbed_by, because the work still has to be done by whoever is there. 0 = an unstaffed role simply costs nothing, which is how versions before this one behaved.
split_shared_role_fte | 1 | 1 = when several people hold the same role on one project in a month, the role factor is divided between them. 0 = each is charged the whole factor, which is how versions before this one behaved.