## 00_Cover
PRAP — UI component list
Step 3, task 3.1 — high-level design for review
Version | v0.1
Date | 2026-08-01
Author | Claude Code
Prototype | app/PRAP_Prototype_v0.1.html
Governing plan | PRAP_Development_Plan_v1.3.xlsx (FINAL)
Specification | PRAP_Programming_Specification_v0.2.xlsx (draft)
How to review this
The prototype is DESIGN ONLY. Nothing on the page loads, calculates or exports - the figures are a
fixed snapshot baked into the markup, and the only script is tab switching. That is deliberate: the
plan has you approve the component design before any application code is written.
Open the prototype, then work down sheet 01. For each component, mark the Decision column:
Keep - as designed
Change - keep the component, change what it does or shows (say what in your comment)
Drop - not needed in v1.0
Add - something missing; add a row at the bottom
Approving this list fixes WHAT each component is and does. Exact layout, spacing, colour and
typography stay open until task 3.3, so do not spend review time on pixels.
Sheet 02 lists the design decisions taken while building the prototype that you may want to overturn -
each one is a real choice, not a default.

## 01_Components
Component list
31 components across the three tabs. Mark each one in the Decision column.
ID | Area | Component | What it does | REQ-IDs | Decision | Your comment
G-01 | Global | Header | Application name, version, expected schema version. | REQ-VC-02
G-02 | Global | Loaded-file line | Which workbook is loaded and when it was read. | REQ-IMP-05
G-03 | Global | Load workbook | File picker / drag-and-drop. Warns first if edits are unsaved. | REQ-IMP-01, REQ-IMP-08
G-04 | Global | Export | Writes all ten sheets back in template layout, edits included. | REQ-IMP-04, REQ-IMP-07
G-05 | Global | Findings banner | Summary of the last import; opens the full report. | REQ-IMP-02
G-06 | Global | Unsaved-edit counter | Always visible once anything is edited. | REQ-IMP-08
G-07 | Global | Tab bar | Overall ¦ Source data (project) ¦ Source data (person). | REQ-DSH-01..04
G-08 | Global | Empty state | With nothing loaded: one load panel and a template download link. | REQ-IMP-03
O-01 | Overall | Horizon control | From/to month, defaulting to 24 months. | REQ-CAL-01
O-02 | Overall | Expand to all projects | One click widens the horizon to the latest project end date. | REQ-DSH-07
O-03 | Overall | Filters | Project type, project, person, role, department. Combined with AND. | REQ-DSH-05
O-04 | Overall | Unit toggle | FTE or hours, seeded from Config.capacity_unit. | REQ-CAL-08
O-05 | Overall | Summary tiles | Projects, people, total demand, over-allocated months, under-allocation runs. | REQ-DSH-08
O-06 | Overall | Demand chart | Stacked monthly demand. Split by CLINICAL PHASE, not by project - see D-01. | REQ-DSH-02
O-07 | Overall | Resource by project (table) | Project x month heatmap, row and column totals, expandable rows. | REQ-DSH-01
O-08 | Overall | Mean load per person (chart) | One bar per person against both thresholds; breaching bars labelled. | REQ-DSH-02, REQ-DSH-08
O-09 | Overall | Resource by person (table) | Person x month, summed across projects, over/under flagged. | REQ-DSH-01, REQ-DSH-08
O-10 | Overall | Project timeline (Gantt) | Period bands shaded by weight, milestone and inspection markers. | REQ-DSH-02, REQ-PRJ-05
P-01 | Project tab | Project table | All 23 columns, sortable, filterable, editable. | REQ-DSH-03, REQ-IMP-07
P-02 | Project tab | Milestone sub-table | Milestones of the selected project in date order; Inspection may repeat. | REQ-PRJ-05, REQ-PRJ-13
P-03 | Project tab | Period sub-table | Derived periods with seq, dates, weight and note. | REQ-PRJ-06, REQ-CAL-09
P-04 | Project tab | Recompute periods | Re-derives from current milestones; warns before replacing hand-set dates. | decision C-10
P-05 | Project tab | Export visible table | Current table to .xlsx. | REQ-DSH-06
S-01 | Person tab | Person table | All 12 columns, sortable, filterable, editable. | REQ-DSH-04, REQ-IMP-07
S-02 | Person tab | Utilisation strip | Selected person's monthly load with both thresholds drawn. | REQ-DSH-08
S-03 | Person tab | Assignment sub-table | Project, role, dates and person weight. | REQ-PSN-02, REQ-PSN-03
S-04 | Person tab | Override sub-table | PersonPeriodWeight windows for the selected assignment. | REQ-PSN-05
S-05 | Person tab | Export visible table | Current table to .xlsx. | REQ-DSH-06
E-01 | Editing | Inline cell edit | Every field editable, validated at the point of entry. | REQ-IMP-09
E-02 | Editing | Cascade confirm | Changing an identifier states how many rows will follow, then rewrites them. | REQ-IMP-10, V-17
E-03 | Editing | Delete guard | Refuses to delete a row that is still referenced, naming what points at it. | V-17
Count
Add a row at the bottom for anything missing.

## 02_Design_Decisions
Design decisions taken in the prototype
Each is a real choice with a cost. Overturn any of them here.
ID | Decision | Why | The alternative, if you want it | Decision | Your comment
D-01 | The demand chart stacks by CLINICAL PHASE, not by project. | At 62 projects a stacked-by-project chart is unreadable: the top seven become slivers against a grey mass of the other 55. Phase is a five-category split that fits the palette and carries meaning, since phase is what selects a trial's period weights. The per-project numbers are still in the table directly below. | Stack by project anyway, capped at the top 7; or by product category; or by department.
D-02 | The project table lists the ten busiest projects plus an aggregate row. | 62 rows x 12 months does not fit on screen. The real table lists all 62 with sort and filter; the prototype shows the shape, not the whole. | Show all 62 with a scroll region instead.
D-03 | Heat shading in the tables is one blue ramp, light to dark. | Magnitude is a sequential quantity, so it takes one hue. The aggregate row is deliberately NOT shaded - including it in the scale would flatten every row actually on screen. | No shading at all; or shade relative to each person's capacity rather than the global maximum.
D-04 | Over- and under-allocation carry an icon and a value, never colour alone. | Red-green colour blindness affects around 8% of men. A cell that says only 'red' is unreadable to them, and unprintable in mono. The arrow and the number carry the meaning; colour only speeds it up. | None recommended - this one is an accessibility floor rather than a preference.
D-05 | Both thresholds are drawn on the person chart and the utilisation strip. | A ceiling without a floor makes under-use invisible, and under-use is half of what you asked the tool to show. | Draw only the ceiling; or make the floor a toggle.
D-06 | The Gantt shades period bands by weight rather than by period name. | Weight is what drives the simulation. Naming the periods by colour would spend the palette on labels that are already in the tooltip and the period sub-table. | Colour by period name instead, with weight in the tooltip only.
D-07 | Editing is inline in the tables, not in a separate form or dialog. | You asked for every field to be editable. A dialog per row would make bulk correction - the common case after a timeline slips - slow enough that people would go back to editing the workbook by hand. | A row-level edit dialog; or a dedicated edit mode.
D-08 | The findings banner persists until dismissed rather than fading. | A toast that disappears is a finding nobody read. Import findings are the mechanism that stops bad data reaching the simulation silently. | Auto-dismiss after a delay.
D-09 | Dark mode is supported, with its own selected colour steps. | Not a flip of the light palette: the heatmap ramp, the categorical hues and the status inks are each re-stepped for the dark surface and validated against it. | Light mode only, which would remove about 30 lines of CSS.
D-10 | The page is one scrolling column per tab, not a fixed dashboard grid. | It prints, it works on a laptop screen, and it needs no layout engine. A fixed grid would look denser on a large monitor at the cost of both. | A fixed multi-pane grid with independent scroll regions.

## 03_Deferred
Deliberately not in the prototype
So their absence is not read as an oversight.
Not shown | Why
Any loading, calculation, filtering or export behaviour | Task 3.1 is design only. The figures shown are a fixed snapshot computed in Python and baked into the markup.
Exact spacing, type scale and final colour values | Fixed at task 3.3, once the components are agreed.
Hover tooltips beyond the native SVG title | The full crosshair/tooltip layer is specified but not built until code generation.
Keyboard shortcuts and full accessibility pass | Reviewed against the working prototype at task 3.3, where they can be tried rather than described.
Row expansion (project to people, person to projects) | Shown as a caret in the row header; the behaviour is specified on sheet 06 of the specification.
The validation findings report itself | Specified on sheet 04 of the specification; the banner that opens it is in the prototype.