## 00_Cover
Project Resource Assignment Program (PRAP)
Programming Specification
Document ID | PRAP-SPEC-001
Document type | Programming specification (Step 2 deliverable)
Version | v1.43
Status | APPROVED - Dan, 2026-08-02. Step 2 gate closed; this governs Step 4.
Issue date | 2026-08-01
Author | Claude Code
Governing document | PRAP_Development_Plan_v2.74.xlsx - APPROVED BASELINE, Dan 2026-08-02
Schema version specified | 16
Repository | Dan5050-now/project1
Branch | claude/project-resource-assignment-app-1vjdzh
What this document is
The plan says WHAT the application must do. This says HOW, in enough detail that the code can be written
from it and checked against it. Every section cites the REQ-IDs it implements, and sheet 09 shows the
reverse: each of the 70 requirements mapped to the section that satisfies it.
Two things make this specification unusual, and both are deliberate:
- The data schema is not described in prose. It already exists as a working file,
templates/PRAP_SourceData_Template_v1.21.xlsx, and sheet 03 documents the parse contract against it.
- The calculation and validation logic already has a reference implementation in
tools/verify_source_workbook.py, which runs against the dummy data. Sheet 05 gives the pseudocode;
that script is the executable check that the pseudocode is right.
So the specification describes behaviour that has been exercised, not behaviour that is only imagined.
Contents
Sheet | Contents
00_Cover | Document control and reading guide.
01_Version_History | Change log.
02_Scope | What is specified here, what is deferred to Step 3, and the source documents.
03_Data_Schema | The parse contract: every sheet, column, type and coercion rule.
04_Validation | V-01..V-24 with trigger, severity and the exact message shown.
05_Calculation | Period derivation, the load formula, aggregation and the two thresholds.
06_UI_Spec | The four tabs, their components, filters and states.
07_Editing_IO | Edit buffer, dirty state, cascading identifier edits, import and export.
08_Versioning | Schema compatibility check and version display.
09_Traceability | Every requirement in the plan, mapped to the section that implements it.
10_Open_Points | The six points raised at the v0.3 review, with the answers given and what changed. None open.

## 01_Version_History
Version history
Version | Date | Author | Reviewer | Summary of change | Status
1.0 | 2026-08-02 | Claude Code | Dan | APPROVED. Content identical to v0.9; the version number changes because 1.0 marks an approved issue rather than a draft. Approved together with development plan v2.0 and UI component list v1.0. This document now governs Step 4: the code is written from it and checked against it. | APPROVED 2026-08-02 by Dan
0.9 | 2026-08-01 | Claude Code | Dan | Plan change R-13, from the component-list v0.7 review. Sheet 06 gains two entries: the interim and final DB lock milestones are emphasised on the timeline in red and at a larger size, and the project source-data tab gains a utilisation graph with RELATIVE reference lines (REQ-DSH-12). The relative framing is the point - a project has no absolute ceiling or floor, so the person tab's threshold model does not transfer. Written against plan v1.10. | Draft
0.8 | 2026-08-01 | Claude Code | Dan | Plan change R-12, from a reviewer question: why does the PersonPeriodWeight key include period_start when assignment_id is unique in Assignment? The key is unchanged and sheet 03 now says why - PersonPeriodWeight is a CHILD of Assignment and one assignment may carry several non-overlapping windows, so assignment_id alone would cap overrides at one per assignment. Answering it exposed two rules specified but never implemented: V-06's assignment-window overlap half, and referential integrity on PersonPeriodWeight.assignment_id. Both are now in the reference implementation, the second as new rule V-24. The dummy fixture gains an assignment with two windows. No schema change. | Draft
1.43 | 2026-10-12 | Claude Code | Dan | R-65, REQ-DSH-21 and REQ-DSH-22. ui/07_state.js gains today(), nowKey(), nowFrac() (days into the month over its length) and todayLabel(), all from the machine's clock, and markNow(cells, G), which adds class `now` to the current month's <td>. monthAxis() takes an optional plot [left, right] and, where nowKey() is in G, draws g.nowmark: a dashed line.nowln at xOf(i) + bw x nowFrac(), clamped to the plot, and a 'Today' label beside it. chartGantt() draws the same through every row when today falls inside the projects' span, and with opts.assign {pid: [{from, to, role, weight}]} a rect.asgbar under each row per assignment. monthHead() marks th.now with a 'Today' pill; every row of month cells in tableProjects() and tablePeople() goes through markNow(); a MonthlyEstimate row of the current month carries data-now. persTimeline(sid) in ui/11_tabs.js draws the person's Project timeline below their Utilisation chart, from M.assignments regardless of S.f. No figure moves. | Draft
1.42 | 2026-10-11 | Claude Code | Dan | R-64, REQ-PRJ-17. HIGHLIGHT_WORDS (core/03_parse.js and tools/prap_io.py alike) holds thirteen words in rainbow order; hlToken() matches HL_RE, (?<![a-z])(word¦...)(?![a-z]) case-insensitively, so the earliest colour word standing on its own wins. HIGHLIGHT_FILL is built from the list (var(--hl-<word>)), each word defined in all four theme blocks; HIGHLIGHT_PALE (yellow, lime, cyan, pink) takes the dark band label. suggestionsFor() on milestone_highlight and period_highlight returns the file's own values plus 'Highlight (<Word>)' for every palette word they do not already name; the chooser prefixes a .swc swatch. No schema change. | Draft
1.41 | 2026-10-09 | Claude Code | Dan | R-62, REQ-DSH-20. SOURCE SCHEMA STEPS 15 TO 16: a thirteenth sheet, IssueReview (project_id, month, issue, status, gap_fte, rationale, reviewed_by, reviewed_at), in LATER_SHEETS, keyed for the import comparison by project_id ¦ month ¦ issue. M.reviews maps 'pid¦YYYY-MM¦issue' to its row (first row wins). reviewOf(pid, k, dir, gap) returns the review and whether it CLOSES the month: status 'Confirmed - no issue' or 'Accepted' AND gap_fte equal to the current gap in cents. A closed month keeps its gapc / unal marking and gains class rev (muted); gapRows() carries r.rev, and the control, the tile and the list count open issues by direction plus the closed ones apart. S.gapf.rev filters the list (open / closed); #projIssue gains 'reviewed'. A click on [data-gap] is handled BEFORE tr.parent and is a control to the pop-up handler, so it opens openGap(pid, k, dir); drawGap() adds reviewPanel(): #revStatus, #revBy, #revWhy, #revRun over issueRun()'s consecutive months. saveReview() refuses a closing status without a reason and upserts rows through newRow/S.pending; clearReview() deletes over the same reach. reportReviews() (V-40, information) runs after reportUnstaffed in the browser and the Python reference, message for message. The Standard vs staffed list is ordered by project ID then month, ascending, and draws every month (GAP_SHOW 40 -> 500, a safety cap). No figure moves. | Draft
1.40 | 2026-10-08 | Claude Code | Dan | R-60, REQ-PRJ-16. SOURCE SCHEMA STEPS 14 TO 15: a twelfth sheet, PeriodHighlight (period_name, period_highlight, note_1), listed in LATER_SHEETS beside MonthlyEstimate so a workbook or interchange file without it opens with V-09 information and no defaults. M.periodHl maps a period name to its default colour (first row wins). periodColour(): ProjectPeriod.period_highlight, else M.periodHl[period_name], else gray; the pop-up names which. blankSheets() seeds the template's rows (SEED_PHL). Sheet 07 gains V-39. R-61 (Python shell): saveMine() writes sheetsNow() through ws/saveAs to a new file in the person's workspaces folder, named base_<name>_<stamp>.prap and checked with ws/stat so it never lands on an existing file; offered by #pm-keep on claim_lost, superseded and the takeover detector, and on the File menu. No figure moves. | Draft
1.39 | 2026-10-08 | Claude Code | Dan | R-59, REQ-PRJ-15. SOURCE SCHEMA STEPS 13 TO 14: ProjectPeriod gains period_highlight after period_end, OPTIONAL and part of no key, read through hlToken() as milestone_highlight is; its values come from Lists.period_highlight. Sheet 06's timeline colour rule changes: a band is drawn in its period's chosen colour (fill-opacity 0.78 to 1.00 by weight), or GRAY (#c4c4c9, lightness by weight) when none is chosen - superseding the hue per period name. Band labels are dark on gray and yellow, white on the other four. The legend keeps the period names, each still picking its period out, under one gray swatch, then each colour in use in the file's words (M.perHlLabels). Sheet 07 gains V-38, the period twin of V-37: warning, never a refusal. No figure moves. Template v1.18, examples v1.20 and v1.12. | Draft
1.38 | 2026-10-07 | Claude Code | Dan | R-56. Sheet 06: the Project and Person filters are labelled by name (identifier only where a name is blank or shared) and searchable past eight entries, the values staying identifiers. A row added with + row on Project or Person is the selection (S.newKeys) and is not reset by the filters until a load. Resource by project carries estimationPill per project, td.man on a month whose lines carry a stated figure, and #projIssue, which narrows the rows only. gapRows() gains the projUnallocated months as direction 'unstaffed', so the control, the tile and the list count them. Exported names are base_YYYY-MM-DD_HHMM, with an earlier stamp removed from the base. Python shell: fs/list carries folders' mtime and the browser lists by modified time, newest first. No schema change and no figure moves. | Draft
1.37 | 2026-10-04 | Claude Code | Dan | R-55, REQ-OUT-06 amended. Sheet 08's results workbook: ProjectMonth gains demand_fte, staffed_fte (the whole project's, whatever filter is on), gap_fte = staffed - demand and gap_dir (short / over / unallocated / empty), and a row for every month in projUnallocated, with fte 0 and people 0. All four come from the calculation's maps - projDemand, projMonth, projGap, projUnallocated - and none is recomputed. Flags gains project_id and project_name and three project kinds, one row per run of consecutive months the same way; Summary gains Standard demand and the three totals, summed from ProjectMonth. PersonMonth gains a row at fte 0, flag 'unassigned', for every month in view inside employment_start..employment_end that has no figure; it breaks an under-allocation run rather than extending it. Seven sheets still, and no figure moves. | Draft
1.36 | 2026-10-01 | Claude Code | Dan | R-54. A DEFECT AND A COLUMN. The three cell marks drawn through CSS content: - the two gap arrows and the V-33 warning sign - escaped their own backslash, so each printed the text of its escape instead of the character it names. Fixed, and guarded three ways; the suite that covered them asked only whether the content was non-empty, which the wrong string satisfies. And milestone_seq is no longer drawn in the Milestones table: it orders nothing, since both engines place a milestone by its DATE, and it is still carried in the file and allocated on insert. period_seq is NOT hidden - sheet 05's period derivation sorts by it, V-18 reports a duplicate as an error, and V-05 names a period by it. No schema change and no figure moves. | Draft
1.35 | 2026-10-01 | Claude Code | Dan | R-53, REQ-DSH-15 amended and REQ-DSH-19 added. (a) The Standard vs staffed list takes three controls - direction, project, smallest gap - and sheet 06 records the rule they are bound by: they narrow the LIST, never the count. The tile and the control in Resource by project's head read the unnarrowed rows, because they are the alarm. A narrowed list states 'n of m', and one emptied by its own filter says so rather than reporting that there is nothing to report. (b) A source-data table may FREEZE a leading run of columns - the row handle, the identifier and the name - at its left edge while the rest scrolls under them. Declared per sheet. The frozen cells stay editable, must be opaque in every row state, and overlap their neighbours by a pixel so no seam is left for the row behind. No schema change, no validation rule, and no figure moves. | Draft
1.34 | 2026-10-01 | Claude Code | Dan | R-52, REQ-DSH-15 amended. STANDARD VS STAFFED IS NO LONGER A SECTION OF THE OVERALL TAB; it opens from a control in Resource by project's head, which is where its figures live - every month it lists is a cell in that table. Sheet 06 records what the control must do, and it is not 'name the screen behind it': it states how many project-months are off their standard and in which direction, because the requirement's reason for putting that list on the page at all was that a silent fault must not sit behind a click. The control is drawn even with nothing to report. A row opens the month dialog ON TOP of the list, so closing it returns to the list. Nothing else moves: the tile still counts it, every cell is still marked where it is drawn, and V-34 is unchanged in severity, wording and reach. No schema change and no figure moves. | Draft
1.33 | 2026-10-01 | Claude Code | Dan | R-51, REQ-DSH-18. ANY SECTION CAN TAKE THE WHOLE WINDOW, AND IS STILL EDITABLE THERE. Sheet 06 gains the rule under Global, because it applies to every panel on every tab rather than to one of them: a panel holding a bounded scroll region carries a control in its head that draws that panel against the viewport instead of against the page column, and the region then takes the height of the screen rather than the cap REQ-DSH-13 gives it. NOTHING IS MOVED AND NOTHING IS COPIED - it is the same panel in the same place in the page, which is why every behaviour specified elsewhere in this document still holds inside it: the cell editor, the validation, the type-ahead, the column filters and the pop-ups are none of them told it is happening. The sticky band carrying the unsaved-edit counter, Save and the tab bar is lifted ABOVE the section rather than covered by it; the filter bar is covered, and Escape gives the page back. Panels now carry a stable name, which is what the state is held as - an element does not survive the re-render every committed edit causes, and a position does not survive a change of selected row. No schema change, no validation rule, and no figure moves. | Draft
1.32 | 2026-09-23 | Claude Code | Dan | R-50, REQ-PRJ-14. SOURCE SCHEMA STEPS 12 TO 13: Milestone gains milestone_highlight, beside the date it marks. A milestone may be marked in a colour and the mark finds it wherever the Project timeline is drawn - the Overall tab's and the project's own. The value comes from the Lists sheet and what the application reads is the COLOUR WORD inside it, so a team may record what their colour means and keep both; the legend then prints their words rather than the word 'red'. Sheet 07 gains V-37 for a value naming no colour: warning, never a refusal, because the milestone simply draws as it did before the column existed and a mark changes no figure. The column is OPTIONAL and part of no key. Nothing in the calculation moves - the highlight is carried beside the milestone dates rather than inside them, so the structure the period derivation reads is unchanged. Template v1.17, examples v1.19 and v1.11. | Draft
1.31 | 2026-09-13 | Claude Code | Dan | R-49, REQ-DSH-17. Sheet 06's Table A now specifies what a project-month inside the project's own run with NOBODY ON IT shows: the figure its standard asks for, rather than a dot. Drawn as demand and never as resource - no filled sequential scale, an outline and a hatch, italic, and a hollow ring glyph so the distinction is not carried by colour alone (D-04) - and never added to any total. The reconciliation note above the table is amended to say so outright: unallocated demand belongs to no person, so counting it into Table A would break the guarantee that its grand total equals Table B's, and would assert that somebody is doing the work. It is totalled on a line of its own. Filled ONLY where the calculation produced no figure at all - a month that already carries one keeps it, because the month_run on a line is the greatest coverage any assignment has in that month while this is the project's own run, and recomputing would move figures nobody asked to move. No schema change and no calculation change. | Draft
1.30 | 2026-09-13 | Claude Code | Dan | R-48. Sheet 07 gains V-36: a project that has periods and nobody assigned to it at all. INFORMATION, classed INCOMPLETE, raised from the CALCULATION and carrying the figure - what the project needs in FTE-months, over how many months, and the peak with the month it falls in. Raised from the calculation and not from the validation for the reason V-34 is: it states a number, and a number has to come from the arithmetic that would produce it rather than from a second lookup that could drift from it. Every term is the one an assignment with blank dates would get (REQ-CAL-15), so what the rule predicts and what the project shows once staffed are the same figure to the hundredth. Skipped for a project with no periods - there is no demand to state and V-12 or V-16 already reports it - and for a Completed project, whose finding would never answer itself and so does not belong in the INCOMPLETE class. No schema change, no calculation change, and no existing figure moves. | Draft
1.29 | 2026-09-13 | Claude Code | Dan | R-47. The 'Rendering at the target volume' section is rewritten from ESTIMATES into MEASUREMENTS, because REQ-NFR-03 has been amended to 100 projects and 150 people and the old section reasoned about 1,000. Every figure in it is now reproducible from two commands (tools/build_stress_workbook.py --projects N --people M, then tools/measure_scale.py) against budgets fixed before the numbers were seen. The section also states the quantity it had been missing: rows is PROJECTS PLUS PEOPLE, so 50 x 200 and 100 x 150 are the same rendering problem and measure within 10 ms of each other - reasoning about the people figure alone was wrong by the project count. Row virtualisation is recorded as NOT BUILT AND NOT REQUIRED at the named volume, with the one property that matters either way kept as a requirement: sorting, filtering and totals run over the whole model and never over the drawn slice, so adding virtualisation later would change what is drawn and nothing that is computed. The chart aggregation half of REQ-DSH-09 is unchanged and explicitly not retired by any measurement: 200 bars in a 1,200px panel is a legibility problem, not a speed one. No code change, no schema change, no figure moves. | Draft
1.28 | 2026-09-12 | Claude Code | Dan | R-46. Sheet 03 loses MonthlyEstimate.edited_at and gains RETIRED_COLS, the mechanism for taking a column OUT of the schema - the first time this schema has done so. The column is dropped on the way in, before row objects are built, so nothing downstream sees it and a schema 11 workbook both opens and SAVES; the JSON interchange reader drops it too, since that path refuses unknown columns outright and would otherwise reject a file over a column this application asked for and then stopped wanting. Nothing is migrated - a retired column has nowhere to go, which is what distinguishes it from a rename. Sheet 05 records that the engine no longer carries manual_at on a line: it was read by no export, report or rule. Sheet 06 records that both Monthly estimation panels lose the column. WHY IT WENT, because a removal needs a better reason than a fix: it was stamped by the switch, by 'fill the missing months' and by the gap dialog, but never by somebody typing a figure into the cell - the one action it existed to mark - and it was stored as a locale string rather than a date, because the sheet never declared it a date column. The change log archived on Save answers the same question with a timestamp, an identity and the value before and after. Schema steps to 12; the version check is a warning, so a schema 11 file still opens. No calculation change and no figure moves. Written against plan v2.54. | Issued
1.27 | 2026-09-12 | Claude Code | Dan | R-45, REQ-DSH-16. Five screen changes, no rule and no figure. Sheet 06 records the four that are drawing decisions. A CHART WHOSE X AXIS IS THE HORIZON takes its width from the month count - W = max(Wmin, padL + padR + months x Wper) - and its panel scrolls; the two utilisation charts were the last fixed-width ones, and a fixed width is legible only over the span it was chosen for and fails silently outside it. Wper is chosen so the DEFAULT horizon still falls under Wmin, which is what keeps the change invisible to the view almost everybody opens on. PANELS ARE TILED ONLY WHERE BOTH ARE NARROW: the person tab's three wide tables are one column, in work order. A PANEL THAT IS A CHILD OF A SELECTION names its parent from one shared helper, so two panels stating the same assignment cannot drift. LEGEND PICKING is recorded with the two decisions that are not obvious: the pick is scoped to the TAB, since series keys are ids and the same project is the same id on every chart that knows it; and a chart with NO mark for the key is left untouched rather than dimmed whole, because a chart with nothing lit reads as absent data. Marks carry a second key where they stand for two series at once, and marks belonging to the MONTH - thresholds, baselines, the V-34 outline - carry none and never fade. Sheet 03 records COLUMN_LABEL beside COLUMN_HELP: a plain name for every column, and it is now the WHOLE of what a heading prints. The column's own name went on a second line for one release and was taken off at review: the need for it is occasional - editing the workbook, chasing a finding - and a heading is read on every glance, so it belongs in the pop-up, which every heading now carries, and on the element as data-cid. Nothing is renamed, the schema stays at 11, validation messages still name the column, and the cell still writes back through the identifier. Sheet 07 records the one mechanical consequence: a test reading a column name off a heading reads data-cid, not the heading's text. Written against plan v2.53. | Issued
1.26 | 2026-09-12 | Claude Code | Dan | R-44. Sheet 04 gains V-35: capacity_fte is bounded 0.00 to 1.00 and, alone among the rules added this year, it REFUSES. The distinction is recorded because it is the one that decides a rule's class: a period weight, a role factor and a stated month are judgements somebody is entitled to make, and their rules report; a capacity of 1.5 is a number in the wrong unit, and refusing it at the cell is the only moment the person who knows what they meant is still there. Sheet 03 records the bound on the column without a schema change - the schema stays at 11 and no column moves. Sheet 07 records that a workbook already breaking the rule still opens: both the save and the edit path compare the COUNT of blocking findings before and after, which is what stops a new rule locking somebody out of their own plan, and which is now written down rather than merely true. The template carries a matching decimal range so Excel refuses it at entry as well. No rule changes for the calculation and no figure moves. Written against plan v2.52. | Issued
1.25 | 2026-09-11 | Claude Code | Dan | R-43. Sheet 06 records that EVERY Stated cell in the Standard vs staffed dialog is editable, and the three states it has to tell apart: a row that exists (an ordinary cell over MonthlyEstimate), a row that does not exist on a thing already manual (V-31 - created without a question, because the months are already the user's), and a row that does not exist on a thing still AUTOMATIC (asked, then switched, seeded and set together - REQ-CAL-18 makes estimation_type one-way-in precisely because the alternatives are a figure nothing reads or every other month counted as 0.00). Sheet 07 records the one mechanical consequence: the generic contenteditable handler now skips a cell with no data-sheet, which is what lets a creating cell carry its own handler rather than reaching applyEdit with an undefined sheet. No rule changes, no schema change and no figure moves. Written against plan v2.51. | Issued
1.24 | 2026-09-11 | Claude Code | Dan | R-42, REQ-DSH-15. Sheet 04 gains V-34, a WARNING: a project-month whose demand and applied figure have come apart. Sheet 05 records why the obvious pair cannot - projMonth is built from the lines, so a project's month IS the sum of its people - and what calculate() therefore returns instead: projDemand, kept off the lines like every other map here, and projGap, the two compared in integer hundredths so a rounding difference cannot be reported as a decision. Sheet 06 records the four surfaces: the rule, the mark on the figure itself in Resource by project and on the project utilisation chart, the tile, and the Standard vs staffed section on Overall - deliberately a SECTION and not a tab, for the reason recorded there. Its rows open a dialog carrying the stated figures as ORDINARY contenteditable cells over MonthlyEstimate, so the editing path of sheet 07 handles them unchanged and there is no second way to change a figure. Both directions are counted apart and never netted. No rule changes, no schema change and no figure moves. Written against plan v2.50. | Issued
1.23 | 2026-09-06 | Claude Code | Dan | R-41. Sheet 06 records that the derivation column carries the WHOLE expression term by term rather than the period alone, and sheet 05 writes down the shape it must take. Two halves on a person's, and the split is a correctness requirement rather than a layout choice: since R-32 the terms make a CLAIM normalised against the other claims on that project-month, so their product is not the figure and a single product would assert an arithmetic the application does not do. The demand closes with '=', the person's terms close with a PERCENTAGE of it. A PersonPeriodWeight override is ONE TERM WITH TWO SOURCES, never a second factor - it replaces person_weight rather than multiplying it (REQ-PSN-05) - and every fallback names its rule, V-19, V-23 or V-12, because a bare 1.00 cannot be told from a standard that really is 1.00. Absorbed cover names the roles it came from (REQ-CAL-16). The sharer count keeps its own short column: a sentence cannot be sorted or filtered. dataTable now tags a derived cell with data-drv (never data-col, which is what makes a cell editable) so one derivation can be given width without widening every lookup column, and derived text may carry a newline. No rule changes and no figure moves. Written against plan v2.49. | Issued
1.22 | 2026-09-06 | Claude Code | Dan | R-40, REQ-DSH-14. Sheet 06 records three LOOKUP columns - read-only, marked as such, and belonging to no sheet. The Periods table on tab 2 names the standard monthly FTE its period selects and multiplies it by the project's own weight, so the row carries the month's demand rather than one term of the expression for it. Both Monthly estimation panels name the period the month falls in with its weight; the assignment panel also names the sharer count, the divisor in (role factor / sharers). The project panel does not carry that count, and sheet 06 says why: a project month is divided between several roles, each with its own, so one number would average things that do not compare. Sheet 05 records that calculate() now returns periodAt alongside projPeriod - projPeriod answers the period for every month that produced a figure, periodAt for the one month that produces none, a manual project month with nobody assigned (V-32) - so both answers come from one function and cannot drift apart. NONE OF THE THREE IS A SHEET COLUMN: the schema on sheet 03 is unchanged, and a stale standard copied onto a period row is the failure the lookup exists to prevent. A missing standard reads 'none - V-19' rather than the 1.00 the calculation falls back to. No rule changes and no figure moves. Written against plan v2.48. | Issued
1.21 | 2026-09-05 | Claude Code | Dan | R-39. Sheet 04 gains V-33, a WARNING: a manual assignment figure that the project's own manual figure overrode. No rule changes - REQ-CAL-18 already made the project month the mother figure and already scaled every person on it, including anyone whose own figure is manual, so that the people still add up to the month. What is new is that the two figures are now CONNECTED on screen: calculate() keeps stated_assignment_fte, overridden_by_project and manual_project_total on any line the project overrode. From those three, V-33 names the month, the stated figure and the applied one; the Monthly estimation panel tabulates them; and the editor soft-stops at the cell, offering to keep or undo. It is a warning and not an error because both figures were deliberately typed and which is wrong is not the application's judgement. Sheet 05 gains 'Stated figures, and the decimal rule', which writes down the two levels of REQ-CAL-18, those three fields, and the largest-remainder arithmetic of REQ-CAL-20 the v1.20 entry announced but did not actually set out. Sheet 06 records the Monthly estimation panel on both source-data tabs: automatic_fte and difference to two decimals like every other FTE on screen - they were the last four-place figures left, and read as a discrepancy the user had caused - plus the override table and the soft stop. No figure moves. Written against plan v2.47. | Issued
1.20 | 2026-09-05 | Claude Code | Dan | R-38. Sheet 05 gains REQ-CAL-20, THE DECIMAL RULE: every FTE figure is a whole number of hundredths, rounded once where a person-month is decided rather than at each place it is shown, and a project-month's hundredths handed out by largest remainder with assignment_id breaking ties. That is what keeps REQ-OUT-06 (rows sum to the month) and REQ-CAL-19 (shares add to one) exact instead of approximate - rounding each share separately missed on 644 of 1,629 project-months. Sheet 08 records that a detail row can sit up to 0.01 from the exact product of its own terms, and that the rows of a project-month nonetheless add to it with nothing left over. Every figure moves slightly. Sheet 09: the in-app change-log export is removed - the archive at save is the only route out - and the archive is one folder for the installation rather than one per person. A central server with real logins is NOT built and is recorded as specified-but-unbuilt. Written against plan v2.46. | Issued
1.19 | 2026-09-05 | Claude Code | Dan | R-37. Sheet 10: the chart pop-ups name the PROJECT PERIOD the month falls in, with its weight - the row of the plan that decided the size of the figure being hovered over. Graphs 1 and 2 on Overall and the Utilisation chart on each source-data tab. Sheet 08 records that calculate() returns projPeriod, built from the same lines as every other map so the period named cannot differ from the one the figure used. Where a band spans several projects the tag sits against each project, not the band. No calculation change and no figure moves. Written against plan v2.45. | Issued
1.18 | 2026-09-04 | Claude Code | Dan | R-36. Sheet 10 gains the CHANGE LOG and the COLUMN FILTERS; no schema change and no figure moves. The log records each saved change with its UTC time, the author, the record's natural key, the column and both values, plus the errors and warnings standing at each save and which were knowingly kept. It lives in memory for the session; the desktop shell APPENDS it to a monthly CSV in an audit folder at every save, and the browser - which has no folder to append to - hands it over from Export narrowed by a date range. Author comes from the Windows account in the desktop shell and is asked for once in the edit bar in the browser. The column filters are on the six tables named in the request and narrow the table only, never the figures. Written against plan v2.44. | Issued
1.17 | 2026-09-04 | Claude Code | Dan | R-35, the date picker. Sheet 10 records two corrections. The month arrows stepped once and no further, because step() re-read the cell and snapped the grid back before stepping; the panel now distinguishes the cell steering the grid (opening, typing) from the user steering it (the arrows), and the cell keeps its text while navigating. 'Today' wrote the UTC date rather than the date on the user's clock - a day out either way for anyone not near Greenwich - and now reads the local calendar date. No calculation changes. Written against plan v2.43. | Issued
1.16 | 2026-09-04 | Claude Code | Dan | The 'Monthly demand by project' pop-up now states THE MONTH'S TOTAL across every project in view, under a rule, and the band's share of it - the two things 'Monthly demand by person' already carried and this one did not. A band read on its own cannot say whether the month came to five FTE or to fifty. Sheet 10 Graph 1 updated. No change to any figure: the total is the sum the chart was already drawing, and it is the same figure Graph 2 states for that month summed along the other axis - test_charts.py now holds the two to agreeing in WORDS as well as in pixels, month for month. Written against plan v2.42. | Issued
1.15 | 2026-09-04 | Claude Code | Dan | R-33, SCHEMA 11, and no change to any figure - the 62-project fixture totals 4,333.46 FTE-months before and after. Sheet 03 renames the sheet PeriodWeightStandard to PeriodFTEStandard: schema 10 already renamed its column to standard_fte on the grounds that it holds a magnitude in FTE, and leaving the SHEET called a weight kept the misreading alive that R-32 had to correct. A schema 10 workbook still opens - the old sheet name is translated on read and reported once, as a renamed column is. Sheet 10 renames the panel to 'Standard period FTE for project types'. Sheet 05 corrects the monthly-estimation notes, which still described the pre-R-32 product of four factors; they now state the project month and the assignment month separately, because under R-32 the two are arrived at differently. Sheet 09 records that the Python shell's sticky chrome and the page's sticky band no longer overlap. Written against plan v2.41. | Issued
1.14 | 2026-09-03 | Claude Code | Dan | R-32: REQ-CAL-19 amended. A project-month IS its standard x period weight x the month it ran, and the people on it DIVIDE that - person_weight, coverage and the role factor all make a CLAIM, and the share is the claim over the sum of the claims. Sheet 05 replaces the formula with demand x share and records that the shares add to one by construction. Sheet 08 records month_run and demand_fte on the results export, and that every row is now two numbers rather than five. Written against plan v2.40. | Issued
1.13 | 2026-09-02 | Claude Code | Dan | R-31, REQ-CAL-19, SCHEMA 10: the standard monthly FTE reaches the calculation. Sheet 05 replaces the formula: standard_fte x period weight x role_share x person weight x month coverage, with role_share normalised over the roles ACTUALLY STAFFED so the shares add to one. Sheet 03 renames PeriodWeightStandard.weight to standard_fte and records that it is a magnitude rather than a multiplier, and that ProjectPeriod.weight is now an adjustment around 1.00. Sheet 08 records the four columns the results export gains so a reader can see where a figure got its size. Written against plan v2.39. | Issued
1.12 | 2026-08-30 | Claude Code | Dan | R-30, REQ-CAL-18, SCHEMA 9: a monthly figure may be STATED instead of calculated. Sheet 03 gains the MonthlyEstimate sheet and its key - scope + ref_id + month, the only key in the workbook that carries the name of its own parent table, because `scope` decides whether ref_id points at a project or an assignment - and estimation_type on Project and Assignment. Sheet 04 gains V-31 and V-32, both raised from the CALCULATION rather than from a sheet, so neither can refuse an edit. Sheet 05 records the order the two levels are applied in and why a project figure SCALES its people rather than replacing them: the results export guarantees every total is exactly the sum of its detail rows, and a project month that did not equal the sum of its people would break it. Sheet 08 records the four columns the results export gains so a stated row can be told from a calculated one. Written against plan v2.38. | Issued
1.11 | 2026-08-28 | Claude Code | Dan | R-29, REQ-OUT-06: the calculated-results export. Sheet 08 gains its seven sheets column by column, the two properties that make it checkable - monthly figures summed FROM the detail rather than from the engine, and every detail row reconciling to its own four numbers - and why it deliberately does not round-trip. Sheet 05 records that calculate() now returns `lines`, one per assignment-month, so the explanation and the figure come from the same pass. Written against plan v2.37. | Issued
1.10 | 2026-08-28 | Claude Code | Dan | R-28, REQ-IMP-14. Sheet 07 gains the config check on import: what is compared, when, and why a Config row is not treated like any other row in the file - every other sheet describes the plan, Config describes how the plan is read. The comparison itself is in core/06a_diff.js beside the import difference engine, because both shells import. Written against plan v2.36. | Issued
1.9 | 2026-08-27 | Claude Code | Dan | R-26: the parse contract's row for capacity_unit named 'percent', which the application has never implemented - anything that is not 'hours' displays as FTE. The row now names the two real values and says what the unit means: FTE is a WEIGHT, 1.00 being one person for a full month, so ordinary values run about 0.1 to 1.0. R-27: sheet 04 gains V-30, and sheet 06 records that the Configuration table offers neither 'Delete' nor '+ row' - its nine settings are read BY NAME, so a new row is read by nothing and a deleted one hands its figure to a built-in default without saying so. What a user changes there is a VALUE, and the value cell stays as editable as any other. Written against plan v2.35. | Issued
1.8 | 2026-08-27 | Claude Code | Dan | R-21 to R-25, all in the application rather than the arithmetic - no figure moves. Sheet 04 gains the RULE CLASS: must / conditional / incomplete, what each one does at a cell edit and at Save, and the class of every rule that is not must. Sheet 06 gains the calendar on a date column (an offer beside the cell, never a gate in front of it), the drawn scrollbars and why the browser's own could not be used, the single opaque sticky band, and the rule that a generator is only offered where it can run. Written against plan v2.34. | Issued
1.7 | 2026-08-27 | Claude Code | Dan | R-19 and R-20. Sheet 04: V-03 and V-23 are marked REPORTED, NEVER REFUSING - the retirement of V-28 at v1.6 fixed one third of the problem, because all three rules asked the same question and all three refused the row. V-23 also moves out of the validation pass and into the CALCULATION: keyed on the whole composition the lookup uses and counted in the person-months actually calculated at 1.00, which is both the right grouping and the reason it can no longer refuse anything. Sheet 05 gains REQ-CAL-17: a project's window is the span of its PERIODS, not of its milestones, so no month outside the plan draws resource at weight 1.00. Written against plan v2.33. | Issued
1.6 | 2026-08-26 | Claude Code | Dan | R-18: V-28 IS RETIRED. Sheet 04 records the retirement rather than dropping the row. The rule was right about the data and wrong about the moment: an error refuses the edit that raised it, and V-28 was the first assumptions error that did not need the project to have periods, so it fired on a project still being built and stopped a user entering their own assignments until the standing assumptions caught up. V-03 and V-23 still cover the case at the point where it can be acted on. V-27, REQ-CAL-16 and the absorption arithmetic are unchanged; no figure moves. Written against plan v2.32. | Issued
1.5 | 2026-08-26 | Claude Code | Dan | R-17, REQ-CAL-16 and three new rules. Sheet 05 gains the ABSORPTION rule - an unstaffed role's factor lands on the role named to cover for it, per month, one hop - and says why the mapping is a column on RoleFactor rather than two role names in the code. Sheet 04 gains V-27 and V-28, which ask on the PROJECT what V-19 and V-23 ask on its periods, and V-29, which reports the case absorption cannot fix. Schema 7 to 8. Written against plan v2.31. | Issued
1.4 | 2026-08-25 | Claude Code | Dan | R-16, SCHEMA 7. outsourcing_type becomes outsourcing_scope_det and becomes FREE TEXT - a note for a person, never read by the calculation. V-25 is RETIRED: it existed only to police two controlled vocabularies on the same axis, and there is now only one. Sheet 04 records the retirement rather than dropping the row, because a rule id that vanishes leaves a reader wondering whether they have an old document. Sheet 03 gains the RENAMED-COLUMN rule: a workbook carrying the old name is read, its values moved across, and the reader told once - a rename is the one schema change that otherwise loses a filled-in column in silence. Written against plan v2.30. | Issued
1.3 | 2026-08-25 | Claude Code | Dan | R-15, REQ-CAL-15: both assignment dates are optional and a blank one means the project's own, so an assignment with neither runs for the whole project. Sheet 05 gains the window rule and says why it is one function rather than two - the months a person is counted IN must not differ from the months they are counted AMONG, or a shared role stops adding up to one. Written against plan v2.29. | Issued
1.2 | 2026-08-22 | Claude Code | Dan | TWO CHANGES. (1) R-13: the role factor is DIVIDED between the people holding that role on that project in that month. Sheet 05 carries the formula, the counting rule and the worked example; the count is per month, by distinct people, and each person's own weight applies to their share afterwards. New setting split_shared_role_fte, default 1, restores the previous arithmetic when set to 0. (2) R-14: PeriodWeightStandard and RoleFactor are DELIVERED FILLED IN - 84 and 429 rows of default assumptions - and the application's blank start seeds the identical figures, read from the template rather than restated. Sheet 03 records where they come from and what a company is expected to do with them. Written against plan v2.28. | Issued
1.1 | 2026-08-20 | Claude Code | Dan | SCHEMA 6. Two changes to the data model, requested 2026-08-20. (1) work_scope_type joins PeriodWeightStandard and RoleFactor beside clinical_phase, so the keys become (project_type, clinical_phase, work_scope_type, period_name) and that plus role_name. Project gains the same column, because the key selects a row FOR A PROJECT and nothing could choose between the scope rows without it. A ROW WHOSE work_scope_type IS EMPTY APPLIES TO EVERY SCOPE, and a project falls back to it - which is what keeps RoleFactor at 429 rows instead of 1,269, and what lets a schema 5 file go on calculating. (2) 'Biosimilar CT' becomes 'Biosimilar CT (Healthy)' and 'Biosimilar CT (Patient)'; a type is recognised as a clinical trial by the START of its name. New rules V-25 (the two scope columns must not contradict) and V-26 (the retired type, reported with the two it became). Sheets 03, 04, 05 and 06 updated. Written against plan v2.27. | Issued
0.7 | 2026-08-01 | Claude Code | Dan | Plan change R-11 applied. The conduct phase is split by NAME: 'Conduct (interim)' where the project has an interim DB lock and the stretch runs before it, 'Conduct (final)' after it or where there is no interim lock. Period names are therefore unique within a project, and ProjectPeriod is keyed on (project_id, period_name) - sheets 03 and 05 updated, V-18 becomes a plain uniqueness check, and period_seq carries order only. The clinical period set grows to seven names, so PeriodWeightStandard is 56 rows and RoleFactor 289. Schema 4 to 5. Weights unchanged: the dummy dataset returns identical load figures, which is the evidence that this renamed without reweighting. Written against plan v1.8. | Draft
0.6 | 2026-08-01 | Claude Code | Dan | Plan change R-10 applied: the role factor is keyed on project type, clinical phase, period and role rather than type and role alone. Sheet 03 documents the two new RoleFactor columns and the four-part key; sheet 05 selects the factor by the period the month falls in; V-03 reworded and V-23 added for a factor missing on a period an assignment actually spans. Schema version 3 to 4. Sheet 05 also records the double-counting risk this creates, since RoleFactor and PeriodWeightStandard now vary over the same three dimensions. Sheet 06 gains the scroll-containment rule for every table on the source-data and assumptions tabs. Written against plan v1.7. | Draft
0.5 | 2026-08-01 | Claude Code | Dan | Component-list v0.3 review applied (plan change R-09). Sheet 06 gains a fourth tab, 'General assumptions', carrying PeriodWeightStandard, RoleFactor, Config and Lists (REQ-DSH-11) - and the FTE/hours unit moves there, since it is a setting rather than a filter. The filter set gains clinical phase. Row insertion is specified: a new row lands immediately below the row acted on (REQ-IMP-11). The load stamp carries its time zone. The timeline is specified as coloured by period name with weight as a lightness step, which supersedes design decision D-06 on the reviewer's own instruction. Tooltip content specified for the demand chart and the timeline. Written against plan v1.6. | Draft
0.4 | 2026-08-01 | Claude Code | Dan | Answers to the six open points applied. S2-01 and S2-05: both thresholds stay ABSOLUTE, with the under-allocation floor moved 0.80 -> 0.60; the relative-threshold proposal is withdrawn and V-22 added to catch a capacity below the floor. S2-04: repeated period names are numbered on screen, 'Conduct (1)' and 'Conduct (2)' (REQ-DSH-10). S2-06: target volume re-baselined to 100 projects and 1,000 people, which makes table virtualisation and chart aggregation requirements rather than optimisations (REQ-DSH-09). S2-02 and S2-03 confirmed as drafted. ProjectPeriod is keyed on project_id + period_name + period_start. Written against plan v1.5. | Draft
0.3 | 2026-08-01 | Claude Code | - | Change R-05: project_type split into 'NewDrug CT' and 'Biosimilar CT'. Parse contract, keys and schema version updated; RoleFactor and PeriodWeightStandard are now keyed on the type. Sheet 06 gains the UI changes requested at the Step 3 review: a global filter bar with Reset, per-project stacking, horizontal scroll regions, and row expansion on both Overall tables. | Draft
0.2 | 2026-08-01 | Claude Code | - | Parse contract updated for change R-04: a free-text note column on every sheet, and source schema version 2. Column counts on the sheet-index table adjusted. No change to validation, calculation, UI or IO behaviour. | Draft
0.1 | 2026-08-01 | Claude Code | - | First draft. Written against development plan v1.2 (approved baseline). Data schema documented from the delivered template; calculation and validation cross-checked against the reference implementation in tools/verify_source_workbook.py and the dummy dataset. | Draft
Version alignment across plan, specification and application is recorded on sheet 09 of the plan.

## 02_Scope
Scope and source documents
Source documents
Document | What it is | Relationship to this specification
PRAP_Development_Plan_v2.74.xlsx | Development plan, v1.3 baseline approved by Dan 2026-08-01 plus changes APPROVED BASELINE 2026-08-02. 70 requirements, 24 validation rules, 11 decisions, source schema version 5. | Governs this document
templates/PRAP_SourceData_Template_v1.21.xlsx | The blank source workbook as delivered. | The schema on sheet 03 documents this file
templates/PRAP_SourceData_Dummy_v1.23.xlsx | 16 NewDrug CT + 17 Biosimilar CT (Healthy) + 17 Biosimilar CT (Patient) + 12 'Others', 20 people, 277 assignments over 74 months. | The acceptance data for sheet 05
tools/verify_source_workbook.py | Reference implementation of parsing, validation and the monthly engine. | Executable check on sheets 04 and 05
docs/STEP2_OPEN_POINTS.md | Points raised while building the template. | Carried into sheet 10
In scope for this specification
In scope
The parse contract for the source workbook: sheets, columns, types, coercion and defaults.
All 21 validation rules with their exact severity and message.
Period derivation for both project types, including every degenerate timeline.
The monthly load calculation, aggregation, and the over- and under-allocation rules.
The behaviour of each dashboard tab: components, filters, interactions and empty states.
On-screen editing: the edit buffer, dirty state, cascading identifier changes, and export round-tripping.
Schema version checking and version display.
Deferred to Step 3
Deferred | Why
Exact visual layout, spacing, colour and typography. | Step 3 fixes the UI design; sheet 06 fixes behaviour and content, not pixels.
Which chart library, if any, is embedded. | Sheet 06 specifies what each graph must show. The rendering choice is made at Step 3 against the prototype.
Keyboard shortcuts and accessibility details. | Reviewed with the prototype, where they can be tried rather than described.

## 03_Data_Schema
Data schema - the parse contract
Documents templates/PRAP_SourceData_Template_v1.21.xlsx. Sheet and column names are matched exactly and case-sensitively.
Reading the workbook
for each required sheet:
if absent -> fatal, abort the load and report (V-00)
read row 1 as the header
for each column in the contract below:
locate it by exact name; if absent -> fatal for a required column,
ignore for an optional one
read rows 2..n; a row whose every cell is empty is skipped, not an error
coerce each cell per its type; a failed coercion is an error on that row
Type coercion
Type | Coercion | Why it matters
Text | Trim leading and trailing whitespace. An empty string becomes null. | Never coerce a number to text silently - a project_id of 001 read as 1 breaks every join.
Date | Accept an Excel serial date or an ISO yyyy-mm-dd string. Normalise to a date with no time part. | Any other format is an error, never a guess (REQ-NFR-05). A dd/mm vs mm/dd guess is silently wrong half the time.
Decimal | Accept a number, or a string parseable as one with '.' as the decimal separator. | A percentage-formatted cell reads as its underlying fraction; 40% is 0.4, which is what person_weight expects.
Integer | As Decimal, then require a whole number. | A fractional period_seq is an error.
List | Text, then checked against the Lists sheet by V-11. | The check is a warning, not a coercion - an unrecognised value is kept and reported.
Sheets and keys
Sheet | Key | References | Cols | Note
Project | project_id | - | 23 | Master.
Milestone | project_id + milestone_name + milestone_date | Project | 7 | milestone_name is NOT unique alone - 'Inspection' repeats (REQ-PRJ-13). Schema 13 adds milestone_highlight, which is OPTIONAL and part of no key: two rows differing only in their colour would be the same milestone twice.
ProjectPeriod | project_id + period_name | Project | 7 | Since R-11 no period name repeats in a project, so the name alone identifies the row. period_seq carries order, not identity (V-18).
PeriodFTEStandard | project_type + clinical_phase + work_scope_type + period_name | - | 6 | 84 baseline rows at schema 6: three trial types keyed separately (R-05, R-12), four phases, seven periods (R-11), with work_scope_type EMPTY. A row per scope as well would be 252. 'Others' take manual weights (Q-28).
RoleFactor | project_type + clinical_phase + work_scope_type + period_name + role_name | - | 7 | 429 baseline rows at schema 6 - the largest sheet in the workbook, and 1,269 if every scope were spelled out. Keyed on all five so a role's burden can vary across the life of a project (R-10) and with how much of the work is kept (R-12). clinical_phase is EMPTY on the nine 'Others' rows - the lookup must match null to null, not fall through.
Person | person_id | - | 12 | Master.
Assignment | assignment_id | Person, Project, RoleFactor | 11 | One row per person + project + role.
PersonPeriodWeight | assignment_id + period_start | Assignment | 5 | Optional. Overrides person_weight for its window. period_start IS part of the key: one assignment may carry several non-overlapping windows, so assignment_id alone does not identify a row. See the note below.
MonthlyEstimate | scope + ref_id + month | Project or Assignment | 6 | Schema 9. Monthly FTE STATED rather than calculated (REQ-CAL-18). The only sheet whose parent depends on a value IN the row: scope says whether ref_id names a project or an assignment, which is why it is part of the key. Read only where the owning row carries estimation_type = 'manual'.
Lists | list_name + value | - | 3 | Value lists, long format. Each list occupies a contiguous block.
Config | parameter | - | 3 | Thresholds and settings.
Why PersonPeriodWeight is keyed on TWO columns [R-12]
assignment_id is unique in Assignment - it is that sheet's primary key. It is NOT unique in
PersonPeriodWeight, and it is not meant to be: this is a child table of windows, and one assignment
may carry several.
ASG-902 2026-07-01 .. 2026-09-30 0.20 part-time, parental leave
ASG-902 2027-04-01 .. 2027-06-30 0.75 covering the start-up peak
everything outside those windows -> the assignment's own person_weight
One person, one project, one role, one assignment - three different weights over its life. That is
what the table is for, and REQ-PSN-05, V-06 and the data model all assume it.
If the key were assignment_id alone | Consequence
An assignment could carry at most ONE override window. | The case above becomes inexpressible. A second spell of changed capacity would need a second Assignment row.
Splitting into ASG-902a / ASG-902b / ASG-902c would be the workaround. | It breaks Assignment's own meaning - one row per person + project + role - and fragments the person's history across rows that are not really different assignments.
V-06's assignment-window half becomes dead. | Two windows could never coexist, so they could never overlap. A rule that can never fire is worse than no rule: it reads as protection.
So the key stays (assignment_id, period_start). period_start is the right second column because windows are ordered in time and cannot overlap - which V-06 enforces - so the start date identifies one window unambiguously.
Two gaps surfaced while answering this, both now closed. V-06's assignment-window half was specified from plan v1.0 but never implemented, so an overlapping pair passed silently and the weight that applied in the shared months depended on the order rows happened to sit in the file. And nothing checked that a PersonPeriodWeight row pointed at a real assignment, so an orphan override was accepted and then ignored without a word - the user's typed weight simply never applied. V-24 covers the second. The dummy fixture only ever had one window per assignment, which is why neither surfaced: a fixture that does not exercise a path cannot test it.
Derived columns - read, do not trust
Column | On import | Reason
Project.total_period_months | Recompute from start_date and end_date. | The template holds a formula, but an exported or hand-edited file may not. Recomputing costs nothing and cannot disagree with the dates.
Milestone.project_name | Recompute by lookup on project_id. | Denormalised for display only. V-13 reports a mismatch; the master value always wins.
Assignment.person_name | Recompute by lookup on person_id. | As above.
Free-text note columns [R-04]
Every sheet carries at least one. They are parsed as Text, carried through export unchanged, and never
read by the calculation - so a note can hold anything without affecting a single figure.
Sheet | Note column(s)
Project | note_1 .. note_5
Milestone | note_1
ProjectPeriod | note_1
PeriodFTEStandard | note_1
RoleFactor | role_note
Person | note_1 .. note_5
Assignment | note_1 .. note_3
PersonPeriodWeight | reason
MonthlyEstimate | note_1
Lists | note_1
Config | note
A note column that is absent is not an error - it is optional on every sheet. An import must not fail because someone deleted a column they were not using.
Renamed columns [R-16]
A rename is the one schema change that can lose data in SILENCE. The old column is
read, assigned to a key nothing looks at, and the new column comes back empty: the file
still opens, every rule still passes, and the value is simply gone.
So both readers translate the header on the way in, and the reader is told once:
schema 6 -> 7 Project.outsourcing_type -> Project.outsourcing_scope_det
This is not leniency about the schema - the workbook is still expected to be the current
one, and V-09 still reports the version mismatch. It is refusing to be the reason
somebody loses a column they filled in last week.
The delivered default assumptions [R-14]
PeriodFTEStandard and RoleFactor are DELIVERED FILLED IN - 84 and 429 rows. They used
to arrive empty, and a plan started inside the application filled both grids with a
placeholder 1.00.
1.00 everywhere is not a cautious starting point; it is the absence of one. At 1.00 the
period weight and the role factor cancel out of the multiplication, so every project
reduced to person_weight x coverage and the application produced figures that looked
like an answer and were not one. Nothing said so, because nothing was wrong.
Point | Detail | Basis
Defined once | tools/build_source_workbook.py - DEFAULT_PHASE_PROFILE and the tables beside it. | One definition
Read by the template | PeriodFTEStandard and RoleFactor are written from it at build time. | R-14
Read by the blank start | tools/build_app_seed.py lifts the same rows OUT OF THE TEMPLATE into SEED_PWS and SEED_RF. Not restated - lifted, so 'the workbook and the application hold the same assumptions' is a fact rather than a promise. | R-14
Read by the dummy data | The same baseline, plus illustrative scope-specific rows on top. | R-12
Checked | check_consistency.py compares the embedded seed with the template row for row, and fails if either grid has reverted to one flat value. | R-14
Still built from the lists | The blank start builds the GRID from the value lists, so a company that adds a role gets that combination immediately. It arrives at 1.00, marked as a placeholder, because nobody has supplied a figure for a role nobody had yesterday. | -
Baseline only | Every default row has work_scope_type EMPTY, which covers every scope. Shipping scope-specific defaults would mean asserting how much cheaper an outsourced trial is - the judgment a company has to make for itself. | R-12
Marked as defaults | Every row carries 'Default assumption - replace with your own figure' in its note column, so a figure nobody has reviewed can be told from one somebody chose. | R-14
Config parameters
parameter | Type | Default | Use
schema_version | Integer | 16 | Compared with the version this application expects (sheet 08).
absorb_unstaffed_role_factor | Integer | 1 | 1 = where nobody holds a role on a project, its factor is added to the role named in RoleFactor.absorbed_by (sheet 05). 0 = an unstaffed role costs nothing, the arithmetic of every version before this one.
split_shared_role_fte | Integer | 1 | 1 = the role factor is divided between the people sharing a role in a month (sheet 05). 0 = each carries the whole factor, the arithmetic of every version before this one. A switch, not a threshold - so the Config reader must distinguish a value of 0 from an absent value, which is the defect this setting exposed.
fte_hours_per_month | Decimal | 160 | Converts FTE to hours for display.
over_allocation_fte | Decimal | 1.50 | Absolute, not scaled by capacity_fte (S2-01). See sheet 05.
under_allocation_fte | Decimal | 0.60 | Absolute, not scaled by capacity_fte. Moved from 0.80 at S2-05. See sheet 05.
under_allocation_min_months | Integer | 3 | Consecutive months before a run is flagged.
default_horizon_months | Integer | 24 | Months shown on opening.
capacity_unit | List | FTE | 'FTE' or 'hours'. FTE is a WEIGHT - 1.00 is one person for a full month, so ordinary values run about 0.1 to 1.0; 'hours' multiplies it by fte_hours_per_month. Anything else displays as FTE. 'percent' was named in the contract until v1.9 and was never implemented.
schema_version stepped from 3 to 4 at R-10 (RoleFactor gained two columns), from 4 to 5 at R-11, and from 5 to 6 at R-12. R-11 changed no columns at all - but it retired the period name 'Conduct', so every ProjectPeriod row of a v4 file would fail V-15. A value set is part of the contract, not decoration. R-12 does both: three new columns AND a retired project_type. V-09 reports the mismatch, and a schema 5 file still CALCULATES - its standards rows carry no scope, which is exactly the every-scope row - so what it needs is the type renamed, which V-26 names.
A missing Config row falls back to the default above and raises a warning. A Config value that fails coercion is an error - a threshold read as text would silently disable a flag.
What a column is called on screen [COLUMN_LABEL, R-45]
Every column carries TWO names in the parse module, in one place so that adding one and forgetting
the other takes effort: COLUMN_HELP, a sentence saying what the column is for, and COLUMN_LABEL, a
plain name for it. A table heading prints the PLAIN NAME AND NOTHING ELSE; the column's own name is
in the heading's pop-up and on the element as data-cid. The same two-part head - plain name, then
column name in the quieter type - opens the heading's pop-up, every cell's, and the filter buttons'.
WHERE THE IDENTIFIER BELONGS WAS SETTLED TWICE, and the reasoning is recorded because the first
answer was defensible and still wrong. It was printed on a second line under the label, on the
argument that the screen and the file are the same thing, so a heading must be findable in the
spreadsheet, quotable in a mail and lookup-able here. Right about the need, wrong about the place:
looking a column name up is OCCASIONAL - editing the workbook, chasing a finding - and a heading is
read on EVERY glance by everyone, so printing it charged the common case for the rare one while the
pop-up already answered it in full.
THIS IS NOT A RENAME. The workbook's column names stay in every validation message, stay reachable
from every heading, and stay as the key the editing path writes back through (data-col on the cell is
the identifier, never the label). The schema is unchanged at 11 and no file is affected. What changes
is that a reader who has never seen this document can now read the table: work_scope_type,
outsourcing_scope_det, absorbed_by and ref_id were legible to whoever wrote the schema and to nobody
else, and their meaning lived in a pop-up - which is to say it was there only for a reader who
already knew to hover.
COLUMN_LABEL must cover every column in SHEET_HEADERS, plus the read-only lookup columns the
application adds beside them (standard_fte, automatic_fte, difference, period, sharers). A missing
entry is not an error - the heading falls back to the bare identifier - which is exactly why it is
held by a test rather than left to notice: a silent fallback to the old behaviour is the failure
mode this replaces. tools/test_labels.py checks the map against the schema, not against the screen.

## 04_Validation
Validation rules
Every rule runs on import and again on any on-screen edit (REQ-IMP-09). The load never stops at the first problem: findings are collected and presented as one report (REQ-IMP-02).
Severities
Severity | Meaning | Behaviour | Example
Fatal | The workbook cannot be used at all. | Abort the load. Show what is missing and the template download link. | Missing sheet; missing required column.
Error | This row cannot be trusted. | Reject the row, keep loading the rest, list it with its sheet and row number. | Unknown project_id on an assignment; end before start.
Warning | Usable, but someone should look. | Keep the row, list the finding. | A value not in its list; an assignment outside its project's dates.
Information | Explains a decision the reader might otherwise question. | List only. | V-21: an early inspection did not open period 7.
The rules
ID | Severity | Trigger | Message shown to the user
V-00 | Fatal | A required sheet or column is absent. | Sheet 'Assignment' not found. The workbook must contain all 10 sheets - download the template to compare.
V-01 | Error | Assignment.project_id not found in Project. | Assignment ASG-014 refers to project PRJ-099, which does not exist.
V-02 | Error | Assignment.person_id not found in Person. | Assignment ASG-014 refers to person PSN-099, which does not exist.
V-03 | Error | Assignment.role_name appears nowhere in RoleFactor for that project's type. | Assignment ASG-014: role 'Main staff' is not valid for a project of type 'NewDrug CT'. Valid roles for this type: ...
V-04 | Warning | project_category empty on either clinical trial type. | Project PRJ-003 is a clinical trial with no product category.
V-05 | Error | An end date precedes its start date. | Project PRJ-003: end_date 2026-01-01 is before start_date 2026-06-01.
V-06 | Error | Two periods of one project, or two override windows of one assignment, overlap. | ASG-902: override windows overlap - 2026-07-01..2026-09-30 and 2026-08-15..2026-11-30. Which weight applies in the shared months would depend on row order.
V-07 | Warning | Assignment dates fall outside the project's own dates. | Assignment ASG-014 runs to 2029-06-30, after project PRJ-005 ends on 2029-03-31.
V-08 | Error | A duplicate identifier. | person_id PSN-004 appears on rows 5 and 12.
V-09 | Warning | Config.schema_version differs from the expected version. | This file is schema version 2; this application expects version 1. Some columns may be ignored.
V-10 | Warning | A clinical trial missing clinical_phase or any *_setup value. | Project PRJ-004 has no RBQM_setup recorded.
V-11 | Warning | A list-typed value not found in the Lists sheet. | Project PRJ-002: outsourcing_type 'Partial in house' is not a known value. Did you mean 'Full In-house'?
V-12 | Warning | A project's periods leave a gap or do not cover its full span. | Project PRJ-006: 2026-07-01 to 2026-07-31 belongs to no period. Those months are calculated at weight 1.00.
V-13 | Warning | A denormalised name does not match its master row. | Assignment ASG-014 records person_name 'Kim' but PSN-001 is 'Kim S.'. The master value is used.
V-14 | Error / Warning | A boundary milestone is out of chronological order, or a milestone falls outside the project window. | Project PRJ-003: 'First SIV' 2025-12-01 precedes 'CTA submission' 2026-01-15, so periods cannot be derived.
V-15 | Error | A period_name not in the set for that project's type. | Project PRJ-006 is type 'Others' but has a period named 'Conduct (final)'. Valid: Planning, Develop, Close.
V-16 | Error | A clinical trial lacking CTA submission or any DB lock. | Project PRJ-007 has no DB lock milestone, so its periods cannot be derived. Enter them manually or add the milestone.
V-17 | Error | An edit would orphan a reference (see sheet 07). | PSN-001 cannot be deleted: 3 assignments still refer to it.
V-18 | Error | Within a project, period_name is not unique, or period_seq is duplicated. | Project PRJ-003: period_name 'Conduct (final)' appears 2 times; (project_id, period_name) must be unique. period_seq must also be unique - it fixes their order.
V-19 | Error | A clinical trial with no clinical_phase, or no PeriodFTEStandard row for its phase AND scope - counting the every-scope row. | Project PRJ-005: no standard weight for NewDrug CT / Phase 3 / fully in-housed / Start-up. Add a row for that scope, or one with work_scope_type empty to cover every scope.
V-20 | Warning | A milestone other than 'Inspection' recorded more than once. | Project PRJ-002 records 'CTA submission' twice. Only 'Inspection' is expected to repeat.
V-21 | Information | An 'Inspection' dated on or before the final DB lock. | Project PRJ-002: 1 inspection on or before the final DB lock is treated as a marker and does not open the final period.
V-24 | Error | PersonPeriodWeight.assignment_id not found in Assignment, or two windows of one assignment share a period_start. | ASG-999: PersonPeriodWeight refers to an assignment that does not exist; its override is silently ignored.
V-23 | Error | No RoleFactor row for a (project_type, clinical_phase, work_scope_type, period_name, role_name) that an assignment actually spans - counting the every-scope row. | No role factor for NewDrug CT / Phase 3 / fully outsourced / Conduct (final) / Data Analyst - assignments covering that period would be calculated at factor 1.00.
V-25 | Warning | A project's work_scope_type contradicts its outsourcing_type at one of the two unambiguous ends. | Project PRJ-012: outsourcing_type says 'Full In-house' but work_scope_type says 'fully outsourced'. The weights follow work_scope_type; check which is right.
V-26 | Error | A project carries a project_type that schema 6 retired. | Project PRJ-003: project_type 'Biosimilar CT' was split in schema 6. Change it to Biosimilar CT (Healthy) or Biosimilar CT (Patient).
V-22 | Warning | Person.capacity_fte is below config.under_allocation_fte. | PSN-018: capacity 0.50 FTE is below the under-allocation floor of 0.60, so this person can never clear it however fully they are booked. Lower the floor or raise the capacity.
V-31 | Error | A project or assignment set to estimation_type = 'manual' has months it covers with no MonthlyEstimate row. | Project PRJ-019 is set to MANUAL but MonthlyEstimate has no figure for 3 of its month(s): 2028-01, 2028-02, 2028-03. Those months are counted as 0.00.
V-32 | Error | A manual PROJECT has a figure for a month in which nobody is assigned to it, so there is nobody to share it out to. | Project PRJ-019 has a manual figure for 2 month(s) in which nobody is assigned to it. It has NOT been applied - the project would otherwise show a total that none of its people account for.
V-37 | Warning | Milestone.milestone_highlight names no colour the application can draw. The value comes from the Lists sheet and what is read is the COLOUR WORD inside it - one of the thirteen of REQ-PRJ-17, standing as a word - so a team may write what their colour means beside it and keep both. The rule fires only when no such word is there at all. The milestone is drawn unmarked, exactly as an empty column would draw it, and no figure changes. | Project PRJ-004: milestone_highlight 'Hilight (Read)' names no colour this application can draw, so 'Inspection' is left unmarked. Valid: Highlight (Red), Highlight (Yellow), Highlight (Blue), Highlight (Green), Highlight (Orange).
V-36 | Information | A project that has periods and NO assignment rows at all. Raised from the CALCULATION, one finding per project. Classed INCOMPLETE, so it never refuses and never asks. Skipped where the project has no periods (V-12 or V-16 already says so, and there is no demand to state) or where its status is Completed (history, not a gap - a finding that will never answer itself does not belong in the INCOMPLETE class). Every term is the one an assignment with blank dates would get (REQ-CAL-15), so the figure it names is to the hundredth the figure the project shows once somebody is assigned. | Project PRJ-099 has periods but NOBODY ASSIGNED TO IT. It is listed in Resource by project and drawn on the timeline, but EVERY ONE OF ITS MONTHS IS EMPTY, and it adds nothing to the demand charts - a row of blanks, which reads as a project that costs nothing rather than one nobody has been put on yet. Its own standard says it needs 38.05 FTE-months across 24 month(s), from 2025-03, peaking at 1.86 FTE in 2026-10. That demand is real and unallocated: a project-month IS its standard and the people on it divide it (REQ-CAL-19), so having nobody on it does not make the figure nought - it leaves it unstated. Assign somebody and the project fills in across every table and chart, at exactly these figures. This is a note, not a fault: it is the state every project is in until its first assignment, so it never refuses an edit and never questions a save.
V-35 | Error | Person.capacity_fte outside 0.00 to 1.00, in either direction. REFUSES - the only rule added this year that does. | PSN-001: capacity 1.50 FTE is outside 0.00 to 1.00. capacity_fte is how much of ONE PERSON there is, so 1.00 is full-time and 0.50 is half a week - there is no such thing as 1.50 of a person. A figure above 1.00 is usually hours typed into an FTE column: 1.50 hours a month is 0.01 FTE. Somebody who does the work of two people is TWO ASSIGNMENTS, or a person weight above 1.00 on one of them - not a capacity above 1.00.
V-34 | Warning | A project-month where what the project NEEDS - standard FTE x period weight x the part of the month it runs - is not what it is being GIVEN, in either direction. Raised from the calculation; one finding per project. | Project PRJ-019 is not being given what its own standard says it needs: 2 month(s) SHORT of it by up to 5.00 FTE, and 1 month(s) OVER it by up to 3.00 FTE. Worst is 2026-09, which needs 10.00 and is getting 5.00. It is reported because it is otherwise invisible: the charts simply draw a different project.
V-33 | Warning | A manual ASSIGNMENT figure that the project's own manual figure overrode. REQ-CAL-18 makes the project month the mother figure, so the stated figure for the person is not what they are given. | Assignment ASG-001 states a monthly figure that its PROJECT'S own manual figure overrode in 1 month(s) - 2025-03: stated 99.00, applied 9.97. Either change the project's figure to one that leaves room for this person's, or take this assignment off manual and let it take its share.
Messages name the row and the offending value, and where there is an obvious fix they suggest it. A validation report that says only 'invalid data' forces the user to hunt, which is how findings get ignored.
The findings report
Behaviour | Reason
Grouped by severity, then by sheet. | Fatals first - if any exist, nothing else matters yet.
Each finding shows sheet, row number, rule ID and message. | The row number is the Excel row, so the user can go straight to it.
A one-line summary banner persists until dismissed. | e.g. '3 errors, 11 warnings - 2 rows were not loaded'.
Exportable to .xlsx. | So a data maintainer can work through it away from the application.

## 05_Calculation
Calculation
Pure functions: no DOM, no file access (plan sheet 07, layer 5). tools/verify_source_workbook.py is the reference implementation.
Period derivation - clinical trial, either type [REQ-CAL-09, REQ-CAL-12, REQ-CAL-13]
protocol = milestone 'Protocol (v1)' cta = milestone 'CTA submission'
siv = 'First SIV' else 'FPI' idbl = 'interim DB lock'
fdbl = 'final DB lock' else idbl insp = all 'Inspection' dates
if cta is null or fdbl is null: raise V-16 and derive nothing
su_start = max( protocol + 1 day if protocol else cta - 1 month , project.start )
su_end = siv if siv and siv >= su_start else su_start + 4 months - 1 day
later = [ d in insp where d > fdbl ] # V-21: earlier ones stay markers
p7_start = min(later) if later else null
p7_end = max( max(later), project.end ) if later else null
cof_start = fdbl - 3 months
cof_end = p7_start - 1 day if p7_start else max( fdbl, project.end )
segments = []
if su_start > project.start: segments += ('Before-Start-up', project.start, su_start - 1 day)
segments += ('Start-up', su_start, su_end)
if idbl and idbl < fdbl: # R-11: the split case
coi_start = idbl - 3 months
segments += ('Conduct (interim)', su_end + 1 day, coi_start - 1 day)
segments += ('Close-out (interim)', coi_start, idbl)
cof_start = max( cof_start, idbl + 1 day )
segments += ('Conduct (final)', idbl + 1 day, cof_start - 1 day)
else: # no interim lock to be interim to
segments += ('Conduct (final)', su_end + 1 day, cof_start - 1 day)
segments += ('Close-out (final)', cof_start, cof_end)
if p7_start: segments += ('After Close-out (final)', p7_start, p7_end)
drop every segment whose end < start # REQ-CAL-12, decision C-11
number the survivors 1..n as period_seq
'Conduct (interim)' is emitted ONLY in the split branch, so the name is never a lie: it exists only where there is an interim DB lock to be interim to. Every other conduct stretch - including the single one of a project that never has an interim lock - is 'Conduct (final)'. That is what makes period_name unique within a project and gives ProjectPeriod its natural key (R-11).
A project may legitimately end up with 'Conduct (interim)' and no 'Conduct (final)': where the two locks are less than three months apart, the final stretch is squeezed to nothing and dropped by the rule above. The names describe position, not a required pair.
'month' arithmetic clamps to the end of a short month: 31 Mar minus 1 month is 28 Feb (29 in a leap year). Test that explicitly - it is the classic off-by-one in this kind of code.
For 'Others' the derivation does not run at all: periods are read from ProjectPeriod as entered (Q-25, Q-28).
Monthly load [REQ-CAL-02, REQ-CAL-05, REQ-CAL-08, REQ-CAL-14]
load(assignment, month) = project_period_weight( project, month )
role_factor( project.type, project.phase, project.scope,
period_name( project, month ), assignment.role )
x -------------------------------------------------------------
sharers( project, assignment.role, month )
x person_weight( assignment, month )
x coverage( assignment, month )
project_period_weight : weight of the period containing the FIRST DAY of the month (decision C-08)
no period covers it -> 1.00, and raise V-12
role_factor : selected by the SAME period as the weight above, so the two always
agree about which period the month is in (R-10)
project.phase is NULL for 'Others'; the lookup matches null to null
project.scope falls back to the empty-scope row (R-12)
no row matches -> 1.00, and raise V-23
sharers : how many DISTINCT PEOPLE hold that role on that project in that
month, counting anyone whose assignment touches it (R-13)
never 0; when nobody else holds the role it is 1
config.split_shared_role_fte = 0 -> always 1, the old arithmetic
person_weight : PersonPeriodWeight.weight_override if a window covers the
first day of the month, else assignment.person_weight
coverage : calendar days of the month inside the ASSIGNMENT WINDOW,
divided by the days in that month
THE ASSIGNMENT WINDOW [REQ-CAL-15]
start = assignment.assign_start_date or project.start_date
end = assignment.assign_end_date or project.end_date
Both dates are OPTIONAL. Most people are on a project for the whole of it, and asking
for two dates that repeat the project's means copying the same pair onto every row and
keeping them in step when the project moves. Fill them in for a PARTIAL involvement.
The end date always behaved this way. The start did not, and a blank one made the
assignment contribute NOTHING - the row on screen, the person apparently unassigned,
and no finding to say why. That was a defect rather than a rule.
ONE FUNCTION, used by the calculation AND by the sharing pre-pass above. The months a
person is counted IN must not differ from the months they are counted AMONG; two
copies of this rule would eventually disagree, and the symptom would be a shared role
that does not add up to one.
result is FTE. hours = FTE x config.fte_hours_per_month
WHEN NOBODY HOLDS A ROLE [REQ-CAL-16]
role_factor answers 'what does this ROLE cost the project'. If nobody is holding it,
that cost does not disappear - the work is done by whoever is there. So the factor is
added to the role named in RoleFactor.absorbed_by, and the project stops looking
cheaper than it is simply because a post was never filled.
effective(role) = factor(role)
+ SUM factor(x) for every x with absorbed_by = role
that NOBODY holds in this month
PER MONTH, so cover ends by itself the month somebody arrives.
ONE HOP: if the absorbing role is unstaffed too, the work is not passed further along.
There is nobody to pass it to, and a chain would pile three absent roles onto whoever
happened to be left. V-29 reports that case rather than inventing an answer.
THE MAPPING IS DATA. Which role covers for which is a judgment about how a team works,
and REQ-CAL-06 has said since the first plan that factors live in the workbook.
WHY THE FACTOR IS DIVIDED [REQ-CAL-14]
role_factor answers 'what does this ROLE cost the project in this period', not 'what
does each person holding it cost'. Charge every holder the whole factor and a trial run
by two data managers costs twice a trial run by one - the same work, priced by how many
people happen to be named against it. The property to preserve is that the PROJECT'S
total does not move when the same work is shared out differently, and dividing by the
headcount is what preserves it.
COUNTED PER MONTH, not once per assignment. When one of two sharers leaves in June, the
other must be back to a full share in July - by itself, with nobody editing anything.
A per-assignment divisor would halve them for the whole project.
COUNTED BY PEOPLE, not by rows. Two rows for one person on the same project and role are
one person doing one job, and must not halve their own load.
PERSON WEIGHT APPLIES AFTERWARDS, to the share. Two people at 1.00 and 0.50 on a factor
of 2.00 carry 1.00 and 0.50, not 1.33 and 0.67: the division is by headcount, which is
what was asked for, and a person's own weight then says how much of their share they
actually give it.
The two weight tables now overlap [R-10, R-12]
PeriodFTEStandard is keyed on (project_type, clinical_phase, work_scope_type, period_name).
RoleFactor adds role_name to the same key.
The calculation multiplies them, so the pair is mathematically collapsible into one table.
THE LOOKUP, IN BOTH TABLES, IS TWO STEPS AND NOT ONE:
1. the row for this project's own work_scope_type -> use it
2. otherwise the row whose work_scope_type is EMPTY -> use that; it means any scope
3. otherwise nothing -> V-19 or V-23 says so
An empty scope is not a missing value. It is a row that deliberately declines to distinguish,
and it is what keeps the two tables a size a person can fill by hand. Any program reading these
sheets must do the same, or it will report a missing weight where the application finds one.
Table | Answers | Change it when
PeriodFTEStandard | How busy is the PROJECT in this period? | The shape of a project changes - e.g. Phase 3 close-out is heavier than assumed. One edit covers every role.
RoleFactor | How much of that falls on THIS role? | The split between roles changes - e.g. the analyst starts earlier than assumed. Five edits, one per role.
The separation is a maintenance convention, not something the arithmetic enforces. Raising a project's Conduct load by editing all five RoleFactor rows produces the right answer today and double-counts the next time PeriodFTEStandard moves. The application cannot detect this - both tables are legitimate inputs - so it belongs in the workbook README and in whatever process maintains the file.
If the distinction ever stops being maintained in practice, the honest fix is to collapse the two into one table keyed on all four columns, not to keep a separation that exists only on paper. That would be a schema change, so it is flagged here rather than done.
Stated figures, and the decimal rule [REQ-CAL-18, REQ-CAL-19, REQ-CAL-20]
A project's month is its own demand, and the people on it divide that month between them (R-32):
demand(project, month) = standard_fte( project, month ) x period_weight x month_run
claim(assignment, month) = ( role_factor / sharers ) x person_weight x coverage
fte(assignment, month) = demand x claim / SUM( claims on that project-month )
TWO LEVELS OF STATED FIGURE, APPLIED IN THIS ORDER (REQ-CAL-18):
1. an ASSIGNMENT figure REPLACES that person's share for that month;
2. a PROJECT figure is the WHOLE month, and every line on that project-month - including
any line stated at level 1 - is SCALED so the people still add up to it.
The project figure is therefore the mother figure and wins. That is not a tie-break invented
for the edge case: a project total that did not equal the sum of its own people would put the
two utilisation charts in disagreement and cost the results export its one guarantee.
WHICH MEANS A PERSON CAN TYPE ONE NUMBER AND BE GIVEN ANOTHER. Sheet MonthlyEstimate holds
99.00 against an assignment; the project's own month is 10.00; the person is given 9.97. Both
figures were deliberately typed and which of them is wrong is not the application's judgement,
so this is REPORTED and never refused. calculate() keeps three fields on any line it overrode:
Field on the line | Meaning
stated_assignment_fte | what MonthlyEstimate says for this assignment-month, before the project scaled it
overridden_by_project | true where the applied figure differs from the stated one by 0.01 or more
manual_project_total | the project's own stated month - the figure that did the overriding
From those three, and nothing else: V-33 in the findings, the stated-against-applied table in the Monthly estimation panel, and the soft stop the editor raises at the cell. One source, so the sheet, the screen and the report cannot name different numbers.
Demand against applied, and the pair that cannot differ [REQ-DSH-15, V-34]
A PROJECT'S MONTH IS ALWAYS THE SUM OF ITS PEOPLE. projMonth is accumulated FROM the lines, so it
is that sum by construction and REQ-OUT-06 rests on it. Checking it would be checking that addition
works, and no rule does.
THE PAIR THAT DOES COME APART is what the project NEEDS against what it is BEING GIVEN:
demand = standard_fte x period weight x month_run # what its kind takes
applied = SUM( fte of every line on that project-month ) # what it is getting
gap = applied - demand # in integer hundredths, so rounding is never a finding
gap < 0 -> SHORT of the standard: asked to run on less than its kind takes
gap > 0 -> OVER it: deliberately staffed heavier
AN AUTOMATIC MONTH HAS THEM EQUAL, always: shareOut hands out exactly the demand's hundredths and
the shares add to one (REQ-CAL-19). So a file nobody has edited raises nothing, which is what keeps
the rule worth reading. A figure stated by hand at either level REPLACES the standard rather than
adjusting it, and the two part company - after which the application simply drew a different
project. A study needing 10.00 and staffed at 5.00 looked exactly like a study that only ever
needed 5.00, and that is what V-34 exists to say.
COUNTED APART, NEVER NETTED. Five short in September and five over in October sum to zero and are
not a plan in balance. The two directions are counted, coloured and worded separately everywhere,
and no net figure is shown anywhere.
calculate() returns projDemand (project¦month -> demand) and projGap (project¦month -> {demand,
applied, gap, dir}), both built from the lines like every other map here.
WHAT calculate() HANDS BACK FOR THE SCREENS TO READ (REQ-DSH-14). A table that shows a figure has
to be able to say what decided its size, and every such answer comes from the calculation's own
workings rather than from a second lookup - otherwise a screen can name one period while the
figure beside it came from another:
Returned by calculate() | Answers
lines[].standard_fte, .period_name, .period_weight, .sharers | the terms behind one person-month, as the arithmetic used them
projPeriod: project¦month -> {name, weight} | the period of every month that produced a figure
periodAt(project_id, year, month0) | the period of a month that produced NONE - a manual project month with nobody assigned to it (V-32) has a stated figure and no line to read a period off. The same function the calculation itself used, so the two answers cannot drift apart.
THE SHAPE THE DERIVATION MUST TAKE, which is a correctness requirement and not a layout choice:
project month Start-up (standard 4.00) x period weight (1.00) x month run (1.00) = 4.00
person month ...the same line, then, separately:
role factor (0.60) / sharers (1) x person weight (1.00, no override)
x coverage (1.00) = 60.0% of it -> 2.40
TWO HALVES, NOT ONE PRODUCT. Since R-32 a person's figure is the project's month TIMES a share,
and the share is their claim over the sum of the claims. The terms above multiply to 0.60 and the
figure is 2.40. Written as a single product the cell would assert an arithmetic this program does
not perform, and would be wrong by whatever the other claims on that project-month came to. So
the demand closes with '=', and the person's terms close with a PERCENTAGE of it.
AN OVERRIDE IS ONE TERM WITH TWO SOURCES. PersonPeriodWeight REPLACES person_weight for the
months it covers - it does not multiply it (REQ-PSN-05) - so the two are never shown as two
factors, however naturally that reads. The cell names both and says which was used:
'weight override (0.50, replacing person weight 1.00)'.
A FALLBACK SAYS IT IS ONE, and names its rule: V-19 where no PeriodFTEStandard row matched,
V-23 where no RoleFactor row did, V-12 where no period covers the month. A bare 1.00 cannot be
told from a standard that really is 1.00, which is why those rules exist at all. Absorbed cover
is named with the roles it came from (REQ-CAL-16).
These feed READ-ONLY lookup columns. None of them is a column of the sheet it is shown beside, and none is written on save: a standard copied onto a ProjectPeriod row would survive the standards being edited afterwards, which is the failure the lookup exists to prevent. A missing standard is shown as missing, naming V-19, rather than as the 1.00 the calculation degrades to - printing the fallback as a standard would hide what V-19 reports.
THE DECIMAL RULE (REQ-CAL-20). Every FTE figure the application produces IS a whole number of
hundredths - not a longer figure displayed to two places. The rounding happens ONCE, where a
person-month is decided (shareOut for a calculated month, applyManual for a stated one).
Rounding each share on its own would not do: three shares of 4.27 rounded separately come to
4.26 or 4.28, so the detail rows would stop summing to the month (REQ-OUT-06) and the shares
would stop adding to one (REQ-CAL-19). Measured on the 62-project fixture, that missed on 644
of 1,629 project-months. So THE MONTH IS ROUNDED FIRST AND ITS HUNDREDTHS ARE HANDED OUT:
total_cents = round( demand x 100 )
exact[i] = weight[i] / SUM(weights) x total_cents
out[i] = floor( exact[i] )
left = total_cents - SUM(out)
give the remaining hundredths, one each, to the lines with the largest exact[i] - out[i];
where two remainders are EQUAL, to the line whose assignment_id sorts first.
THE TIE-BREAK IS PART OF THE RULE, not an implementation detail. It is a total order that does
not depend on array order or on the order rows were read from a sheet; without it two of the
four independent implementations could differ by 0.01 and both be right.
A detail row therefore sits up to 0.01 - a full hundredth, since largest remainder gives a line
either its floor or its floor plus one - from the exact product of its own terms; measured worst
0.0070 on the fixture. The rows of a project-month nonetheless add to that month exactly, with
nothing left over. The results export says both things in its own words.
Hundredths are counted as INTEGERS throughout, so the arithmetic cannot introduce the error it
exists to remove.
Aggregation [REQ-CAL-03, REQ-CAL-04, REQ-CAL-07]
Output | Definition | Where it surfaces
project_month[p][m] | sum of load over assignments on project p | Overall tab, table A and the stacked graph
person_month[s][m] | sum of load over all assignments held by person s | Overall tab, table B and the person graph
cell[s][p][m] | the individual load | Drill-down under a person or project row
headcount[p][m] | count of assignments with load > 0 | Compared with planned_member_count
over[s][m] | true where person_month > config.over_allocation_fte - the same figure for everyone | Red cell, counted in the summary tiles
under_runs[s] | maximal runs of >= min_months consecutive months where 0 < person_month < config.under_allocation_fte | Amber across the run, counted once per run
Thresholds [settled at S2-01 and S2-05]
Both thresholds are ABSOLUTE. They are not scaled by capacity_fte.
over when person_month > config.over_allocation_fte (1.50)
under when person_month < config.under_allocation_fte (0.60)
The v0.3 draft proposed scaling both by capacity, because a part-timer at 0.60 could never reach an
absolute 0.80 floor and so was flagged permanently. The review kept the thresholds absolute but moved
the floor to 0.60, which resolves the same defect a different way - every capacity in the data can now
clear it:
capacity_fte | utilisation needed to clear the 0.60 floor
1.00 | 60%
0.80 | 75%
0.60 | 100%
The risk returns only for a capacity BELOW the floor, which V-22 warns about on import. Nothing else in the calculation depends on capacity_fte, so it is now used for display and for that one check rather than in the arithmetic.
Under-allocation runs
walk the person's months in order across the horizon
a month counts toward a run when 0 < person_month < under_threshold
a month at exactly 0 BREAKS the run # no assignments at all is not under-allocation
a run of >= config.under_allocation_min_months is reported once, at its first month,
carrying its length
Reporting the run once rather than flagging each month is what makes the signal readable: three separate amber cells look like three problems.
Acceptance test
Element | Value | Note
Assignment | PSN-001 on PRJ-001 (Clinical Trial), role 'Lead data manager'
person_weight | 0.40
Window | 2026-03-10 to 2026-12-31 | Joins part-way through March
Periods | Start-up to 2026-06-30 at weight 1.50; Conduct (final) from 2026-07-01 at 1.00 | From the trial's clinical phase
role_factor | 1.20 | Illustrative; the real value is data
March 2026 | 1.50 x 1.20 x 0.40 x (22/31) = 0.511 FTE | 81.8 hours
April 2026 | 1.50 x 1.20 x 0.40 x 1.0000 = 0.720 FTE | 115.2 hours
July 2026 | 1.00 x 1.20 x 0.40 x 1.0000 = 0.480 FTE | 76.8 hours
Plus the whole dummy dataset: running tools/verify_source_workbook.py against PRAP_SourceData_Dummy_v1.23.xlsx must give no errors and no warnings, across 62 projects, 20 people, 277 assignments and 308 periods spanning 74 months. Every period set must be contiguous, all 50 trials must carry 'Conduct (final)', 30 must also carry 'Conduct (interim)', and 12 must carry the final inspection period. No project may carry a repeated period name. Those figures are the regression baseline for Step 4.

## 06_UI_Spec
User interface
Behaviour and content. Layout and typography are fixed at Step 3. Colour is fixed there too, with one exception now settled here: on the timeline, colour carries the period name, so it is meaning rather than styling.
Global
Component | Behaviour | REQ-ID
Header | Application name, application version, expected schema version, loaded file name, and the load time WITH ITS TIME ZONE - offset and abbreviation both, e.g. '2026-08-01 09:14 (GMT+9, KST)'. A bare timestamp is ambiguous to a reader in another country. | REQ-VC-02, REQ-IMP-05
Tab bar | Overall ¦ Source data (project) ¦ Source data (person) ¦ General assumptions. Tab state survives a re-import. | REQ-DSH-01..04, REQ-DSH-11
Findings banner | Appears when the last load or edit produced findings; opens the full report on click. | REQ-IMP-02
Unsaved-edit counter | Always visible once any edit exists, and states the validation standing of those edits - 'n unsaved edits, all n pass validation'. Warns before unload or a new import. An edit that fails a rule is rejected at entry and never enters the buffer, so everything counted here is exportable. | REQ-IMP-08, REQ-IMP-09
Empty state | With nothing loaded, every tab shows the same load panel plus a template download link. | REQ-IMP-03
Frozen columns | A source-data table may freeze a LEADING run of columns at its left edge so that a row's identity stays on screen while the rest of the table scrolls sideways: on Project, the row handle, project_id and project_name. Which columns is declared per SHEET, not per place the table is drawn. The frozen cells are ordinary editable cells, are opaque in every row state - striped, hovered, selected, edited - and overlap their neighbours by one pixel, which is what leaves no seam for the row passing underneath to show through. | REQ-DSH-19, REQ-DSH-13
Full screen | Every panel holding a bounded scroll region carries a control in its head that gives that panel the whole window: same table, every column, at the height of the screen rather than the cap REQ-DSH-13 applies. The panel is NOT moved - it is drawn against the viewport where it stands - so editing, validation, the type-ahead, the column filters and the pop-ups behave exactly as they do on the page. The sticky band (unsaved-edit counter, Save, tab bar) is lifted above it and stays reachable; the filter bar is covered. A shell with its own window bars - the desktop and Python editions - keeps those in front as well, with the section starting below them; the room they take is MEASURED from elements the shell marks as its own top chrome, so this layer names no shell. Escape closes it, as does changing tab or loading a plan. A panel with no bounded region offers no control. | REQ-DSH-18, REQ-DSH-13
Tab 1 - Overall
Component | Behaviour | REQ-ID
Horizon control | From/to month. Defaults to 24 months from the current month. One control expands it to span every project's dates. | REQ-CAL-01, REQ-DSH-07
Filters | project type (NewDrug CT / Biosimilar CT / Others), CLINICAL PHASE, project, person, role, department. Multi-select, combined with AND. GLOBAL: one setting drives every tab, not just the Overall tab. Clinical phase sits immediately right of project type, so the two type-ish controls read as a pair. | REQ-DSH-05
Unit toggle | FTE or hours, seeded from config.capacity_unit. NOT in the filter bar: it changes how every figure is written, not which figures are shown, so it is a setting and lives on the assumptions tab. | REQ-CAL-08, REQ-DSH-11
Table A - by project | Rows projects, columns months, cells FTE. Row and column totals. A project row expands to its people. A MONTH INSIDE THE PROJECT'S RUN WITH NOBODY ON IT carries what the standard asks for rather than a dot (REQ-DSH-17), drawn as demand and not as resource - no filled scale, an outline and a hatch, italic, and a hollow ring glyph (D-04) - and never added to any total. Filled ONLY where the calculation produced no figure at all, so no existing figure moves. | REQ-DSH-01, REQ-DSH-17
Table B - by person | Rows people, columns months, cells FTE summed across projects. Over-allocated cells red, under-allocation runs amber. A person row expands to their projects. | REQ-DSH-01, REQ-DSH-08
Graph 1 | Stacked bar: total monthly demand, ONE BAND PER PROJECT, ordered by total resource with the largest on the baseline. 'Others' projects are grey; trials take the extended colour set. NO LEGEND - a list of 62 entries cannot be matched against the chart. Identity comes from the hover pop-up, which carries project name and type, that month's FTE and its hour equivalent, its share of the month, the headcount, every person on the project that month with their role, and - under a rule - THE MONTH'S TOTAL ACROSS EVERY PROJECT IN VIEW. The total is what a band on its own cannot give: 4.02 FTE means nothing until you know whether the month came to five or to fifty. It is the same figure Graph 2 states for that month, summed along the other axis, so the two pop-ups are held to agreeing in words as well as in pixels. | REQ-DSH-02
Graph 2 | Monthly FTE per person, with reference lines at the two thresholds - one pair of lines, since both are absolute. Above the bar budget it shows a ranked subset with the rest rolled into one 'others' band, and says which it is showing. | REQ-DSH-02, REQ-DSH-08, REQ-DSH-09
Graph 3 | Timeline per project - the FIRST panel on the tab, above the summary tiles. Each row carries the project name with its start, end and length beneath. Bands are coloured BY PERIOD NAME (see the colour rule below), with the period weight as a lightness step inside each hue. Milestones are inverted triangles in a lane above the bands; 'Inspection' takes the same marker as every other milestone. A milestone carrying milestone_highlight is drawn in that colour and takes the larger marker (schema 13, REQ-PRJ-14) - a colour chosen by hand beats the DB-lock red the chart applies by itself, and the legend lists only the colours in use, labelled with the words the file gives them. The hover pop-up gives the period, its dates, its weight and the FTE per month the project draws across it. | REQ-DSH-02, REQ-PRJ-05, REQ-DSH-10
Summary tiles | Active projects; people assigned; total FTE in the horizon; over-allocated person-months; under-allocation runs; and project-months OFF THEIR STANDARD, split short/over and never netted. The last one is clickable and scrolls to the section below; it is counted by the same function that draws that section, so the two cannot disagree. | REQ-DSH-08, REQ-DSH-15
Standard vs staffed | OPENED FROM RESOURCE BY PROJECT's own head (R-52), not a section of its own: every month it lists is a cell in that table. THE CONTROL STATES THE FINDING - how many project-months are off their standard and in which direction, with the same arrows and ground the cells use - rather than naming the screen behind it, because the reason for putting this list on the page at all was that a silent fault must not sit behind a click; it is drawn even when there is nothing to report, since a control that comes and goes is one nobody learns the position of. THE LIST CAN BE NARROWED by direction, by project (offering only the projects that have a gap) and by a smallest gap worth looking at; the narrowing reaches the list and nothing else, the heading states n of m whenever anything is set, and a list emptied by its own filter says that rather than that there is nothing to report. Cleared on load. The list itself: every project-month where what the project needs is not what it is getting, IN ORDER OF PROJECT ID THEN MONTH, both ascending (numbers inside an ID compare as numbers, so PRJ-2 precedes PRJ-10), with the project, the month, needs, staffed, the gap, its direction and the manager review (R-62). Every month is drawn - GAP_SHOW, 500, is a safety cap a real plan does not reach - because a cap on a list in project order would cut whole projects off the end. Deliberately NOT a tab - a tab is the surface you visit only once you already suspect a problem, which is the wrong property for something whose whole danger is that it is silent, and the findings report is already the list of everything wrong. Clicking any row opens that month in a dialog: the demand term by term, everyone on it with their applied figures, and EVERY Stated figure editable in place. A month that already has a MonthlyEstimate row is an ordinary contenteditable cell over it, so the editing path of sheet 07 handles it unchanged. A month with NO row has nothing to write through, so its cell CREATES one - and where the assignment is still automatic it asks first, because a lone row against an automatic assignment is read by nothing and setting estimation_type without seeding the other months counts each of them as 0.00 (REQ-CAL-18); the switch, the seeding and the typed figure are then applied together or not at all. Already manual with no row for that month is the V-31 case and is not asked. A cell with no data-sheet is skipped by the generic handler, which is what lets a creating cell carry its own. A row whose Applied is not its Stated carries the V-33 mark. The dialog redraws after an edit; one still showing the gap just closed would read as an edit that did nothing. Empty when there is nothing to report, and it says why rather than disappearing. | REQ-DSH-15
Reset filters | Clears every filter and restores the default 24-month horizon in one action. | REQ-DSH-05
Scroll regions | Every chart and table sits in its own scroll region - horizontal for wide content, and a bounded height with vertical scroll for tall content. Wide or long content scrolls INSIDE its panel; the page body never scrolls sideways, and a long sub-table never pushes the panels below it down the page. A scrolled table keeps its header row visible. | REQ-NFR-02
Row expansion - project | Clicking a project name reveals one row per person and role on it, each with its own monthly figures. Clicking again collapses. | REQ-DSH-01
Row expansion - person | Clicking a person name reveals one row per project and role they hold, ordered NewDrug CT, Biosimilar CT, Others, then earliest project first. | REQ-DSH-01
Type and phase pills | Project type and clinical phase shown as labelled pills. The text carries the meaning; the colour only speeds recognition. | REQ-PRJ-01, REQ-PRJ-09
Repeated period labels | Retained as a guard only. Since R-11 no period name repeats in a project, so the numbering never fires and a name alone identifies a period on screen. V-18 rejects a repeat on import; this keeps the renderer honest if one ever reaches it another way. | REQ-DSH-10
Row virtualisation | NOT BUILT, AND NOT REQUIRED at the volume REQ-NFR-03 names since R-47: both tables render EVERY row, and at 252 rows x 60 months that is 810 ms to draw against a 1,000 ms budget. The property that would have mattered either way holds and is required: sorting, filtering and totals run over the WHOLE MODEL, never over the rendered slice - so adding virtualisation later changes what is drawn and nothing that is computed. If a volume past about 400 people is ever asked for, the build is the visible window plus a small overscan with row height fixed so the scrollbar stays truthful. | REQ-DSH-09, REQ-NFR-03
UNALLOCATED DEMAND IS NOT PART OF EITHER TOTAL (REQ-DSH-17). It belongs to no person, so counting it in Table A would break the reconciliation below and would also assert that somebody is doing the work. It is totalled on a line of its own.
Both tables are the same numbers aggregated differently, so they must always reconcile: the grand total of table A equals that of table B. Worth asserting in code, not just hoping.
Timeline colour rule [O-10, supersedes design decision D-06]
Hue carries the PERIOD NAME. Weight carries a lightness step inside that hue, over a deliberately
narrow range so it never competes with the hue for the reader's attention.
Period | Hue | Why
Before-Start-up | grey, light | Not started. The two greys bracket the active work.
Start-up | red, shifted toward orange | Requested as red. Shifted because red beside green is the pair red-green colour blindness collapses, and REQ-DSH-08's principle - never colour alone - applies here too.
Conduct (interim) | green, light | The stretch before an interim DB lock. Exists only where there is one.
Conduct (final) | green, deep | The stretch that runs to the final lock - one green family, two steps, because they are the same phase of work at different points.
Close-out (interim) | orange, light | Split from the final close-out: a trial with an interim DB lock shows both in one row, and a single shared orange read as one interrupted band.
Close-out (final) | orange, deep | As above.
After Close-out (final) | grey, dark | Both greys are chosen to stay legible on the dark surface as well as the light one.
Planning / Develop / Close | grey / green / orange | The 'Others' period set, mapped to the same semantics.
Colour is never the only carrier. A band wide enough to hold its name shows it as text, the pop-up
names the period outright, and a repeated name carries its number (REQ-DSH-10).
This overturns D-06, which shaded bands by weight on the grounds that weight is what drives the simulation. The reviewer accepted D-06 and then asked for the opposite in O-10. O-10 is the more specific instruction, so it governs - and D-06's point is preserved by keeping weight as the lightness step and exact in the pop-up.
Rendering at the target volume [S2-06, R-47, REQ-DSH-09, REQ-NFR-03]
REQ-NFR-03 reads 100 projects and 150 people over a 60-month horizon, AMENDED AT R-47 from 100 projects
and 1,000 people - a figure set at S2-06 and never measured. The figures below are measurements of the
application at those volumes, not estimates of it: tools/build_stress_workbook.py builds a fixture at any
--projects / --people, tools/measure_scale.py drives it and times four interactions against budgets fixed
before any number was seen. Every number in this section is reproducible from those two commands.
THE BINDING QUANTITY IS ROWS x MONTHS, AND ROWS IS PROJECTS PLUS PEOPLE. The Overall tab carries both
tables, so 50 projects x 200 people and 100 x 150 are the SAME rendering problem - 252 rows - and measure
within 10 ms of each other. A specification that reasoned about the people figure alone would be wrong by
a factor of the project count.
Component | What the volume implies | What the specification requires
Overall pair | At 100 x 150: 252 rows x 60 months = 15,372 cells across the two tables. | Render every row. MEASURED 810 ms to switch to the tab, worst case 894, against a 1,000 ms budget - so row virtualisation would change no number a user feels and is NOT required (R-47).
Overall pair, beyond | At 400 people the same tab takes 1,044 ms; at 1,000 it is 3,058 ms, drawing 67,222 cells in 1,102 rows. | The budget is first crossed at about 400 people. Virtualisation - visible window plus overscan, fixed row height so the scrollbar stays truthful - becomes a requirement only if a volume past that is asked for.
Person chart | 200 bars across a 1,200px panel is 6px each; 1,000 bars is 1.2px - narrower than the gap beside them. | Aggregate, at EVERY volume. Show a ranked subset (default: the 20 most loaded) with the remainder as one named band. This is legibility, not speed, so no measurement retires it.
Project chart | 100 stacked bands per month, against 8 hues that can be told apart. | Unchanged from decision D-11: identity comes from legend order, the hover pop-up and - since R-45 - clicking a legend entry to pick the series out. Band order is by total resource.
Calculation | 100 x 150 x 60 is bounded by assignments, order 1,000, so about 60,000 month-rows worst case; the fixture yields 13,512. | Compute once per import or edit into arrays keyed by month index; never recompute inside a render. MEASURED: import 1,182 ms against a 5,000 ms budget at the named volume.
Editing and filtering | One cell edit rebuilds the model and re-renders; a column filter panel is built over the whole column. | MEASURED at the named volume: edit 60 ms against 1,000, filter 51 ms against 600. Both stay inside budget even at 1,000 people (98 ms and 49 ms), so neither is a scale question.
The figure in REQ-NFR-03 is an upper bound to design against, not the expected daily dataset - today's real use is about 50 projects and 100 people, which measures at 53% of the tightest budget. Nothing in the design may assume the small case: a table that is fast at 20 rows and unusable at 250 fails the requirement. What CHANGED at R-47 is the size of the bound, not that principle - and the bound moved because it was measured rather than asserted.
Why the requirement was not simply set to the volume in use. 50 x 100 leaves no room to grow into, and 100 x 200 measures at 98% of the tab budget with a worst case of 1,225 ms - over. 100 x 150 is the largest volume measured whose WORST case is still inside budget, which is a reason rather than a preference. Medians reproduce to a few per cent between runs; worst cases move much more, so choosing on the median alone would have been choosing on the kinder number.
Tab 2 - Source data (project)
Component | Behaviour | REQ-ID
Project table | All 23 Project columns, sortable and filterable, total_period_months recomputed. Editable. | REQ-DSH-03, REQ-IMP-07
Milestone sub-table | Milestones of the selected project in date order. 'Inspection' may appear several times. milestone_highlight is offered from the Lists sheet and its cell carries a chip in the chosen colour, drawn as a pseudo-element so it is never part of what the cell contains. | REQ-PRJ-05, REQ-PRJ-13, REQ-PRJ-14
Period sub-table | Derived periods with seq, dates and weight, in seq order. Names are unique within a project since R-11, so project_id + period_name identifies a row. Shows whether each date was derived or hand-set. A LOOKUP column beside the weight names the standard monthly FTE this period selects for a project of this type, phase and work scope, and multiplies the two - so the row carries the month's demand rather than one term of the expression for it. Missing, it reads 'none - V-19' rather than the 1.00 the calculation falls back to. | REQ-PRJ-06, REQ-CAL-09, REQ-DSH-10, REQ-DSH-14
Recompute periods | Re-derives from current milestones, warning that hand-set dates will be replaced. | decision C-10
Utilisation graph | The selected project's monthly resource across the horizon, as bars, with THREE reference lines: 2x and 0.5x the average an ACTIVE project-month draws across the portfolio, and the project's own average over its full life. Sits directly under the project table, mirroring the person tab's strip. Months where the project draws nothing are excluded from the portfolio average - averaging them in would drag the norm toward zero and make every running project look heavy. | REQ-DSH-12
Monthly estimation panel | Opened by 'Switch to manual'. One row a month: the stated figure, automatic_fte and difference - all three to TWO decimals, like every other FTE on screen (REQ-CAL-20) - then a LOOKUP column carrying the whole derivation of that month, term by term: the period, the standard it selects, the project's weight, the part of the month it ran, and their product. Where the project's own stated month overrode a person's stated figure, the panel also tabulates month / stated here / actually given / the project's month, and the cell carries a mark. Editing such a figure SOFT-STOPS at the cell: the dialog names both numbers and offers 'Keep what I typed' or 'Put it back'. It never refuses - see V-33. | REQ-CAL-18, REQ-CAL-20, REQ-DSH-14
Export | Visible table to .xlsx. | REQ-DSH-06
The reference lines are RELATIVE, and that is the whole design. A person has a capacity, so an absolute ceiling and floor mean something. A project does not: 3 FTE a month is heavy for a Phase 1 and light for a Phase 3 close-out. Comparing a project to the portfolio and to its own history is the only framing that carries meaning across 62 projects of different types and phases. The lines are context, not pass or fail, and the caption must say so - a dashed line above a bar reads as a limit unless it is labelled otherwise.
Tab 3 - Source data (person)
Component | Behaviour | REQ-ID
Person table | All 12 Person columns, sortable and filterable. Editable. | REQ-DSH-04, REQ-IMP-07
Assignment sub-table | The selected person's assignments: project, role, dates, person_weight. | REQ-PSN-02, REQ-PSN-03
Override sub-table | PersonPeriodWeight windows for the selected assignment. | REQ-PSN-05
Utilisation strip | The person's monthly FTE across the horizon with both absolute thresholds marked, and capacity_fte shown alongside for context. | REQ-DSH-08
Monthly estimation panel | The assignment-level half of the same panel as tab 2, for the selected assignment, with the same two decimals, the same override table and the same soft stop. Its derivation column adds a SECOND LINE - this person's claim on the month: role factor / sharers x person weight x month coverage, ending in the percentage of the month it won (see sheet 05 for why the two halves are closed off separately). It also carries ONE column tab 2's does not: the sharer count on its own, where it can be sorted and filtered - the divisor in (role factor / sharers), and the usual explanation for a share that halved with nothing of the person's own changing. Tab 2's panel deliberately omits it: a project month is divided between several roles, each with its own count, so one number there would average things that do not compare. | REQ-CAL-18, REQ-CAL-20, REQ-DSH-14
Export | Visible table to .xlsx. | REQ-DSH-06
Tab 4 - General assumptions [REQ-DSH-11, added at the component-list review]
Every figure on the Overall tab starts from the standard monthly FTE for the project's type, phase and
work scope, adjusted by the project's own period weight, and is then shared out among the people on it
by the role factors and their own weights. Those standards lived only in the workbook, so a reader who
wanted to know why a number was what it is had to leave the application. This tab is the fix.
Component | Behaviour | REQ-ID
Role factors | RoleFactor as TWO matrices - clinical trials (type + phase + role down the side, the six periods across) and 'Others' (role down the side, the three periods across). 249 rows flat is unreadable, and reading a role ACROSS the periods is the whole point of keying it that way. Both sit in a bounded scroll region. | REQ-DSH-11
Standard period FTE for project types | PeriodFTEStandard as a MATRIX - project type and clinical phase down the side, period name across, cells shaded on the same ramp as the Overall tables. It is a standard, and a standard is read across; 48 flat rows read as a list. 'Others' projects are absent by design - their weights are hand-entered per project (Q-28). | REQ-DSH-11
Configuration | Config in full, with each parameter's note. The display-unit control sits here, with a line saying why it is not in the filter bar. | REQ-DSH-11, REQ-CAL-08
Value lists | Lists, one row per list, showing every accepted value and the count. Answers 'what may I type here' without opening the workbook. A value outside its list is kept and reported by V-11, never dropped. READ-ONLY and with no insert control: a value added here with nothing referring to it is noise. | REQ-DSH-11
Editing | The role-factor and config tables are editable and insertable like any other table, and an edit here recalculates everything - these are the multipliers. | REQ-IMP-07, REQ-IMP-11
This tab is read-mostly but not read-only. A role factor is exactly the kind of figure a planner wants to try a different value for, and locking it would send them back to the workbook - which is what the tab exists to avoid.
Reading the screen at the size the plan actually is [REQ-DSH-16, R-45]
Four drawing rules that apply across every tab, not to one panel. None of them changes a figure.
Rule | Behaviour | REQ-ID
Charts grow with the horizon | A chart whose x axis is the month grid takes its width from the month count: W = max(Wmin, padL + padR + months x Wper), and its panel scrolls sideways past the point where they all fit. A FIXED WIDTH IS LEGIBLE ONLY OVER THE SPAN IT WAS CHOSEN FOR, and it fails SILENTLY - the chart still draws, it simply stops being readable, and it does so on exactly the long plans that most need reading. Wper is chosen so the DEFAULT horizon still falls under Wmin: the two-year view almost everybody opens on is unchanged, and the rule is visible only to the reader who needed it. The two utilisation charts were the last fixed-width ones. | REQ-DSH-16
Panels are tiled only where both are narrow | Two panels share a row only if each is readable in half a screen. The person tab's Assignments, Weight overrides and Monthly estimation are eleven, seven and eight columns wide - one of them a sentence of arithmetic - so they are ONE COLUMN, full width, in the order the work is done in: pick the assignment, then its override windows, then its months. Tiled, all three scrolled sideways permanently, which is a layout that costs every reader something to save space no reader asked for. | REQ-DSH-16
A child panel names its parent | A panel that is a child of a selection states the selected row under its title - the id, and the fields a reader needs to recognise it. From ONE helper shared by every panel that names the same thing, so two statements of the same assignment cannot drift apart. Monthly estimation was the panel without one: eight columns of months and no statement of what they belonged to. | REQ-DSH-16
Legend picking | Clicking a legend entry fades back every mark that is not that series; a second click, another entry, or Escape brings the chart home. Twenty bands in twenty shades of one palette read as a total and not as a series, and the answer is not more colours. THREE DECISIONS WORTH RECORDING. (1) The pick is scoped to the TAB, not the chart: series keys are ids, the same project is the same id wherever it is drawn, and the question being asked is 'where is this project on this page'. (2) A chart with NO mark for that key is left untouched. Dimming it whole would light nothing and fade everything, which reads as 'this has no data' rather than 'this chart cannot answer that' - charts on one tab are cut along different axes, and a person's id means nothing to a chart stacked by project. (3) A mark standing for two series at once carries a SECOND key and answers to either: a timeline band is a period OF a project, so picking a period lights it across every project and picking a project lights that project's whole row. Marks belonging to the MONTH rather than to any series - thresholds, baselines, the V-34 outline, milestone markers - carry no key and never fade. Every entry is a button: focusable, driven by Enter and Space, and it states whether it is pressed (D-04). | REQ-DSH-16, D-04
A heading is the plain name | Every column heading shows a PLAIN NAME and nothing else. work_scope_type, outsourcing_scope_det, absorbed_by and ref_id are legible to whoever wrote the schema and opaque to whoever fills the plan in, and their meaning existed only in the heading's pop-up - which is to say only for a reader who knew to hover. THE COLUMN'S OWN NAME IS IN THE POP-UP AND ON THE ELEMENT, NOT ON THE PAGE, and the reasoning is worth recording because it was settled twice. The first attempt put it on a second line under the label, on the argument that the screen and the file are the same thing, so a heading must be findable in the spreadsheet. That argument is right about the need and wrong about the place: looking up a column name is OCCASIONAL - editing the workbook, chasing a finding - and a heading is read on EVERY glance, so printing it charged the common case for the rare one when the pop-up already answered it. Every heading therefore carries a pop-up naming both, and the identifier as data-cid for whatever must read it. A badge that names another column ('sets ...') uses that column's plain name too, since a heading row that has stopped printing identifiers must not keep one in a badge. NOTHING IS RENAMED: the schema is unchanged, validation messages still name the column, and the cell still writes back through the identifier. The same two-part head is used on the heading's pop-up, on every cell's and on the filter buttons', so it is learned once. COLUMN_LABEL sits beside COLUMN_HELP in the parse module, so a column gets a sentence and a name in the same place. | REQ-DSH-16, REQ-IMP-07

## 07_Editing_IO
Editing, import and export
Import [REQ-IMP-01, REQ-IMP-02]
user picks a file, or drops one on the page
parse -> validate -> build the model -> derive periods -> calculate -> render
a fatal finding stops after validate and shows the report
a successful load replaces the model entirely; unsaved edits are warned about first
The edit buffer [REQ-IMP-07, REQ-IMP-09]
Rule | Basis
Every field is editable, identifiers included. | Q-20. Consistency is protected by rule, not by locking fields.
An edit is validated with the same rules as an import, at the moment of entry. | REQ-IMP-09. A rejected edit never reaches the model, so the model is always valid.
An edited cell is marked; the count of unsaved edits is always visible. | REQ-IMP-08.
Editing a milestone date re-derives that project's periods, unless its period dates were hand-set. | Decision C-10. This is the frequent-timeline-change case the tool exists for.
Editing a weight, date or assignment recalculates immediately. | The dashboard must never show numbers that disagree with the data on screen.
Inserting a row [REQ-IMP-11, added at the component-list review]
every editable table shows an insert control on EVERY row, not once per table
the control LEADS the row: at the end of a 23-column table it scrolls out of view
on press:
create a blank row of that sheet's shape
position it IMMEDIATELY BELOW the row the control was pressed on
pre-fill the parent key where the table is a child of a selection
(a period inserted under project PRJ-003 gets project_id = PRJ-003)
leave every other field empty and focus the first editable cell
mark the row unsaved; it joins the edit count like any other change
validation runs on entry, exactly as for an edit (REQ-IMP-09):
a blank row is INCOMPLETE, not invalid - it is not reported until a field is filled
a row still missing its identifier when export is pressed blocks the export, naming it
Position matters and is worth stating. Appending to the bottom of a 62-row table means the user has to
find the new row and then move it; inserting where they are looking means they can just type. The stored
order follows the display order, so the export carries the row where the user put it.
Deleting stays asymmetric with inserting, as it already is with editing: a row can be created freely because an empty row references nothing, while a row that is referenced cannot be deleted at all (V-17). Creation is cheap to undo; deletion is not.
Cascading identifier edits [REQ-IMP-10, V-17]
on changing an identifier:
count the rows referencing the old value
if 0 : apply
else : confirm ('PRJ-003 is referenced by 14 rows. Update them all?')
on confirm, rewrite every reference in one atomic step
on deleting a row:
if anything still references it -> refuse, naming what does (V-17)
never cascade a delete: losing 14 assignments to one keystroke is unrecoverable
Cascading an edit and refusing a delete are deliberately asymmetric. A cascaded rename is visible and reversible; a cascaded delete is neither.
Export [REQ-IMP-04, REQ-IMP-07]
Behaviour | Reason
Writes all 11 sheets in template order, with the template's headers and formats. | So the export re-imports without edits.
Includes every edit made on screen. | REQ-IMP-07 - this is the point of the feature.
Derived columns are written as values, not formulas. | A formula referencing a row that moved would be wrong; the importer recomputes them anyway.
Filename defaults to the loaded name with a date suffix. | Never silently overwrite the source of record.
Clears the unsaved-edit state on success. | REQ-IMP-08.

## 08_Versioning
Versioning and compatibility
Item | Behaviour | REQ-ID
Application version | Constant in the HTML, shown in the header and footer. | REQ-VC-02
Expected schema version | Constant in the HTML. Currently 10. | REQ-VC-02
Check on load | Compare Config.schema_version with the expected value. | REQ-VC-03
Equal | Proceed silently. | REQ-VC-03
File older | Proceed; warn that columns added since may be missing. | REQ-VC-03
File newer | Proceed; warn that columns may be ignored, and suggest updating the application. | REQ-VC-03
Missing | Treat as version 1 and warn. | REQ-VC-03
The check never blocks a load. A planner with a slightly stale file still needs an answer today; a warning gives them one with the caveat attached.

## 09_Traceability
Requirement traceability
Read directly from PRAP_Development_Plan_v2.74.xlsx sheet 03, so a requirement cannot be lost between the two documents.
REQ-ID | Requirement (from the plan) | Priority | Specified in
REQ-OUT-01 | The application is a single HTML file that runs on a local Windows PC by double-click, with no install and no network access. | Must | 02_Scope, 07_Editing_IO
REQ-OUT-02 | All program logic (HTML, CSS, JavaScript, libraries) is embedded in that one HTML file so it can be copied between PCs as a single artifact. | Must | 02_Scope, 07_Editing_IO
REQ-OUT-03 | Source data lives in ONE Excel workbook held separately from the HTML file, and that workbook is the archive of record. | Must | 02_Scope, 07_Editing_IO
REQ-OUT-04 | The application reads the source workbook and uses it to drive every table and graph. | Must | 02_Scope, 07_Editing_IO
REQ-OUT-05 | Plans and specifications are delivered as Excel workbooks. | Must | 02_Scope, 07_Editing_IO
REQ-PRJ-01 | Each project records a project type, restricted to 'NewDrug CT', 'Biosimilar CT' or 'Others'. The first two are clinical trials and every clinical tri | Must | 03_Data_Schema
REQ-PRJ-02 | Each project records a project category. For either clinical trial type the category is the product name; the field is optional for 'Others'. | Must | 03_Data_Schema
REQ-PRJ-03 | Each project records a project name, unique within the source workbook. | Must | 03_Data_Schema
REQ-PRJ-04 | Each project records its conditions: outsourcing type ('Full outsourcing' / 'Partial outsourcing' / 'Full In-house') and the number of project members | Must | 03_Data_Schema
REQ-PRJ-06 | Each project carries a resource weight per period. For a clinical trial the weight is seeded from a standard keyed on clinical phase; for 'Others' it | Must | 03_Data_Schema
REQ-PRJ-05 | Each project records a timeline: start date, major milestone dates, and total period. | Must | 03_Data_Schema
REQ-PRJ-07 | The project record accepts further project-related information without a schema change (free/extension columns). | Should | 03_Data_Schema
REQ-PRJ-08 | Total period is derived from start and end dates rather than typed by hand, so it cannot contradict the timeline. | Should | 03_Data_Schema
REQ-PRJ-12 | The set of periods a project carries depends on its type: either clinical trial type uses Before-Start-up / Start-up / Conduct (interim) / Close-out ( | Must | 03_Data_Schema
REQ-PRJ-13 | A milestone name may occur more than once in one project. 'Inspection' in particular may record several events; the others are expected once. | Must | 03_Data_Schema
REQ-PRJ-16 | The colour each PERIOD is drawn in is a standing assumption: one default per period name, held on the PeriodHighlight sheet and edited on the General | Should | 03_Data_Schema
REQ-PRJ-17 | THE HIGHLIGHT PALETTE OFFERS AT LEAST TWELVE DISTINCT COLOURS - thirteen: red, orange, yellow, lime, green, teal, cyan, blue, navy, purple, magenta, p | Should | 03_Data_Schema
REQ-PRJ-15 | A project's period may be given a COLOUR, and the Project timeline draws the period in it - on the Overall tab and on the project's own tab. The colou | Should | 03_Data_Schema
REQ-PRJ-14 | A milestone may be MARKED IN A COLOUR, and the mark finds that milestone wherever the Project timeline is drawn - on the Overall tab and on the projec | Should | 03_Data_Schema
REQ-PRJ-09 | A clinical trial of either type records its clinical phase (phase 1 / 2 / 3 / 4). The phase determines the project's period weights, so it drives the | Must | 03_Data_Schema
REQ-PRJ-10 | A clinical trial of either type records who performs each of EDC set-up, data-review-system set-up, RBQM set-up and DM conduct ('by CRO' / 'by SB'). | Must | 03_Data_Schema
REQ-PRJ-11 | A clinical trial of either type records the EDC system, data review system and RBQM system in use, from data-driven value lists. | Must | 03_Data_Schema
REQ-PSN-01 | Data is managed by person, by project assigned, and by project role assigned. | Must | 03_Data_Schema
REQ-PSN-02 | Each assignment records the project(s) the person is assigned to. | Must | 03_Data_Schema
REQ-PSN-03 | Each assignment records the role(s) the person holds on that project, drawn from the role list valid for that project's type. | Must | 03_Data_Schema
REQ-PSN-04 | Each assignment records the start date the person joins and the end date they leave that study. | Must | 03_Data_Schema
REQ-PSN-05 | Each assignment carries a person weight saying how much that person works on that project, with optional period-specific overrides. | Must | 03_Data_Schema
REQ-PSN-06 | The person record accepts further project-related information without a schema change. | Should | 03_Data_Schema
REQ-PSN-07 | One person may hold assignments on several projects simultaneously, and may hold more than one role on the same project. | Must | 03_Data_Schema
REQ-CAL-01 | Resource is simulated on a monthly grid, default horizon 24 months, expandable to the latest project end date. | Must | 05_Calculation
REQ-CAL-02 | Monthly load for an assignment = project period weight x (role factor / people sharing that role) x person weight x fraction of the month covered. The | Must | 05_Calculation
REQ-DSH-22 | THE PERSON TAB SHOWS THE SELECTED PERSON'S PROJECTS AS A TIMELINE - the Project timeline of the Overall tab, cut to the projects the person has an ass | Should | 06_UI_Spec
REQ-DSH-21 | TODAY IS MARKED WHEREVER MONTHS ARE DRAWN: a line at today's day within the current month on every chart drawn over months, and through every row of t | Should | 06_UI_Spec
REQ-DSH-20 | AN ISSUE A MANAGER HAS REVIEWED IS SHOWN AS REVIEWED, AND THE REVIEW CAN BE READ FROM THE ISSUE. Each short, over or not-staffed project-month (REQ-DS | Should | 06_UI_Spec
REQ-DSH-19 | A ROW'S IDENTITY STAYS ON SCREEN WHILE ITS TABLE SCROLLS SIDEWAYS. A source-data sheet can be far wider than the panel that holds it - the Project she | Should | 06_UI_Spec
REQ-DSH-18 | ANY SECTION CAN BE GIVEN THE WHOLE WINDOW, AND THE DATA IN IT IS STILL EDITABLE THERE. Every panel holding a bounded scroll region carries a control i | Should | 06_UI_Spec
REQ-DSH-17 | A PROJECT-MONTH THE PLAN ASKS FOR AND NOBODY IS ASSIGNED TO SHOWS WHAT IT ASKS FOR. Resource by project used to print a dot there, and a dot is a stat | Should | 06_UI_Spec
REQ-DSH-16 | THE SCREEN IS READABLE AT THE SIZE THE PLAN ACTUALLY IS, AND SAYS WHAT ITS COLUMNS MEAN. Five things, none of which changes a figure. (a) A CHART THAT | Should | 06_UI_Spec
REQ-DSH-15 | WHERE A PROJECT IS NOT BEING GIVEN WHAT ITS OWN STANDARD SAYS IT NEEDS, THE APPLICATION SAYS SO. Two figures can come apart and the obvious pair is no | Should | 06_UI_Spec
REQ-DSH-14 | WHERE A FIGURE'S SIZE WAS DECIDED SOMEWHERE ELSE, THE TABLE SHOWING THE FIGURE NAMES WHAT DECIDED IT, in a column that is looked up and cannot be edit | Should | 06_UI_Spec
REQ-DSH-13 | Every bounded scroll region draws its own scrollbars rather than relying on the browser's. A region deliberately capped on both axes is only honest if | Must | 06_UI_Spec
REQ-CAL-20 | EVERY FTE FIGURE THE APPLICATION PRODUCES IS A WHOLE NUMBER OF HUNDREDTHS - not displayed to two places, but IS two places. The rounding happens once, | Must | 05_Calculation
REQ-CAL-19 | A PROJECT-MONTH IS ITS STANDARD. PeriodFTEStandard.standard_fte is the DEMAND in FTE for a project of this type, clinical phase and work scope in this | Must | 05_Calculation
REQ-CAL-18 | A PROJECT, OR ONE ASSIGNMENT, MAY HAVE ITS MONTHLY FTE STATED RATHER THAN CALCULATED. estimation_type on Project and on Assignment selects which; Mont | Must | 05_Calculation
REQ-CAL-17 | A PROJECT'S WINDOW, wherever the calculation needs one, is the span of its ProjectPeriod rows: the earliest period_start to the latest period_end. Mil | Must | 05_Calculation
REQ-CAL-16 | Where NOBODY holds a role on a project, its role factor is added to the factor of the role named in RoleFactor.absorbed_by - because the work still ha | Must | 05_Calculation
REQ-CAL-15 | BOTH ASSIGNMENT DATES ARE OPTIONAL. A blank assign_start_date means the project's own start date, and a blank assign_end_date the project's own end da | Must | 05_Calculation
REQ-CAL-14 | Where SEVERAL PEOPLE hold the same role on the same project in the same month, the role factor is DIVIDED BETWEEN THEM. The role factor states what th | Must | 05_Calculation
REQ-CAL-03 | Project monthly load is the sum of its assignments; person monthly load is the sum across all their projects. | Must | 05_Calculation
REQ-CAL-04 | A person-month whose total exceeds the over-allocation threshold (default 1.50 FTE) is flagged as over-allocated. The threshold is absolute, not scale | Must | 05_Calculation
REQ-CAL-05 | A partial first or last month is pro-rated by calendar days worked, not counted as a whole month. | Must | 05_Calculation
REQ-CAL-06 | All weights, factors and thresholds are data, held in the source workbook, never hardcoded in the program. | Must | 05_Calculation
REQ-CAL-07 | A person whose monthly total stays below the under-allocation threshold (default 0.60 FTE) for three or more consecutive months is flagged as under-al | Must | 05_Calculation
REQ-CAL-08 | Load is expressed in FTE, where 1.00 FTE = 160 hours per month (8 h/day x 5 days/week x 20 days/month). Hours are shown alongside FTE where useful. | Must | 05_Calculation
REQ-CAL-09 | For a clinical trial of either type, period boundaries are computed from milestone dates plus fixed month offsets (sheet 05), so a timeline change re- | Must | 05_Calculation
REQ-CAL-10 | Every month of a project's timeline falls in exactly one period. A month left uncovered by the derivation is reported and carries weight 1.00 rather t | Must | 05_Calculation
REQ-CAL-11 | Where an interim DB lock splits the conduct phase, the two stretches are separate rows carrying DIFFERENT names: 'Conduct (interim)' before the interi | Must | 05_Calculation
REQ-CAL-13 | Where a period boundary has both a milestone and a month-offset definition, a recorded milestone date wins. The offset is the fallback for a project t | Must | 05_Calculation
REQ-CAL-12 | Where a timeline squeezes a derived period to zero or negative length, that period is omitted and the omission reported. Boundaries are applied in ord | Must | 05_Calculation
REQ-DSH-01 | Tab 'Overall' shows monthly resource simulation per project and per person as tables. | Must | 06_UI_Spec
REQ-DSH-02 | Tab 'Overall' shows appropriate graphs of the same simulation. | Must | 06_UI_Spec
REQ-DSH-03 | Tab 'Source data (project)' shows project information as a table. | Must | 06_UI_Spec
REQ-DSH-04 | Tab 'Source data (person)' shows person information as a table. | Must | 06_UI_Spec
REQ-DSH-05 | One filter set drives every tab: date horizon, project type, clinical phase, project, person, role and department, with a single action to clear them | Should | 06_UI_Spec
REQ-DSH-06 | Any table on screen can be exported to Excel. | Should | 06_UI_Spec
REQ-DSH-07 | The horizon control offers 24 months by default and a one-click expansion to cover the latest project end date across all projects. | Must | 06_UI_Spec
REQ-DSH-08 | Over-allocated and under-allocated person-months are distinguishable at a glance, and both are counted in the summary tiles. | Must | 06_UI_Spec
REQ-DSH-09 | THE PER-PERSON CHART SHOWS AN AGGREGATE OR A RANKED SUBSET rather than one bar per person, and says which it is showing. A thousand bars is not a char | Must | 06_UI_Spec
REQ-DSH-10 | Every period of a project is distinguishable from every other on screen. Since R-11 this is satisfied by the data model rather than by a display rule | Must | 06_UI_Spec
REQ-DSH-12 | The project source-data tab shows the selected project's monthly resource over the horizon, against RELATIVE reference lines - a multiple and a fracti | Should | 06_UI_Spec
REQ-DSH-11 | The standing assumptions the simulation multiplies by - standard period weights, role factors, configuration and value lists - are presented on their | Must | 06_UI_Spec
REQ-IMP-01 | The user loads the source workbook through a file picker or drag-and-drop, chosen because a local HTML page cannot open a file from disk unaided. | Must | 07_Editing_IO
REQ-IMP-02 | Loading validates the workbook and reports every problem found - missing sheet, missing column, bad date, unknown project reference - without stopping | Must | 07_Editing_IO
REQ-IMP-03 | A blank source workbook template with correct sheet names, headers, value lists and one example row is delivered with the application. | Must | 07_Editing_IO
REQ-IMP-04 | The user can export current data back to .xlsx, preserving the template layout so the export can be re-imported. | Must | 07_Editing_IO
REQ-IMP-05 | The application records which file was loaded and when, and shows it on screen with its time zone - a bare timestamp is ambiguous to anyone reading it | Should | 07_Editing_IO
REQ-IMP-06 | Loaded data may be cached in the browser so re-opening the page does not force a re-import; the cache never replaces the workbook as the record. | Could | 07_Editing_IO
REQ-IMP-07 | After import, the application lets the user update the data on screen, and those updates are carried into the file produced on export. | Must | 07_Editing_IO
REQ-IMP-08 | Unsaved edits are visible as such, and the user is warned before any action that would discard them (closing the page, loading another file). | Must | 07_Editing_IO
REQ-IMP-09 | Every field is editable, including identifiers. An on-screen edit is re-validated against the same rules as an imported value, so editing cannot intro | Must | 07_Editing_IO
REQ-IMP-10 | Editing an identifier that other sheets reference cascades to every referencing row, after showing how many rows will change. Deleting a referenced ro | Must | 07_Editing_IO
REQ-IMP-14 | An import that changes any Config setting says so. The settings in force are captured before the model is replaced and compared by name afterwards; ev | Must | 07_Editing_IO
REQ-OUT-06 | The application exports the CALCULATED MONTHLY FTE as well as the source plan, and the export control offers the choice with each option described. Th | Must | 02_Scope, 07_Editing_IO
REQ-IMP-12 | A column that holds a DATE offers a calendar panel beside the cell being edited, and the cell stays fully typeable while it is open: the caret does no | Should | 07_Editing_IO
REQ-IMP-13 | Every validation rule carries a CLASS saying what the application may do about it, separately from its severity. MUST: something is wrong with the row | Must | 07_Editing_IO
REQ-IMP-11 | A new row can be inserted into any editable table, positioned immediately below the row the user acts on rather than appended at the end, and validate | Must | 07_Editing_IO
REQ-VC-01 | Development plan, programming specification and output files are version-controlled together and their versions are cross-referenced. | Must | 08_Versioning
REQ-VC-02 | The application displays its own version, and the version of the source data schema it expects. | Must | 08_Versioning
REQ-VC-03 | Loading a source file whose schema version is newer or older than the application expects produces a clear warning. | Should | 08_Versioning
REQ-VC-04 | Every document re-issue adds a version-history row stating what changed and why. | Must | 08_Versioning
REQ-NFR-01 | The application is built so later requirements can be added without restructuring: parsing, calculation and presentation are separated. | Must | 02_Scope, 07_Editing_IO
REQ-NFR-02 | Works in Microsoft Edge and Google Chrome on Windows 10/11, offline. | Must | 02_Scope, 07_Editing_IO
REQ-NFR-03 | HANDLES 100 PROJECTS AND 150 PEOPLE over a 60-month horizon, with the assignments that implies (order 1,000). MEASURED AT THAT VOLUME, NOT ESTIMATED ( | Must | 02_Scope, 07_Editing_IO
REQ-NFR-04 | No data leaves the PC: no network calls, no external CDN, no telemetry. | Must | 02_Scope, 07_Editing_IO
REQ-NFR-05 | Dates are handled unambiguously (ISO yyyy-mm-dd internally) regardless of Windows regional settings. | Must | 02_Scope, 07_Editing_IO
95 requirements, all mapped. Regenerated from the plan on every build, so a requirement added there appears here automatically rather than being remembered.

## 10_Open_Points
Open points - all answered at the v0.3 review
The six points raised in v0.3, the answer given on 2026-08-01, and what changed in this document as a result. No point remains open.
ID | Topic | Question as raised in v0.3 | Answer (Dan, 2026-08-01) | What changed in v0.4 | State
S2-01 | Calculation | The under-allocation threshold is an absolute 0.80 FTE while Person.capacity_fte allows a part-timer at 0.60, who can therefore never clear it and is flagged permanently. Should both thresholds be relative to capacity_fte? | No, both thresholds (alerting over work-load, and under work-load) not to be relative to capacity_fte. | Answered - draft overturned. The relative-threshold proposal is withdrawn; sheet 05 now specifies both thresholds as absolute, and capacity_fte no longer appears in the arithmetic. The part-timer defect this point raised is instead resolved by S2-05, and V-22 (new) warns on import about the one case that remains - a capacity below the floor. Plan change R-07. | Closed
S2-02 | Data model | period_name and role_name cannot carry an Excel dropdown, because the valid list depends on the project's type. | No need to carry out the dropdown list to period_name and role_name. | Answered - draft confirmed. No dependent dropdowns are built. V-15 and V-03 remain the enforcement, at import and at edit. No change to this document. | Closed
S2-03 | Data model | Adding a value to a list means inserting a row inside that list's block on the Lists sheet, since dropdowns bind to a contiguous range. | Keep current setting. | Answered - draft confirmed. The Lists sheet keeps its long format with contiguous blocks, documented in the template README. No change to this document. | Closed
S2-04 | UI | Should the two 'Conduct' stretches of one project be distinguishable on screen, or shown as one Conduct total? | The two 'Conduct' stretches needs to be distinguishable on screen. | Answered - draft extended. They were already separate bands on the timeline but summed in the tables, which is not 'distinguishable'. Sheet 06 now numbers any repeated period name wherever it is named - 'Conduct (1)', 'Conduct (2)' - in bands, tooltips, the period sub-table and exports. New REQ-DSH-10; plan change R-08. | Closed
S2-05 | Calculation | A month with zero load breaks an under-allocation run rather than continuing it - somebody with no assignments at all is not 'under-allocated', they are unassigned. | The person who has under 0.6 FTE should be considered an under-allocated person. | Answered - the zero-breaks-the-run rule stands as drafted, and the floor moves from 0.80 to 0.60 FTE in Config and in the template and dummy workbooks. At 0.60 every capacity in the data can clear the floor (1.00 needs 60% utilisation, 0.80 needs 75%, 0.60 needs 100%), which is what settles S2-01. Plan change R-07. | Closed
S2-06 | Non-functional | The dummy dataset now holds 62 projects and 289 assignments, above REQ-NFR-03's headroom figure of 50 projects and 500 assignments. The requirement's working-volume figure (20 projects, 30 people) is well below what the dataset represents. | Change the requirement: 100 projects, 1,000 people. | Answered - requirement re-baselined, and raised from Should to Must. REQ-NFR-03 read 100 projects and 1,000 people over 60 months (order 8,000 assignments). At that volume the person table is 60,000 cells and the person chart 1,000 bars, so virtualisation and chart aggregation stop being optimisations - see the section on sheet 06 and REQ-DSH-09. Plan change R-06. AMENDED LATER AT R-47, once the figure was MEASURED rather than reasoned about: the rendering budget is crossed at about 400 people, so REQ-NFR-03 now reads 100 projects and 150 PEOPLE and the virtualisation half of REQ-DSH-09 is withdrawn. The chart-aggregation half stands - it was never a speed argument. This answer is kept as the record of what was asked and why; it is not the current requirement. | Closed - volume superseded at R-47
Two of the six were confirmed as drafted, three changed a rule the application reads as data, and one (S2-06) changed what the design has to survive. Only the last has architectural weight, which is why it produced a requirement rather than a configuration value.
Nothing in this document is now waiting on an answer. What it is waiting on is signature of plan v1.5, which carries the three changes these answers produced.